|  |  |
| --- | --- |
| **Plenipotentiary Conference (PP-14) Busan, 20 October – 7 November 2014** |  |
|  |  |
|  |  |
|  |  |
|  | **18 June 2014** |
|  |  |
|  | |
| Note by the Secretary-General | |
| DRAFT TIME MANAGEMENT PLAN | |
|  | |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Plenipotentiary Conference (Busan, 2014) – Monday 20 October to Friday 7 November 2014 DRAFT TIME MANAGEMENT PLAN | | | | | | | | | | | | | | | | |
|  | | | | | | | | | | | | | | | | |
|  | | | **Monday** | | | **Tuesday** | | | **Wednesday** | | | **Thursday** | | | **Friday** | | | | |
|  | | | *0930-1230* | *1430-1730* | *1930-2230* | *0930-1230* | *1430-1730* | *1930-2230* | *0930-1230* | *1430-1730* | *1930-2230* | *0930-1230* | *1430-1730* | *1930-2230* | *0900-1200* | *1430-1730* | | *1930-2230* | |
| **Week 1** 20-24.10 | | | ***0930\* 1100\*\**** | **PL[[1]](#footnote-1), [[2]](#footnote-2), [[3]](#footnote-3)** |  | **PL[[4]](#footnote-4),[[5]](#footnote-5)** | **PL5 + 2** + **6** |  | **PL5 +**  **3 + WG-PL** | **PL5**  **+**  **5** |  | **PL[[6]](#footnote-6)**  *followed by*  **WG-PL + 6** | **5 + 6**  *followed by*  **PL[[7]](#footnote-7) *Steering Committee*** |  | **PL[[8]](#footnote-8)**  *followed by*  **5 +**  **WG-PL** | **6 +****WG-PL**  *followed by*  **PL[[9]](#footnote-9)** | |  | |
|  | | |  |  |  |  |  |  |  |  |  |  |  |  |  |  | |  | |
| **Week 2** 27-31.10 | | | **PL** **[[10]](#footnote-10),[[11]](#footnote-11)**  *followed by*  **5** + **6** | **5 + 6** |  | **5 + WG-PL** | **6 +**  **WG-PL *Steering Committee*** |  | **5 +  2** *(end)* **+**  **WG-PL** | **6 +**  **WG-PL** |  | **5 + 6** | **5 + WGPL**  *followed by*  **PL[[12]](#footnote-12) *Steering Committee*** |  | **5 +**  **WG-PL** | **6 + WG-PL** | |  | |
|  | | |  |  |  |  |  |  |  |  |  |  |  |  |  |  | |  | |
| **Week 3**  3-7.11 | | | ***Steering Committee***  **5 + 6 +  3** *(end)*  *followed by* **WG-PL** | **WG-PL + 5**  *followed by*  **PL** |  | **PL[[13]](#footnote-13)**  *followed by*  **WG-PL + 6** | **5 +6** |  | **5** *(end)* **+ 6** | **WG-PL + 6** *(end)*  *followed by*  **PL** |  | **PL** | **PL** |  | **PL** | **PL\*\*\*** | |  | |
| ***\* Formal meeting of Heads of delegation \*\* Opening ceremony \*\*\* Signing ceremony*** | | | | | | | | | | | | | | | |

1. First Plenary Meeting - Structure of the conference, setting up of committees, chairmanship, allocation of documents, organization of work [↑](#footnote-ref-1)
2. Other organizational matters [↑](#footnote-ref-2)
3. Policy statements [↑](#footnote-ref-3)
4. Set definitive upper limit of contributory unit [↑](#footnote-ref-4)
5. Policy statements (continued) [↑](#footnote-ref-5)
6. Election: SG and DSG [↑](#footnote-ref-6)
7. Election: DSG (continued) [↑](#footnote-ref-7)
8. Election: DSG (continued) followed by Directors of the Bureaux [↑](#footnote-ref-8)
9. Election: Directors of the Bureaux *(continued)* [↑](#footnote-ref-9)
10. Deadline for MS to announce definitive choice of class of contribution to Secretariat [↑](#footnote-ref-10)
11. Election: RRB and Council [↑](#footnote-ref-11)
12. Com 2 (Credentials) report to PL [↑](#footnote-ref-12)
13. Com 3 (Budget Control) report to PL [↑](#footnote-ref-13)