| INTERNATIONAL TELECOMMUNICATION UNION |  |
| --- | --- |
| RADIOCOMMUNICATION ADVISORY GROUP GENEVA, 11-14 MARCH 1997 | Corrigendum 1 to Document RAG97-1/1-E 11 March 1997 Original: English |

Director, Radiocommunication Bureau

Replace pages 29, 30 and 31 with the attached new pages.

This document shows the updated Radiocommunication Sector draft financial plan as of 31 December 1996 including foreseen expenditures until 31 December 1997.

# 8	Financial matters

## 8.1	General ITU-R budget

The current 1996-1997 budget of the Radiocommunication Sector has been decided in Resolution 1071 of the 1995 session of the Council and was supplemented by Resolution 1088 in 1996.

Table 4 gives the foreseen breakdown of expenditures for the activities of the Sector as of 31 December 1996 and the expected situation on 31 December 1997.

## 8.2	Budget of the Radiocommunication Study Groups

The principle of establishing a biennial budget for each Radiocommunication Study Group to be managed by the Study Group Chairman with the assistance of Bureau staff was successfully implemented in 1996 in consultation with the Chairmen and Vice-Chairmen. The Study Group budgets were based on the foreseen workload and particularly on the number of meetings and volume of documentation to be produced.

Table 5 gives the foreseen breakdown of expenditures for each Study Group as of 31 December 1996 and the expected situation on 31 December 1997.

| Table 4 | Radiocommunication Sector draft financial plan 1996-1997 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DIRECT COSTS (Swiss Francs) |  | WRC | RA | Res 18 | Seminars | RRB | RAG | Study Groups | BR | TOTAL |
| STAFF COSTS: BR established posts, | Resources 1996-97 | 1'670'267 | 482'134 | 373'520 | 199'500 | 305'570 | 304'802 | 3'043'036 | 48'192'125 | 54'570'954 |
| ad hoc fixed term contracts, short-term | Expenditures as of 31.12.96 | 694 | 309 | 68'466 | 23'699 | 57'376 | 69'547 | 676'313 | 23'097'125 | 23'993'529 |
| contracts, interpreters, and other staff | Planned expenditures 31.12.97 | 1'503'240 | 289'280 | 190'140 | 179'550 | 189'556 | 152'401 | 2'270'019 | 46'334'949 | 51'109'135 |
| costs (insurance, overtime, etc.…) | Expected balance 31.12.97 | 167'027 | 192'854 | 183'380 | 19'950 | 116'014 | 152'401 | 773'017 | 1'857'176 | 3'461'819 |
| OTHER DIRECT COSTS: missions, | Resources 1996-97 | 269'500 | 149'000 | 0 | 436'135 | 414'080 | 48'000 | 845'000 | 2'115'000 | 4'276'715 |
| contractual services, logistics, | Expenditures as of 31.12.96 | 4'777 | 3'648 | 96'034 | 250'266 | 191'719 | 0 | 490'171 | 821'846 | 1'858'461 |
| equipment, other acquisitions, services, | Planned expenditures 31.12.97 | 290'050 | 87'000 | 114'250 | 492'635 | 328'842 | 22'000 | 733'363 | 1'490'822 | 3'558'962 |
| miscellaneous | Expected balance 31.12.97 | -20'550 | 62'000 | -114'250 | -56'500 | 85'238 | 26'000 | 111'637 | 624'178 | 717'753 |
|  |  | WRC | RA | Res 18 | Seminars | RRB | RAG | Study Groups | BR | TOTAL |
| Total direct costs | Resources 1996-97 | 1'939'767 | 631'134 | 373'520 | 635'635 | 719'650 | 352'802 | 3'888'036 | 50'307'125 | 58'847'669 |
| Staff costs, other direct costs and | Expenditures as of 31.12.96 | 5'471 | 3'957 | 164'500 | 273'965 | 249'095 | 69'547 | 1'166'484 | 23'918'971 | 25'851'990 |
| miscellaneous | Planned expenditures 31.12.97 | 1'793'290 | 376'280 | 304'390 | 672'185 | 518'398 | 174'401 | 3'003'382 | 47'825'771 | 54'668'097 |
|  | Expected balance 31.12.97 | 146'477 | 254'854 | 69'130 | -36'550 | 201'252 | 178'401 | 884'654 | 2'481'354 | 4'179'572 |
| INVOICED COSTS |  | WRC | RA | Res 18 | Seminars | RRB | RAG | Study Groups | BR | TOTAL |
| Translation, typing and reproduction | Resources 1996-97 | 1'711'000 | 1'018'000 | 60'000 | 42'000 | 128'000 | 85'000 | 4'547'546 | 3'498'000 | 11'089'546 |
| of documents | Expenditures as of 31.12.96 | 71'167 | 1'960 | 123'658 | 82'747 | 36'015 | 58'424 | 2'258'945 | 1'176'990 | 3'809'906 |
|  | Planned expenditures 31.12.97 | 1'711'000 | 712'600 | 60'000 | 90'427 | 80'198 | 85'000 | 4'093'181 | 1'749'000 | 8'581'406 |
|  | Expected balance 31.12.97 | 0 | 305'400 | 0 | -48'427 | 47'802 | 0 | 454'365 | 1'749'000 | 2'508'140 |
|  |  | WRC | RA | Res 18 | Seminars | RRB | RAG | Study Groups | BR | TOTAL |
| GRAND TOTAL | Resources 1996-97 | 3'650'767 | 1'649'134 | 433'520 | 677'635 | 847'650 | 437'802 | 8'435'582 | 53'805'125 | 69'937'215 |
| Direct and invoiced costs | Expenditures as of 31.12.96 | 76'638 | 5'917 | 288'158 | 356'712 | 285'110 | 127'971 | 3'425'429 | 25'095'961 | 29'661'896 |
|  | Planned expenditures 31.12.97 | 3'504'290 | 1'088'880 | 364'390 | 762'612 | 598'596 | 259'401 | 7'096'563 | 49'574'771 | 63'249'503 |
|  | Expected balance 31.12.97 | 146'477 | 560'254 | 69'130 | -84'977 | 249'054 | 178'401 | 1'339'019 | 4'230'354 | 6'687'712 |

| Table 5 | Radiocommunication Sector draft Study Group financial plan 1996-1997 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DIRECT COSTS (Swiss Francs) |  | SG 1 | SG 3 | SG 4 | SG 7 | SG 8 | SG 9 | SG 10 | SG 11 | CPM | SC | CVC |
| STAFF COSTS: BR established posts, | Resources 1996-97 | 170'294 | 256'310 | 237'590 | 256'310 | 372'178 | 274'455 | 256'310 | 280'890 | 544'855 | 260'178 | 133'665 |
| ad hoc fixed term contracts, short-term | Expenditures as of 31.12.96 | 64'116 | 0 | 61'660 | 62'541 | 90'647 | 109'617 | 29'663 | 157'575 | 45'744 | 38'401 | 16'349 |
| contracts, interpreters, and other staff | Planned expenditures 31.12.97 | 217'869 | 111'930 | 190'373 | 134'595 | 168'017 | 224'331 | 96'420 | 270'593 | 641'957 | 144'930 | 69'003 |
| costs (insurance, overtime, etc.…) | Expected balance 31.12.97 | -47'575 | 144'380 | 47'217 | 121'715 | 204'161 | 50'124 | 159'890 | 10'297 | -97'102 | 115'248 | 64'662 |
| OTHER DIRECT COSTS: missions | Resources 1996-97 | 54'250 | 102'200 | 81'650 | 102'200 | 136'450 | 102'200 | 102'200 | 115'900 | 20'550 | 6'850 | 20'550 |
| contractual services, logistics, | Expenditures as of 31.12.96 | 70'181 | 4'255 | 64'523 | 19'833 | 74'884 | 79'785 | 41'321 | 120'399 | 7'480 | 7'420 | 90 |
| equipment, other acquisitions, services, | Planned expenditures 31.12.97 | 87'133 | 139'856 | 76'253 | 28'703 | 75'894 | 107'512 | 40'921 | 146'119 | 14'974 | 14'917 | 1'081 |
| miscellaneous | Expected balance 31.12.97 | -32'883 | -37'656 | 5'397 | 73'497 | 60'556 | -5'312 | 61'279 | -30'219 | 5'576 | -8'067 | 19'469 |
|  |  | SG 1 | SG 3 | SG 4 | SG 7 | SG 8 | SG 9 | SG 10 | SG 11 | CPM | SC | CVC |
| Total direct costs | Resources 1996-97 | 224'544 | 358'510 | 319'240 | 358'510 | 508'628 | 376'655 | 358'510 | 396'790 | 565'405 | 267'028 | 154'215 |
| Staff costs, other direct costs and | Expenditures as of 31.12.96 | 134'297 | 4'255 | 126'183 | 82'374 | 165'531 | 189'402 | 70'984 | 277'974 | 53'224 | 45'821 | 16'439 |
| miscellaneous | Planned expenditures 31.12.97 | 305'002 | 251'786 | 266'626 | 163'298 | 243'911 | 331'843 | 137'341 | 416'712 | 656'931 | 159'847 | 70'084 |
|  | Expected balance 31.12.97 | -80'458 | 106'724 | 52'614 | 195'212 | 264'717 | 44'812 | 221'169 | -19'922 | -91'526 | 107'181 | 84'131 |
| INVOICED COSTS |  | SG 1 | SG 3 | SG 4 | SG 7 | SG 8 | SG 9 | SG 10 | SG 11 | CPM | SC | CVC |
| Translation, typing and reproduction | Resources 1996-97 | 272'853 | 181'901 | 545'705 | 272'853 | 773'083 | 318'329 | 272'853 | 636'656 | 318'329 | 45'475 | 45'475 |
| of documents | Expenditures as of 31.12.96 | 141'897 | 154'039 | 208'133 | 241'801 | 691'406 | 308'645 | 40'077 | 326'655 | 49'943 | 54'516 | 7'660 |
|  | Planned expenditures 31.12.97 | 537'063 | 248'944 | 589'097 | 291'411 | 731'671 | 451'180 | 97'416 | 620'806 | 330'822 | 168'204 | 26'567 |
|  | Expected balance 31.12.97 | -264'210 | -67'043 | -43'392 | -18'558 | 41'412 | -132'851 | 175'437 | 15'850 | -12'493 | -122'729 | 18'908 |
|  |  | SG 1 | SG 3 | SG 4 | SG 7 | SG 8 | SG 9 | SG 10 | SG 11 | CPM | SC | CVC |
| GRAND TOTAL | Resources 1996-97 | 497'397 | 540'411 | 864'945 | 631'363 | 1'281'711 | 694'984 | 631'363 | 1'033'446 | 883'734 | 312'503 | 199'690 |
| Direct and invoiced costs | Expenditures as of 31.12.96 | 276'194 | 158'294 | 334'316 | 324'175 | 856'937 | 498'047 | 111'061 | 604'629 | 103'167 | 100'337 | 24'099 |
|  | Planned expenditures 31.12.97 | 842'065 | 500'730 | 855'723 | 454'709 | 975'582 | 783'023 | 234'757 | 1'037'518 | 987'753 | 328'051 | 96'651 |
|  | Expected balance 31.12.97 | -344'668 | 39'681 | 9'222 | 176'654 | 306'129 | -88'039 | 396'606 | -4'072 | -104'019 | -15'548 | 103'039 |

______________