| INTERNATIONAL TELECOMMUNICATION UNION |  |
| --- | --- |
| TELECOMMUNICATION DEVELOPMENT BUREAU ITU-D STUDY GROUPS | RGQ16/2/008-E 22 February 2000 Original: English only |
| Meeting of Rapporteur’s Group on Question 16/2 Geneva, 23-25 February 2000 |  |

Question 16/2: 	Preparation of Handbooks for developing countries

###### STUDY GROUP 2

SOURCE:	TELECOMMUNICATION DEVELOPMENT BUREAU (BDT)

TITLE:	DRAFT MANUAL ON NEW TECHNOLOGIES AND NEW SERVICES: PROGRESS REPORT

________

# PROGRESS REPORT

| Chapter | FASCICLE H.1 | Author | Status | Comments |
| --- | --- | --- | --- | --- |
|  | NEW TECHNOLOGIES SUPPORTING NEW NETWORKS |  |  |  |
| 1. | Introduction and general review | Ms. Gospic | To be redrafted. |  |
| 2. | New transport media technologies (optical fibers, radio, satellite) | Mr. F. Rahe, Alcatel Mr. R. Parlow, Iridium Mr. C. Hyde, ICO Global Communications? Mr. P. Mege, Thomson | - Contributions received for optical fibers and satellite aspects. - Contributions on radio aspects by Mr. Mege are expected by February 2000 - no contribution from ICO | For Satellite systems Mrs. Gospic made the contribution using the documents form old version of the Handbook. This contribution is updated by Mr. Parlow contribution |
| 3. | Digital switching systems |  | No contribution received | We need a contributor for the other aspects of digital switching systems: Dr. M. Jagodic is proposed by Natasa |
| 4. | New signalling systems and SS No7 | Mr. Distler, France | Contribution received. |  |
| 5. | Synchronization technics and methods | Mr. Y. Shmaliy, Ukraine | Contribution received. | The title was changed from Synchronization systems and methods. |

| Chapter | FASCICLE H.1 | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 6. | Digital transmissions (SDH, WDM, ATM, xDSL) | - W. Widl, Sweden (SDH, WDM, ATM, xDSL) - Mr. Antoine Nehme from Ericsson on ATM | Contribution received. | Final version for ATM was prepared with contributions from Mr. Widl, Mr. Nehme and Dr. Reljin. |
| Coordi-nation work |  | Editor to be recruited |  |  |

| Chapter | FASCICLE H.2 | Author | Status | Comments |
| --- | --- | --- | --- | --- |
|  | TELECOM SYSTEMS, NETWORKS AND SERVICES |  |  |  |
| 1 | Introduction and general review | Ms. Gospic | To be redrafted when all contributions are received |  |
| 2 | Digital switched networks and services (PSTN, ISDN, IN, X.25, Frame relay, ATM) | Mr. L. Chae Sub Chairperson, ITU-T, WP 1/13 Mr. F. Rahe, Alcatel | Contributions received. |  |
| 3 | Satellite networks | Mr. R. Parlow, Iridium Globalstar Mr. C. Hyde, ICO Global Communications | No contribution received for all. |  |
| 4 | Mobile digital cellular systems, networks and services | Mr. J. Costa, Nortel Networks | 1Contribution not received | There are two handbooks available on both subjects. Mrs. Gospic used the Alcatel contribution to create the subchapter Fixed-mobile convergence. This Chapter should be elaborated. |

| Chapter | FASCICLE H.2 | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 5 | Local (access) networks | Mr. J. Costa, Nortel Networks Mr. P. Mège | No contribution received from Mr. Costa. Contribution received from Ericsson Lebanon Contribution from Mr. Mege expected in Feb. 2000. | Another contribution “Mobility in the network” has been used for Chapter 1. |
| 6 | Network and service management | Mrs. N. Gospic, Community of Yugoslav PTT | Contribution received. |  |
| 7 | Planning aspects | Mr. N. Kisrawi | No contribution received. | Corrections of the existing document have been and two Annexes added. |
| 8 | HRD | Alcatel | Contribution received for the Annex. | This Chapter from existing document should be amended. |
| 9 | Financial and economic aspects | Mr. N. Kisrawi, Chairman ITU-D SG2 | New contribution not received. | Adaptation of the existing document is to be done. |
| 10 | Case studies and Annexes | Mr. Hua Jieping, China | Contribution received. | Addition of case studies to be considered during February meeting. |
| Coordi-nation work |  | Editor to be recruited |  |  |

| Chapter | FASCICLE H.3 | Author | Status | Comments |
| --- | --- | --- | --- | --- |
|  | DIGITAL IP BASED NETWORKS AND SERVICES |  | Contribution received | Addition of a subchapter: ITU publication |
| 1 | Introduction and general review | Mr. Embro and Mr. Nehme, Ericsson | Contribution received | Need to co-ordinate with the manual: “Internet for Development” In the received contribution Mme Gospic. |
| 2 | Internet protocol-IP | Mr. Embro and Mr. Nehme, Ericsson | Contribution received |  |
| 3 | Internet | Mr. Embro and Mr. Nehme, Ericsson | Contribution received |  |
| 4 | E-Commerce | Mr. Embro and Mr. Nehme, Ericsson | No contribution received |  |
| Coordi-nation work |  | Editor to be recruited | Recruitment of an editor not planned in the budget. The contributions received should be coordinated with the above-mentioned |  |

| ###### Chapter | ###### FASCICLE H.4 | ###### Author | ###### Status | ###### Comments |
| --- | --- | --- | --- | --- |
|  |  | ### ABU is the author for Chapters 1 to 4. |  |  |
| 1. | Introduction and general review |  | Contributions expected for February 2000. |  |
| 2 | Digital audio broadcasting |  | Contributions expected for February 2000. |  |
| 3 | Digital television broadcast services |  | Contributions expected for February 2000. |  |
| 4 | Planning strategies for digital television broadcasting |  | Contributions expected for February 2000. |  |
| 5 | MVDS, MDDS |  |  | Document exists. |
| Coordi-nation work |  | Editor to be recruited. |  |  |

###### SUMMARY OF CONTIBUTIONS RECEIVED

| Fascicles | Missing Chapters | Comments |
| --- | --- | --- |
| 1 | 2 (Sub Chapter radio systems), 3 |  |
| 2 | 3, 4 (3rd generation of mobile is missing) |  |
| 3 | OK |  |
| 4 | No contribution received. |  |

______

Contribution for the Fascicle 3 is received from Mr. Ghazal, Mr. Nehme and Mr. Embro