PAGE  

	[image: image1.wmf]
	INTERNATIONAL TELECOMMUNICATION UNION
	

	
	Council Oversight Group (COG)
	Document COG-04/4-E

10 September 2003

English only

	GENEVA    —    FOURTH MEETING    —    (17 SEPTEMBER 2003)


Report by the Secretary-General

ITU NEAR TERM RECOMMENDATIONS

I.
INTRODUCTION

The 2003 Ordinary Session of Council adopted 10 near-term recommendations that had been proposed by the Group of Specialists (GoS) established under Decision 7 of the Marrakesh Plenipotentiary Conference (Res. 1210).  That Resolution called on the Secretary–General, in consultation with the Coordination Committee, to implement with immediate effect R. 2, 4-6, 8-9 and 13-15.   It requested the Bureau Directors to immediately implement R.3.  In addition, in Annex 3 to Res. 1210, the Council requested the Secretariat to prepare 8 reports on matters related to the budget and finances of the Union.

The 2003 Council also established the Council Oversight Group (COG), one main purpose of which is to monitor the implementation of the near-term recommendations.  The Chairman of Council chairs the COG.  The terms of reference of the COG state that the near-term recommendation should be implemented by the time Council 2004 meets, or earlier if possible (Res. 1210, Annex 2). The COG has held four physical meetings since the May session of Council:  5 June, 24 June, 16 July (Paris) and 17 September.  Summary of the Decisions of each meeting have been posted on the COG website and circulated to Member States.

Immediately following the conclusion of the May 2003 Council, the Secretariat developed a plan for the implementation of the near-term recommendations, as well as for preparation of the 8 reports required under Annex 3 to Res. 1210 concerning principles and conditions for the draft budget 2004-05.  This Plan and timetable was approved by the Coordination Committee (CoCo) at its meeting on 29 May 2003 (see Annex A, distributed to the COG at its first meeting).
The Plan focused on the need to establish priorities for the work and also established a timetable for reporting to the COG and to the Council on the action taken.  The Plan reflected the commitment of the elected officials for the timely and full implementation of the near-term recommendations.  The timetable proposed a staggered set of deadlines, recognizing that some of the recommendations could be immediately implemented, while others called for further study and analysis to determine the most appropriate action.  As noted by the Secretary–General in his report to Council (C03/42) elements of some of the near-term recommendations had already been implemented.  The Plan adopted by the Coordination Committee was submitted to the first meeting of the COG on 5 June 2003 and was supported.

To implement the recommendations, the Coordination Committee assigned a focal point for each of the 10 near-term recommendations.  A similar approach was adopted with respect to the work requirements set forth in Annex 3 to Council Res. 1210.

The role of the focal point is to: (1) assemble a project team from the General Secretariat and the Bureaux to work on the recommendation or report (2) prepare a detailed work plan showing how the recommendation will be studied and implemented, with staff and resource implications (3) provide periodic written progress reports to the COG Secretary (4) prepare and submit a report to the CoCo by the deadline, where required, and (5) prepare the final report for the COG by the deadline.  Focal points were designated in mid-May and they submitted their work plans by end May 2003.  

The Secretariat provided an interim progress report on implementation of all the near-term recommendations to the COG at its third meeting on 16 July in Paris.  In addition, reports on specific recommendations have been provided to COG meetings.  As a matter of priority, the COG has emphasized the need for rapid action on near-term recommendations concerning TELECOM (R.14-15) and the Information Services (IS) Department (R.6).

II.
ACTIONS TO DATE

This section summarizes the actions already taken by the Secretariat to fulfill the requests of the Council as expressed in Res. 1210.  A more complete description of actions taken with respect to each near-term recommendation and the reporting requirements in Annex 3 are set forth in Annex B.
Fully implemented

The following near-term recommendations have been fully implemented through final reports submitted to COG and /or the additional session of Council:

· R.9 (function and responsibilities of SPU)

· R.13 (quarterly report to Council) 

· R. 15.2 (TELECOM administrative budget)

Work is well advanced to implement R.2 (modifications to the Financial Regulations on budget preparations) and on R. 5 (internal audit function), namely through recruitment of an internal auditor.  The final report on prioritization of sector activities (R.3) awaits the fall meetings of the sector advisory groups.

Concerning the reports required under Annex 3 to Res. 1210, the following subsections have been fully implemented through the providing of final reports to the COG and/or Additional Session of Council:

· 1a (cost reduction plan)

· 1b (staff reduction plan)

· 1l (WSIS Finances)

· 1n (new budget format) and

· 1n (Financial Implications of SPU involvement in TELECOM) 

Partially implemented

Preliminary reports have been submitted to COG on:

· R. 6 (IS Department)

· R.14 (TELECOM re-organization)

· R.15.1 (External Audit of TELCOM cost methodology)

  Preliminary status reports on R.8 (review of Secretariat functions) and 1m (use of languages) are set forth in Annex B.

*******

ANNEX A

(distributed to COG at its first meeting)

ANNEX B

NEAR-TERM COUNCIL RECOMMENDATIONS (Res. 1210)
R.2
Process for Preparation and Review of Budget 


Focal Point: 
Chief, Finance Department

Deadline:  The Finance Department will provide its proposed modifications to the financial regulations directly to the Council Working Group chaired by Mr. Bruce Gracie, which will hold its first meeting on 2-3 October 2003.

R.3

Prioritization of Sector Activities



Focal Points: 
Deputy-Director, BR; 




Deputy-Director, TSB; 




Deputy-Director, BDT.

Deadline: Report to CoCo by late Nov. 2003  (Note: this deadline accommodates scheduled meetings of Sector Advisory groups.)

ITU-R

1. Objectives:

1.1. To meet the goals and objectives set in the ITU Strategic Plan for the ITU-R Sector.

1.2. To carry-out the activities mandated by the Radio Regulations

2. Work Plan

2.1. The ITU-R was the first Sector to adopt a two-year Operational Plan, which was endorsed by the Radiocommunication Advisory Group (RAG) for 2002-2003.

2.2. ITU-R is currently developing its four-year Operational Plan for 2004-2007.

2.3. Consultation of the RAG will take place during its meeting in November 2004.

3. Preliminary views

As most of the work undertaken by the BR is mandated by the Radio Regulations, BR is not in a position to propose prioritization that would foresee low priority/deletion of some of that work. The main areas of activity are:
1. Processing of Terrestrial and Space notices (workload dictated by the number of notices received from Administrations). This includes development of specialized technical and administrative software as well as the maintenance of the ITU-R website data.

2. Study Group meetings (decided by Members within available budget).

3. Treatment of Harmful Interference Reports.

4. Conference preparation, both WRC and RRC (difficult to reduce, ever increasing).

5. Radiocommunication seminars (within available time and budget).

6. Regulatory publications, as defined in the Radio Regulations.

7. Other publications on a cost recovery basis.

4.
Operational Plan 2004-2007

The bi-annual ITU-R Operational Plan has been reviewed by the RAG before its implementation so that Member States and Sector Members had the opportunity to provide advice to the Director on prioritization. This Operational Plan is already presented on an activity basis. Due to budgetary constraints, the next RAG meeting will be held only in November 2004. Consequently, the Operational Plan for 2004-2007 will need to be implemented on a temporary basis until the ITU-R membership can comment on it.

ITU-T

TSB will complete the ITU-T Operational Plan for 2004 and 2005 by 5 September 2003. The document will be posted on the TSAG-website and be discussed by TSAG at its meeting from 10-15 November 2003. In addition, TSB is preparing various input documents for the November TSAG meeting that reflect on the achievements of 2003 and outline the objectives for 2004. The suggestions of TSAG will be incorporated, and the Operational Plan for 2004 and 2005 will be submitted to Council.

ITU-D

1. Objectives

1.1.
To meet the goals and objectives set in the ITU-D strategic plan and the Istanbul Action Plan (IsAP).

1.2
To prioritize/ rationalize the actions requested by the membership within the priority 
areas defined in the IsAP and the ITU-D strategic plan.

1.3
The goals and objectives as well as the priority areas of the ITU-D for the period 2004-2007 have been approved by WTDC-02 and PP-02.  Following Council Resolution 1210, and in close collaboration with TDAG, measures have already been taken to reduce costs and maximize the benefits of ITU-D activities for the membership prioritizing the concrete actions according to its urgent needs. 

2. 
Work Plan

2.1 Elaboration of Guidelines for the preparation of the ITU-D four year Operational plan 2004-2007 (ITU-D OP 04-07) – June 2003.

2.2 Prioritization of the Actions in ITU-D Operational Plan for 2003 – July 2003.

2.3 Consultation of ITU-D membership about the concrete priorities in the elaboration of ITU-D OP 04-07 – July 2003.

2.4 Preparation of the ITU-D OP 04-07 – September 2003.
2.5 Consultation with TDAG on the ITU-D OP 04-07 (especially for year 2004) – January 2004.

2.6 Regular updating of the Guidelines in consultation with the TDAG – yearly

2.7 Regular updating of the 4 year ITU-D OP 04-07 in consultation with the TDAG and the ITU-D membership - yearly

3. 
Work done so far

The Guidelines for the preparation of the ITU-D OP 04-07 were elaborated, discussed and sent to all BDT “P “ staff. The Guidelines emphasize the project approach. The projects are aiming at the goals of the ITU-D Strategic Plan, thus combining the objectives of Istanbul Action Plan (IsAP) Programmes and Initiatives and the PP-02 decisions. They should have tangible, measurable and achievable results. The projects should be prepared in consultation with the developing countries and should reflect the most urgent (priority) needs of the countries in the framework of the IsAP Programmes and Initiatives. Separate Actions also can be proposed in order to complete the achievement of the expected results.

3.1. The implementation of the ITU-D Operational Plan for 2003 was thoroughly evaluated by TDAG and the subsequent recommendations adopted by this body were carefully analyzed. In consultation with the recipient countries, a number of planned actions were identified and cancelled or postponed because they were not considered as top priorities. This resulted in savings which amount to more than 2 million CHF.

3.2. The ITU Regional Offices have been requested to check with the countries priority activities for the next 4 years period. As an example, Africa Regional Office sent a special questionnaire to all countries in order to match priority areas defined in the IsAP and the ITU-D strategic plan with the most urgent needs of the countries. The answers received by Africa RO helped in preparing accurate proposals for the next Operational plan. In addition the regional telecommunication organizations were consulted. For example in Americas a proposal for a large project was jointly prepared by ITU and CITEL.

R.4
Cost-Accounting Process

Focal Point:
Chief, Finance Department

Deadline:  Report to CoCo by October 2003

1
The Group of Specialists proposes that a consulting firm be recruited to assist the ITU in implementing Recommendation. 4.

2
The terms of reference which could be used should be established by the Group of Specialists and ITU as a basis for an international call for bids.

3
In the terms of reference, special consideration should be given to the financial system currently in use in ITU, particularly the SAP system.

4
The Finance Department is requesting the participation of the Sectors and the IS Department to elaborate a first report to be submitted mid-October to the Coordination Committee.

R.5
Enhance internal audit functions

Focal point:
Chief, Personnel Department

An APB was held on 29 May 2003 and a short list established to recruit an internal auditor. A first round of interviews with the seven short-listed candidates, some by telephone and some in person, was held during July. A second round of interviews in person with five remaining candidates with the Secretary-General and members of the Coordination Committee will be held early September. An appointment may be made before end September.

R.6
Current Use of Information Systems at ITU

Focal Point: 
Chief, IS Department

Deadline:  Report to CoCo by October 2003

1
The Chief of the IS Department provided oral and written status reports to the COG at its 2nd and 3rd meetings.  These reports informed on the recommendation that had been made by the External Auditor in 2001 as well as actions taken to date and provided some comparison with IT spending at comparable organizations.  To better compare ITU’s ICT expenditures with those of other organizations, the Deputy Secretary-General sent a questionnaire requesting information to other agencies by 15 September 2003.  The replies should be compiled and available by early October.

2
The new organization for the IS Department is detailed in Service Order 03/14, effective 1 September 2003.  Priority would be given to implementation of projects including HRM, storage capacity and SAP usage.

3
The Strategic Plan will include a detailed description of the status of ICT technologies at ITU.   Its extended outline may be made available to COG by early October.  The Strategic Plan itself is being worked on with a wide consultation within the IS Department, and with the participation of ITU Sectors and User departments. The Plan will be refined with an external consultant. 

R.8
Review of Various Functions to Reduce Duplication

R.8.1
Library, Archives and Reference services

Deadline:
Report to CoCo by Sept. 2003

1) Working arrangements
The group on “Library and Archives services” was composed of representatives from the Common Services Department, the Conference Department, The General Secretariat Coordination Unit and the Telecommunication Standardization Bureau, namely: Ms. Kristine Clara, Ms. Claude Briand, Ms. Patricia Janin, Ms. Marie-Laure Schifferli, Ms. Evelyne Metz, Mr. Dimonique Pittet, Mr. Thierry Berrod, Mr. Serge Dubois, Mr. Nelson Verastegui.

This group met three times; on the 24th of June, the 8th of July and the 26th of August. It is planned to have its final report will be available by the end of September 2003.

2) Overall considerations
As far as the tasks carried out by the Reference Service of the Conference Department and those of the Library Service of the Common Services Department are concerned, the study shows there is no duplication. Furthermore, it has been confirmed that continuation of both services is very important. 

Although the timing of this study made the task difficult due to multiple priority tasks throughout the secretariat, the study proved to be beneficial in that it has identified potential actions to improve effectiveness of the tasks in question. 

The above-mentioned final report will include a preliminary indication of some improvements and enhanced effectiveness that the study has identified.

R.8.2
Functions of Corporate Communications, publications, documentation

Focal Point: 
Chief, Common Services

Deadline:
Report to CoCo by Nov. 2003

1. Work plan summary

· Study objective: elimination of any duplication of work and of inefficient use of resources. 

· Scope of functions / activities: the functions involving corporate communications, publications, documentation, document control and marketing.

· The study comprises three phases. Phase 0 is to form a Task Management Team (TMT).

· Objective of Phase I is to document the basic facts regarding each function under review. To do this, design and distribute two questionnaires, one to the manager of each service-provider unit concerned, and the second to the respective users concerned (within the secretariat only). The end-users who are outside the secretariat (e.g. customers of ITU publications) were excluded from the scope of the study due to lack of time and resources.

· Objective of phase II is to identify and evaluate concrete improvements for increased effectiveness, both relating to working methods and tools and relating to organisational changes.

2. Actions to date

TMT was constituted.  After review by TMT, the first questionnaire to service provider units was distributed by Email to the service-providers concerned. The second questionnaire to users has been designed based on the same criteria and methodology as the first questionnaire. It is planned to distribute it after review by TMT in September 2003. 

3. Preliminary recommendations

There are currently two QuickPub teams handling the publication of ITU-T Recommendations in two different departments of the General Secretariat. Integration of both teams within the Conferences Department is part of the draft budget. 

It is too early for other suggestions or recommendations. 

4. Financial implications
In spite of the usage of Email and electronic methods, this complex study is very effort intensive. Budgetary implications of the final recommendations will be part of the final report to the council in 2004.

R.8.3
Cost of Travel Processes

Focal Point: 
Chief, Personnel Department

Deadline:  Report to COG by Oct. 2003

A first meeting of a small working group consisting of members of the Personnel and Finance Departments has been held on 30 July. A second meeting will be held early September and a report will be submitted towards the end of September.

R.8.4
Management of Facilities and Building

Focal Point:
Chief, Common Services

Deadline:  Report to COCO by Sept. 2003

1. Work plan summary

· Study objective: how to ensure that the management of facilities and buildings is both efficient and effective. 

· Scope of activities: a) major works for the maintenance of facilities and buildings; and (b) management and allocation of office space. Security-related functions are considered outside the scope of this study. It is proposed to recreate the Building Committee, with a revised variable membership to include one bureau representative on a rotation basis. The Task Management Team is established and will prepare a revised service order on the mandate and composition of the Building Committee. 

2. Actions to date

There have been two meetings of the TMT to date. Part (a) of the scope of the study has been analysed, and an analytical report for COCO is under preparation for September 2003.  

3. Preliminary recommendations

It is too early for any suggestions or recommendations. 

R.8.5
Allocation of more costs for services to users

Focal Point: 
Chief, Finance Department

Deadline:  Report to CoCo by Nov. 2003

This Recommendation being closely linked to Recommendation 4, it will be considered at the same time.

R.9
Functions and Responsibility of SPU

Focal Point: 
Chief, SPU

Deadline:  Report to CoCo and COG done in July 2003

A report describing the history and function of the SPU and proposing a mission statement for the Unit was considered and revised by the CoCo on 7 July 2003 and reviewed by the COG on 16 July 2003.  COG members emphasized the need to avoid duplication between the work of the sectors and the function of the SPU.  The document is appended to this report.

R.13
Report to Council every 3 months

Focal Points: 
Chiefs, SPU and Finance Department

The draft format of this report was approved by the CoCo in early September 2003 and a first report will be provided to the Additional session of Council.

R.14
Reorganize TELECOM along Project Lines

Focal Point: 
Business Manager, TELECOM

Deadline:  Report to CoCo by November 2003.

 

Team

1
A project team has been established, including staff from TELECOM, SPU, Staff Council, Finance and Personnel.  The team has held four meetings.

Estimated Timetable:

August 2003:  
Revise core budget for Telecom and cost recovery and other direct costs

September 2003: 
Presentation to TMT and Telecom Staff

September 2003:
Discussion of scenarios for reorganization of Telecom - taking into account potential consequences of staff cuts including those of non- Telecom staff paid by Telecom in the context of the reduced budgets 

October 2003:
Presentation to TMT and Telecom staff

November 2003:
Report to COCO

December 2003:
Revision based on comments from COCO

January 2004:
Presentation of revised proposal to SG

February 2004:
Report to COG

March-May 2004:
Prepare potential reorganization agreed by COG

June 2004:
Implementation of potential reorganization agreed by COG

2
In an effort to use Telecom resources more effectively and improve efficiency, the Working Group for Recommendation 14 is preparing a proposal for the reorganization of Telecom.

3
Obviously central to successful ITU Telecom operations over the next two years is the budget. WG14 has concluded that the number of staff, post-reorganization, should depend on the budgets for the events. The first and most urgent task, therefore for the Working Group was to establish a sustainable TELECOM budget for 2004-2005, which must be presented to the additional Council in October 2003 (see Resolution 1210, Annex 3, recommendation n).

4
The Working Group analyzed the income from earlier events in the periods 1999-2000, 2001‑2002, and the most recent budget of 2002-2003.  Based on this information and the experience of the Working Group, an estimate of potential income for 2004-2005 was determined.  As a result of discussions during ITU Council in May, the Secretary General proposed that the frequency of the future Telecom events be once again discussed at the next ITU Telecom Board meeting, which will take place in October/November 2003. 

5
ITU has projected income reduced by around 4% for the 2004-2005 draft budget, compared to the 2002‑2003 budget.

6
ITU Telecom, which is not a part of the regular ITU budget, expects to be hit harder than the ITU because the telecommunications industry has experienced a strong downturn in the market and is spending remarkably less on exhibitions and sponsorships. This downturn in the market is affecting telecommunications events worldwide.

7
For ITU Telecom World 2003, Telecom has sold only approximately 37,500 m2 of indoor ground level exhibition space, received cancellation fees for 2,500 m2 and has gross area of approximately 5 000 m2 in Telecom Village, compared with peak sales of 64 500 m2 net sold space in 1999. For Africa 2001 and Asia 2002 approximately 57% and 41% less space was sold than for the previous Africa and Asia events. Despite signals of the start of a recovery, income from ITU Telecom events is expected to increase slowly and it will take considerable time to reach pre-1999 levels.

8
Naturally, to establish a sustainable budget for 2004-2005, expenditure levels must be reduced in proportion to the reduction in income foreseen for the smaller events in 2004‑2005.  Based on estimated lower income figures foreseen from smaller events in 2004‑2005, core expenses should not exceed a ceiling of 19,8 million CHF for the budget period of 2004‑2005. This would result in a reduction of 28% of the approved budget for 2002-2003 of 27.5 million CHF, and of approximately 10% over anticipated expenditure, 2002‑2003.  This budget reduction for 2004-2005 would mean a reduction of staff months from 1,347 for the 2002-2003 budget to around 1,075 for the 2004-2005 budget (20%). The staff cost estimates should decrease from a total of 16.7 million CHF for 2002-2003 to 12.8 million CHF for 2004‑2005.

9
This reduction of core expenses will have a significant impact on how Telecom is reorganized, how it operates, from whom it buys its services (in-sourcing/out-sourcing), and the level of services it is able to offer to ITU membership and TELECOM clients (-25%). 

10
The Working Group will therefore begin to look into if and how Telecom could be organized with reduced staff and whether or not this can be done without reducing the quality of services to its clients. We will identify which functions are essential to operate successfully in the future and which functions and tasks can be reduced, cut or outsourced. We will also review the non-Telecom ITU services and staff that Telecom pays for to determine which will be retained, which reduced and which eliminated in order for Telecom to survive. 

R.15.1
External Audit of TELECOM Costing Methodology

Focal Point:
Internal Auditor

To implement this recommendation, the Secretary-General, following consultation with the COG, sent a letter to the Swiss External Auditors on 8 July 2003 requesting an audit of the TELECOM costing methodology and proposing Terms of Reference for the audit.  On 30 July 2003, the Swiss auditor replied that it would not be able to conduct this audit by the deadline. Pursuant to this reply, the Secretary-General requested the external auditor to specify a period during which his office could undertake the study and a date at which it could be produced.

R.15.2

Council Approval of TELECOM Administrative Budget

Focal Point: 
Telecom Financial Officer

At its second meting, the COG reviewed a secretariat report and proposed timetable for preparation of the TELEOCM budget.  The draft budget guidelines were submitted to the COG at its third meeting and revised on the basis of comments made by Committee members, including the need t itemize source of revenue.  The administrative budget of TELECOM was submitted to the COG at its fourth meeting.

LIST OF PRINCIPLES AND CONDITIONS TO REVISE BUDGET (Res. 1210; Annex 3)

1a
Cost Reduction Plan

Focal Point:  
Chief, Finance Department

Deadline:  Done

This plan was submitted to the 2nd meeting of the COG for approval.  The COG stressed that further cost reductions should be achieved through implementation of the Specialist recommendations.
1b
Staff Reduction Plan


Focal Point:  
Chief, Personnel Department

Deadline:  Done

The COG indicated that the staff reduction plan should be applied flexibly to minimize the impact on staff and should serve as a basis for budget calculations.  Council should be made are that the plan would result in a real decline in the quality of services in some areas and might hamper the ITU in adapting to the new environment.

1i
Strategic Plan on Information System

See report under R.6.

1k
Clear billing procedures

Focal Point: 
Chief, Finance Department

Deadline:  Report to CoCo by Nov. 2003

These billing procedures should be established in collaboration with the Sectors and the service providers and should take into consideration the results of the Working Group on the review of the methodology applied for the satellite network filings.

A report will be prepared in November.

1l
Report on WSIS Finances

Focal Point:  
Chief, Conference Department

Deadline:  Done

This Report was submitted to the COG at its fourth meeting and is separately submitted to the Additional session of Council.

1m
Use of Languages

Focal Point:  
Chief, Conference Department

Deadline:  Report to CoCo by Nov. 2003

1. Pursuant to Resolution 115 (Marrakesh 2002) entitled “Use of the six official and working languages of the Union on an equal footing,” the ITU is to set the date of 1 January 2005 as the date by which all ITU work will be carried out in the six official and working languages of the Union on an equal footing.  Pursuant to that resolution, a plan is required for the transition to the use of the six official and working languages on an equal footing in all of its spheres of activity, along with a concrete assessment of the funding that will be required to implement the plan; this should be in the form of a separate document.  The full funding requirements necessary for the effective use, from 1 January 2005, of all six languages of the Union on an equal footing, should be listed as a separate item in the ITU budget.  It is noted, however, pursuant to Resolution 115, that some work in ITU (for example working groups, study groups, and regional conferences) might not require the full use of all six languages.

2
Pursuant to Resolution 115 (Marrakesh, 2002) an ITU working group, on the establishment of a “transitional plan” concerning the implementation of this Resolution, has been created. This working group is composed of one representative of each Bureau and one representative of each Department of the General Secretariat.  Also, inside the Conference Department, the six chiefs of the translation sections will be deeply involved in this work, in particular by supporting and advising the Chief of Conference Department, as appropriate.

3
Due to unforeseen delays in the appointment of the new Chief of Conference Department, the initial work programme has been delayed. Table below shows the revised work programme.

	Date/Period
	Activity
	Responsibilities

	Early September
	Circulation of report framework for comments and approval
	Focal point

	End September
	Solicit, coordinate and collate inputs for preparation of draft report
	All sectors and General Secretariat

	Early October
	Prepare draft report


	Focal point

	Mid-October
	Discussion and approval of draft report
	All sectors and General Secretariat

	Mid-November
	Submission of final report to COG secretary
	Focal point

	End November
	Submission of report to CoCo
	


1n
Presentation of new Budget Format

Focal Point:  
Chief, Finance Department

Deadline:  Done

A revised budget format was submitted to the COG at its 2nd meeting.

1n
Financial implications of SPU involvement in Telecom
[See report under R.9]

__________

�  The members of the COG are:  Brazil; United States; Portugal; Switzerland; Kenya; Senegal; Bulgaria; Russia; Iran and Korea. 





13

