Page 4

	INTERNATIONAL  TELECOMMUNICATION  UNION
	

	[image: image1.wmf]
	COUNCIL WORKING GROUP ON THE WORLD SUMMIT ON THE INFORMATION SOCIETY
	Document: WG-WSIS- 10/4 Rev. 1

	
	
	Date: 13 September 2006

	
	
	English only

	10th meeting, Geneva    —   12-13 September, 2006
	

	
	

	Note by the ITU Secretary-General

	WSIS Implementation plan within itu


At the June 27-28 2006 meeting of the Council Working Group on the elaboration of the draft strategic and financial plans 2008-2011
, a request was made for a document detailing the planned implementation of WSIS within ITU and the division of labour between ITU Sectors and departments.

The table below is based on an internal memo circulated by the ITU Secretary-General in May 2006 as well as other relevant inputs (e.g., from WTDC-06, Council 2006, draft financial plan 2008-2011 etc). Please note that this situation continues to evolve, as tasks previously carried out by the WSIS-ES are absorbed by the ITU secretariat.

	Activity
	Allocation of responsibilities within ITU
	Comments

	Multi-stakeholder implementation

	Organisation of Action Line Facilitators/ Moderators meeting (para 108-110 + Annex of Tunis Agenda)
	Lead: SPU, CEC.

Assisted by WSIS-ES  (logistics)

Close coordination with UNESCO and UNDP.
	First meeting held 24 February with closed, informal meeting of CEB members on 23 Feb (Room 21, Palais des Nations).



	Action Line C1 (Role of stakeholders)
	Lead: BDT

Assisted by SPU, CEC
	UN-DESA is the focal point with ITU as co-facilitator. First meeting held on 16 May. 

	Action Line C2 (information and communication infrastructure)
	Lead: BDT.

Assisted by BR and TSB (for standardization issues), SPU (for stocktaking) and CEC (general).
	ITU is focal point, assisted by APC as co-facilitator. First meeting held during WTDC-06 in Doha on 9 March.

Second meeting held 18 May, and electronic follow-up process organised.

	Action Line C3 (Access to Information)
	Lead: BDT.

Assisted by TSB for standards.
	UNESCO is the focal point with ITU as co-facilitator.

	Action Line C4 (Capacity-building) and C7 Theme eLearning
	Lead: BDT.
	UNDP is the focal point with ITU as co-facilitator. First meeting held on 11 May

	Action Line Facilitation Meeting for C5, (building confidence and security in the use of ICTs)
	Lead: TSB.

Assisted by SPU and BDT.

Note: BDT has also been assigned specific responsibilities under Programme 3 and WTDC-06 Res. 45 Res and TSB under WTSA-04 Resolutions.
	ITU is focal point and sole-facilitator. First meeting held 15-16 May, in Geneva, as “Partners for Global Cybersecurity”, which was theme of World Telecommunication Day 2006. A meeting on WTDC Res. 45 is planned for 31 Aug/1 Sept.

	Action Line C6 (Enabling environment)
	-- Internet Governance: see below

-- e-Commerce: Lead: BDT

-- Regulatory issues: Lead: BDT, assisted by TSB and SPU

-- National e-Strategies: Lead BDT

-- Financing mechanisms for SMEs: Lead: BDT

-- Countering spam: Lead: SPU, assisted by TSB and BDT

-- Spectrum management: Lead: BR, assisted by BDT and SPU
	Focal point is UNDP with ITU as co-facilitator. First meeting held on 11 May

	Action Line C7 (ICT Applications) – Theme eGovernment
	Lead: BDT.


	Focal point is UNDESA, with ITU as co-facilitator. First meeting held on 16 May

	Action Line C7, Theme eBusiness
	Lead: BDT.

Assisted by TSB.
	Focal point is UNCTAD with ITU as co-facilitator. First meeting held on 17 May.

	Action Line C7, Theme eLearning
	See C4 above
	

	Action Line C7, Theme eHealth
	Lead: BDT.

Assisted by TSB and SPU.
	Focal point is WHO with ITU as co-facilitator. First meeting to be held in October 2006.

	Action Line C7, Theme eEmployment
	Lead: BDT.
	Focal point is ILO with ITU as co-facilitator. First meeting held on 17 May.

	Action Line C7, Theme eEnvironment
	Lead BDT.

Assisted by TSB and BR.
	Focal point is WMO, with ITU as co-facilitator.

	Action Line C7, Theme Agriculture
	Lead BDT
	Focal point is FAO, with ITU as co-facilitator.

	Action Line C7, Theme eScience
	Lead BR.

Assisted by TSB.
	Focal point is UNESCO, with ITU as co-facilitator.

	Action Line C8 (Cultural diversity and identity, linguistic diversity and local content)
	TSB, assisted by BDT.
	Focal point is UNESCO. First meeting held on 12 May, ITU and UNESCO co-organised a workshop on promoting the multilingual Internet on 9-11 May, in Geneva.

	Action Line C9 (Media)
	No ITU lead nominated.
	Focal point is UNESCO.

	Action Line C10 (Ethical dimensions)
	No ITU lead nominated.
	Focal point is UNESCO.

	Action Line C11 (International and regional co-operation)
	Lead: CEC

Assisted by  Sectors.
	Focal point is UN-DESA with ITU as co-facilitator. First meeting held on 15 May.

	ITU action related to specific paragraphs of the Tunis Agenda

(see also below under Internet Governance)
	26(g) and 90:  actions to bridge the standardization gap (TSB)

91:  work on Emergency Telecom Services and Telecoms for Disaster Relief (TSB and BDT)

92:  action to provide numbers for child helplines (TSB)

59:  work on QoS and network management (TSB)

93:  Technology Watch (TSB)


	

	UN system-wide implementation

	Creation and Operation of UN Group on the Information Society (UN GIS) (para 103)
	Lead: CEC

Assisted by   SPU.


	ITU participation in meeting of HLCP, 27-28 Feb, and in CEB meeting in Madrid in April.

ITU invited to chair UNGIS during first year. First meeting held on 14 July, in Geneva.

	Report by UN Sec-Gen to ECOSOC on modalities of system-wide coordination (para 104)
	Lead:  CEC 

.


	Report to ECOSOC meeting in July 2006 in Geneva.

	Revision of mandate of CSTD (para 106)
	Lead: CEC 

Assisted by SPU.
	Review meeting, 13 Feb.

Main CSTD session May 15-19 2006, in Geneva.

	ITU-SG Report to UNGA and UNGA Resolution on WSIS
	Lead:  CEC 
	Discussed by UNGA agenda on 27 March. Resolution adopted on WSSI by UNGA, thanking ITU

	ECOSOC:  WSIS follow-up
	Lead:  CEC
	Discussion in ECOSCOC on 10 July

	Internet Governance

	Creation of Internet Governance Forum (paras 67, 72-79)
	Lead: TSB

Assisted by SPU and BDT.

Focal point for Greece regarding organizational matters:  WSIS-ES Executive Director
	Consultation meetings on, 16-17 February and on 19 May in Geneva. First meeting of advisory committee on 22-23 May.

IGF meeting, 30 October – 2 November, in Athens.

	Public Policy Development Process (paras 68-71)
	Lead: SPU

Assisted by TSB and BDT.
	Consultations taking place in NY.

	International Internet Connectivity (IIC) (paras 27 and 50)
	Lead: TSB (Study Group 3)

Assisted by BDT and SPU.
	Special session of ITU-T Study Group 3 on this topic, 19 June.

	Other implementation issues

	Council WG-WSIS
	Secretariat: SPU

Focal points in Sectors and GS.
	10th meeting held 12-13 September 2006

	WSIS stocktaking and Golden Book (para 120)
	Lead: SPU

Assisted by WSIS-ES, BDT and sectors
	Stocktaking report (first edition) published in November 2005. Database remains open to new entries.

Golden Book published in February 2006. Database closed for new entries in January 2006.

	Maintenance of WSIS website
	Lead:  CEC

Assisted by SPU
	Main website frozen as from 31 January and website now focuses on implementation and stocktaking..

	Publication of WSIS outcome documents, in all languages
	Lead: WSIS-ES.

Assisted by CEC (Coordination Unit), SPU
	WSIS outcome documents published in 6 languages.

	Publication of World Information Society Report
	Lead: SPU.

In partnership with UNCTAD, KADO and others
	New series of annual reports tracking WSIS implementation. Series launched in May and first edition published 5 July 2006.

	WSIS archiving
	Lead: CEC

Assisted by Libraries and Archives Services, WSIS-ES and WSIS content team
	Service order issued.

	Production of “E-Flash”
	Lead: WSIS-ES.

Assisted by SPU, CEC.
	Most recent edition in June 2006.

	Multistakeholder partnership (para 98)
	Lead: BDT.

Connect the World, lead CEC
	Connect the World pavilion to be organised at ITU TELECOM World 2006.

	Partnership for Measuring ICT for Development (para 114 of Tunis Agenda and para 28 of Plan)
	Lead: BDT

Assisted by SPU.
	Core set of indicators developed by Partnership. Analysis published in World Telecom Development Reports, March 2006. Joint ITU/UNESCO/UNCTAD workshop to be held in Bangkok, 26-28 July.

	Composite Indices (para 115 of Tunis Agenda and para 28a of Plan)
	ICT Opportunity Index, Lead: BDT 

Digital Opportunity Index, Lead: SPU
	IOI published in November 2005.

DoI launched in November 2005, and published in full May 2006.

	World Information Society Day (para 121)
	Lead: CEC.

.
	17 May adoped by UNGA as WIS day. Two awards (to Mohamed Yunus and president Wade) at ceremony held on 17 May.   

	Coordination with non-governmental stakeholders
	Lead: CEC, WSIS-ES Executive Director.
	WSIS-ES Executive Director is assisting IGF with civil society participation.

	UN Global Alliance
	Lead:  CEC
	Launch meeting held in Kuala Lumpur, June 2006.


�  This document is crossposted as input documents both for the Council Working Group on the elaboration of the draft strategic and financial plans 2008-2011, and for the Council Working Group on WSIS (WG-WSIS).





