|  | Telecommunication Development Advisory Group (TDAG) 28th Meeting, Virtual, 24-28 May 2021 |  |  |
| --- | --- | --- | --- |
|  |  | Document TDAG-21/INF/3-E |  |
|  |  | 15 April 2021 |  |
|  |  | Original: English |  |
| Director, Telecommunication Development Bureau |  |  |  |
| Detailed information on the implementation of WTDC Resolution 9 |  |  |  |
| Summary: This document provides an overview on the ITU activities for implementation of Resolution 9 in addition to the corresponding section in Document TDAG-20/2. Action required: TDAG is invited to note this document. References: WTDC Resolution 9 (Rev. 2017, Buenos Aires) |  |  |  |

DETAILED INFORMATION ON IMPLEMENTATION OF RESOLUTION 9

TYPE OF ASSISTANCE

1. Assistance in raising the awareness of national policy-makers as to the importance of effective spectrum management for a country's economic and social development

2. Training and dissemination of available ITU documentation

3. Assistance in developing methodologies for establishing national tables of frequency allocations and spectrum redeployment

4. Assistance in setting up computerized frequency management and monitoring systems

5. Economic and financial aspects of spectrum management

6. Assistance with preparations for world radiocommunication conferences (WRC) and with follow-up and implementation of WRC decisions

7. Assistance with participation in the work of the relevant ITU-R study groups and their working parties

8. Transition to digital terrestrial television broadcasting

9. Assistance in identifying the most efficient ways to utilize the digital dividend

10. Emerging technologies and approaches in using spectrum

11. Innovative ways of spectrum licensing

12. Assistance with interference caused by devices in derogation of national spectrum allocations

13. Assistance in resolving seasonal interference caused by anomalous propagation of radiowaves

14. SMS4DC Training

| Country | Region | Date | Activities | URL |  |  |  |  |  |  | Topic |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| Trinidad and Tobago | AMS | Oct-20 | Spectrum Management Policy Framework | https://ituint.sharepoint.com/sites/TNS/Shared%20Documents/General/Resolution%209/CountriesReports/Spectrum%20Management%20Policy%20Final%20Report_8_2020.docx | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Regional (EUR/CIS) | EUR | 22-23 October 20 | ITU Regional Forum for Europe: 5G Strategies, Policies and Implementation Providing information and capacity building on BDT activities on 5G implementation, spectrum management and broadcasting. Providing platform to exchange information and best practices among key stakeholders in the region | https://www.itu.int/en/ITU-D/Regional-Presence/Europe/Pages/Events/2020/5G_EUR/5G_Europe.aspx | 1 | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |
| Moldova | EUR | May-June 2020 | Assistance to Moldova Providing technical assistance in the elaboration of the Spectrum Management Programme 2021-2025. Spectrum Management Programme 2021-2025 approved by the government in December 2020. |  | 1 | 1 |  |  | 1 |  |  |  | 1 |  | 1 |  |  |  |
| Albania | EUR | June-September 2020 | Assistance to Albania 1 Providing technical assistance in the elaboration of the “700 MHz band de-allocate” Plan for Albania. Plan fully approved at the national level in September 2020. |  | 1 | 1 |  |  |  |  |  |  | 1 |  |  |  |  |  |
| Albania | EUR | October-December 2020 | Assistance to Albania 2 Providing technical assistance to Albania through twinning with NMHH (Hungary) on frequency planning (allotment and assignment). Plan being finalized in Q1 2021. |  |  |  | 1 |  |  |  |  |  | 1 |  |  |  |  |  |
| Regional (EUR and CIS) | EUR CIS | 1-2 July 2020 | ITU Seminar for Europe and CIS on Spectrum Management and Broadcasting Providing information and capacity building on BDT activities on Spectrum management and broadcasting. Providing regional follow up to WRC-19 decisions and process towards WRC-23 . Providing platform to exchange information and best practices among key stakeholders in the region. | ITU Seminar for Europe and CIS on Spectrum Management and Broadcasting | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  |  |  |
| Regional (CIS) | CIS | Jul-Dec 2020 | Development of a capacity building toolkit to facilitate implementation of the WRC-19 decisions in CIS Developed a capacity building toolkit covering WRC-19 outcomes and key changes for the CIS countries (additional IMT bands; non-GSO satellites fixed-satellite service; regulatory changes for the use of spectrum and satellite orbits; HAPS for implementing broadband access in rural and remote areas; WiFi networks; RSTT; ITS; BSS; GMDSS; ESIM) |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  |  |  |  |
| Regional (CIS) | CIS | 16-18 Dec 2020 | 4th CIS & CEE Spectrum Management Conference Contributed to the 4th CIS & CEE Spectrum Management Conference organized by Forum Global | Webpage | 1 | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  |
| Worldwide | ALL | 30 Nov –11 Dec 20 | ITU World Radiocommunication Seminar 2020 (WRS-20) Capacity building on RR and NFAT; stations notifications procedures; WRC cycles | Event webpage | 1 | 1 | 1 |  |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 |
| Regional (AMS) | AMS | 13-24 July 2020 | ITU Regional Radiocommunication Seminar 2020 for the Americas (RRS-20-Americas) Capacity building on RR and NFAT; stations notifications procedures; WRC cycles | Event webpage | 1 | 1 | 1 |  |  | 1 | 1 |  | 1 | 1 |  | 1 |  | 1 |
| Regional (ASP) | ASP | 19-30 Oct. 2020 | ITU Regional Radiocommunication Seminar 2020 for Asia and the Pacific (RRS-20-Asia&Pacific) Capacity building on RR and NFAT; stations notifications procedures; WRC cycles | Event webpage | 1 | 1 | 1 |  |  | 1 | 1 |  | 1 | 1 |  | 1 |  | 1 |
| Worldwide | ALL | 16 Sept. / 07 Oct. / 11 Nov. 2020 | ITU Satellite Webinars Episode #1 #2 # 3 Provide Member States, Industry players and stakeholders worldwide relevant info about regulatory framework of Satellite Systems both GSO and Non-GSO | Event Webpage | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 |  |  |
| Regional (AFR) | AFR | 21-23 Sept. 28-30 Sept. 6-8 Oct. 12-14 Oct | Workshops - GE84 Plan optimization African countries – CG1 to CG4 E/F To achieve an efficient use of the 87.5-108 MHz (FM) band for analogue sound broadcasting and to identify additional frequencies to FM broadcasting to meet the increasing need for additional frequencies in African countries. |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  |  |  |
| Regional (AFR) | AFR | 20 April- 1st may 11-22 May | ITU/ PRIDA Workshop on Spectrum Management – E/F Providing information on Modern Spectrum Management | Event webpage | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 |  |  | 1 |
| Regional (ARB) | ARB | 9-12 November 2020 | ITU Workshop on Spectrum Monitoring for the Arab Region Facilitated dialogue between policy makers/regulators on spectrum policy |  | 1 | 1 |  | 1 | 1 |  | 1 |  |  | 1 |  | 1 |  |  |
| Fiji | ASP | 2020 | Development of NTFA, detailed channeling plans for FX, Band plans for IMT bands and other high in demand services, Wall chart | FIJ-National Table of Frequency Allocations 26 05 2020 - with TAF comments- Fard10-03-2020 |  |  | 1 |  |  | 1 |  |  |  |  |  |  |  |  |
| Tonga | ASP | 2020 | Development of NTFA, detailed channeling plans for FX, Band plans for IMT bands and other high in demand services, Wall chart |  |  |  | 1 |  |  | 1 |  |  |  |  |  |  |  |  |
| Indonesia | ASP | 10-Dec-20 | Conference on Indonesia 5G Roadmap and Digital Transformation Presentation on IMT2020 (5G): Specifications and considerations |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  |
| Brunei | ASP | 06-May-20 | BRUNEI DARUSSALAM 5G TASK FORCE 1st PLENARY MEETING Presentation on 5G and Regional Development on Policy, Regulatory & Spectrum |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  |
| AFG and Pacific | ASP | 18-May-20 | Introduction to National Spectrum Management and Spectrum Management System for Developing Countries (SMS4DC) · Introduction to National Spectrum Management · Automation of Spectrum Management · SMS4DC training |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  | 1 |
| AFG and Mongolia | ASP | Q3/4 2020 | SMS4DC training Step by step exercises provided for offline training |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |
| Regional (ASP) | ASP | Q4 2020 | ASP regional survey report on: A Framework for Effective Spectrum Management Training in Asia Pacific |  |  | 1 | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |
| Regional (ASP) | ASP | 19-30 Oct 2020 | ITU Regional Radiocommunication Seminar 2020 for Asia and the Pacific (RRS-20-Asia&Pacific) RRS with focus on regional issues like cognitive radios addressed in forum | https://www.itu.int/en/ITU-R/seminars/rrs/2020-Asia-Pacific/Pages/default.aspx | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 | 1 |  |  |  |
| Regional (ASP) | ASP | 17-28 Aug 2020 | SPECTRUM MANAGEMENT AND RADIO FREQUENCY (RF) MONITORING | https://academy.itu.int/training-courses/full-catalogue/spectrum-management-and-radio-frequency-rf-monitoring Additional blog on long term partnership with SRMC: https://www.itu.int/en/myitu/News/2021/01/04/10/43/Spectrum-management-capacity-building-Asia-Pacific-Region | 1 | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |
| Regional (ASP) | ASP | 23 Nov – 6 Dec 2020 | HUMAN EXPOSURE TO RADIO FREQUENCY ELECTROMAGNETIC FIELDS ASP COE training with SRMC China 7 highly interactive webinar style sessions delivered by experts from SRMC and ITU on following areas: 1. Outcomes of World Radio Conference 2019 2. Study activities in ITU-R Working Party 1C 3. Satellite monitoring and interference geolocation: Development & Challenges 4. Monitoring Techniques Based on Radio Sensors 5. Civil UAVs monitoring techniques 6. Data Acquisition and Processing Technology Based on Internet plus Radio Sensor 7. 5G NR Downlink Signal OTA Measurement in the field All the sessions saw excellent participation with an average of 45 questions per sessions. In addition, the ITU Academy online platform provided the opportunity of discussions and sharing knowledge through forums created by both tutors and participants. In total, the course was conducted using 7 content presentations combined with relevant interactive sessions, discussion forums, 2 quizzes and one assignment. |  | 1 | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |
| Samoa | ASP | Q2 2020 | SMS4DC tool Provided replacement tool to Samoa as the office of OOTR was damaged in an incident |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |
| Colombia | AMS | 2020 | Technical assistance to validate, plan and execute the assignment of permits for the use of IMT spectrum and for the use of best practices to increase Internet penetration in Colombia. Determine possible methods to assign permits for the use of the 3500 MHz band at national and regional level. Analysis of active and passive infrastructure sharing schemes Identify relevant trends on the deployment of 5G technologies Technical conditions of spectrum use permit in 5G scenarios |  | 1 |  | 1 |  | 1 |  |  |  | 1 | 1 |  |  |  |  |
| Regional (AMS) | AMS | 2020 | Capacity building on Spectrum Management 123 professionals from 15 different countries certified with basic modules OM1 (85) and OM2 (38) of the SMTP |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |
| Ecuador | AMS | 4Q 2020 | Specialized Technical Assistance for the valuation of the 700MHz and 2.5GHz bands for the Advanced Mobile Service within a possible process for their assignment or renewal of enabling titles in Ecuador. |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |
| Cuba | AMS | 2020 Ongoing | Radio Spectrum Monitoring for Cuba Project completion to 66% |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |
| Regional (AFR) | AFR | 2-4 March 2020 | Workshop on modern spectrum management, Zanzibar (English) A workshop covering spectrum harmonisation, results of WRC-19 spectrum sharing, mobile infrastructure sharing, spectrum refarming and EMF | Event webpage | 1 |  |  |  |  | 1 |  |  |  | 1 | 1 |  |  |  |
| Regional (AFR) | AFR | 5-6 March 2020 | Workshop on the ITU spectrum management software for developing countries (SMS4DC), basic, Zanzibar (English) | Event webpage |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |
| Regional (AFR) | AFR | 20-24 April 2020 | Online workshop on modern spectrum management (French) A workshop covering spectrum harmonisation, results of WRC-19 spectrum sharing, mobile infrastructure sharing, spectrum refarming and EMF | Event webpage | 1 |  |  |  |  | 1 |  |  |  | 1 | 1 |  |  |  |
| Regional (AFR) | AFR | 27 April – 1 May 2020 | Online workshop on the ITU spectrum management software for developing countries (SMS4DC), basic, workshop (French) | Event webpage |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |
| Regional (AFR) | AFR | 11-15 May 2020 | Online workshop on modern spectrum management (French) A workshop covering spectrum harmonisation, results of WRC-19 spectrum sharing, mobile infrastructure sharing, spectrum refarming and EMF | Event webpage | 1 |  |  |  |  | 1 |  |  |  | 1 | 1 |  |  |  |
| Regional (AFR) | AFR | 18-22 May 2020 | Online workshop on the ITU spectrum management software for developing countries (SMS4DC) workshop (French) | Event webpage |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |
| Regional (AFR) | AFR | 24-28 August 2020 | Online workshop on IoT and digital services – in French Awareness about business model, policies and regulations of IoT and digital services (including Spectrum aspects). | Event webpage |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |
| Regional (AFR) | AFR | 7-11 September 2020 | Online workshop on IoT and digital services – in English Awareness about business model, policies and regulations of IoT and digital services (including Spectrum aspects). | Event webpage |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |
| Seychelles | AFR | 2020 | Online workshop on spectrum management and SMS4DC General aspect of spectrum management and SMS4DC |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  | 1 |
| Regional (AFR) | AFR | 11-13 January 2021, | Online workshop on Spectrum Auctions (English) A workshop covering the common spectrum auctions types and formats used for the award public mobile licenses | Event webpage | 1 |  |  |  | 1 |  |  |  |  |  | 1 |  |  |  |
| Regional (AFR) | AFR | 18-20 January 2021 | Online workshop on Spectrum Auctions (French) A workshop covering the common spectrum auctions types and formats used for the award public mobile licenses | Event webpage | 1 |  |  |  | 1 |  |  |  |  |  | 1 |  |  |  |
| Regional (ARB + AFR) | ARB and AFR (66 countries) | 1 October – 15 November 2020 | ITU-ITSO Online Course on Satellite Communications and Radio Regulations Procedures for Arab and Africa regions | Event Webpage |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |
| Regional (ARB) | ARB (21 countries) | 9- 12 November 2020 | ITU Online Regional Training Workshop on Spectrum Monitoring for the Arab Region | Event Webpage | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |
| Sudan | ARB | 2020 ongoing | Ongoing assistance to Sudan on Spectrum Utilization roadmap Project implemented in cooperation with the Telecommunication and Postal Regulatory Authority (TPRA) of the Republic of Sudan |  | 1 | 1 | 1 |  |  |  |  |  |  |  | 1 |  |  |  |

________________