| Telecommunication Development Advisory Group (TDAG) 33rd Meeting, Geneva, Switzerland, 7-10 April 2026 |  |
| --- | --- |
|  | Revision 1 to |
|  | Document TDAG-26/2(Add.1)-E |
|  | 31 March 2026 |
|  | Original: English |
| Director, Telecommunication Development Bureau |  |
| Update on the Report on implementation of the Kigali Action Plan (KAP) 2023-2025 |  |
| Summary: This document provides an update to WTDC-25 Document 2 on the implementation of the Kigali Action Plan (KAP) and covers the period from September 2025 to December 2025. In addition to the activities deployed through the Operational Plan of the Telecommunication Development Bureau (BDT) and extra-budgetary projects, emphasis is placed on the results achieved during the implementation of the ITU-D priorities, outcomes and outputs of the Sector. Action required: TDAG is invited to note this document. References: TDAG-26, Document 2 WTDC-25, Document 2 WTDC-22 Kigali Action Plan |  |

# Introduction

The 2022 ITU World Telecommunication Development Conference (WTDC-22) convened in Kigali, Rwanda, from 6 to 16 June 2022, and adopted the Kigali Action Plan (KAP). The plan, which includes the priorities, enablers, regional initiatives, new and revised resolutions, recommendations, and study group Questions defines the mandate of the ITU Development Sector (ITU-D) for the period of 2023 to 2025.

The priorities are closely linked to and aligned with the priorities and objectives identified by the larger development framework of the Sustainable Development Goals (SDGs), the ITU strategic plan and the World Summit on the Information Society (WSIS) action plan. The priorities share a common vision of achieving sustainable development by leveraging the opportunities of digital tools and ICTs.

This document provides an update to WTDC-25 Document 2 on the implementation of the Kigali Action Plan (KAP) and covers the period from September 2025 to December 2025. In addition to activities undertaken under the Operational Plan of the Telecommunication Development Bureau (BDT) and extra-budgetary projects, emphasis is placed on the results achieved during the implementation of the ITU-D priorities, outcomes and outputs of the Sector.

# Report

September - December 2025

| ## ITU-D Priority 1: Affordable connectivity Fostering the development of secure, modern and affordable infrastructure and services through telecommunications/ICTs |  |  |
| --- | --- | --- |
| ### Emergency telecommunications Outcome: Strengthened capacity of Member States to use telecommunications/ICTs for disaster risk reduction and management, to ensure availability of emergency telecommunications, and support cooperation in this area |  |  |
| Outputs |  | Highlights |
| From September 2025, BDT continued its efforts to strengthen Member States’ capacity to use ICTs for disaster risk reduction and management. The work focused on enhancing preparedness, ensuring the availability and resilience of emergency telecommunications, and advancing the implementation of the Early Warnings for All (EW4All) initiative, with particular emphasis on Pillar 3 of EW4All, Warning Dissemination and Communication, for which ITU serves as the global lead. At the global level, BDT contributed to policy dialogue, coordination, and knowledge products development to advance ICT-enabled early warning systems. From 10 to 14 October 2025, BDT participated in the G20 Disaster Risk Reduction Group Ministerial Meeting, in Cape Town, South Africa, contributing to discussions on global resilience, enhancing early warning systems, and building preparedness and recovery strategies. The Ministerial Final Declaration highlighted the importance of cell broadcast and recognized the role of technologies and artificial intelligence in early warning monitoring and dissemination. The meeting provided a platform for South Africa to launch its national EW4All Roadmap. On 13 October, International Day for Disaster Risk Reduction, BDT launched the paper “Scaling Up Cell Broadcast for Last-mile Early Warning Delivery: Progress, Barriers, and Enabling Mechanisms”, developed in collaboration with UNDRR, GSMA, WMO, IFRC/Risk-informed Early Action Partnership, WFP, and supported by the G20 South African Presidency. The publication examined regulatory, technical and operational barriers, a well as enabling mechanisms for scaling mobile-based early warning systems, providing a global evidence base to inform policy and investment decisions. Further, BDT advanced EW4All through technical training, knowledge sharing, and global coordination. Activities included staff training on connectivity gap assessments, contributions to global webinars on governance and multi-channel dissemination, engagement with humanitarian partners on the use of satellite technologies, participation in the Global EW4All Coordination Meeting, and a joint coordination meeting with GSMA to align country support to Pakistan, Uganda, Kenya, Sri Lanka and Ecuador. On 09-11 December, BDT co-facilitated a workshop titled “Scaling up Early Warning Systems in Conflict and Post-Conflict contexts”, held in Nairobi, Kenya. The event emphasized the challenges and opportunities for warning dissemination and communication in the world’s most challenging environments. The event brought together participants from the Democratic Republic of Congo (DRC), Burundi, South Sudan, Sudan, Somalia and Djibouti to attend this workshop and enhance their knowledge on integrating early warning systems in fragile settings. In the Africa region, BDT supported the strengthening of early warning communication and dissemination ( under the EW4All initiative )and emergency telecommunications across the region through national consultations and capacity-building workshops. In Zambia, BDT contributed to the national launch by developing and validating a Pillar 3 roadmap with stakeholders, laying the groundwork for implementation funding. In Senegal, BDT, in collaboration with the Telecommunications and Postal Regulatory Authority, organized an online session to introduce EW4All with a view to promote multi-channel warning dissemination, and plan follow-up engagement with mobile operators and media. In Chad, BDT facilitated a multi-stakeholder workshop to enhance coordination, finalize Pillar 3 assessments and gap analyses, draft the roadmap and priority actions, and establish a draft coordination mechanism with key inter-pillar activities. In Liberia, BDT delivered a national Pillar 3 workshop and CAP training. In Cape Verde, Angola and Sao Tome and Principe, BDT delivered technical missions to support national gap assessment and the formulation of national roadmaps. Capacity development was further strengthened through remote GIS training for Madagascar, enhancing national capacity for the use of Disaster Connectivity Mapping. In Mozambique, BDT supported national monitoring and evaluation processes and the integration of warning dissemination priorities, including cell broadcast, into national planning and budgeting. BDT also participated in a regional workshop in Kenya focused on early warning and early action in least developed and fragile settings. Emergency telecommunications planning advanced across the region. BDT participated in preparedness workshops in Burundi, supported the official launch and adoption of the National Emergency Telecommunication Plan (NETP) in Rwanda, and continued to support NETP finalization in Madagascar, Liberia, Senegal and Guinea. In addition, BDT organized, together with UNHCR, GSMA and the Government of Luxembourg, a Connectivity for Refugees stakeholder roundtable to brief the international community on a joint mission to Chad and raise awareness on the initiative to attract more partners. In the Americas region, BDT supported EW4All implementation, emergency telecommunications planning and disaster response in Belize, Ecuador, Guatemala, Guyana, Haiti, Jamaica and Grenada. In October 2025, BDT participated in the GSMA EW4All Workshop in Ecuador, contributing to discussions on regulatory frameworks, CAP implementation and Pillar 3 priorities, and supporting a national tabletop simulation exercise. Further, BDT supported Guatemala by developing technical specifications for the acquisition and implementation of a cell broadcast system, enabling national authorities to proceed with procurement and deployment. In collaboration with UNDRR, WMO and IFRC, BDT finalized EW4All gap analyses and implementation plans for Belize and Guyana. In Haiti, BDT supported a local governance workshop for the Multi-Hazard Early Warning System in Cap-Haïtien under the Making Cities Resilient 2030 initiative. Under the NETP programme, BDT continued to support NETP development in Haiti and Jamaica, and delivered capacity development training on WINLINK for emergency communications in Grenada. Following the impact of Category 5 Hurricane Melissa in Jamaica on 28 October 2025, BDT deployed 17 Iridium satellite phones to support humanitarian operations and coordination. In the Arab States region, BDT supported EW4All and emergency telecommunications in Djibouti, Egypt, Mauritania, Somalia and Sudan. In Mauritania, BDT organized a national workshop in Nouakchott to strengthen emergency telecommunications, validate the NETP, and advance the implementation of CAP and cell broadcast-based early warning systems. In Somalia, BDT delivered remote GIS training and technical assistance on Disaster Connectivity Mapping and EW4All methodology, strengthening national capacity for data-driven early warning planning. At the regional level, BDT supported the participation of Djibouti, Somalia and Sudan in a workshop on early warning and early action in least developed and fragile settings. BDT also co-led the First Arab Regional Forum on Early Warning and Disaster Preparedness Systems in Egypt, bringing together more than 200 stakeholders to strengthen policy dialogue, coordination and knowledge exchange across the region. In the Asia-Pacific region, BDT supported EW4All implementation through regional knowledge exchange, national consultations, developing partnerships and capacity-building activities involving Bangladesh, Cambodia, Fiji, Kiribati, Lao People’s Democratic Republic, Nepal, Samoa, Solomon Islands and Tonga. Key activities included a regional EW4All webinar series addressing institutionalization, inclusion and the use of science, technology and innovation in early warning systems. In September 2025, BDT co-hosted a regional workshop in Japan on resilient infrastructure for early warning dissemination which brought together participants from Bangladesh, Bhutan, Cambodia, China, Fiji, Kiribati, Lao People’s Democratic Republic, Maldives, Mongolia, Nepal, Papua New Guinea, Samoa, Thailand and Tonga. In Bangladesh, BDT supported the launch of the EW4All National Roadmap and the validation of the CAP implementation plan through national multi-stakeholder workshops. In addition, the draft NETP and preliminary assessment on cell broadcast were submitted to Bangladesh. BDT also engaged with media and disaster management stakeholders through contributions to the ABU Media Summit in Sri Lanka and the United Nations Economic and Social Commission for Asia and the Pacific (UNESCAP) Committee on Disaster Risk Reduction in Thailand, highlighting the role of ICT infrastructure, broadcast media and cell broadcast. In addition, BDT along with the EW4All pillar leads (United Nations Office for Disaster Risk Reduction, World Meteorological Organization and International Federation of Red Cross and Red Crescent Societies) and UNESCAP conducted three webinars on Asia-Pacific EW4All focusing on the themes of institutionalising early warning systems; inclusivity; and science, technology and innovation. National capacity was further strengthened through the GSMA Cell Broadcast Readiness Workshop in Nepal. Technical assistance was initiated for the Republic of the Marshall Islands under the MIC-Japan phase 2 project to develop NETP and updated the draft NETP of Kiribati, strengthening alignment with national early warning systems, CAP and cell broadcast adoption. BDT participated in the 1st ASEAN Emergency Telecommunications Network (ETN) Workshop in Bali, Indonesia and provided technical inputs on early warning dissemination (channels such as cell broadcast and satellite, and CAP) and disaster response (NETP, harmonisation of radiofrequency, Tampere Convention) in alignment to the ETN Masterplan. Under MIC-Japan phase 3 project, BDT carried out assessment for a cloud-based Cell Broadcast (CB) system for 12 Member States in the Pacific SIDs. In the CIS region, BDT co-facilitated the Interpillar Workshop, held in Armenia, for the official launch of the EW4All initiative, organized in collaboration with United Nations Office for Disaster Risk Reduction (UNDRR), the World Meteorological Organization (WMO), the International Federation of Red Cross and Red Crescent Societies (IFRC), the United Nations Development Programme (UNDP), and the Government of Armenia. The workshop enabled national institutions, United Nations entities, and partners to conduct a gap analysis across the four EW4All pillars and begin developing a National Roadmap. BDT led sessions for Pillar 3, focusing on multi-channel systems for warning dissemination and communication. In the Europe region technical assistance was provided to North Macedonia and Montenegro to advance on Early Warning Systems development with particular emphasis on cell-broadcast system rollout. As a result, decision-makers from North Macedonia and Montenegro were equipped with a technical, economic, and regulatory analysis for implementing a national public warning system aligned with European Union and international standards. These feasibility studies are also providing clear cost estimates, risk analysis, and implementation pathways to proceed with national deployment. As part of the feasibility study development process for the cell-broadcast system in North Macedonia and Montenegro, National Validation Workshops were organized in Skopje and Podgorica for the establishment of a national public warning system (PWS). The workshops raised awareness among the key stakeholders and validated technical, regulatory, and institutional aspects of a CAP-based, multi-channel warning system and initiated an agreed implementation roadmap, with sessions on CAP v1.2, multi-channel strategies, and alignment with European Union and international frameworks. Overall, BDT engaged more than 40 countries across Africa, the Americas, the Arab States, Asia-Pacific, Europe and the CIS. The AI for EW4All Group advanced several key activities. The AI for Early Warning Systems report was launched, laying the foundation to position AI as a strategic enabler across the early warning value chain. During this period, the group also intensified its focus on operationalizing pilot initiatives, engaging partners to co-develop country-level applications. Notably, the Early Warning Connectivity Map (EWCM) was presented at WTIS in September. In October, collaboration with UNDRR led to the development of an AI-enhanced Common Alerting Protocol (CAP) concept, showcased at the UN-ETH Forum (Zurich, Switzerland). A new project was signed in December funded by the Republic of Korea 'Advancing Early Warnings through AI Matchmaking & Pilot Accelerator', aimed at implementing AI pilot initiatives in Kenya and Bangladesh. These efforts were complemented by ongoing development of the AI Solutions Catalogue and continued partner engagement, further strengthening the pipeline of validated AI tools and use cases to support implementation on the ground. Through policy advocacy, technical assistance, capacity development and operational support, BDT strengthened national and regional capacities to design, implement and sustain people-centred, multi-hazard early warning systems and resilient emergency telecommunications. The development of national roadmaps, gap analyses, NETPs, feasibility studies and technical specifications has enhanced the readiness of countries to deliver timely warnings, particularly in least developed countries and small island developing States. Collectively, BDT work during this last quarter of 2025, reinforced the role of ICTs as critical enablers of disaster risk reduction and preparedness, contributing to global efforts to ensure that no one is left behind when disasters occur. |  | NETPs: - Africa: 4 NETPs for Senegal, Guinea, Liberia and Madagascar - Arab States: 2 NETPs for Libya and Mauritania - Asia-Pacific: Kiribati, RMI and Bangladesh - Americas: Haiti, Jamaica CB baseline studies: - Arab States: Somalia - Asia-Pacific: Bangladesh, Nepal Europe: Montenegro, North Macedonia EW4ALL: 30+ countries supported since 2022 - Africa: Botswana, Ghana, Liberia, Madagascar, Mozambique, Namibia, Niger, Rwanda, São Tomé and Príncipe, Seychelles, Tanzania, Uganda - Americas: Antigua and Barbuda, Barbados, Belize, Ecuador, Guatemala, Guyana, Haiti - Asia-Pacific: Bangladesh, Bhutan, Cambodia, China, Fiji, Indonesia, Kiribati, Lao P.D.R., Maldives, Nepal, Philippines, Samoa, Thailand, Sri Lanka - Arab States: Comoros, Djibouti, Iraq, Somalia, Sudan - Europe: Montenegro, North Macedonia - CIS: Armenia, Tajikistan ITU-D Study Group 1 - Final report of Question 3/1 (2022-2025) published |
| ### Network and digital infrastructure Outcome: Improved telecommunication/ICT infrastructure and service, in particular broadband coverage |  |  |
| Outputs |  | Highlights |
| BDT continued to advance network and digital infrastructure as a foundation for connectivity and equitable digital transformation. Building on connectivity gap analysis, BDT expanded its focus to address resilience, inclusivity, and sustainability in the systems underpinning the digital economy. Its integrated approach combined global tools, the use of artificial intelligence technologies, targeted technical assistance, and regional partnerships, linking infrastructure mapping and spectrum management with satellite integration, 5G readiness, and school connectivity. In Africa, through the Africa Broadband Maps project, BDT contributed to improved network and digital infrastructure outcomes by establishing the institutional and technical foundations for national broadband mapping systems across the region. From September to December 2025, national broadband mapping foundation-building events were conducted in Benin, Uganda, Zimbabwe, Malawi, Ethiopia, Burundi, and Zambia. These engagements brought together national regulatory authorities and key stakeholders to introduce the broadband mapping programme, validate country-specific requirements, and agree on governance and data scope, as well as institutional ownership arrangements. The activities focused on preparing countries to develop country-owned broadband mapping systems that consolidate infrastructure, coverage, and service availability data into a single authoritative evidence base. This work strengthened national capacity to identify broadband coverage gaps, prioritize infrastructure investments, and support universal service strategies, while ensuring alignment with regional and global connectivity initiatives. In collaboration with TSB and GSMA, BDT held a Quality of Service (QoS) workshop in Benin, which highlighted the shared responsibility of regulators and operators in ensuring high quality service. Further on 20 October 2025, BDT, in collaboration with GSMA, the East African Community (EAC) and the Intergovernmental Authority on Development (IGAD), held a Spectrum Management Workshop in Kigali, Rwanda, which discussed regional harmonization to advance cross-border connectivity in Eastern Africa. Drawing 36 participants from Burundi, Democratic Republic of Congo, Djibouti, Ethiopia, Kenya, Rwanda, Somalia, Sudan, South Sudan, Tanzania and Uganda, the training on spectrum management emphasized regional integration and cross border coordination within Eastern Africa and empowered regulators and policy-makers to implement interoperable, resilient and future-ready spectrum governance models that transcend national boundaries. In the Americas, BDT conducted training on 5G network-related topics in Costa Rica, with a total of 8 courses and 182 participants. Additionally, the BDT Workshop on emerging technologies for innovative connectivity solutions: policy, economic and technical aspects, took place during IPEC-25. In December, BDT delivered to Colombia (Ministry of Information and Communication Technologies) the General Plan for the Cessation of Analogue Television Broadcasts (PGCEA – version 3). This product was developed under the technical cooperation of ITU-MinTIC on Digital Terrestrial Television and Universal Access. The General Plan was fully approved. In the Arab States, work progressed on the development of a practical analytical study designed to support the 22 Arab States in addressing national connectivity priorities. The study provided evidence-based recommendations on spectrum management, regulatory reform, and infrastructure investment, and included in-depth country case studies of some countries in the region. This study has been facilitating discussions with administrations and regulators with a view to accelerating digital maturity and narrowing connectivity gaps in a manner tailored to the specific context of each country. In Asia-Pacific, BDT advanced spectrum management, satellite connectivity, and IMT2020 (5G) adoption through technical assistance and regional cooperation. From 20 to 29 October 2025, the ITU Regional Office for the Asia-Pacific supported and participated in the ITU Regional Radiocommunication Seminar and Workshop on Modern Spectrum Management in Chengdu, China, highlighting regional work on spectrum management and radio frequency monitoring and introducing BDT tools such as the Spectrum Management System for Developing Countries (SMS4DC). Technical assistance was provided to Palau by BDT to develop a draft National Table of Frequency Allocations aligned with the ITU Radio Regulations 2024. In December 2025, BDT collaborated with the Radiocommunication Bureau in organizing a seminar on science services in preparation for WRC-27 in Kuala Lumpur, Malaysia, at the request of the Malaysian Communications and Multimedia Commission (MCMC). BDT also contributed to a regional dialogue on emerging technologies. In September 2025, BDT participated in the ASEAN 5G Skilled Workforce Programme webinar on 5G security and zero-trust architectures and delivered a keynote presentation at the MCMC–APT LEO training programme on the transformative impact of low-Earth orbit (LEO) satellites for global connectivity and bridging the digital divide. Through the Giga project, BDT engaged with Cambodia and Sri Lanka to collect connectivity data for school connectivity modelling and also launched the beta version of the Connectivity Planning Platform, which has been applied across regions, mapping approximately 36 000 points of interest and identifying priority fibre-optic connections. Furthermore, Pakistan and Fiji have expressed interest in joining the initiative. In the CIS, following Tajikistan official accession the Giga initiative in November 2025, BDT engaged with national counterparts to initiate the collection of the ICT Infrastructure data including data on cell towers, mobile coverage, optical fibre nodes, and infrastructure construction and maintenance costs in the country. This information is facilitating ICT infrastructure modelling at the national level and revealing potential connectivity scenarios, along with implementation cost estimates, to close gaps in school connectivity in Tajikistan. BDT is providing guidance on sustainable business models to ensure the viability of these connectivity scenarios and the attractiveness of related investment cases for development partners. BDT also provided expert assistance to the Kyrgyz Republic in developing appropriate methodology for conducting a preliminary assessment of the potential for connecting the national telecommunication networks of Kyrgyzstan to international backbone communication infrastructure, including submarine cable systems. The proposed methodology outlines how to select the most suitable connection scenario and technology to achieve the required bandwidth, ensure the necessary quality-of-service indicators, and maintain economic feasibility. In addition, an overview of relevant policy and regulatory measures was prepared, together with recommendations to support the more effective development of the broadband backbone network and the ICT sector in Kyrgyzstan. In December2025, BDT finalized a package of assistance activities for countries in the South Caucasus to support coordination and replanning for digital audio broadcasting (DAB). Through this assistance, national regulatory authorities were provided with the necessary tools to advance the harmonization of spectrum plans to facilitate cross-border coordination, improve the efficiency of spectrum use, and establish a foundation for regional DAB deployment. These efforts are expected to contribute towards greater availability and quality of digital audio services across the South Caucasus, helping to bridge broadcasting coverage gaps, and promote cultural and information access, particularly in rural and underserved communities. Finally, BDT provided comprehensive regulatory and technical assistance to Uzbekistan through a dedicated workshop on procedures for coordination, notification, and registration of terrestrial and satellite frequency assignments in accordance with the Radio Regulations. This assistance included practical training on ITU tools and software, such as BR IFIC, SpaceCom, and GIMS, guidance on implementation and protection of national frequency assignments and allotments, and tailored support to address specific coordination and compliance issues raised by the administration of Uzbekistan. In the Europe region, BDT focused on regulatory preparedness, infrastructure resilience, and capacity development. From 14 to 15 October 2025, a workshop on Quality of Service and Resilience of Mobile Infrastructure for Regulatory Authorities was held in Nicosia, Cyprus, bringing together 60 participants from 18 countries. The workshop, organized under trilateral cooperation between ITU, EMERG, and EaPeReg, focused on fostering trust and confidence through regulatory preparedness and network resilience Technical Assistance was provided to Moldova on wireless digital infrastructure, supporting the development of the 2026–2030 high-speed network roadmap, and delivering evidence-based recommendations on spectrum management and pricing to support effective regulation and future broadband deployment. Further, a National Workshop was conducted on 23 September 2025 to strengthen human capacity in Moldova in the field of EMF, facilitating the exchange in best practices with experts from Moldova and Romania, Poland, Switzerland, and the United Kingdom. In parallel, seven European countries, Croatia, Italy, Netherlands, Romania, Poland, Slovenia and Lithuania engaged in knowledge and best practice exchanges with African counterparts under the Africa-BB-Maps project, which promotes the transfer of European regulatory and technical expertise to support broadband mapping systems in the Sub-Saharan Africa region. Overall, the work carried out by BDT strengthened the foundations for resilient, inclusive, and sustainable digital connectivity by enabling countries transition from identifying connectivity gaps to implementing evidence-based policies and investment-ready strategies. Through the deployment of global planning tools, targeted technical assistance, and regional partnerships, BDT enhanced national and regional capacities in broadband mapping, spectrum management, infrastructure resilience, satellite integration, and emerging technologies such as 5G. this support also equipped regulators with the skills capacity to optimize spectrum use, prioritize infrastructure investments, improve quality of service, and facilitate cross-border coordination. |  | - Africa: Benin, Burundi, DRC, Djibouti, Ethiopia, Kenya, Malawi, Somalia, South Sudan, Rwanda, Tanzania, Uganda, Zambia, Zimbabwe - Americas: Colombia, Costa Rica - Asia-Pacific: Cambodia, Malaysia, Palau, Sri Lanka - CIS: Kyrgyzstan, Tajikistan, Uzbekistan - Europe: Croatia, Cyprus, Italy, Lithuania, Moldova, Netherlands, Poland, Romania, Slovenia ITU-D Study Group 1 - Final report of Question 1/1 (2022-2025) published - Final report of Question 2/1 (2022-2025) published - Final report of Question 5/1 (2022-2025) published ITU-D Study Group 2: - Final report of Question 4/2 and Final report of Question 7/2 (2022-2025 study period) published |
| Contributing to SDG Targets | SDGs 1, 3, 4, 5, 8, 9, 10, 11, 16, 17 |  |
| WSIS Action | C1, C2, C3, C4, C5, C6, C7, C11 |  |
| Resolutions | PP 136; WTDC 9, 10, 11, 34, 43, 66; WRC 646, 647; |  |
| ITU-D study group Questions | Questions 1/1 (Broadband), 2/1 (Broadcasting), 3/1(Disaster risk reduction), Question 5/1 (Rural telecommunications) of Study Group 1 on Enabling environment for meaningful connectivity and Question 4/2 (Conformance and interoperability), Question 7/2 (EMF) of Study Group 2 on Digital transformation. |  |

| ## ITU-D Priority 2: Digital transformation Accelerating digital transformation through ICT entrepreneurship and increased ICT innovation in the ICT ecosystem |  |
| --- | --- |
| ### Digital innovation ecosystem Outcomes: Strengthened capacity of the ITU membership to integrate telecommunications/ICT innovation and digitalization in their national development agendas and to develop strategies to promote innovation initiatives, including through public, private and public-private partnerships. Enhanced human and institutional capacity of the ITU membership in telecommunications/ICTs to foster digital transformation |  |
| Outputs | Highlights |
| BDT continued to support Member States in strengthening national innovation ecosystems and accelerating digital transformation. Activities continued to be delivered through multi-stakeholder engagement and partnerships to create sustainable models that shape resilient digital ecosystems, aligning country support with national priorities, and regional initiatives. In the Americas, BDT, in collaboration with INDOTEL , organized the third meeting of the Digital Innovation Board of the Innovation and Entrepreneurship Alliance for Digital Development on 1-2 October 2025 in Santo Domingo, Dominican Republic. The event brought together Board members and partners to review progress across key pillars of the Alliance, including the Acceleration Centres, the Expert Network, and the Regional Initiative Accelerator. In addition, from September to December, BDT released three foresight report briefs (Shaping Education for Tomorrow, Shaping the future of startups and SMEs, and Shaping the future of an African VC landscape) which explored how inclusive digital futures can take shape through education, entrepreneurship, and the venture capital landscape. Two additional foresight briefs on smart cities and healthcare were reviewed and approved by the Digital Board and are expected to be launched in the first quarter of 2026. In November 2025, BDT launched a Regional Acceleration Centre, in Baku, Azerbaijan, on the sidelines of WTDC-25. This nationally owned and financed centre, under the framework of the ITU acceleration centre network of the Innovation and Entrepreneurship Alliance for Digital Development, serves as a hub for startups, businesses, and government to foster digital transformation in the CIS region. In addition, BDT launched a new advanced course for ITU Acceleration Centres on ecosystem initiative development (Ecosystem initiative development 201). In December 2025, BDT completed the initial draft of the toolkit for the Regional Initiative Accelerator, which will be further refined and finalized for use in implementing the newly approved WTDC-25 regional initiatives. BDT continues to support the ITU Acceleration Centres through targeted capacity-building activities, including capstone projects that serve as service launches by the centres. Notably, two Acceleration Centres launched their first strategic foresight reports at WTDC-25. Across the regions, BDT continues to support Members States in advancing their digital development priorities through a range of products and services. In Africa, a number of capacity development initiatives were deployed. In December 2025, BDT conducted an Entrepreneurship Training Bootcamp Delivery and Chatbot Validation Workshop in Cotonou, Benin, under a joint project with UNFPA aimed at strengthening youth resilience and empowerment. Additionally, a strategic foresight workshop was held in Maputo, Mozambique to prepare inputs for the national digital transformation strategy under the Vamoz Digital project. In the Asia-Pacific region, four innovation cafes, conducted either in-person or virtually, were held during various sub-regional and national workshops, covering topics including AI and standards, AI for whole-of-government, and digital health in Malaysia, Cambodia, Vietnam and Thailand. Under the project, "Artificial Intelligence Technology and Standards Capacity Building", four additional workshops took place in Malaysia, Bhutan, and Cambodia providing training for government officials, industry professionals, and academia on AI standards and technological aspects of AI. These sessions were delivered through face-to-face as well as online training via ITU Academy. Nepal and Bangladesh were engaged to initiate the planning of the innovation profile in Q4 of 2025. In the CIS region, the concluding Roundtable and Training on Smart and Sustainable Cities for Government Officials was held in Belarus from 23-24 October 2025, with support from the Belarusian State Communication Academy, marking the conclusion of a four-year collaboration on advancing smart cities across Belarus. The final roundtable brought together regional administrators and urban planners to discuss the implementation of digital solutions in line with the national "Smart City" programme. These workshops aimed at strengthening local governance through capacity building, promoting the adoption of smart technologies, fostering sustainable urban development, and enhancing the quality of life for citizens. The initiative underscores the ITU ongoing commitment to supporting digital transformation in the CIS region. Digital innovation and entrepreneurship through startups continued to serve as a platform for Digital Ministries, Academia members and University partners, to empower youth with digital skills in digital entrepreneurship and startups through a series of hackathons. From 26 to 30 September 2025, “The Hackathon: AI ERA” was conducted in Minsk as an AI-focused intensive event for young specialists, bringing together teams from across Belarus to develop applied solutions to partner-defined challenges. From 27 to 29 October 2025, “The Hackathon: Gomel” was held in Gomel, Belarus, with over 60 university and school students from across Belarus participating. Participants applied skills in software development, business analytics, product management and UX/UI design, working on their solutions over two days and presenting outcomes to a jury on the third day. The participants received guidance and mentorship from experts provided by BDT, Zborka Labs and the partner organizations supplying the challenge cases. In November 2025, the BDT delivered two online capacity-building trainings in cooperation with the “StartUp Skills” educational programme hosted by Gomel State University in Gomel, Belarus, targeting students and early-stage entrepreneurs. The training focused on digital tools for validating target audiences and estimating market size, as well as unit economics. Guidance on building and testing unit economic models and assessing convergence toward sustainable business metrics was also provided. In Kazakhstan, to support the youth innovative entrepreneurship, the “Qostanai AI-Sana Industry Hackathon: Allur Challenge” was held in Kostanay from 1 to 3 November 2025 as a youth innovation and entrepreneurship activity connecting academia and industry through a real-world manufacturing use cases. Organized by BDT in collaboration with Qostanai Hub and the Kostanay Engineering and Economics University named after M. Dulatov (KinEU), the hackathon provided space for the students to develop MVP-level prototypes using machine learning and computer vision. In the Arab States, the launch of Digital Innovation Profiles (DIPs) for Qatar, Jordan, the State of Palestine, and Tunisia have equipped these countries with a data-driven framework to assess and strengthen their ICT ecosystems. By identifying specific gaps and opportunities within their national innovation landscapes, these profiles allow policymakers to transition from generic digital strategies to targeted interventions that foster entrepreneurship and technological growth. This systematic approach ensures that each country can build a more competitive and resilient digital economy tailored to its unique socio-economic context. In addition, the partnership with the United Arab Emirates TDRA under, the iCodi initiative concluded in December 2025. This cooperation agreement institutionalized global and regional workshops as recurring opportunities for dialogue. At the global level, the I-CoDI initiative has driven significant collective participation by engaging over 60 participants from 15 countries, successfully building foundational capacity across key strategic objectives such as Strategic Foresight, Ecosystem Initiative Development, and Policy Experimentation. This global framework is effectively localized through regional interventions, notably exemplified by the November 2024 strategic foresight workshop in Dubai for the Arab States. This intensive, co-creative exercise convened over 40 regional stakeholders to master advanced methodologies and directly apply them to identifying the region's most pressing digital development priorities for the next four years, ensuring that global innovation tools are translated into high-impact, region-specific strategic action. In the Europe region, the Innovation Challenge on Digital Innovative Solutions was organized during the Accessible Europe 2025 edition, with the aim of strengthening the innovation ecosystem for digital accessibility. Overall, the work of BDT strengthened national and regional innovation ecosystems by translating policy dialogue, foresight tools, and capacity development into platforms for digital transformation. Through the establishment of acceleration centres, delivery of foresight tools, support to regional initiatives and hands-on activities such as bootcamps, workshops and hackathons, BDT enabled governments, academia, startups, and youth to collaborate on innovation in alignment with national priorities. These efforts enhanced institutional capacity, empowered young entrepreneurs with future-ready digital skills, and fostered sustainable, locally owned models that support inclusive and resilient digital ecosystems across regions. | - Two foresight workshops and outcome delivered for South Africa - Two foresight reports launched for the Digital Innovation Board - Development of strategies, policies, roadmaps and digital innovation profiles. - Africa: Benin, Mozambique - Arab States: Qatar, Jordan, Tunisia, United Arab Emirates and the State of Palestine - Asia-Pacific: Bangladeh, Bhutan, Cambodia, Malaysia, Nepal, Thailand, Vietnam - CIS: Belarus, Kazakhstan |
| ### Digital services and applications Outcome: Enhanced capacity of the ITU membership to accelerate digital transformation and sustainable economic and social development by leveraging and using new and emerging telecommunications/ICTs and services of the ITU membership in telecommunications/ICTs to foster digital transformation |  |
| ### Outputs | ### Highlights |
| BDT continued to advance its work on Digital Public Infrastructure (DPI), combining global policy engagement with concrete implementation support. From September to December, BDT provided technical inputs and coordination support to the G20 DPI agenda, contributing to discussions on scalable, interoperable and inclusive DPI as a foundation for digital transformation. BDT also participated and contributed to the DPI Summit in Cape Town, South Africa strengthening engagement with governments, development partners and the broader DPI ecosystem. In parallel, BDT worked closely with the World Bank on DPI related activities and successfully completed the Horn of Africa GovStack project, supporting alignment with GovStack building blocks and strengthening country capacity for DPI implementation. This body of work reinforced the role of BDT as a technical convener linking global policy processes with practical, country level DPI delivery. Across regions, BDT advanced various initiatives with global reach. The Be He@lthy, Be Mobile initiative, in collaboration with WHO, was transformed into a more open, scalable, and adaptable model for developing countries, leveraging artificial intelligence, large language models, and retrieval-augmented generation to enhance digital health interventions. In parallel, the Women in GovStack programme strengthened women’s leadership in digital public infrastructure, engaging 180 mentees through mentorship, technical training, and hands-on prototyping within the GovStack sandbox. BDT also launched multiple foresight reports on education, entrepreneurship, and venture capital, with additional briefs on smart cities and healthcare approved for launch in early 2026. In the Africa region, BDT continued to focus on strengthening digital public infrastructure and governance through GovStack-aligned interventions and strategic consultations. With support from World Bank–financed projects, BDT conducted high-level consultations in Guinea-Bissau, Gambia, Guinea, Nigeria and Senegal, bringing together government stakeholders to align national digital transformation efforts with GovStack and the Public Administration Ecosystem Reference Architecture (PAERA). These engagements operationalized key components such as interoperability frameworks, enterprise architecture, service bus specifications, and capacity development, contributing to tangible progress in modernizing public administration systems. In the Arab States region, BDT delivered targeted initiatives to address structural digital divides and advance emerging technologies. In Mauritania, a BDT-led GovStack project supported the transition of digital systems toward a unified, building-block-based government architecture. The initiative combined capacity building, the development of a national digital services roadmap, and the launch of three practical use cases, enabling the Government of Mauritania to independently scale digital services in a more agile, cost-effective, and citizen-centric manner. In Jordan, BDT supported the development of a national strategy for immersive technologies, building on a 2024 assessment. Through high-level workshops and extensive engagement with government, private sector, and academic stakeholders, priority applications were identified in healthcare, education, tourism and gaming, positioning Jordan as a regional testbed for immersive technologies aligned with its Economic Modernization Vision. In Egypt, in collaboration with the National Telecommunications Regulatory Authority, BDT finalized the Smart Sustainable Cities and Communities Evaluation Framework and launched the procurement process for a software-based evaluation tool integrating ITU-T standards, the SDGs, and international best practices. In the Americas region, BDT advanced inclusive digital and secure digital financial services. In Antigua and Barbuda and Saint Lucia, BDT implemented the project “Optimizing innovative finance for underserved groups to build resilience and accelerate the achievement of the SDGs,” in collaboration with UN Women and UNDP. The project strengthened the digital financial services ecosystem through policy, regulatory, and cybersecurity measures, including the establishment of fully equipped DFS Security Labs in both countries. This initiative equipped more that 20 participants of multi-agency technical teams with the skills to conduct independent security audits of mobile payment applications across Android, iOS, and USSD platforms, ensuring alignment with international ITU-T security recommendations. Beyond technical training, the project fostered regulatory capacity for more than 60 participants by operationalizing National DFS Security Task Forces, embedding these security functions into permanent national governance frameworks to ensure long-term oversight and resilience. Over 80 people in the legislative, policy, and regulatory field on DFS participated and contributed to the development of draft recommendations. In Trinidad and Tobago, BDT supported the onboarding of the Ministry of Public Administration and Digital Transformation into the Global Digital Transformation Centre Initiative. This validated the network of ICT Access Centres in Trinidad and Tobago as a certified national hub, aligning local delivery with international standards and expanding access to digital literacy programmes for youth, senior citizens, persons with disabilities, and migrant communities, with a minimum target of 30 per cent female participation. In the Asia-Pacific region, BDT continued assistance to countries including Maldives and Mongolia, in Q4 2025, on digital transformation and the Whole of Government approach using GovStack. BDT supported the FAO Inter-regional Digital Agriculture Solutions Forum (IDASF) 2025, held from 3-5 September 2025, in collaboration with ADB, IFAD and IITA. The event engaged about 400 participants, enhancing awareness and knowledge on digital transformation and emerging technologies in the agriculture sector. Smart Villages and Smart Islands programmes in Fiji, Kiribati, Pakistan, Papua New Guinea, Tonga, and Vanuatu were strengthened in Q4 of 2025, through community engagements and digital skills events. In November 2025, a new project was also signed with DITRDCSA with a focus on enhancing the sustainability of Smart Villages and Smart Islands in the Asia-Pacific region. In the CIS region, BDT advanced digital government transformation through a regional project supporting digital public services. A series of technical webinars was delivered between September and December 2025 for countries in Central Asia and the South Caucasus, engaging 40 experts from seven countries. The sessions facilitated peer learning on digital government components and GovStack implementation, leveraging international expertise. In addition, a dedicated national training was delivered in Turkmenistan on 14 November 2025, engaging approximately 100 civil servants and students alongside the Turkmentel Conference. In Europe, BDT supported digital transformation at the local and sectoral levels. In Montenegro, the Digital Transformation of Local Self-Governments Project was successfully completed, building on a series of capacity-building activities launched in May 2025. The project combined stakeholder engagement, hands-on service design and GovStack methodologies, resulting in three digital service prototypes developed using low-code/no-code platforms. In Albania, BDT organized a GovStack workshop from 21 to 23 October 2025 under the Digital Agriculture and Rural Transformation project, strengthening national capacity to design interoperable digital services for the agriculture sector. By strengthening digital public infrastructure, BDT enabled governments and communities to adopt interoperable, inclusive, and future-ready digital systems. The work supported more resilient governance, expanded access to digital services and skills, empowered women and youth, and strengthened Member States’ capacity to harness digital transformation as a driver of sustainable development across regions. |  |
|  | - G20 - DPI Summit - GovStack - Smart Villages and Smart Islands - Africa: Gambia, Guinea, Guinea-Bissau, Nigeria, Senegal - Americas: Antigua and Barbuda, Saint Lucia, Trinidad and Tobago - Arab States: Mauritania, Jordan and Egypt - Asia-Pacific: Fiji, Kiribati, Maldives, Mongolia, Pakistan, Papua New Guinea, Tonga, Vanuatu - CIS: Armenia, Azerbaijan, Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan, Uzbekistan - Europe: Albania, Montenegro ITU-D Study Group 2: - Final report of Question 1/2 and Final report of Question 2/2 (2022-2025 study period) published |

| ## ITU-D Priority 3: Enabling policy and regulatory environment Promoting an enabling policy and regulatory environment conducive to sustainable telecommunication/ICT development |  |
| --- | --- |
| ### Capacity development Outcome: Improved human and institutional capacity of the ITU membership in telecommunications/ICTs to tap into the full potential of the digital economy and society |  |
| Output | Highlights |
| During the reporting period (1 September – 31 December 2025), the ITU Academy welcomed 9 649 new users, bringing the total userbase to 83 306 as of 31 December 2025, delivering training to participants from 193 Member States with users from developing countries accounting for 71 per cent of the community. During the same period, the platform hosted 74 courses, processed 11 900 registrations, accepted 8 354 participants across 5 476 unique learners, and awarded 2 124 certificates. A total of 27 courses were delivered under the ITU Academy Training Centres (ATC) programme, accounting for more than one third of the training conducted via the platform during the reporting period. Over 200 participants were certified, nearly 90 per cent of which are from developing countries, with the main represented regions being Africa, the Americas, and Asia-Pacific. In terms of affiliation, participants come from diverse professional backgrounds including ministries, regulatory authorities, telecommunication agencies, the private sector, and academia. Under the framework of the Capacity Development for Digital Transformation project, funded by the European Union, 11 additional training courses were delivered. These included 5 in-person training course as well as 6 online training courses with 399 additional participants trained. The total number of courses delivered under the project has reached 63, comprising 3 summer schools, 26 in-person training courses, and 34 online training courses, and a total of 3 454 policy-makers and government officials benefitted from training. The satisfaction rate for courses delivered under the project has been maintained at 96 per cent. In collaboration with Cisco and other partners, the Digital Transformation Centres (DTC) initiative continues to scale up its activities, providing sustained support to DTCs. By the end of 2025, more than 758 000 course participants had been trained in basic and intermediate digital skills since the inception of the programme, with women accounting for 51 per cent of participants. Through DTC training activities, more than 101 000 course participants were reached during this reporting period, with gender parity achieved among learners. In addition, two new centres, in Trinidad and Tobago and Nigeria, joined the DTC Initiative, bringing the total number of countries with Digital Transformation Centres to 16. The Initiative also welcomed a new partner, the Airtel Africa Foundation, which has begun by providing connectivity support to the DTC in Rwanda in 2026. Through the Project “Boosting Digital Skills through the Digital Transformation Centres", BDT in partnership with the Government of Norway continued to support the activities implemented under the DTC Initiative, with a particular focus on scaling up the delivery of digital skills training and strengthening digital literacy in local communities and among marginalized groups. Under this Project, and during the reporting period, ITU and DTCI partners supported five DTCs in Ghana, Rwanda, Senegal, Sierra Leone, and Uganda in conducting citizen training activities. In addition, support was provided to three DTCs in Ghana, Pakistan, and Uganda implementing outreach and promotional activities aimed at engaging communities and raising awareness on digital literacy. Training course delivery under the Giga Learning Hub, the umbrella platform for capacity development and training within the ITU-UNICEF Giga initiative, included two online courses and one in-person training course related to school connectivity held in Geneva during the reporting period. In total, 74 government officials, policy-makers, and regulators were trained. The Learning Hub launched its first training course in February 2025. The Giga Learning Hub initiative now comprises 48 countries across all regions. Following the release of the Digital Skills Toolkit in 2024, an eLearning course was developed during the reporting period. The course incorporates structured roadmap, international case studies, and practical exercises designed to support ITU Members in formulating and developing national digital skills strategies and policies. Through the African Blended Training Programme for ICT Network Managers in Indigenous and Rural Communities, five courses were successfully completed between September and December. The programme, which was virtually launched on 18 June 2025, was delivered in partnership with APC, Rhizomatica, AFRALTI, and other partners. A total of 99 participants from 23 countries enrolled in the programme. Of these, 49 participants representing 20 countries were pre-selected for the 2026 Bootcamp, from which 30 participants will be selected for the inaugural African regional edition. Overall, the programme achieved a 51 per cent completion rate across the five courses, with participation comprising 77.6 per cent men and 22.4 per cent women. In October 2025, ITU collaborated with Deutsche Internationale Schule (German international school) Johannesburg, South Africa to deliver the AGCCI online course through the Reach360 platform to 62 Grade 9 learners. Of these, 52 learners successfully completed at least one submodule. The course formed part of the preparation of students for an ICT-related bootcamp and hackathon organized by the school. In December 2025, ITU, in partnership with Women’s World Wide Web (W4) Kenya and the Communications Authority of Kenya, supported training for 71 girls under the African Girls Can Code Initiative (AGCCI). A total of 67 participants successfully completed the course during a five-day, offline-supported bootcamp. In addition, ITU, in collaboration with UN Women, the Communications Authority of Kenya, and Women’s World Wide Web Kenya, delivered training to 48 AGCCI trainers from 14 African countries. The training aimed to strengthen trainers’ capacity to effectively use the ITU Academy AGCCI course in face-to-face bootcamp delivery. The workshop also provided a platform for trainers to share feedback on course improvements and strategies for scaling up AGCCI across Africa to increase its reach and impact. In the Asia Pacific region, a week-long in-person training “AI Governance in Practice: Developing Secure and Innovative Frameworks”, took place in December 2025 in Thailand, in collaboration with the Office of the National Broadcasting and Telecommunication Commission of Thailand (NBTC) as part of the EU Global Gateway initiative. The training was tailored for policymakers, regulators, civil society leaders, and professionals aiming to enhance their AI governance skills and scenario-based exercises tackled sector-specific challenges, risk mapping, and cross-border regulatory negotiations. The aforementioned workshops on AI and standards in India, Malaysia, Bhutan and Cambodia also integrated the ITU Academy training programme. | ITU Academy: 83 000+ users, 193 Member States, 71% developing countries, 40% female. ATCs: 14 participating institutions, 159 courses, 4048 people certified since the launch of the programme DTCs: 16 DTCs, 758,000 course participants (51% female) trained since the launch of the Initiative. Digital skills development impacting: - ICT professionals - People in remote communities - Women and girls - Youth - Persons with disabilities - Entrepreneurs and MSME owners - Africa: Ghana, Kenya, Nigeria, Rwanda, Senegal, Sierra Leone, South Africa, Uganda - Americas: Trinidad and Tobago - Asia-Pacific: Bhutan, Cambodia, India, Malaysia, Thailand ITU-D Study Group 2: - Final report of Question 5/2 (2022-2025 study period) published |

| ### Policy and regulation Outcome: Strengthened capacity of Member States to enhance their telecommunication/ICT policy, legal and regulatory frameworks conducive to sustainable development and digital transformation. |  |
| --- | --- |
| Output | Highlights |
| The 23rd edition of the Global Symposium for Regulators (GSR-25) was held in Riyadh, Saudi Arabia, from 31 August to 3 September 2025 under the theme “Regulation for sustainable digital development”. GSR-25 featured thematic sessions that brought together regulators, policymakers, and digital stakeholders from around the world, providing a global platform for knowledge exchange around the topic “Regulation for sustainable digital development”. The event attracted 1 200 participants from more than 80 countries. A key outcome from GSR-25 was the adoption of the Best Practice Guidelines on "Empowering regulators as digital ecosystem builders” developed on the basis of over 50 contributions submitted through the annual stakeholder consultation. A series of special events were held on 31 August and 1 September, including the Executive Masterclass on Strategic Foresight for AI Collaborative Frameworks, and meetings of the Regional Regulatory Associations (RA), the Digital Regulation Network (DRN), and the Heads of Regulators' Executive Roundtable. The Industry Advisory Group on Development Issues and Private Sector Chief Regulatory Officers (IAGDI-CRO) convened on 1 September (IAGDI_CRO Outcome Statement), and a session of the Network of Women (NoW) was held on 2 September. The Regional Regulatory Associations/Digital Regulation Network (DRN) held their annual meeting on 1 September during the Global Symposium for Regulators (GSR-25). The meeting brought together 12 regional regulatory associations. This high-level gathering enabled Regional Regulatory Associations and their members to exchange experiences and practical insights (Report). Key themes of discussion included universal broadband access, competition, cybersecurity, innovation-enabling regulatory tools and strategies, and regional approaches to cross-border issues such as artificial intelligence, satellite-based communications, and data protection. New core content posted on the online ITU-World Bank Digital Regulation Platform included a Guide towards AI collaborative frameworks, and a Guide to meaningful public consultations (developed in collaboration with Ofcom, United Kingdom of Great Britain and Northern Ireland). New core materials included Monitoring sustainability: Incorporating ESG into ICT policymaking and regulation, as well as others on Collaborative governance, and Evidence-based approaches in digital policy, regulation and governance. In addition, the core resources on Access for all were updated and further developed. A collaborative digital regulation country review of Oman was launched at GSR-25, as part of the series of national country reviews on collaborative digital regulation that delivers targeted assessments of regulatory and governance frameworks, policies, and practices across the ICT and digital sectors. The Oman review was conducted in collaboration with government authorities, national stakeholders and recognized experts, drawing on ITU evidence-based tools and regulatory benchmarks. ITU policy and regulatory metrics continued to track global and regional trends across 194 countries. The 2024 ICT Regulatory Tracker and the 2025 G5 Benchmark releases highlighted global and regional trends shaping ICT and broader digital-enabling environments. Together, these tools offer a practical blueprint for reform, supporting evidence-based decision-making and enabling a global assessment of countries' capacities and readiness for digital transformation. Originally launched as the Unified Framework, the Digital Readiness Framework was launched on the G5 Accelerator platform to assess the readiness of national legal, policy, and governance frameworks for digital transformation. The online space features country profiles, interactive analytics, and maps. In September, a training on regional digital transformation regulations for the Association of Southeast Asian Nations (ASEAN) and Timor Leste was held in Jakarta, Indonesia. This training was organized with the joint support of ITU and the UK Foreign, Commonwealth and Development Office (FCDO), and of the Republic of Korea Ministry of Science and ICT (MSIT) projects and was hosted by the Ministry of Communications and Digital Affairs of Indonesia. The training attracted over 40 participants from 10 ASEAN countries and Timor Leste. In October, a training on satellite regulation for Sub-Saharan African countries was held in Lusaka, Zambia, organized with the World Bank, with the support of ITU FCDO, and hosted by the Zambia Information and Communications Technology Authority (ZICTA), and Smart Zambia. The training benefitted 31 participants from six countries. In the Africa region, the Laying the foundation for VaMoz Digital! project, financed by the European Commission, in support of the digital transformation journey of the Government of Mozambique, continued to support the Ministry of Communications and Digital Transformation in the design of the collaborative process towards developing the first digital transformation strategy for Mozambique. The official launch of the consultative national process will take place in early 2026. In Uganda, the ITU-Government of Uganda- China Global Development Fund Technical assistance training to Uganda on National ICT Development Strategy project officially concluded at the end of 2025. The project delivered 10 major policy documents, and a national digital skills assessment, as well as comprehensive digital skills and emerging technologies training which benefitted over 6 000 participants including government officials, students, and ICT professionals. Four pilot projects were also delivered with assessment reports to inform nationwide scaling Under the Africa-BB-Maps project, national broadband mapping policy assessments were conducted in Nigeria, Côte d’Ivoire, Kenya, and Botswana during the last quarter of 2025 with a view to strengthening data-driven broadband regulation and policy frameworks. The analyses assessed existing legal, regulatory, and institutional arrangements for broadband data collection, sharing, and use, and identified gaps and recommendations to enable sustainable, country-owned broadband mapping systems. This work supported data-driven regulation and evidence-based policy-making to advance digital transformation and universal connectivity. As part of the European Union-funded ICT Benchmarking in Central Africa project, BDT finalized 23 key policy documents between September and December 2025; two policy documents per beneficiary country and one regional-level document for the Economic Community of Central African States (ECCAS). Building on these outputs, BDT organized a final online workshop on 9 December, bringing together over 50 participants from the 11 countries and sub-regional organizations including ECCAS, the Central African Economic and Monetary Community (CEMAC), and the Africa Regional Technical Assistance Centre (ARTAC). The workshop presented the main findings, shared good practices, and proposed national and regional roadmaps, marking a key milestone and laying the groundwork for follow-up actions and implementation. In the Americas region, the ITU Policy and Economics Colloquium (IPEC-25) for the Americas was held in Montevideo, Uruguay, from 6 to 10 October 2025, organized by the BDT in collaboration with the Dirección Nacional de Telecomunicaciones (DINATEL) . The programme included the ITU-D Regional Economic Dialogue on 6-7 October, featuring a session on ITU-D Study Group 1 Question 4/1 (economic aspects of national telecommunications/ICT) and the ITU Digital Regulation Network (DRN) high-level session on building an innovative ecosystem to address regional and global challenges. With support from the Ministry of Science and ICT (MSIT) of the Republic of Korea, IPEC-25 also included a workshop on emerging technologies for innovative connectivity solutions, covering policy, economic, and technical aspects of new technologies, as well as the meeting of the ITU-T Study Group 3 Regional Group for Latin America and the Caribbean (SG3RG-LAC), and the meeting of the ITU-T Study Group 2 Regional Group for the Americas (SG2RG-AMR). Further progress was made through the Technical Assistance project implementing regulatory innovation mechanisms in Panama, the Dominican Republic, Honduras, El Salvador, Costa Rica, Belize, and Guatemala. During the last quarter of the year, two national regulatory innovation training courses were held, one in the Dominican Republic and the other in Costa Rica, and the advisory committee of the Technical Assistance project met in the Dominican Republic bringing together participants from all seven countries. Additionally, in coordination with the Arab Regional Office, the Digital Regulation Programme for the Americas was held in Managua, Nicaragua and brought together participants from Colombia, Nicaragua, Honduras, Costa Rica, Ecuador, El Salvador, and the Dominican Republic of which 48 were certified by the ITU Academy. Within the framework of the Project for the Implementation of Regulatory Impact Analysis (RIA) Methodologies, the first phase of technical assistance to Paraguay was completed. This phase supported the integration of RIA into the regulatory design processes of the National Telecommunications Commission (CONATEL). Following its successful completion, the project was extended for an additional year to implement a pilot project on Regulatory Impact Analysis and Regulatory Simplification in Paraguay. BDT provided technical input to the Government of Peru to support the work of the Ministry of Transport and Communications in updating the Telecommunications Law. The contribution of ITU is being incorporated into the deliberations of the dedicated working group established for this purpose. A first draft report was shared with Peru in December 2025, initiating a process of technical exchanges and comments that will inform the final version, expected in early 2026. In the Arab States region, significant progress was achieved in advancing digital regulatory frameworks and digital transformation initiatives. BDT successfully finalized the collaborative digital regulation country reviews in Oman and Qatar, assessing regulatory maturity, governance structures, and alignment with international best practices, and providing actionable recommendations to strengthen regulatory ecosystems. In addition, BDT provided country-level technical assistance to Comoros to enhance data-driven regulatory decision-making. This support strengthened regulatory analytics capabilities and reinforced institutional capacity to implement evidence-based oversight mechanisms. Finally, BDT successfully concluded its support to Somalia in the development of a national digital transformation strategy. This assistance advanced policy reform priorities, strengthened institutional readiness, and laid the foundation for inclusive and sustainable digital development. In the Asia-Pacific region, as part of the strengthening and enabling policy harmonization of Timor Leste into the ASEAN block, technical assistance was provided to Timor Leste on digital transformation analysis and alignment with ASEAN frameworks. This complemented efforts by Timor Leste to enable digital integration as the 11th Full Member of ASEAN. As a follow up to the technical assistance delivered to Lao Telecom Regulatory Authority in preparing its telecommunication and Internet development strategy, the National Telecommunications and Internet Development Strategy (2026-2040) was officially approved under Prime Minister Decree No. 825/PM on 24 December 2025, representing a transformative step toward a modernized regulatory framework in Lao P.D.R. BDT also supported Kiribati to accelerate the finalization of its digital transformation policy which was at the advanced stage in Q4 of 2025. In September, during the CRC Regulatory Forum in Mongolia, awareness on best regulatory practices in building digital ecosystem as per GSR-25 guidelines was raised among 125 participants. In September, with support from FCDO‑UK, MSIT‑Korea and KomDigi (Ministry)‑Indonesia, a regional training on digital regulations for ASEAN and Timor‑Leste was held in Jakarta, Indonesia. Under the ITU–FCDO partnership, further efforts to enhance Indonesia’s enabling environment continued in several areas, including e‑waste regulation, guidance & study on the use of village development funds for digital connectivity in rural and remote areas, and a policy and regulatory checklist for satellite services. Further, a policy briefing on spectrum management and processes was also arranged for the KomDigi and Audit teams (Indonesia). In the CIS region, two countries received targeted assistance. In Kyrgyzstan, BDT provided support on an assessment of price affordability of mobile and fixed connectivity to support national efforts in ensuring that Internet access remained accessible and affordable to the public, along with measures to support infrastructure modernization by the operators. BDT also worked closely with the Government of Tajikistan on ITU Regulatory Tracker data to ensure a proper data reflection and analysis and progress the development of Internet connectivity. In the Europe region, the ITU-EKIP Regional Regulatory Forum for Europe 2025 took place in September in Budva, Montenegro, and focused on “Building a Resilient and Human-Centric Digital World”. The Forum brought together over 180 participants and advanced discussions on gigabit connectivity, resilient infrastructure, and an enabling environment for universal coverage. A series of ITU, EMERG, EaPeReg workshops aimed towards building the capacities of nine countries in the field of digital regulation, infrastructure mapping, and resilience, while contributing to actions under the Digital Regulators Network. The ITU-powered Techritory Forum 2025, held in October, in Riga, Latvia, welcomed over 1 600 high-level participants, and served as a vibrant platform for digital innovation and collaboration among industry, regulators, and academia. | - Improving national policy and regulations: - GSR - 1200 + participants - 100+ countries - 50+ contribution to the consultation for GSR Best Practice Guidelines - Knowledge resources published on the digital regulation platform - Collaborative digital regulation country reviews for Oman and Qatar. Africa: - Botswana, Côte d’Ivoire, Kenya, Mozambique, Nigeria, Uganda - ITU-EU ICT benchmarking in Central Africa project - ITU-EUDEL-Government of Mozambique laying the foundation for VaMoz Digital! project - ITU-China GDF-Government of Uganda technical assistance and training to Uganda on National ICT Development Strategy project Americas: - Belize, Costa Rica, Dominican Republic, El Salvador, Guatemala, Honduras, Nicaragua, Panama, Paraguay, PeruIPEC –25 was held in Uruguay - Regulatory innovation mechanisms provided to Panama, the Dominican Republic, Honduras, El Salvador, Costa Rica, Belize, and Guatemala Arab States: - Comoros, Oman, Qatar, Somalia - Collaborative digital regulation country reviews for Oman, and Qatar - Country technical assistance to Comoros on data driven regulation and digital transformation strategy for Somalia. Asia-Pacific - Indonesia, Kiribati, Lao People's Democratic Republic, Mongolia, Timor-Leste - National Telecommunication and Internet Development Strategy for Lao PDR (2026-2040) - Digital transformation analysis for Timor Leste - Policy advice to Mongolia - Strengthening enabling environment in Indonesia on e-waste, funding for rural connectivity CIS: - Kyrgyzstan, Tajikistan Europe - Capacity development for over 2000 European stakeholders thanks to actions in Montenegro, Latvia, and Cyprus |
| ### Statistics Outcome: Strengthened capacity of Member States to produce and collect high quality, internationally comparable statistics which reflect developments and trends in telecommunications/ICTs, empowered by new and emerging technologies and services, based on agreed standards and methodologies. |  |
| Output | Highlights |
| BDT continued its efforts to spearhead the development of key indicators, tested innovative methodologies, and modernized statistical platforms, further increasing a broad range of validated data points available for public use. In September, ITU ICT Data Week 2025 gathered over 270 participants from 85 countries. The 20th edition of the World Telecommunication/ICT Indicators Symposium took place under the theme “WTIS@20: The Past, Present, and Future of Digital Development Statistics.” For the first time, the annual meetings of ITU Expert Groups on Telecommunication/ICT Indicators and on ICT Household Indicators (EGTI and EGH) featured a workshop for ICT statistics practitioners. In November, the 2025 edition of Measuring digital development: Facts and Figures was released at the World Telecommunnication Development Conference 2025 (WTDC-25). The ITU annual publication on the state of global digital connectivity showed that about three-quarters of the global population were using the Internet in 2025: 6 billion people up from a revised estimate of 5.8 billion in 2024. Released on the closing day of WTDC, the Global Connectivity Report 2025 assessed progress towards universal and meaningful connectivity (UMC), highlighting both the benefits of digital transformation and the persistence of digital divides and emerging online and environmental risks. The report provided evidence-based insights on addressing affordability, skills and device gaps, strengthening infrastructure resilience, and reinforcing national data ecosystems to support policymaking. In December, the 2025 ICT price basket statistics were published, providing insights into fixed- and mobile-broadband affordability for nearly 200 economies. This represents the first set of statistics based on the revised methodology agreed by the Expert Group on Telecommunication/ICT Indicators (EGTI) members in the previous year. In October, as part of the implementation of the project “Promoting and Measuring Universal and Meaningful Connectivity (UMC)”, BDT kicked off the Data Hackathon “Bridging the Digital Divide by Uncovering Digital Deserts”, designed to mobilize creativity and data analysis to identify connectivity gaps and sub-populations left behind in the process of achieving UMC. In November, BDT held a regional workshop for Portuguese-speaking African countries in Sao Tome and Principe as part of an 11-workshop series launched in 2024 in the context of the project. A new microsite on data science for official statistics was launched in December 2025, showcasing opportunities, case studies, practical guides, and tools. In November, a three-day workshop in Maldives brought together stakeholders from the national statistical office, the telecommunication regulator, mobile network operators, government officials, and international experts. Participants received hands-on training on the ITU Jupyter Notebooks, supporting the use of mobile phone data for official statistics. In October, the ICT Data and Analytics Division (IDA) launched the first issue of ITU Statistics Update, a new information bulletin for the global community of ICT statistics focal points. The second issue was released in December. In addition, IDA participated in the meetings of the Committee of Chief Statisticians of the United Nations System (CCS-UN) and the Committee for the Coordination of Statistical Activities (CCSA-UN) held in October, and representing the organization at both forums attended by Chief Statisticians of the United Nations system. Participation in these meetings ensures that ITU continues to be recognized as a global leader in ICT statistics and remains informed of discussions on cross-cutting statistical issues with direct relevance to the work of the division. In the CIS region, in Kyrgyzstan a Digital Skills assessment for civil servants and municipal workers was organized in collaboration with the State Agency for civil service and local self-governance. The outcomes of survey and data analysis were presented at a Roundtable in December, attended by representatives from 17 ministries and agencies of Kyrgyzstan. Cooperation and assistance will continue in 2026 through development of methodologies, assessment criteria and training plans, targeted to address national legislation requirements. A revised text of WTDC Resolution 8 on the Collection and dissemination of information and statistics (Rev. Baku, 2025) was adopted at WTDC-25 in Baku. | - 20th edition of WTIS - EGTH & EGH work programme - Measuring digital development: Facts and Figures 2025; Global Connectivity Report 2025 - Workshops: - Africa: Sao Tome and Principe - Asia-Pacific: Maldives - CIS: Kyrgyzstan |
| Contributing to SDG Targets SDGs 1, 3, 4, 5, 8, 9, 10, 11, 16, 17 |  |
| WSIS Action C1, C2, C3, C4, C5, C6, C7, C1 |  |
| Resolutions PP 2, 8, 10, 18, 21, 22, 131, 135, 138, 139, 174, 191, 195, 196, 201 / WTDC 8, 16, 17, 22, 23, 25, 30, 37, 48, 64, 71, 77, 78, 79, 80, 84, 85 |  |

| ## ITU-D Priority 4: Resource mobilization, partnerships and international cooperation Strengthening resource-mobilization strategy through international cooperation. |  |  |
| --- | --- | --- |
| Outcome: Strengthened cooperation and coordination with the United Nations and its agencies, other international organizations, regional telecommunication organizations and regional and global development institutions in the implementation of ITU-D priorities. |  |  |
| Outputs |  | Highlights |
| BDT continued to consolidate partnerships and resource mobilization as central drivers of digital transformation. From September to December 2025, BDT signed 35 new partnership agreements with a wide range of partners, bringing the overall number of partnerships for the year 2025 to a total of 76 partnership agreements, representing USD 7.6 million in commitments. During the last quarter of 2025, 8 new digital development projects, for a value of USD 1.2 million were signed, bringing the total of projects signed in 2025 to 26 new projects for a value of USD 5.5 million. With a view to further strengthening cooperation and coordination with the United Nations, BDT in collaboration with UN-Habitat, organized a webinar for United Nations country teams on “Harnessing the opportunities of innovation and emerging technologies to accelerate implementation of smart sustainable cities and communities in Africa.” Overall, the webinar reinforced a common understanding among United Nations country teams of how innovation and emerging technologies can be strategically leveraged to advance digital development, with a strong emphasis on alignment with United Nations Sustainable Development Cooperation Frameworks (UNSDCFs). Furthermore, it strengthened inter-agency collaboration at country level, and contributed to accelerating the collective implementation of UNSDCFs in support of inclusive, resilient and sustainable development. Figure 1: United Nations Sustainable Development Cooperation Frameworks (UNSDCFs) signed in 2025 Region; UNSCDF Benefiary Country; UNSCDF Timeframe. Africa; Eswatini; 2026-2030. Ethiopia; 2025-2030. Namibia; 2025-2029. Rwanda; 2025-2029. Uganda; 2026-2030. Americas; Cuba; 2026-2030. Guatemala; 2026-2030. Panama; 2026-2030. Arab States; Bahrain; 2025-2029. Djibouti; 2025-2030. Asia-Pacific; Indonesia; 2026-2030. CIS; Armenia; 2026-2029. Azerbaijan; 2026-2030. Belarus; 2026-2030. Kazakhstan; 2026-2030. Turkmenistan; 2026-2030. Uzbekistan; 2026-2030. Europe; Georgia; 2026-2030. North Macedonia; 2026-2030. Serbia; 2026-2030. | - 76 new partnership agreements for a value of USD 7.6 million - 20 UNSDCF signed - 8 new digital development projects for a value of USD 1.2 million |
| Contributing to SDG Targets | SDGs 1, 3, 4, 5, 8, 9, 10, 11, 16, 17 |  |
| WSIS Action | C1, C2, C3, C4, C5, C6, C7, C11 |  |
| Resolutions | WTDC 1, 2, 24, 25, 52, 58 |  |

| ## ITU-D Priority 5: Inclusive and secure telecommunications/ICTs for sustainable development Fostering national cybersecurity strategies and strengthened digital skills |  |  |
| --- | --- | --- |
| ### Cybersecurity Outcome: Support to Member States in developing national cybersecurity strategies and CIRTs. Increased secured online services, including child online protection, and mobilization of resources for marginalized groups and persons with specific needs. |  |  |
| Outputs |  | Highlights |
| The Cyber for Good project has continued to provide tailored assistance to vulnerable countries, supporting the creation of computer incident response teams (CIRTs), maturing CIRTs and laying the groundwork for national cybersecurity strategies. BDT promotes a culture in which cybersecurity is seen as a continuous and iterative process, built into products from the beginning and continuing throughout their lifetime, and is accessible and understandable for users. New beneficiary countries from the Asia-Pacific region, Tonga and Samoa, were onboarded under the Cyber for Good project. Through this project, both countries benefit from access to tools and solutions provided by ITU-D Private Sector Members. The ITU Child Online Protection (COP) programme continued to focus on consolidating global normative guidance, strengthening multi-stakeholder governance, and advancing prevention education, in line with WTDC Resolution 67 (Rev. Kigali). A key milestone was the finalization of the Joint Statement on Child Rights in the Context of Artificial Intelligence, led by ITU in collaboration with the United Nations Committee on the Rights of the Child and UNICEF, and co-developed with ten additional United Nations entities, including the International Labour Organization (ILO), UNESCO and the Office of the United Nations High Commissioner for Human Rights (OHCHR). Completed in late 2025 ahead of its January 2026 launch, the Statement provides high-level, non-binding recommendations to ensure children’s rights are embedded in AI design, development and deployment, reinforcing UN system coherence and ITU leadership in child online protection. In December 2025, BDT and partners launched the Protection through Online Participation (PoP) Global Principles. Grounded in global mapping, consultations with children and youth, and broad multi-stakeholder engagement, the PoP Principles provide practical, evidence-based recommendations to governments, helplines, and the ICT industry to strengthen online support systems and improve children’s access to protection and assistance in digital environments. Implementation of the Global Online Safety Alliance for Educational Resources (GO-SAFER) also progressed, with the activation of its Steering Committee and Advisory Board. Led by ITU, in collaboration with the World Health Organization and the University of New Hampshire, and supported by Safe Online, the initiative advanced governance structures and technical preparations for a centralized global resource hub to scale evidence-based prevention education on online child sexual exploitation and abuse. In the Africa region, Digital Financial Services (DFS) Security Clinics were delivered in at least ten countries, advancing several national DFS Security Labs to higher maturity phases. The African Telecommunications Regulator Assembly (ARTAC) DFS Clinic was organized in Chad with strong participation from regulators, Central Bank of Central African States (BEAC), and operators. This was held back-to-back with a workshop on geospatial information for optical fiber infrastructure planning, creating valuable synergies. Additionally, three DFS Security webinars were held between July and December 2025, and attracted nearly 300 participants across Africa, strengthening awareness of threats such as social engineering, weak encryption, and phishing‑resistant credentials. In the Americas region, BDT deployed the CIRT Readiness Assessment for Guatemala and Honduras. The technical assessment delivered the results and recommendations of the GCI and CIRT Readiness Assessment plus on-site technical training necessary for the further deployment of the national CIRT. During the onsite training, readiness was assessed against the effectiveness of their incident response plan and procedures, including the national computer incident response team (CIRT). The interactive sessions were built to improve coordination and communication among stakeholders such as governmental agencies, the private sector, and civil society in responding to cyber threats and incidents. The technical training included several bilateral meetings with representatives from the regulatory authorities, and national stakeholders to guide Member States in strengthening National Cybersecurity capacity. In the Arab States region, BDT continued to advance cybersecurity capacity building across the region through a series of targeted technical and governance initiatives, reaching and training more than 130 participants across key stakeholder groups. Mauritania and Djibouti benefited from ISO/IEC 27005 Risk Management trainings, equipping national stakeholders with structured methodologies for cyber risk assessment and strengthening readiness for Critical Information Infrastructure (CII) designation and protection. Djibouti additionally received support on Cybersecurity Governance Development, resulting in a nationally tailored CIIP framework, enhanced interagency coordination, and the deployment of a digital platform for CII data collection and oversight. Kuwait received ISO/IEC 27001 Lead Implementer training, improving institutional competencies for implementing and maintaining Information Security Management Systems aligned with international standards. Within the framework of the Global Child Online Protection project, BDT is working to implement the Child Online Protection (COP) Guidelines in Morocco in partnership with the Agence du Développement du Digital (ADD). As a key component of this collaboration, a series of capacity-building and awareness-raising workshops were organized for educators, child parliamentarians, parents, children, and young people from May to November 2025. These sessions were designed to strengthen national capabilities in addressing online risks, and to empower young people with crucial digital safety skills. To ensure sustainability and wide reach of these initiatives, comprehensive support was provided by BDT for the development of key awareness-raising materials. In close collaboration with the ADD, BDT oversaw the conception and production of a suite of resources, including four full-colour brochures for children and parents, each available in both Arabic and French. In addition, two educational motion design videos were created, one tailored for parents and tutors, and another for children and youth. Each video, lasting three to five minutes, was produced in Arabic with French subtitles to maximize accessibility and impact. Regionally, BDT delivered multiple operational exercises, including the Arab International Cybersecurity Conference and Exhibition (AICS 2025) in Bahrain, which strengthened capacities in cyber crisis management, threat detection, and critical infrastructure protection, and a a joint CyberDrill with Interpol and NCSC Qatar at the 15th MENA Working Group Meeting on Cybercrime in Qatar, improving ransomware response and investigative capabilities. Collectively, these activities contributed to enhanced national resilience, strengthened institutional frameworks, and improved operational readiness across Arab States. In Egypt, the joint initiative between ITU, UN Women, and UNODC advances efforts to eradicate cyberviolence against women by strengthening national coordination and response mechanisms. Through a human security approach, the programme enhances evidence-based policymaking, builds the capacity of law enforcement, technology actors, and civil society, and promotes safer digital engagement. By addressing technology-facilitated violence while reinforcing the empowering potential of digitalization, the project contributes to more secure, inclusive, and resilient online environments for women and girls. In the Asia-Pacific region, BDT, in collaboration with the Ministry of Digital Development, Innovation and Communications (MDDIC) and with the support of the Cyber Security Council of Mongolia, delivered the 2025 ITU Regional Asia-Pacific CyberDrill, in Ulaanbaatar, Mongolia in September 2025. The CyberDrill brought together over 2 00 attendees at the regional conference. Additionally, over 80 attendees joined in the training sessions and scenario-based exercises, in which participants strengthened their capacity to manage cyber incident response. Through the Ministry of Internal Affairs and Communications (MIC), Japan supported the Pathways to Cybersecurity in the Pacific project. BDT has been building and enhancing cybersecurity capacities through the development of a certified cybersecurity capacity building programme for entry-level professionals in Pacific Island Member States. The project is being implemented in collaboration with the Asia Pacific Network Information Centre (APNIC) Foundation, and the National University of Vanuatu (NUV). The pilot training course was implemented from July – December 2025, and featured 230 hours of content that included both virtual content and one-week of physical exercises in December 2025. BDT has advanced efforts in cybersecurity, child online protection, and capacity-building initiatives. In terms of cybersecurity technical assistance, ITU delivered CIRT assessments in Mongolia and Maldives in September and December 2025 respectively, providing recommendations for cybersecurity stakeholders in both countries. ITU also delivered National Cybersecurity Strategy assistance to Palau in September 2025. In line with ITU global programming on child online protection, BDT delivered Child Online Protection (COP) policy assistance in Palau in September 2025. Additionally, in December 2025, BDT delivered a training of trainers of educators in Maldives. In the CIS region, the ITU and World Bank CIRT establishment project in Kyrgyzstan was finalized in December. The project deployed a network of sensors nationwide and launched a centralized monitoring centre within the Ministry of Digital Development and Innovative Technologies. This milestone strengthens the capabilities of Kyrgyzstan in detecting, preventing, and responding to cyber threats, and lays a foundation for ongoing cybersecurity collaboration with regional and international partners. Enhancing capacity at the national level is promoted by BDT. Activities delivered include national cyberdrills in Kyrgyzstan (24–26 September), and in Armenia (22–24 October 2025), and a cybersecurity training for telecommunication operators in Belarus (13–17 October). The cyberdrill in Kyrgyzstan was co-organized with the Organization for Security and Co-operation in Europe(OSCE)country office and the Ministry of Digital Development and Innovative Technologies of Kyrgyzstan, and in Armenia with the Information Security Authority of Armenia (ISAA). These exercises provided hands-on scenarios simulating real-world cyber incidents, enhancing the operational readiness of national CIRTs and relevant agencies. The drills strengthened national and regional collaboration, improved incident response procedures, and fostered knowledge exchange on emerging cybersecurity threats. Specialized cybersecurity training for Belarusian telecommunication operators co-organized with the Belarusian State University of Informatics and Radioelectronics (BSUIR) focused on improving incident detection, mitigation strategies, and operational response capabilities, contributing to enhancing resilience of critical national infrastructure and a safer digital ecosystem across Belarus and the CIS region. BDT continued to support Child Online Protection within the CIS Region. During the “KazHackStan 2025” Conference in September in Almaty, Kazakhstan, a dedicated panel session “Protecting children online: The ICT sector’s role” was co-organized with TSARKA which is an ITU-D Sector Member, and the UNICEF country office to bring together representatives from government, industry, and international organizations to share achievements, best practices, and recommendations in creating a safe and empowering digital space for children. In September, in the Europe region, BDT, in partnership with the Western Balkans Cyber Capacity Centre (WB3C), organized a four-day training in Montenegro on Critical Infrastructure Protection and the Malware Information Sharing Platform (MISP). The event brought together experts from the Western Balkans, Georgia, and Ukraine to strengthen national cyber resilience and information-sharing frameworks. In Andorra, the Child Online Protection Assessment was carried out and led to the development of the national strategy and implementation plan. A dedicated Child Online Protection (COP) session at the Andorra Digital Forum (30 October) with over 120 participants, emphasized safeguarding younger users and developing safe digital environments for children. In addition, the ITU COP Guidelines were translated into Catalan, the national language of Andorra, enabling the country to conduct a nationwide dissemination campaign and strengthen public awareness on child online safety. Finally, the International Scientific and Practical Conference on “Digital Transformation: Strengthening Cybersecurity Capacities in the Modern World" was held in November in Krakow, Poland. It brought together over 100 stakeholders, including Member States, the private sector, and Academia. |  | - Africa: Chad - Americas: Guatemala, Honduras, Nicaragua - Arab States: Bahrain, Djibouti, Egypt, Kuwait, Mauritania, Morocco, Qatar, Somalia - Asia-Pacific: Maldives, Mongolia, Palau, Samoa, Tonga, Vanuatu - CIS: Armenia, Belarus, Kazakhstan, Kyrgyzstan - Europe: Andorra, Albania, Bosnia and Herzegovina, Montenegro, North Macedonia, Poland, Serbia, Georgia, Ukraine ITU-D Study Group 2: - Final report of Question 3/2 (2022-2025 study period) published |
| Contributing to SDG Targets | SDGs 1, 3, 4, 5, 8, 9, 10, 11, 16, 17 |  |
| WSIS Action | C1, C2, C3, C4, C5, C6, C7, C11 |  |
| Resolutions: | PP 130, 174, 179; WTDC 45, 69; WTSA 52, 58 |  |
| ITU-D study group Questions | Question 3/2 (Cybersecurity) of Study Group 2 on Digital transformation |  |

| ## ITU-D Enabler 1: Membership-driven Strengthening the implementation of WTDC decisions and the dialogue among the ITU membership. |  |  |
| --- | --- | --- |
| Outcome: Strengthened implementation of WTDC resolutions. Enhanced knowledge-sharing, research and development, dialogue and partnership among the ITU membership on telecommunication/ICT issues. |  |  |
| Outputs |  | Highlights |
| BDT continued its efforts to facilitate inclusive dialogue with regulators, industry, academia, civil society, and development partners with a view to shaping the digital agenda. During this period, membership continued to diversify, and new platforms evolved into effective vehicles for collective action. Membership ITU-D consolidated and expanded its membership base through a mix of outreach, engagement, and tailored partnerships across the ICT ecosystem. From September to December 2025, BDT welcomed 16 new Sector Members, Associates and Academia, reaching the highest level of total new membership for this period in the past five years. By the end of December 2025, ITU-D counted a total of 550 members, of which 345 were Sector Members, 24 Associates, and 181 Academia members. The Bureau maintained its commitment to outreach and engagement ahead of WTDC-25, holding over 50 briefing sessions with membership in various formats, including physical meetings and virtual consultations, and high-level visits. These gatherings demonstrated how engagement activities evolved into increased participation of ITU-D Sector Members and Academia in WTDC-25, with over 200 delegates attending physically. ITU-D study groups 15 (14 new and 1 revised) final reports of the 2022-2025 study period have been published in all official languages of the Union. They are available for free public download at this web page. Following WTDC-25, the work of the 2026–2029 study period is organized under two study groups: Study Group 1 (SG1, Universal meaningful connectivity for bridging the digital divide), and Study Group 2 (SG2, Digital transformation). The number of study Questions was reduced from seven to five as a result of merging of previous topics into the new Questions, along with some new topics. The scope of the two ITU-D study groups and the Questions assigned by WTDC-25 can be found in Annexes 1 and 2 of WTDC Resolution 2 (Rev. Baku, 2025) respectively. SG1 is chaired by Mr Roberto Mitsuake Hirayama (Brazil), supported by 16 vice-chairs, and SG2 chaired by Mr Fadel Digham (Egypt), assisted by 13 vice-chairs. The list of appointed chairs and vice-chairs can be found in Annex 3 of WTDC Resolution 2 (Rev. Baku, 2025). In preparation for the next study group meetings, the study group web site for the 2026-2029 study period has been completed. A circular letter (BDT/PPS/CSTG-1) to call for nomination of rapporteurs and vice-rapporteurs for the new study Questions was issued on 16 December 2025. The appointment of new rapporteurs and vice-rapporteurs will be confirmed during the SG meetings, scheduled from 13 to 17 April 2026 for SG1, and from 20 to 24 April 2026 for SG2, in Geneva (Switzerland). More information about the upcoming SG meetings is available in the circular letter BDT/PPS/CSTG-2. WSIS implementation and follow-up As per WTDC Resolution 30, Rev. Baku and Plenipotentiary Resolution 140, Rev. Bucharest, all the activities of BDT contribute to the implementation of World Summit on the Information Society (WSIS) Action Lines and achievement of Sustainable Development Goals. In this context, BDT continued addressing all entrusted roles and responsibilities vis-à-vis WSIS and SDG processes, as reported in this document (see references to WSIS Action Lines and SDGs for specific linkages in each section of the document). WTDC-25 agreed on the Baku Action Plan, and adopted a set of new Study Groups’ Questions as well as a series of Regional Initiatives, all directly aligned with WSIS Action Lines and SDGs. It also updated Resolutions, including Resolution 30 on “Role of the ITU Telecommunication Development Sector in implementing the outcomes of the World Summit on the Information Society and the 2030 Agenda for Sustainable Development”, reiterating the importance of the contribution of ITU-D. Moreover, the United Nation General Assembly (UNGA) has completed its 20-year review of the implementation of the WSIS outcomes, looking forward to the next review in 2035. In line with the UNGA Review and revised WTDC-25 Res. 30, BDT will continue play the role of the lead facilitator for WSIS Action Lines C2, C4, C6, and support the General Secretariat in leading WSIS AL C5. BDT will also continue contributing to WSIS Action Lines C1, C3, C7, and C11, in which ITU is now identified as a co-facilitator, as well as C8 and C9, in which ITU is identified as a partner. BDT will also lead on Partnership on Measuring ICTs for Development. At the regional level, with the aim of strengthening coordination and building partnerships for the accelerated implementation of Regional Initiatives, six Regional Development Forums will be convened throughout 2026. In addition, BDT will contribute to five United Nations Regional Forums on Sustainable Development to ensure alignment between WSIS and SDG processes, while underlining the enabling role of digital technology for sustainable development. ITU Partner2Connect (P2C) Coalition Launched by ITU, in close cooperation with the Office of the United Nations Secretary-General's Envoy on Technology, and in line with the United Nations Secretary-General's Roadmap for Digital Cooperation, P2C is a multistakeholder alliance for mobilizing resources and fostering partnerships to achieve universal meaningful connectivity and sustainable digital transformation. Guided by its Action Framework, the Coalition convenes governments, the private sector, civil society, and international organizations to align commitments with national priorities and the WTDC Action Plan. The global reach of the Coalition is complemented by matchmaking sessions organized by BDT at the Regional Development Forums (RDFs), where countries articulate concrete needs, and partners respond with targeted offers of support, ensuring that mobilized resources translate into measurable outcomes. BDT will be organizing a series of RDFs across regions this year (2026) where each region will tackle the challenges and opportunities, from infrastructure gaps and affordability barriers to digital skills, cybersecurity, and emerging technologies, and matchmaking sessions will be undertaken accordingly. |  | Membership: - 16 new members joined between September and December 2025 - 200+ participants from ITU-D Sector Members and Academia in WTDC-25 - 550 members by December 2025 Study groups: - 15 final reports (2022-2025 study period) published. - 2 study groups and 10 new study Questions approved at WTDC-25 - 2 chairs and 29 vice-chairs appointed to lead the work of the SGs - Call for nominations of new rapporteurs and vice-rapporteurs issued - First meetings of SG1 and SG2 scheduled in April 2026 WSIS implementation: - 7 Action Lines facilitated by ITU - Partnership on Measurement of the ICT for Development led by ITU - 5 ICT-related SDG indicators maintained under ITU custodianship - WSIS+20 High-Level Event and follow-ups reaffirmed ITU-D leadership in global digital development |
| Contributing toWSIS SDG Targets | SDGs 1, 3, 4, 5, 8, 9, 10, 11, 16, 17 Contributing to SDG targets and WSIS action lines: see mapping here |  |
| WSIS Action | C1, C2, C3, C4, C5, C6, C7, C11 |  |
| Resolutions | WTDC Res. 1, 2 and 36 mainly PP Res 208, 21, 70, 71, 77, 102, 123, 130, 131, 136, 139, 154, 167, 175, 177, 179, 180, 182, 188, 196, 197, 203, 204, 205, 209. |  |
| ITU-D study Group Questions | All Questions of Study Group 1 on Enabling environment for meaningful connectivity and of Study Group 2 on Digital transformation |  |

| ## ITU-D Enabler 2: Regional presence Strengthening of ITU overall global effectiveness and impact |  |  |  |  |
| --- | --- | --- | --- | --- |
| Outcome: Strengthened joint regional collaboration and cooperation and with the United Nations and its agencies, regional telecommunication organizations and financial and development institutions for achieving the 2030 SDGs related to digital economy development matters |  |  |  |  |
| Outputs |  |  | Highlights |  |
| BDT continued to work closely with ITU Radiocommunication Bureau (BR), the Telecommunication Standardization Bureau (TSB), and the ITU General Secretariat to strengthen the regional presence, aiming to improve service delivery to Member States, including projects implementation and other operational plan activities in a timely, effective, and impactful manner. Regional offices of ITU continued to support United Nations coordination by working with Resident Coordinators and contributing to the United Nations Sustainable Development Cooperation Framework (UNSDCF), ensuring digitalization is embedded in national strategies. Through collaboration with United Nations agencies, regional bodies, governments, and stakeholders, they foster coherence and maximize impact. In order to enhance service delivery to ITU membership, BDT has been implementing a project funded by Australia on the Pacific regional presence. Within the framework of the project, the Pacific situation analysis and needs assessment was conducted and the summary is found in Annex 1 to Add 1 of TDAG Document 2. |  |  |  |  | - Strengthened intersectoral coordination within ITU - Enhanced service delivery to ITU Membership |
| Contributing to SDG Targets |  | SDGs 1, 3, 4, 5, 8, 9, 10, 11, 16, 17 |  |  |  |
| WSIS Action |  | C1, C2, C3, C4, C5, C6, C7, C11 |  |  |
| Resolutions: |  | WTDC 16 |  |  |
| ITU-D study group Questions |  | All Questions of Study Group 1 on Enabling environment for meaningful connectivity and of Study Group 2 on Digital transformation |  |  |

| ## ITU-D Enabler 3: Diversity and inclusion Developing strategies and solutions on digital inclusion |  |  |
| --- | --- | --- |
| Outcome: Strengthened capacity of the ITU membership to develop strategies, policies and practices for digital inclusion and equity, in particular for the empowerment of women and girls, persons with disabilities, persons with specific needs and low-income households. |  |  |
| Outputs |  | Highlights |
| Between September and December 2025, BDT diversity and inclusion work was instrumental in advancing the global commitment to ensure that no one is left behind in the digital age. BDT continued to ensure targeted actions addressing the needs of women and girls, youth, persons with disabilities, older persons, and Indigenous, rural and remote communities. ICT Accessibility continued to serve as a cornerstone of the work. BDT supported the roundtable series of Mainstreaming Knowledge on Ageing through expert presentations on Advancing Digital Inclusion for Older Persons through Age-Friendly ICT on September 10th, and The Role of ICTs in Promoting Access to Justice for Older Persons on October 16th. These contributions strengthened knowledge and reinforced awareness among policymakers and stakeholders on inclusive and universal approaches to digital policy and service/product design to advance digital inclusion of older persons. The Accessible ICTs for All events delivered concrete outcomes in advancing digital accessibility and inclusive ICT deployment, reinforcing the role of ITU as a global convener, capacity builder, and technical partner in digital inclusion. Through these flagship regional platforms, BDT translated universal design principles into practical guidance, policy dialogue, and actionable tools, supporting equitable digital access regardless of age, gender, ability, or location. Furthermore, BDT ensures comprehensive accessibility measures, including live captioning, international sign language interpretation, accessible digital tools, and inclusive physical arrangements, enabling full and effective participation. Gender equality remained a core pillar with measurable progress achieved through strengthened leadership, skills development, and inclusive participation mechanisms. The Network of Women (NoW) in ITU-D initiative increased leadership skills of women delegates for WTDC-25 through targeted mentoring and capacity-building activities. - A NoW in ITU-D interactive session was held at GSR-25 on September 2nd with the participation of women delegates, regulators, and policy-makers to explore how gender-responsive regulation can accelerate inclusive and sustainable digital development across three main themes: regulation for an inclusive digital future, AI for green and digital trust, and empowering women leaders in sustainable digital policy. - The closure session of the Empowering Women Leaders Mentorship Programme was held on October 6th with the participation of 48 delegates including men and women of 27 Member States. The mentoring programme was notable for adopting a more inclusive approach where for the first time, men were invited to participate in the Mentorship Programme, resulting in 30 per cent male participation. - A pre-WTDC training was organized and delivered virtually on October 8th with 143 delegates from 64 countries. The Super Women Series: Enhance your presence, influence, and impact event was also delivered via the ITU Academy between October and November. Over 107 women delegates benefited from this training, representing over 42 Member States. - During WTDC-25, the NoW in ITU-D Breakfast Session on advancing gender empowerment reaffirmed institutional commitment to women’s full and meaningful participation in digital development, while showcasing the progress of the activities of the Network since 2023 with an impactful recap video. The session fostered renewed commitment among ITU officials and over 150 delegates from 80 countries to gender-responsive digital development priorities for the 2026–2029 period. The AI Skills Accelerator for Girls, a two-year global programme jointly implemented by BDT and EY, advanced the development of a global cohort of empowered young women with the skills and confidence to innovate and lead in artificial intelligence through expanded regional delivery. The programme benefited more than 400 young women during the reporting period in three countries (India, Egypt and Uzbekistan). Youth engagement remained a strategic priority, with BDT facilitating structured opportunities for youth participation in digital policy dialogue. The ITU Global Youth Celebration, held on 16 November 2025 in Baku, Azerbaijan under the theme “Voices of Youth Shaping the Digital Future,” convened over 400 young leaders from 45 countries, including representatives from the ITU Generation Connect Youth Envoys alongside ICT policy-makers and global decision-makers at WTDC-25. Through intergenerational dialogue and thematic exchanges, participants contributed perspectives on digital development priorities. Study visits to Azercosmos, STEAM Azerbaijan, and the National Aviation Academy provided participants with exposure to applications of space, aviation, and STEAM technologies, supporting increased understanding of innovation ecosystems relevant to digital transformation. The programme benefited from the TDAG Informal Coordination Group on the Youth Summit and the Global Youth Celebration (TDAG-ICG-GYS) outcomes and the structured youth consultations and the development of youth-led evidence-based knowledge products, facilitated by BDT in a co-creation process engaging Envoys from all six ITU regions. The process supported transparency, alignment, and coordination between youth inputs and ITU decision-making structures, contributing to a more systematic and consistent institutional approach to meaningful youth engagement. See the Global Youth Celebration 2025 Highlights. In the Africa region, at policy level, BDT supported the Government of Burundi in the development of its National Digital Inclusion Strategy through a participatory and multi-stakeholder approach combining consultations and capacity-building. Between September and December 2025, BDT provided technical assistance to facilitate stakeholder engagement and policy formulation. A three-day training and validation workshop, held in Bujumbura from 3 to 5 September 2025, convened over 50 stakeholders from government, the private sector, civil society, and development partners. The strategy was validated, strengthening the national framework for digital inclusion and enabling follow-up collaboration with partners, including the United Nations Development Programme (UNDP) and the European Union. Under the ITU-Government of Mozambique-European Union “Laying the Foundation for VaMoz Digital!” project, BDT advanced national dialogue and evidence-based policymaking by organizing a webinar on Digital and ICT accessibility for persons with disabilities. The activity convened over 80 participants from government, the private sector, academia, and civil society, strengthening shared understanding of core accessibility concepts and validating preliminary findings from a national assessment of digital and ICT accessibility policies. This engagement supported national efforts to embed accessibility within broader digital inclusion frameworks The Her Digital Skills for Life initiative continued to equip girls and young women with essential digital skills linked to employment and entrepreneurship pathways. In October, in-person workshops in Kano and Yobe States, Nigeria, reached 96 young women, strengthening their digital competencies. In the Americas region, BDT advanced community-centred connectivity in Latin America through targeted capacity-building and multi-stakeholder engagement activities focused on Indigenous, rural, and remote communities. In Mexico, from 23 June to 15 December 2025, BDT delivered a workshop under the Training Programme for ICT Network Managers in Rural, Remote and Indigenous Communities, building on an earlier online phase. For the 160 participants the workshop strengthened technical and organizational capacities related to network deployment, governance, and sustainability, supporting more informed community-led connectivity initiatives. In Paraguay, BDT, in collaboration with CONATEL, conducted in-person workshops, between 3 and 7 November 2025, in the Chaco region and facilitated a multi-stakeholder dialogue in Asunción. These activities engaged 50 Indigenous leaders, community communicators, community radios, and public institutions, enabling knowledge exchange and structured dialogue between communities and regulatory authorities. The process resulted in the identification of practical recommendations to inform the development of a national ecosystem for community connectivity. Through the Accessible Americas event in Guatemala City, 28–30 October 2025, BDT provided an inclusive, fully accessible regional platform that convened 150 stakeholders from 15 countries across government, academia, civil society, and the private sector. The event strengthened regional capacity by positioning ICT accessibility as a foundational requirement for inclusive digital transformation, with targeted discussions on emerging technologies, including AI, and their potential to empower persons with disabilities, Indigenous peoples, rural and remote communities, women, youth, and older persons. Participants further benefited from an executive training on ICT accessibility, equipping policymakers and practitioners with practical tools to integrate accessibility into national digital strategies and inclusion programmes. In the Arab States region, national capacity in ICT accessibility was strengthened, with over 100 policy- and decision-makers in the United Arab Emirates equipped through an executive training session delivered during the Second Forum on Digital Accessibility and Inclusive Digital Transformation, held in September 2025, in Dubai. Under the AI Skills for Girls Accelerator project, an in-person workshop in Cairo, Egypt at the Egypt University of Informatics, enhanced knowledge of large language models, AI ethics, and cyber safety, contributing to greater regional capacity in emerging technologies. In the Asia-Pacific region, a report on enhancing ITU engagement of young people in advancing digital transformation in the region was developed, aiming to support the development of evidence-based recommendations to improve youth participation, and of informed strategic planning for regional initiatives. The report is also intended to support Member States in integrating youth perspectives into digital policy and programme design. BDT provided an expert intervention on digital inclusion and safe, inclusive policies at the Digital Safety Forum on 29 September 2025, organized by the Seoul Foundation for Women and Family under the Metropolitan Government of Seoul, Republic of Korea, and strengthened the capacity of participant local, national, and global stakeholders at the Forum. By sharing key priorities in advancing digital inclusion and online protection for young people, and increasing deployment of prevention strategies, ITU reinforced its leadership role in safe and inclusive digital transformation. The AI skills for Girls Accelerator project delivered through four in-person workshops in India (Hyderabad and Bangalore) strengthened the practical AI competencies of participants, and boosted their creativity, confidence, and understanding of responsible AI use. In the CIS region, the Digital Accessibility trainings to support persons with disabilities were held in Armenia, Belarus and Kyrgyzstan, in October and November 2025. BDT, together with Armenian NGO “White cane”, conducted a two-day physical training for persons with visual impairments, on digital accessibility and assessment of accessibility of websites and mobile applications. After the in-person training, participants developed recommendations to improve public websites accessibility to be presented to the relevant national governments. Jointly with Belarusian State Academy of Communications, BDT conducted a training for children with hearing impairments, on the use of artificial intelligence in education. Young participants learned about AI trends and how to use dedicated AI-based tools for their specific education needs. In Kyrgyzstan, together with the Academy of Digital Innovations, an ITU Academia Member, BDT held physical training courses on "The role of digital accessibility and inclusion in the implementation of educational programmes" for teachers from rural areas, and particularly for those in Naryn, Issyk-Kul, Talas, Jalal-Abad, and Chui. An overview of ICT accessibility and educational content used for teaching persons with disabilities, as well as of the possibilities for organizing inclusive education in secondary schools, was the key component of the training. In Uzbekistan, jointly with Tashkent University on Information Technologies (TUIT), ITU Academia member, BDT assisted in implementation of Uzbek Imo Sign Language Development Platform (“Sahiya”) project, aiming at using AI-based accessibility solution that combines a sign-language interpreter application and a browser plugin to improve access to digital content and services for persons with hearing and visual impairments. As part of the AI for Girls Skills Aceelerator project, a foundational AI workshop held in Tashkent, Uzbekistan, at the INHA University, increased the understanding of participants of core AI concepts, ethics, and real-world applications. In the Europe region, support to Moldova was provided in strengthening the policy and regulatory framework on digital accessibility through a comprehensive national assessment. The activity enhanced evidence-based policymaking, stakeholder coordination, and national readiness to advance inclusive digital access. Through the Accessible Europe event held in Brussels, Belgium 2-3 December 2025, BDT delivered an accessible regional platform that strengthened European capacity to implement digital accessibility policies in line with the European Accessibility Act (EAA). The Forum brought together more than 90 in-person participants from 26 countries, representing governments, the private sector, academia, and civil society. It facilitated structured policy dialogue and exchange of good practices on accessibility implementation, as Member States progressed in transposing the national legislation required by June 2025. Discussions also deepened a shared understanding of accessibility challenges and opportunities in emerging areas, including smart cities, virtual worlds, and artificial intelligence. |  | - Africa: Burundi, Kenya, Mozambique, Nigeria - Americas: Guatemala, Mexico, Paraguay - Arab States: Egypt, United Arab Emirates - Asia-Pacific: India, Republic of Korea - CIS: Armenia, Belarus, Kyrgyzstan, Uzbekistan - Europe: Belgium, Moldova Women and Girls - Thousands of girls engaged in coding, mentorship, and STEM activities - Inspiration for girls and young women to join ICT careers - Advance women leadership in ICT sector (NoW in ITU-D) Youth - “Voices of Youth Shaping the Digital Future,” Global Youth Celebration convened over 400 young leaders from 45 countries, - 230+ trainees completed Indigenous ICT network training. - Youth consultations fed into WTDC and Global Youth Summit outcomes Accessible ICT for All - AICTA guidelines updated (2024) and adopted in policy frameworks - 130+ delegates (Americas) and 400+ stakeholders (Europe) advanced inclusive ICT practices - Regional workshops mainstreamed accessibility, moving it from optional to standard ITU-D Study Group 1 Final report of Question 7/1 (2022-2025) published |
| Contributing to SDG Targets | SDGs 1, 3, 4, 5, 8, 9, 10, 11, 16, 17 |  |
| WSIS Action | C1, C2, C3, C4, C5, C6, C7, C11 |  |
| Resolutions: | PP 70, 175, 179, 184, 198; WTDC 46, 55, 58, 67, 76 |  |
| ITU-D study group Questions: | Question 7/1 ‘Access to telecommunication/ICT services by persons with disabilities and other persons with specific needs’ |  |

| ## ITU-D Enabler 4: Commitment to environmental sustainability Developing strategies and solutions on climate-change adaptation. |  |  |
| --- | --- | --- |
| Outcome: Enhanced capacity of the ITU membership to develop telecommunication/ICT strategies and solutions on climate-change adaptation and mitigation and the use of green/renewable energy. |  |  |
| Outputs |  | Highlights |
| BDT continued to advance comprehensive programmes to strengthen the capacity of Member States to sustainably manage e-waste, promote circular economy principles, and monitor the climate impact of the ICT sector. Across regions, BDT further expanded its technical assistance to Member States. In October 2025, a new project entitled “International Exchange Initiative on Regulating E-waste and Engaging Tech Companies” was launched in Bogotá, Colombia. Implemented by ITU in collaboration with the Government of Colombia through the Presidential Cooperation Agency of Colombia, in the Americas region the initiative featured the Colombia Study Tour, held from 6-10 October in Bogotá. The five-day technical programme brought together 74 participants, including representatives from participating countries (Colombia, Dominican Republic, India, Nigeria, Malaysia and South Africa). The programme combined workshops and hands-on activities to promote knowledge sharing and technical exchange on e-waste policy and regulation. With strong engagement from local stakeholders, 37 entities were represented at the in-person event. The outcomes were subsequently presented during the Colombia Study Tour Webinar on 30 October, which registered 233 in-person participants and 71 virtual attendees. BDT also launched the second edition of its “Policy practices for e-waste management: tools for a balanced and fair circular economy”. Based on ITU experience and lessons learned in e-waste management and circular economy, the toolkit was developed for policy-makers and other industry actors. It provides a practical and step-by-step guide to establishing an inclusive and fair e-waste management system that is enhanced by the concept of extended producer responsibility (EPR). In the Africa region, assistance was provided to Rwanda to enhance private sector engagement and identify national champions to strengthen the national EPR framework for electronics. Governance documents were developed to support the establishment of a voluntary producer responsibility organization in e-waste management, and a series of consultations was conducted in October 2025 in Kigali. BDT also developed a practical manual to guide the establishment of voluntary producer responsibility schemes for e-waste management in Zambia. In addition, a series of in-depth consultations on advancing a circular ICT sector was held in October 2025 in Lusaka. In the Asia-Pacific region, BDT supported Mongolia in organizing consultations with government and private sector stakeholders on e-waste management in October 2025, followed by a capacity building workshop in December 2025. In Thailand, a co-design session was held in October 2025 in collaboration with Thai Post and the Universal Postal Union. The session examined the business case for reverse logistics to be carried out by Thai Post, to strengthen e-waste take-back mechanisms. A validation workshop with government representatives was then held in December 2025 to confirm the proposed pathway towards a circular economy for electronics in Thailand. In Indonesia, BDT strengthened the capacity of government stakeholders through a capacity-building training on EPR and e-waste management, held in Jakarta in September 2025. In parallel, BDT continued to develop its work on the monitoring of ICT industry emissions, energy consumption, and climate commitments by digital companies in Asia and the Pacific. In September 2025, BDT continued to lead the review of the assessment methodology used in the annual Greening Digital Companies initiative. The associated Greening Digital Dashboard was launched by the Director of BDT that same month, providing an interactive tool for ITU and partners to monitor the climate impact of the ICT sector. The platform allows users to explore and compare emissions, energy use, and climate targets data between companies, as well as download open datasets. The Report of the EGTI Subgroup on National Greenhouse Gas Emission Monitoring Indicators for the ICT Sector was formally presented and released during the 16th meeting of the Expert Group on Telecommunication/ICT Indicators (EGTI), during the session entitled 'Developing new indicators: measuring the environmental footprint of key players in the ICT sector', held in September 2025. In addition, BDT advanced implementation of the project “Advancing Green Digital Action Towards a Net-Zero Digital Sector in the Philippines and Tanzania”. The two-year project aims to harmonize greenhouse gas (GHG) emissions and energy data collection across the digital sector, while supporting ICT regulators in Tanzania and the Philippines through capacity-building and the development of decarbonization and net-zero digital transition strategies. A StoryMap was developed to highlight BDT’s work on Advancing Green Digital Action Towards a Net-Zero Sector. Progress was also made in content development for an ITU Academy e-learning course on national ICT sector environmental impact. The project advanced to the country implementation phase, with national ICT sector climate data collection and needs assessments conducted in both the Philippines and Tanzania, alongside strengthened engagement with national stakeholders. Additional outputs included drafting an outline for a digital climate transition plan which will be tailored to each country, and the development of a global data collection survey aligned with EGTI indicators, supporting harmonized GHG and energy data collection and capacity-building for net-zero digital transitions. Under the ITU-FCDO partnership on ‘Promoting effective regulation, greater investment and innovative models for connectivity in underserved communities and for broader digital inclusion in Digital Access Programmme (DAP) countries’, activities focused on initiating pilot implementations of the ITU-EGTI National Greenhouse Gas Emission Monitoring Indicators for the ICT sector in Brazil and South Africa. This included convening project kick-off meetings in both countries, developing an indicator questionnaire covering key ICT subsectors, telecommunication operators, data centres and cloud providers, and equipment manufacturers, and coordinating initial data collection efforts. Early stakeholder consultations were conducted to strengthen engagement and assess regulatory and industry capacity for environmental data reporting. Efforts also focused on ensuring harmonization across the two national pilots and on generating preliminary insights to inform further improvements to the global indicator framework developed by EGTI on national GHG emissions. The article Monitoring sustainability: Incorporating ESG into ICT policy-making and regulation , produced by ITU and released during the Global Symposium for Regulators 2025 (GSR-25) in September through the Digital Regulation Platform , offers guidance for ICT regulators on developing and integrating environmental, social and governance (ESG) frameworks into policy. While many ICT regulators and policy-makers already collect operational and financial data on the ICT sector, and also oversee regulations related to ESG issues such as e-waste, universal service, data privacy and child online protection, the adoption of a formalized ESG framework would connect ICT regulator activities more visibly to sustainability efforts of the sector, enhancing analysis and comparability. During the reporting period, BDT contributed to advancing the green digital and climate agenda through high-level technical and policy engagement. This included serving as a speaker and session co-organizer at the 16th meeting of EGTI in Geneva in September 2025, as well as active participation in the United Nations General Assembly (UNGA) and Climate Week New York (19-25 September 2025). Engagements included speaking roles in multiple high-profile dialogues on green digital infrastructure, digital public infrastructure for climate action, AI and environmental sustainability, and climate adaptation. BDT also participated in anchor United Nations events and held bilateral meetings with key public and private stakeholders. In addition, BDT contributed at the Fratel network meeting on sustainable digital technologies in Luxembourg. These engagements strengthened partnerships and reinforced leadership in promoting green and climate-resilient digital development. BDT also provided chapter content contributions to the WIPO Green Technology Book (4th edition), launched at COP30 in November 2025. |  | - Increased electronics producer engagement in regulation-setting - Strengthened GHG emission and energy data collection - Improved monitoring of the ICT sector climate footprint - Africa: Rwanda, South Africa, Tanzania, Zambia - Americas: Brazil, Colombia - Asia-Pacific: Indonesia, Mongolia, Philippines, Thailand ITU-D Study Group 2: - Final report of Question 6/2 (2022-2025 study period) published |
| Contributing to SDG Targets | SDGs 1, 3, 4, 5, 8, 9, 10, 11, 16, 17 |  |
| WSIS Action | C1, C2, C3, C4, C5, C6, C7, C11 |  |
| Resolutions | WTDC 66 |  |
| ITU-D study group Questions | Question 6/2 (Environment) of Study Group 2 on Digital transformation |  |

| ## ITU-D Enabler 5: Excellence in human resources and organizational innovation |  |
| --- | --- |
| Outputs | Highlights |
| BDT continued to ensure accountability, transparency and continuous improvement by conducting end of year reviews of ITU-D projects and ITU-D Operational Plan activities, applying a results-based management approach. These reviews covering outputs delivered by Headquarters and regional offices, reaffirmed that implementation remains aligned with ITU strategic objectives and responsive to the evolving needs of Member States. Staff engagement continued to be priority. The regular staff engagement meetings, open to all personnel regardless of contractual status, create a safe space for open dialogue, encouraging staff to share feedback, exchange ideas, and contribute to shaping an evolving organizational culture within BDT. BDT continued to work closely with the ITU General Secretariat and the other Bureaux on a range of initiatives aimed at improving operational efficiency and effectiveness. | - Staff engagement meetings - Strategic alignment and responsiveness to Member States’s needs. - Strengthened sectoral synergies |

_______________

_______________

Meaningful connectivity is a level of connectivity that allows users to have a safe, satisfying, enriching and productive online experience at an affordable cost.