|  |  |
| --- | --- |
| **Radiocommunication Study Groups** |  |
|  |  |
|  |  |
| Source: [Annex 9](http://www.itu.int/md/dologin_md.asp?lang=en&id=R12-WP5A-C-0079!N09!MSW-E) to [Document 5A/79](http://www.itu.int/md/R12-WP5A-C-0079/en) | **Annex 9 to Document 5A/198-E** |
| **19 November 2012** |
| **English only** |
| Annex 9 to Working Party 5A Chairman’s Report | |
| Working Parties 5A and 5B | |
| work plan for wrc-15 agenda item 1.18 | |

| Working Party 5A/5B meetings | Work plan |
| --- | --- |
| 1st meeting  May 2012 | **Sub-Working Group meetings between WP 5A and WP 5B:**  - develop and adopt a work plan, including.  **Studies on technical and operational requirements (WP 5A/WP 5B according to the case) such as:**  - spectrum requirements needed for automotive radars;  - technical and operational requirements for automotive radars;  - possible Recommendation on the technical and operational requirements for automotive radar applications within ITS;  - review of other relevant existing ITS Recommendations and Reports;  - developing new Recommendation and/or Report as appropriate;  - liaise as needed with concerned Groups requesting further information.  **Sharing studies and regulatory procedures (WP 5B lead) such as:**  - the applicability of the existing Recommendations and other relevant studies to the required sharing studies under Agenda item 1.18;  - possible new Recommendations or Reports needed to support Agenda item 1.18;  - regulatory provisions needed for automotive radars;  - sharing and compatibility studies between existing services and proposed radiolocation service including in-band and adjacent band compatibility;  - liaise as needed with concerned Groups requesting further information. |

|  |  |
| --- | --- |
| Working Party 5A/5B meetings | Work plan |
| 2nd meeting  November 2012 | - continue developing the PDN  Recommendation on characteristics (WP 5A);  - continue developing the PDN Report on  sharing studies (WP 5B);  - develop initial draft CPM text outline (WP 5B lead);  - liaise as needed with concerned groups on progress of CPM text and sharing studies (WP 5B);  - update work plan as needed (WP 5A/5B). |
| 3rd meeting  May 2013 | - continue developing the PDN  Recommendation on characteristics (WP 5A);  - continue developing the PDN Report on  sharing studies (WP 5B);  - start developing draft CPM text (WP 5B lead);  - liaise as needed with concerned groups on progress of CPM text and sharing studies (WP 5B);  - update work plan as needed (WP 5A/5B). |
| 4th meeting  November 2013 | - continue working on CPM text (WP 5B lead);  - continue working on Recommendation/Report (WP 5A/5B);  - liaise as needed with concerned groups on progress of CPM text and sharing studies (WP 5B). |
| 5th meeting  May 2014 | - finalize CPM text and send to CPM management team (WP 5B);  - complete draft Recommendation/Report to be finally considered at the 6th meeting in November 2014 (WP 5A/5B);  - consider possible consequential changes to the existing ITU-R documentation as a result of adoption of proposed draft new Recommendation/Report (WP 5A/5B). |
| 6th meeting  November 2014 | - finalize Recommendation/Report and submit to SG 5 meeting for approval (WP 5A/5B);  - consider possible consequential changes to the existing ITU-R documentation as a result of adoption of proposed draft new Recommendation/Report (WP 5A/5B). |

|  |  |  |
| --- | --- | --- |
| **Contact:** | Satoshi (Sam) Oyama (WP 5A)  Fatih Mehmet Yurdal (WP 5B) | **E-mail:** [s-oyama@arib.or.jp](mailto:s-oyama@arib.or.jp)  **E-mail:** [fatih-mehmet.yurdal@ties.itu.int](mailto:fatih-mehmet.yurdal@ties.itu.int) |