|  |  |
| --- | --- |
| **Radiocommunication Study Groups** |  |
|  |  |
|  |  |
| Source: Document 5A/TEMP/185(Rev.1) | **Annex 7 to Document 5A/421-E** |
| **29 November 2013** |
| **English only** |
| Annex 7 to Working Party 5A Chairman’s Report | |
| workplan for WRC-15 Agenda item 1.3 | |

| Working Party 5A meetings | Workplan |
| --- | --- |
| 1st meeting (Meeting #9 of WP 5A),  May 2012 | 1) Develop the workplan for the studies  2) Determine the necessity of revision of other relevant PPDR ITU-R Recommendations and Reports  (see Report ITU-R M.2033)  3) Develop outline of some of the proposed new/revised Recommendations and/or Reports  4) Send an opening liaison statement to the concerned groups and external organisations advising them that Working Party 5A intends to coordinate with all relevant groups and seeking inputs for proposed development/revision of the Reports/Recommendations to reflect broadband PPDR applications  5) Develop outline of the CPM text |
| 2nd meeting (Meeting #10 of WP 5A),  November 2012 | 1) Consider input contributions related to the scope of work  2) Develop working documents towards new or revised Recommendations and/or Reports reflecting requirements for broadband PPDR; including a Report/Recommendation on technical requirements of broadband PPDR services and applications  3) Further develop draft CPM text outline  4) Liaise as required with other involved WPs and external organizations  5) Revise work plan as appropriate |

| Working Party 5A meetings | Workplan |
| --- | --- |
| 3rd meeting (Meeting #11 of WP 5A),  May 2013 | 1) Develop working documents towards new or revised Recommendations and/or Reports reflecting requirements for broadband PPDR; including a Report/Recommendation on technical requirements of broadband PPDR services and applications  2) Continue drafting the CPM text taking into account the existing Reports and/or Recommendations, as well as those being developed  3) Liaise as required with other involved WPs and external organizations  4) Revise work plan as appropriate |
| 4th meeting (Meeting #12 of WP 5A),  November 2013 | 1) Consider input contributions  2) Continue further work on draft CPM text including the draft text of the revised Resolution **646 (Rev.WRC-12)**  3) Progress the work on development of a new Report to address NB/WB/BB PPDR and the necessary deliverables for WRC-15 agenda item 1.3 with a view to suppressing Report ITU-R M.2033  a) Prioritize completing BB Section of new Report to address NB/WB/BB PPDR  b) Set up Correspondence activities to cut and paste NB/WB sections from Report ITU-R 2033, consider relevant input contributions and revise these sections by correspondence |
| 5th meeting (Meeting #13 of WP 5A),  May 2014 | 1) Consider input contributions including report of CG  2) Complete the draft of the CPM text on review and revision of Resolution **646 (Rev.WRC-12)**, including executive summary, methods, and regulatory and procedural considerations, taking into account the new Report to address NB/WB/BB PPDR and member input on relevant studies  3) Progress the work on the development of the new Report to address NB/WB/BB PPDR and the necessary deliverables for WRC-15 agenda item 1.3 with a view to suppressing Report ITU-R M.2033  a) Prioritize completing BB Section of the new Report to address NB/WB/BB PPDR  b) Provide a summary of the relevant studies from the new Report to address NB/WB/BB PPDR to be used for CPM text for WRC 15 AI 1.3 Sections 1/1.3/3 and 1/1.3/4  c) Continue Correspondence activities on NB/WB sections of the new Report to address NB/WB/BB PPDR, as necessary   1. consider sending liaison statements, if necessary   4) Review and revise work plan as appropriate |
| 6th meeting (Meeting #14 of WP 5A),  [dates TBD] | 1) Consider input contributions  2) Finalise the new Report on NB/WB/BB PPDR and submit to Study Group 5  3) Review and revise work plan as appropriate. |