|  |  |
| --- | --- |
| **Radiocommunication Study Groups** |  |
|  |  |
|  |  |
| Source: Document 5A/TEMP/199 Document 5B/TEMP/169  Subject: WRC-15 agenda item 1.18 | **Annex 9 to Document 5A/421-E** |
| **29 November 2013** |
| **English only** |
| **Annex 9 to Working Party 5A Chairman’s Report**  Working Parties 5A and 5B | |
| work plan for WRC-15 Agenda item 1.18 | |
|  | |

|  |  |
| --- | --- |
| Working Parties 5A/5B meetings | Work plan |
| 13th meeting – May 2014 | – Finalize CPM text and send to CPM management team (WP 5B).  – Complete draft Report to be finally considered at the 14th meeting in November 2014 (WP 5B).  – Consider possible consequential changes to the existing ITU-R documentation as a result of adoption of proposed draft new Report (WP 5B). |
| 14th meeting – November 2014 | – Finalize Report and submit to SG 5 meeting for approval (WP 5B).  – Consider possible consequential changes to the existing ITU-R documentation as a result of adoption of proposed draft new Report (WP 5B). |

|  |  |  |
| --- | --- | --- |
| **Contacts:** | Satoshi (Sam) Oyama (WP 5A)  Fatih Mehmet Yurdal (WP 5B) | **E-mail:** [s-oyama@arib.or.jp](mailto:s-oyama@arib.or.jp)  **E-mail:** [fatih-mehmet.yurdal@ties.itu.int](mailto:fatih-mehmet.yurdal@ties.itu.int) |