|  |  |  |  |
| --- | --- | --- | --- |
|  | **Radiocommunication Study Groups** | |  |
| **INTERNATIONAL TELECOMMUNICATION UNION** | |  | |
|  | |  | |
| Source: Document 5A/TEMP/42 | | **Annex 7 to Document 5A/114-E** | |
| **23 May 2016** | |
| **English only** | |
| Annex 7 to Working Party 5A Chairman’s Report | | | |
| work plan for preparation for WRC-19 Agenda item 1.11 | | | |
|  | | | |

| Meetings | Work plan |
| --- | --- |
| May 2016 | 1 Establish a SWG for A.I. 1.11 Railway.  2 Develop the work plan for A.I. 1.11.  3 Initiate a Survey on Railway Radiocommunication Systems.  4 Initiate the study on technical and operational characteristics and implementation and spectrum needs of railway radiocommunication systems between train and trackside, and draft the working document towards a PDN Report ITU-R [Rail. RSTT[[1]](#footnote-1)].  5 Develop elements of working document towards preliminary draft CPM text on A.I. 1.11.  6 Draft relevant liaisonstatements. |
| Nov 2016 | 1 Review the responses received on the survey and take appropriate course of actions.  2 Improve working document towards PDN Report ITU-R [Rail. RSTT].  3 Initiate study on global or regional harmonized frequency bands for RSTT.  4 Improve elements of working document towards preliminary draft CPM text on A.I.1.11.  5 Draft relevant liaison statement(s).  6 Review and revise the work plan. |
| May 2017 | 1 Complete the Survey Report.  2 Improve working document towards a PDN Report ITU-R [Rail. RSTT].  3 Continue the study on global or regional harmonized frequency bands for RSTT.  4 Improve working document towards preliminary draft CPM text on A.I.1.11.  5 Draft relevant liaison statement(s).  6 Review and revise the work plan. |
| Nov 2017 | 1 Complete PDN Report ITU-R [Rail. RSTT].  2 Improve working document towards preliminary draft CPM text on A.I. 1.11.  3 Achieve preliminary study result on global or regional harmonized frequency bands for RSTT.  4 Review and revise the work plan.  5 Draft relevant liaison statement(s). |
| May 2018 | 1 Upgrade PDN Report ITU-R [Rail. RSTT] to DNR for approval.  2 Complete working document towards preliminary draft CPM text on A.I. 1.11.  3 Complete the study on global or regional harmonized frequency bands for RSTT.  4 Review and revise the work plan.  5 Draft relevant liaison statement(s). |
| Nov 2018 | 1 Finalize above ITU-R Report, if not done in May 2018. |

1. RSTT is the abbreviation of *railway radiocommunication systems between train and trackside*. [↑](#footnote-ref-1)