|  |  |  |
| --- | --- | --- |
|  | **Radiocommunication Study Groups** |  |
| **INTERNATIONAL TELECOMMUNICATION UNION** |  |
|  |  |
| Source: Document 5A/TEMP/42 | **Annex 7 toDocument 5A/114-E** |
| **23 May 2016** |
| **English only** |
| Annex 7 to Working Party 5A Chairman’s Report |
| work plan for preparation for WRC-19 Agenda item 1.11 |
|  |

| Meetings | Work plan |
| --- | --- |
| May 2016 | 1 Establish a SWG for A.I. 1.11 Railway.2 Develop the work plan for A.I. 1.11.3 Initiate a Survey on Railway Radiocommunication Systems.4 Initiate the study on technical and operational characteristics and implementation and spectrum needs of railway radiocommunication systems between train and trackside, and draft the working document towards a PDN Report ITU-R [Rail. RSTT[[1]](#footnote-1)].5 Develop elements of working document towards preliminary draft CPM text on A.I. 1.11.6 Draft relevant liaisonstatements.  |
| Nov 2016 | 1 Review the responses received on the survey and take appropriate course of actions.2 Improve working document towards PDN Report ITU-R [Rail. RSTT].3 Initiate study on global or regional harmonized frequency bands for RSTT.4 Improve elements of working document towards preliminary draft CPM text on A.I.1.11.5 Draft relevant liaison statement(s).6 Review and revise the work plan. |
| May 2017 | 1 Complete the Survey Report.2 Improve working document towards a PDN Report ITU-R [Rail. RSTT].3 Continue the study on global or regional harmonized frequency bands for RSTT.4 Improve working document towards preliminary draft CPM text on A.I.1.11.5 Draft relevant liaison statement(s).6 Review and revise the work plan. |
| Nov 2017 | 1 Complete PDN Report ITU-R [Rail. RSTT].2 Improve working document towards preliminary draft CPM text on A.I. 1.11.3 Achieve preliminary study result on global or regional harmonized frequency bands for RSTT. 4 Review and revise the work plan.5 Draft relevant liaison statement(s). |
| May 2018 | 1 Upgrade PDN Report ITU-R [Rail. RSTT] to DNR for approval.2 Complete working document towards preliminary draft CPM text on A.I. 1.11.3 Complete the study on global or regional harmonized frequency bands for RSTT.4 Review and revise the work plan.5 Draft relevant liaison statement(s). |
| Nov 2018 | 1 Finalize above ITU-R Report, if not done in May 2018. |

1. RSTT is the abbreviation of *railway radiocommunication systems between train and trackside*. [↑](#footnote-ref-1)