|  |  |  |
| --- | --- | --- |
|  | **Radiocommunication Study Groups** |  |
| **INTERNATIONAL TELECOMMUNICATION UNION** |  |
|  |  |
| Source: Document 5A/TEMP/21(Rev.1) | **Annex 9 toDocument 5A/114-E** |
| **23 May 2016** |
| **English only** |
| Annex 9 to Working Party 5A Chairman’s Report |
| DRAFT work plan for WRC-19 Agenda item 1.12 |
|  |

| Working Party 5A/Meeting | Work plan |
| --- | --- |
| 16th meetingMay 2016 | WP 5A, based on input contributions, develop and adopt a work plan, including:– continue developing the PDN Report ITU-R M.[ITS USAGE] (relevant parts thereof maybe referenced in the CPM Text);– review of relevant existing ITS Recommendations and Reports (relevant parts thereof maybe referenced in the CPM Text);– review of relevant existing standards and on-going ITS standardisation activities;– develop initial draft CPM Text outline;– liaise as needed with concerned groups requesting further information. |
| 17th meetingNovember 2016 | WP 5A, based on input contributions, – continue developing the PDN Report ITU-R M.[ITS USAGE] (relevant parts thereof maybe referenced in the CPM Text);– initiating work on a working document towards preliminary draft new Recommendation or Report as appropriate on technical and operational requirements for ITS applications;– review of relevant existing standards and on-going ITS standardisation activities;– working on draft CPM Text outline;– liaise as needed with concerned groups on progress;– update work plan as needed. |
| 18th meeting[May 2017] | WP 5A, based on input contributions, – continue developing the PDN Report ITU-R M.[ITS USAGE] (relevant parts thereof maybe referenced in the CPM Text);– continue working on working document towards a preliminary draft Recommendation or Report as appropriate on technical and operational requirements for ITS applications;– review of relevant existing standards and on-going ITS standardisation activities;– continue working on draft CPM Text;– liaise as needed with concerned groups on progress;– update work plan as needed. |
| 19th meeting[November 2017] | WP 5A, based on input contributions, – continue working on the draft new Report ITU-R M.[ITS USAGE] (relevant parts thereof maybe referenced within CPM Text);– continue working on draft Recommendation or Report as appropriate on technical and operational requirements for ITS applications;– continue working on draft CPM Text;– update work plan as needed. |
| 20th meeting[May 2018]  | WP 5A, based on input contributions,– finalize work on draft new Report ITU-R M.[ITS USAGE] and submit to SG 5 meeting for approval (relevant parts thereof maybe referenced in the CPM Text);– finalize work on a draft new Recommendation or Report as appropriate on technical and operational requirements for ITS applications and submit to SG 5 meeting for approval;– finalize draft CPM Text and send to CPM management team; – update work plan as needed. |
| 21st meeting[November 2018] |  |
| [22nd meetingMay 2019] |  |