|  |  |  |  |
| --- | --- | --- | --- |
|  | **Radiocommunication Study Groups** | |  |
| **INTERNATIONAL TELECOMMUNICATION UNION** | |  | |
|  | |  | |
| Source: Document 5A/TEMP/102 | | **Annex 5 to**  **Document 5A/298-E** | |
| **18 November 2016** | |
| **English only** | |
| Annex 5 to Working Party 5A Chairman’s Report | | | |
| Work plan for WRC-19 Agenda Item 1.1 | | | |
|  | | | |

For effective work on WRC-19 agenda item 1.1 the following work plan has been developed:

| Working Party 5A meetings | Activity |
| --- | --- |
| 16th meeting  May 2016 | • Begin work on identifying amateur service technical and operational characteristics for systems to be operated in the 50-54 MHz frequency band.  • Request any required technical and operational characteristics from contributing groups.  • Prepare liaison statements to the concerned groups with information on amateur systems technical characteristic planned for use in the 50-54 MHz frequency band.  • Catalogue existing ITU Region 1 use by the amateur service in part or the entire 50-54 MHz frequency band.  • Begin drafting Report ITU-R M.[AMATEUR 50MHz] on A.I. 1.1.  • Begin drafting the CPM text.  • Transmit work plan to contributing groups. |
| 17th meeting  November 2016 | • Complete review of amateur service technical and operational characteristics for the 50-54 MHz frequency band.  • Analysis of liaison statements responses from the concerned working parties.  • Begin sharing studies and develop Report ITU-R M.[AMATEUR 50MHz], between proposed amateur service stations and incumbent service stations in ITU Region 1 countries not included in RR footnote **5.169**.  • Request information from concerned groups on the technical characteristics of incumbent services.  • Determine spectrum requirements for the amateur service and plans for implementation of an amateur service allocation in the 50-54 MHz frequency band.  • Develop draft CPM text considering and incorporating feedback from contributing groups.  • Modify the work plan (if needed). |
| 18th meeting  May 2017 | • Continue sharing studies and update preliminary draft new Report(s), taking into account feedback from contributing groups.  • Develop CPM text, considering and incorporating feedback from contributing groups.  • Transmit updated preliminary draft new Report(s) on sharing studies to contributing groups as appropriate for review.  • Transmit draft CPM text to contributing groups for review.  • Modify the work plan (if needed). |
| 19th meeting | • Continue sharing studies taking into account feedback from contributing groups.  • Prepare draft new Report(s) on sharing studies as appropriate.  • Develop CPM text, considering and incorporating from contributing groups.  • Transmit draft new Report(s) on sharing studies to contributing groups as appropriate for final review.  • Transmit draft CPM text to contributing groups for review.  • Modify the work plan (if needed). |
| 20th meeting | • Continue sharing studies taking into account feedback from contributing groups.  • Prepare draft new Report(s) on sharing studies as appropriate.  • Finalize CPM text, considering and incorporating from contributing groups.  • Transmit draft CPM text to Chapter Rapporteur.  • Modify the work plan (if needed). |
| 21st meeting | • Complete sharing studies taking into account feedback from contributing groups.  • Complete draft new Report(s) on sharing studies and send to Study Group 5. |
| 22nd meeting |  |

\_\_\_\_\_\_\_\_\_\_\_\_\_\_