|  |  |
| --- | --- |
| **Radiocommunication Study Groups** |  |
|  |  |
|  |  |
| Source: Document 5A/TEMP/187 | **Annex 5 to****Document 5A/469-E** |
| **12 June 2017** |
| **English only** |
| Annex 5 to Working Party 5A Chairman’s Report |
| Work plan for WRC-19 Agenda Item 1.1 |

For effective work on WRC-19 agenda item 1.1 the following work plan has been developed:

| Working Party 5A meetings | Activity |
| --- | --- |
| 16th meetingMay 2016 | • Begin work on identifying amateur service technical and operational characteristics for systems to be operated in the 50-54 MHz frequency band.• Request any required technical and operational characteristics from contributing groups.• Prepare liaison statements to the concerned groups with information on amateur systems technical characteristic planned for use in the 50-54 MHz frequency band.• Catalogue existing ITU Region 1 use by the amateur service in part or the entire 50-54 MHz frequency band.• Begin drafting Report ITU-R M.[AMATEUR 50MHz] on A.I. 1.1.• Begin drafting the CPM text.• Transmit work plan to contributing groups. |
| 17th meetingNovember 2016 | • Complete review of amateur service technical and operational characteristics for the 50-54 MHz frequency band.• Analysis of liaison statements responses from the concerned working parties.• Begin sharing studies and develop Report ITU-R M.[AMATEUR 50MHz], between proposed amateur service stations and incumbent service stations in ITU Region 1 countries not included in RR footnote **5.169**.• Request information from concerned groups on the technical characteristics of incumbent services.• Determine spectrum requirements for the amateur service and plans for implementation of an amateur service allocation in the 50-54 MHz frequency band. • Develop draft CPM text considering and incorporating feedback from contributing groups.• Modify the work plan (if needed). |
| 18th meetingMay 2017 | • Continue sharing studies and update preliminary draft new Report(s), taking into account feedback from contributing groups.• Develop CPM text, considering and incorporating feedback from contributing groups.• Transmit updated preliminary draft new Report(s) on sharing studies to contributing groups as appropriate for review.• Transmit draft CPM text to contributing groups for review.• Modify the work plan (if needed). |
| 19th meetingNovember 2017 | • Continue sharing studies taking into account feedback from contributing groups.• Prepare draft new Report(s) on sharing studies as appropriate.• Based on contributions develop CPM text.• Transmit draft new Report(s) on sharing studies to contributing groups as appropriate for final review.• Transmit draft CPM text for review.• Modify the work plan (if needed). |
| 20th meeting | • Continue sharing studies taking into account feedback from contributing groups.• Prepare draft new Report(s) on sharing studies as appropriate.• Finalize CPM text.• Transmit draft CPM text to Chapter Rapporteur.• Modify the work plan (if needed). |
| 21st meeting | • Complete sharing studies taking into account feedback from contributing groups.• Complete draft new Report(s) on sharing studies and send to Study Group 5. |
| 22nd meeting |  |