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Scope
This document provides information on the detailed schedule and associated dates for the Revision 1 of Recommendation ITU-R M.2177 “Detailed specifications of the satellite radio interfaces of International Mobile Telecommunications-2020 (IMT‑2020)”. 
References
Recommendation ITU-R M.2177 ‒ “Detailed specifications of the satellite radio interfaces of International Mobile Telecommunications-2020 (IMT-2020)”
Document IMT-2020-SAT/14 ‒ “Procedure for the development of draft revisions of Recommendation ITU-R M.2177”. 
Document IMT-2020-SAT/5 ‒ “Process and the use of Global Core Specification (GCS), references and related certifications in conjunction with Recommendation ITU-R M.2177”.
Document IMT-2020-SAT/2 ‒ “Submission, evaluation process and consensus building for satellite radio interface technology proposals of IMT-2020”.
Document IMT-2020-SAT/1 ‒ “Background on the satellite component of IMT-2020”.
Report ITU-R M.2514-0 (2022) ‒ “Vision, requirements and evaluation guidelines for satellite radio interface(s) of IMT-2020”.
[bookmark: _Hlk71470838]Circular Letter 4/LCCE/146 ‒ Announcement of the Revision 1 of Recommendation ITU-R M.2177 “Detailed specifications of the satellite radio interfaces of International Mobile Telecommunications-2020 (IMT-2020)” 
I)	Procedure to be utilized in the development of the Revision
The procedure outlined in Document IMT-2020-SAT/14 “Procedure for the development of draft Revisions of Recommendation ITU-R M.2177” applies to the development of Revision 1 of Recommendation ITU‑R M.2177.
In conjunction with that generic procedure, it is necessary, for each specific Revision to assign a specific schedule and dates to the timelines and actions/activities presented in the Document IMT‑2020-SAT/14 which is accomplished by this Document IMT-2020-SAT/15.
II)	Baseline document to be used for the Revision 1
The baseline document to be used for the Revision 1 is the published version of Recommendation ITU-R M.2177 “Detailed specifications of the satellite radio interfaces of International Mobile Telecommunications-2020 (IMT-2020)”. 
III)	General schedule aspects for the Revision 1 of Recommendation ITU-R M.2177 
For the Revision 1 of Recommendation ITU-R M.2177 a completion date of the Working Party (WP 4B) meeting #60, currently planned for July 2027, has been chosen. 
[bookmark: _Hlk71116394]The initial announcement of the Revision 1 is indicated by liaison to the relevant External Organizations dispatched from the 29 April to 5 May 2026 meeting #58 of WP 4B.
The detailed timeline for this specific revision of Recommendation ITU-R M.2177 was developed based on the currently planned/anticipated schedule of meetings for WP 4B and Study Group 4 through the 2027 timeframe. Confirmed meeting dates of WP 4B through 2027 will be published on the ITU website.  Due consideration was given towards coordinating with the relevant External Organizations and their understood planned dates and deliverables to the extent they were known.
Working Party 4B announces that the first formal meeting in the meeting cycle (“Meeting Z”) of the update for the Revision 1 of Recommendation ITU-R M.2177 will be WP 4B meeting #59, which is currently scheduled for 14–20 October 2026. This establishes the first action point for the relevant External Organizations to interface with WP 4B on Revision 1.
IV)	Detailed schedule for the Revision 1 update for Existing Technologies in Recommendation ITU-R M.2177
Table 1 below, extracted from Document IMT-2020-SAT/14 and amended with specific dates, provides the detailed timeline for the updates to existing technologies in Recommendation ITU-R M.2177 as indicated in Section 2 of Document IMT-2020-SAT/14.
It is noted that the schedule for this Revision 1 has been compressed somewhat compared to the regular schedule described in Document IMT-2020-SAT/14, since there is currently no 4B meeting planned in October 2027 due to WRC-27 taking place. 
Calendar 1 provides a summary of actions defined in Table 1 for the Revision 1 in a calendar view.
TABLE 1[footnoteRef:1] [1:  	Based on planned meeting dates. Confirmed meeting dates of WP 4B through year 2027 will be published on the ITU website.] 

Framework of a Revision Cycle for updates of existing technologies in Recommendation ITU-R M.2177 applicable to Section 2 of Document IMT-2020-SAT/14
	Item
	Entity
	Meeting designation & timeframe
	Action/Deliverable/Milestone
	Specific dates

	1
	WP 4B
	Meeting “Z-1” or earlier
	Communiqué to GCS Proponent, Transposing Organizations, and relevant External Organizations announcing the next revision of Rec. ITU‑R M.2177 and providing the detailed timelines for the revision.
	WP 4B Meeting #58
29 April – 5 May 2026

	2
	Existing GCS Proponent
	Meeting “Z”
	Delivery to ITU-R by the GCS Proponent of the required information, including a summary and rationale of the proposed update.[footnoteRef:2]* [2: * 	Required in case of an update of the GCS or in the case of a revised Overview, revised synopsis, or other material in Recommendation ITU-R M.2177 under the purview of the GCS Proponent.] 

Delivery to ITU-R by existing GCS Proponent of an updated Form A in the case of an addition or removal of a GCS Proponent entity.
	Contribution Deadline 
2 October 2026
WP 4B Meeting #59
14–20 October 2026

	3
	Existing GCS Proponent
or
Existing Transposing Organization (Scenario 3 only)
	Meeting “Z”
	Case requiring a modification of the GCS 
Delivery to ITU-R by the GCS Proponent of the detailed update, including the compliance templates 8.2.6 from Report ITU-R M.2514-0 (2022) and any related supporting material for the proposed update to Rec. ITU‑R  M.2177, given that the full context of the total satellite radio interface is considered to be the original submission and any previously approved updates as well as this proposed update.
Delivery to ITU-R by the GCS Proponent of the revised/updated GCS.
Delivery to ITU-R of Certification B (section 1, section 2, and section 3, as appropriate) by GCS Proponents.
Cases not requiring a modification of the GCS
Scenario 1 - Case of a revised Overview, synopsis, or other material in Rec. ITU‑R M.2177: 
Delivery to ITU-R by the GCS Proponent of the update of the associated material and a self-declaration indicating that those changes are consistent with existing GCS.
Scenario 2 - Case of a new Transposing Organization(s) or removal of a Transposing Organization(s)
Delivery to ITU-R of Certification B, section 2, and/or section3, by GCS Proponents. 
Scenario 3 – Case of update of only a particular set or sets of the transposition references
Delivery to ITU-R by the Transposing Organization of the complete update information, including a summary and rationale of the proposed update, the updated specific set or sets of the transposition references, and Certification C. At the same meeting as the announcement by the Transposing Organization (s), the GCS Proponent must inform WP 4B of their agreement with the proposed update.
	Contribution Deadline
2 October 2026
WP 4B Meeting #59
14–20 October 2026

	4
	WP 4B
	Meeting “Z”
	WP 4B performs a review of the submitted material and reaches its conclusion on the acceptability of the proposed update for inclusion in the draft revision of Rec. ITU-R M.2177.
WP 4B finalizes and agrees the specific technology update in the draft revision of Rec. ITU‑R M.2177 (not necessarily including the detailed transposition references).
WP 4B liaison of the WP 4B agreed draft Revision of Rec. ITU-R M.2177 to the relevant GCS Proponents and Transposing Organizations for their use in developing their inputs of the detailed references.
	WP 4B Meeting #59
14–20 October 2026

	5
	Transposing Organizations
	Due to ITU-R approximately one month prior to meeting “Z+1”
	Delivery to ITU-R of transposition references by each Transposing Organization for incorporation into the WP 4B preliminary agreed draft revision of Rec. ITU-R M.2177. 
Delivery to ITU-R of Certification C by each Transposing Organization.
Completion of relevant business matters and indication of compliance with ITU policy on IPR, as appropriate.
This Item 5 does not apply to case of a Scenario 1 update. 
In case of Scenario 3, Item 5 does not apply because the Transposing Organization would have already provided the complete information by meeting “Z”.
	Deadline for Submission
to ITU-R Secretariat
1 June 2027

	6
	Radiocommunication Bureau
	Prior to meeting “Z+1”
	The Radiocommunication Bureau is requested to provide to WP 4B a document that incorporates the transposition references
	Anticipated to be before
1 July 2027
for consideration at WP 4B Meeting #60
July 2027

	7
	WP 4B
	Meeting “Z+1”
	WP 4B performs a final quality and completeness check of the draft revision of Rec. ITU-R M.2177.
WP 4B forwards to Study Group 4 the Revision of Rec. ITU-R M.2177.
	WP 4B Meting #60 
July 2027

	8
	Radiocommunication Bureau
	Prior to subsequent SG 4 meeting
	Submission by Counsellor for SG 4 of completed draft revision of Rec. ITU-R M.2177 (with all transposition references) to SG 4, based on currently anticipated SG 4 meeting schedule.
	Date to be determined depending on actual SG 4 meeting schedule
(approximately July 2027)

	9
	Study Group 4
	
	Study Group 4 considers adoption of the Revision 1 of Rec. ITU-R M.2177 for forwarding to Member States for approval.
	Date to be determined depending on actual SG 4 meeting schedule
(approximately July 2027)
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CALENDAR 1 
(For TABLE 1)
Summary of actions for the Revision 1 of existing technologies in Recommendation ITU-R M.2177 organized in a calendar view
	Part 1: Milestone Summary for ITU-R WP 4B and Radiocommunication Bureau (BR) for Revision of Existing Technologies

	

	
	WP 4B #58
	
	
	WP 4B #59
	
	
	WP 4B #60
	
	

	DATE
	29 April – 5 May 2026
	
	
	14–20 October 2026
	
	Before July 2027
	July 2027
	July 2027
	July 2027

	Meeting Designator
	“Z-1”
	
	
	“Z”
	
	Prior to “Z+1”
	“Z+1”
	-
	-

	Table 1
Item #
	1
	
	
	4
	
	6
	7
	8
	9

	Action by Entity
	WP 4B
	
	
	WP 4B
	
	BR
	WP 4B
	BR
	SG 4

	

	Part 2: Milestone Summary for GCS Proponents and Transposing Organizations for Revision of Existing Technologies

	

	
	WP 4B #58
	
	
	WP 4B #59
	
	
	WP 4B #60
	
	

	Action Deadline
	
	2 October 2026
	2 October 2026
	
	1 June 2027
	
	
	
	

	Meeting Designator
	
	12 days before
“Z”
	12 days before
“Z”
	
	1 month before “Z+1”
	
	
	
	

	Table 1
Item #
	
	2
	3
	
	5
	
	
	
	

	Action by Entity
	
	Existing GCS Proponent
	Existing GCS Proponent 
or 
Existing Transposing Organization (Scenario 3)
	
	Transposing Organizations
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