| Radiocommunication Advisory Group |  |
| --- | --- |
|  | Document RAG/62-E |
|  | 23 February 2026 |
|  | Original: English |
| Director, Radiocommunication Bureau |  |
| ITU-R draft operational plan for 2027-2030 and 2025 performance report |  |

This document presents the draft rolling four-year operational plan for the Radiocommunication Sector for 2027-2030 as well as the implementation of the operational plan of 2025.

This Plan is published pursuant to No. 160CA of Article 11A and No. 181A of Article 12 of the ITU convention.

RAG is invited to review this plan and advise the Director, as deemed necessary.

# 1	Introduction

1.1	The ITU Strategic Plan for 2024-2027, Annex 1 to Resolution 71 (Rev. Bucharest 2022), is the instrument that sets the 2 goals and the 5 thematic priorities for the Union and the Radiocommunication Sector for this timeframe.

The Mission of the ITU-R Sector lies within the broader framework of the purposes of the ITU as defined in Article 1 of the ITU Constitution and is:

“to ensure, inter alia, consistent with application of Articles 1 and 12 of the Constitution, the rational, equitable, efficient and economical use of the radio-frequency spectrum by all radiocommunication services, including those using satellite orbits, and to carry out studies and approve recommendations on radiocommunication matters.”

1.2	The Radiocommunication Sector is, moreover, committed to pursuing and developing its 12 outputs, namely:

- Processing of space notices

- Processing of terrestrial notices

- WRC’s outputs (Final Acts and Radio Regulations)

- CPM’s output (CPM Report)

- RRB’s outputs (Rules of Procedure and Decisions)

- Software (not related to Processing of notices, e.g. RR Article 5 TFA software, Radio Navigation Tool search engine etc)

- ITU-R publications (not covered under ITU-R study groups, e.g. Maritime Manual, List IV, List V)

- ITU-R study groups’ outputs (ITU-R Recommendations, Reports and Handbooks)

- RA outputs (e.g. ITU-R Resolutions)

- RAG outputs (Advice to BR Director, inputs to RA)

- Technical Assistance (e.g. PRIDA, BR support for regional initiatives)

- ITU-R Seminars (e.g. WRS, RRS)

1.3	The following success factors are to be considered in the implementation of the mission and outputs as stated above:

- The mission and outputs of the ITU-R are clearly understood and shared by our membership.

- The required resources level for implementing these outputs is made available and economically/efficiently monitored.

- The working methods and activities of the Sector continue to be improved in a cooperative and synergic manner between the membership and the Radiocommunication Bureau.

1.4	The ITU-R Sector will have a demanding schedule during the 2027-2030 timeframe. Besides the regular work of the ITU-R Study Groups, preparations for WRC-27 have already started and will continue through the CPM27-2 in 2027 and conclude with the commencement of the RA-27 and WRC-27. A new cycle of activities of the ITU-R Study Groups will begin in 2028.

The key and most challenging issues for the 2027-2030 four-year timeframe will be the following:

- To ensure that ITU-R meetings are conducted efficiently and effectively, supported by thorough preparatory and organizational work.

- To guarantee business continuity for ITU-R meetings and events during the execution of the new ITU Geneva headquarters project.

- To continue to assist ITU-R Study Groups in their studies according to their work plans, with a focus on the topics identified by WRC-23 and WRC-27.

- The Bureau will organize the preparatory studies for WRC-27 and participate in the relevant preparatory and delivery activities to convene WRC-27.

- To pursue and possibly increase, in the framework of its preparation for WRC-27, the participation of the Bureau in the preparatory activities of the Regional Organizations.

- To coordinate internally and with the Host Country to ensure effective and timely preparation for and delivery of RA-27, WRC-27, and CPM31-2.

- As outputs to WRC-27, the Bureau will oversee the preparation and publication of the Final Acts of WRC-27 and updated Radio Regulations (Edition 2028).

- To finish implementing the decisions of WRC-23, with a particular emphasis on the changes in the regulatory procedures and software.

- To implement WRC-27 decisions, in a timely manner, considering the increase in volume and complexity of satellite systems, and the limited staff implementing modifications to software and applications.

- To be able to meet the regulatory deadlines set up in the Radio Regulations for processing satellite network filings despite budgetary constraints that prevent filling posts related to this processing and that are currently vacant.

- To continue to process notices to terrestrial services under various regulatory procedures, as foreseen in the Radio Regulations and in the applicable Regional Agreements.

- To enhance the level of assistance and support to administrations and BR customers, taking advantage of the high expertise of the BR staff.

- To disseminate the Bureau’s know-how and knowledge in the field of frequency management, in particular with respect to frequency assignments registration procedure, through seminars, workshops, and information meetings, including World Radiocommunication Seminars, and Regional Radiocommunication Seminars.

- To continue to develop, improve and maintain software for regulatory and technical examination, and BR support systems, with a view to reaching a high level of efficiency, reliability, user-friendliness and satisfaction of BR users and administrations.

1.5	Structure of the operational plan

The Union’s operational plan by thematic priorities is presented to the Council. The sector’s operational plans are presented as annexes to the Union’s operational plan.

The ITU-R draft Operational Plan for 2027-2030 has a result-based structure and sets forth details concerning the ITU-R outputs as well as the expected results, key performance indicators and risk assessment. For each of the outputs, the following information is provided (section 2):

- Description of the output and major trends/policy issues relating to the output.

- Performance report for the year 2025, including the comparison between the expected and realized results as well as the key performance indicators (KPIs).

- Detailed statement of expected results and KPIs for the year 2027 as well as measurement indications when applicable.

- Human resources allocation for the 2027 to 2030 timeframe.

A risk assessment in relation to each of the BR output is also provided (section 3).

# 2	ITU-R Outputs

## 2.1	Processing of space notices

Description

In accordance with Nos. 172 and 173 of the Convention, the Radiocommunication Bureau records and registers frequency assignments to space systems in accordance with the relevant provisions of the Radio Regulations (notably Articles 9, 11, 13, 14, 15, 21 and 22, Appendices 4, 5, 7, 8, 30, 30A, 30B, Resolutions 4, 8, 32, 35, 40, 49, 55, 85, 552, 553, 609, 761, 769, 770 of the Radio Regulations) and keeps up to date the Master International Frequency Register. The Bureau also assists in the resolution of cases of harmful interference, at the request of one or more of the interested administrations.

At its 100th meeting held in November 2025, the Radio Regulations Board noted “the slow progress in reducing the backlog, which still exceeded the 4-month regulatory period set out in No. 9.38 of the Radio Regulations. The Board expressed concern that the current ITU budgetary situation might lead to a lack of adequate resources for processing satellite network filings and emphasized the requirement for the Bureau to be funded at a level consistent with the performance of its duties under the Radio Regulations.”

2025 performance report

2025 Statement of achieved results

| Expected results | Achieved results | Key performance indicators | Measurement / performance data |
| --- | --- | --- | --- |
| API New or modified Advance Publication Information (API) submissions: 400 Expected API treatment time (months): ≤ No. 9.2B time limit, i.e. 2 months | API submissions: 456 Average treatment time: 2.6 months | API treatment time ≤ 2 months (No. 9.2B time limit) | BR IFIC (Space Services) |
| CR New or modified coordination request (CR) submissions: 250 Expected CR treatment time (months): ≤ No. 9.38 time limit, i.e. 4 months | CR submissions: 206 Average treatment time: 14.8 months | CR treatment time ≤ 4 months (No. 9.38 time limit) | BR IFIC (Space Services) |
| Notification Article 11 submissions for space stations (S/S): 200 and Earth stations (E/S): 200. Expected Part I-S treatment time (months): ≤ No. 11.28 time limit, i.e. 2 months Expected average notification treatment time for Parts II-S and III-S (months):12 (S/S), 6 (E/S). | Article 11 submissions for space stations (S/S): 254 and Earth stations (E/S): 317 Average treatment time: Part I-S publication: 2.7 months for space stations, 1.7 months for earth stations Parts II-S and III-S publication: 6.9 months for space stations, 6.8 months for earth stations | Part I-S treatment time ≤ 2 months (No. 11.28 time limit) Part II-S and III-S treatment time ≤ 12 months (S/S), 6 months (E/S) from the date of publication of Part I-S | BR IFIC (Space Services) |
| AP30/30A Article 4 New Article 4 Part A submissions: 15 New Article 4 Part B submissions: 5 Expected Article 4 Parts A or B treatment delay (months): 6 | Part A submissions: 16 Part B submissions: 6 Average treatment time: Article 4 Part A: 5.3 months Article 4 Part B: 5.4 months | Article 4 Part A treatment time ≤ 6 months Article 4 Part B treatment time ≤ 6 months | BR IFIC (Space Services) |
| AP30/30A Article 5 New Article 5 submissions: 5 Expected Article 5 treatment delay (months): 6 | Article 5 submissions: 6 Average treatment time: 5.5 months | Article 5 treatment time ≤ 6 months | BR IFIC (Space Services) |

| Expected results | Achieved results | Key performance indicators | Measurement / performance data |
| --- | --- | --- | --- |
| AP30B Articles 6 and 7 New Article 6 Part A submissions: 20 New Article 6 Part B submissions: 15 New Article 7 submissions: 2 to 7 Expected Articles 6 (Parts A or B) and 7 treatment delay (months): 6 | Part A submissions: 20 Part B submissions: 4 Article 7 submissions: 0 Average treatment time: Article 6 Part A: 5.8 months Article 6 Part B: 6.3 months Article 7: No submission | Articles 6 (Parts A or B) and 7 treatment time ≤ 6 months | BR IFIC (Space Services) |
| AP30B Article 8 New Article 8 submissions: 15 Expected Article 8 treatment delay (months): 6 | Article 8 submissions: 3 Average treatment time: 6.3 months | Article 8 treatment time ≤ 6 months | BR IFIC (Space Services) |
| Assistance Number of requests for regulatory/technical assistance under Articles 9 and 11, 20 (S/S) and 50 (E/S) Number of requests for regulatory/technical assistance under AP30/30A/30B: 20 | Requests concerning space stations under Articles 9 and 11: 42 Requests concerning Earth Stations: 134 No request under AP30/30A/30B Pending cases at the end of 2025: 15 request concerning space stations under Articles 9 and 11 25 requests concerning Earth Stations 1 request under AP30/30A/30B (due to communication problems with certain administrations). | To expeditiously provide assistance under the various provisions of the Radio Regulations and processed them in a timely manner | BR IFIC (Space Services) |

2027 Statement of expected results

2027 Statement of expected results

| Expected results | Key performance indicators |
| --- | --- |
| API Forecasted new or modified Advance Publication Information (API) submissions: 450 Expected API treatment time: ≤ No. 9.2B time limit, i.e. 2 months | API treatment time ≤ 2 months (No. 9.2B time limit) |
| CR Forecasted new and modified coordination request (CR) submissions: 200 Expected CR treatment time (months): ≤ No. 9.38 time limit, i.e. 4 months | CR treatment time≤ 4 months (No. 9.38 time limit) |
| Notification Forecasted Article 11 submissions for space stations (S/S): 250 and Earth stations (E/S): 300. Expected Part I-S treatment time (months): ≤ No. 11.28 time limit, i.e. 2 months Expected average notification treatment time for Parts II-S and III-S (months): 12 (S/S), 6 (E/S). | Part I-S treatment time ≤ 2 months (No. 11.28 time limit) Part II-S and III-S treatment time ≤ 12 months (S/S), 6 months (E/S) from the date of publication of Part I-S |
| AP30/30A Article 4 Forecasted Article 4 Part A networks: 15 Expected Article 4 Part A treatment delay (months): 6 Forecasted Article 4 Part B networks: 10 Expected Article 4 Part B treatment delay (months): 6 | Article 4 Part A treatment time ≤ 6 months Article 4 Part B treatment ≤ 6 months |
| AP30/30A Article 5 Forecasted Article 5 networks: 10 Expected Article 5 treatment delay (months): 6 | Article 5 treatment time ≤ 6 months |
| AP30B Articles 6, 7 Forecasted Articles 6 Part A submissions: 20 Forecasted Article 6 Part B submissions: 10 Forecasted Article 7 submissions: 2 to 7 Expected Articles 6 (Parts A or B) and 7 treatment delay (months): 6 | Articles 6 (Parts A or B) and 7 treatment time ≤ 6 months |
| AP30B Article 8 Forecasted Article 8 submissions: 10 Expected Article 8 treatment delay (months): 6 | Article 8 treatment time ≤ 6 months |
| Assistance Forecasted number of requests for regulatory/technical assistance under Article 9 and 11: 50 (S/S) and 300 (E/S) Forecasted number of requests for regulatory/technical assistance under AP30/30A/30B: 10 formal cases | To expeditiously provide assistance under the various provisions of the Radio Regulations and processed them in a timely manner |

2027-2030 human resources allocation

Work/months

| Grade | 2027 | 2028 | 2029 | 2030 |
| --- | --- | --- | --- | --- |
| E2 | 1.2 | 1.2 | 1.2 | 1.2 |
| D1 | 7.6 | 7.8 | 7.8 | 7.1 |
| D2 | 1.1 | 0.6 | 0.6 | 1.2 |
| P5 | 35.5 | 34.4 | 34.4 | 31.4 |
| P4 | 167.6 | 177.5 | 179.1 | 133.9 |
| P3 | 79.2 | 82.3 | 83.2 | 71.0 |
| P2 | 56.8 | 57.8 | 58.2 | 43.2 |
| P1 | 5.5 | 5.5 | 5.5 | 5.5 |
| G7 | 2.1 | 2.1 | 2.1 | 2.1 |
| G6 | 78.7 | 79.4 | 79.4 | 71.8 |
| G5 | 96.0 | 96.0 | 96.0 | 90.4 |
| G4 | 18.0 | 18.0 | 18.0 | 17.5 |
| TOTAL | 549.2 | 562.6 | 565.5 | 476.2 |

## 2.2	Processing of terrestrial notices

Description

In accordance with Nos. 172 and 173 of the Convention, the Radiocommunication Bureau records and registers frequency assignments to terrestrial stations in accordance with the relevant provisions of the Radio Regulations and keeps up to date the Master International Frequency Register; review entries in that Register. The Bureau also assists in the resolution of cases of harmful interference, at the request of one or more of the interested administrations.

2025 performance report

2025 Statement of achieved results

| Expected results | Achieved results | Key performance indicators | Measurement / performance data |
| --- | --- | --- | --- |
| Processing of 50100 notifications under Article 11 of the RR | 59785 notices processed | To process each submission within statutory time-limit, in accordance with the applicable procedures | Fully achieved |
| Processing of all the relevant submissions related to plan modification procedures, viz. - AP25: 12 AP26: 12 - ST61: 36 - GE75: 72 - RJ81: 0 - RJ88:0 - GE84: 2040- GE85: 12 - GE89: 36 - GE06D: 1080 - GE06L: 60 | Processed: AP25: 0 AP26: 0 - ST61: 0 - GE75: 6 - RJ81: 0 RJ88: 0 - GE84: 9285 - GE85:0 GE89: 0 - GE06D: 16954 - GE06L: 9565 | To process each submission, under the relevant plan modification procedure, within statutory time-limits | Fully achieved |
| Processing of 15000 submissions to broadcasting service in the HF bands | 23344 submissions were processed | To process timely the submissions from administrations and to publish them in the HFBC schedules, within the time limits specified in the RR | Fully achieved |
| Processing of 12 coordination requests under RR9.21 pertaining to terrestrial radiocommunication services | 622 coordination requests were processed | To process each coordination request within statutory time- limits | Fully achieved |
| Application of other regulatory procedures, including assistance in the application of the regulatory procedures, viz: - approximately 7 requests for various types of assistance in pursuance to Article 13 of the RR - approximately 1000 reports of harmful interference or infringements; - approximately 28000 monitoring reports in response to the regular and special monitoring programmes in the HF bands - approximately 600 reports in response to Resolution 205 | 4 requests for assistance in pursuance to Article 13 were processed 1140 reports of harmful interference treated 33407 monitoring reports in the HF bands processed 1114 reports in response to Resolution 205 processed | All requests for assistance to be treated in a timely manner. The relevant follow up actions to be conducted with no delay | Fully achieved |
| Application of administrative and operational procedures, viz. - handling of about 40 cases for assistance, including 10 specific requests dealing with allocation of series of call signs, selective numbers and Maritime Identification Digits (MID) as well as ITU- R and ITU-T Recommendations - Some 1 requests under Article 47 and 48 - Some 10 cases under Resolution 647 - Some 2 cases under Article 25. Processing of 2000 notifications under Article 20 of the RR | 14 cases for assistance, including 11 specific requests dealing with allocation of numbering resources - 0 requests under Article 47 and 48 - 0 cases under Resolution 647 - 0 cases under Article 25. Processing of 1918 notifications under Article 20 of the RR | all requests to be treated in time. All relevant data to be made promptly available to all administrations, including the uninterrupted on-line availability of the ship station database through MARS. To process each notification in accordance with the applicable procedures, and to publish the information on MARS and the concerning ITU Service Publications. | Fully achieved Fully achieved |

2027 Statement of expected results

2027 Statement of expected results

| Expected results | Key performance indicators |
| --- | --- |
| Processing of 65000 notifications under Article 11 of the RR | To process each submission within statutory time-limit, in accordance with the applicable procedures. Average treatment time: 2 months |
| Processing of all the relevant submissions related to plan modification procedures, viz. - AP25: 2 - AP26: 2 - ST61: 2 - GE75: 10 - RJ81: 0 -RJ88: 0 - GE84: 8000 - GE85: 2 - GE89: 2 - GE06D: 20000 -GE06L: 6000 | To process each submission, under the relevant plan modification procedure, within statutory time-limits |
| Processing of 26000 submissions to broadcasting service in the HF bands | To process timely the submissions from administrations and to publish them in the HFBC schedules , within the time limits specified in the RR |
| Processing of 200 coordination requests under No 9.21 of the RR pertaining to terrestrial radiocommunication services | To process each coordination request within statutory time- limits |

| Application of other regulatory procedures, including assistance in the application of the regulatory procedures, viz: - approximately 10 requests for various types of assistance in pursuance to Article 13 of the RR - approximately 1000 reports of harmful interference or infringements; - approximately 20000 monitoring reports in response to the regular and special monitoring programmes in the HF bands - approximately 700 reports in response to Resolution 205 | All requests for assistance to be treated in a timely manner. The relevant follow up actions to be conducted with no delay |
| --- | --- |
| Application of administrative and operational procedures, viz. - handling of about 50 cases for assistance, including 10 specific requests dealing with allocation of series of call signs, selective numbers and Maritime Identification Digits (MID) as well as ITU- R and ITU-T Recommendations - Some 2 requests under Article 47 and 48 - Some 3 cases under Resolution 647 -Some 2000 notifications under Article 20 - Some 2 cases under Article 25. | all requests to be treated in time. All relevant data to be made promptly available to all administrations, including the uninterrupted on-line availability of the ship station database through MARS. |

2027-2030 human resources allocation

Work/months

| Grade | 2027 | 2028 | 2029 | 2030 |
| --- | --- | --- | --- | --- |
| E2 | 1.2 | 1.2 | 1.2 | 1.2 |
| D1 | 4.4 | 4.9 | 5.6 | 5.6 |
| D2 | 1.1 | 0.6 | 0.6 | 1.2 |
| P5 | 18.7 | 28.1 | 28.1 | 18.2 |
| P4 | 115.2 | 125.5 | 125.5 | 95.5 |
| P3 | 58.3 | 73.9 | 73.9 | 28.9 |
| P2 | 22.2 | 23.0 | 23.0 | 23.0 |
| P1 | 0.0 | 0.0 | 0.0 | 0.0 |
| G7 | 2.1 | 2.1 | 2.1 | 2.1 |
| G6 | 39.3 | 41.9 | 41.9 | 39.1 |
| G5 | 18.0 | 18.0 | 18.0 | 18.0 |
| G4 | 2.4 | 2.4 | 2.4 | 2.4 |
| TOTAL | 282.8 | 321.7 | 322.4 | 235.1 |

## 2.3	WRC’s outputs (Final Acts and Radio Regulations)

Description

World radiocommunication conferences (WRCs) are held, in principle, every four years. It is the role of WRC to review, and, if necessary, revise the Radio Regulations, the international treaty governing the use of the radio-frequency spectrum and the satellite and satellite orbits. The BR is responsible for the overall planning and support of the WRC, involving document processing and the provision of secretarial support for the Plenary and the Committees.

The general scope of the agenda of world radiocommunication conferences is established four to six years in advance, with the final agenda set by the ITU Council two years before the conference, with the concurrence of Member States.

The last WRC was held in 2023, and the next one is planned for 2027.

2025 performance report

2025 Statement of achieved results

| Expected results | Achieved results | Key performance indicators | Measurement / performance data |
| --- | --- | --- | --- |
| Council decision on WRC-27 agenda, and subsequent concurrence by majority of ITU Member States | Approval of agenda by ITU member states in Council Resolution 1422 (C24) and concurrence by majority of ITU Member States in CL-24/38 (June 2024) and CL-24/49 (Sept. 2024). | Confirmation of the WRC-27 agenda over 3 years before the conference | Compliance with the relevant provisions of the ITU Convention, in particular CV 118. |
| Council decision on RA-27 and WRC-27 dates and place, and subsequent concurrence by majority of ITU Member States | Following C-25 decision, ITU issued the consultation with Member States in CL-25/40 (August 2025) and CL-25/45 (October 2025) | Confirmation of the exact date and place 2 years before the events. | Compliance with CV 42 of the ITU Convention. Confirmation of exact date to allow the start the preparation and coordination with the Host Country. |
| WRC-27 website published | Website published following the results of the consultation with ITU member states on the conference dates and place | Website released 2 years before the conference. | Up to date information available to membership, as new information becomes available. |
| To convene the 1st ITU Inter-Regional Information Session (IRIS) on WRC-27 Preparation | 1st ITU Inter-regional Information Sessions on WRC-27 Preparation held in Geneva from 3-5 December 2025. | Updated information provided on the ITU-R preparatory studies for CPM27-2, RA-27 and WRC-27. Offer membership an opportunity to exchange on the most challenging WRC-27 agenda items and issues as well as of the draft preliminary views. | Event organized accordance with ​Resolution 72 (Rev.WRC-19) about two years prior to WRC-27 |

2027 Statement of expected results

2027 Statement of expected results

| Expected results | Key performance indicators |
| --- | --- |
| Preparation for and delivery of WRC-27 | Adequate planning and coordination of WRC-27 (including logistics, security, visas, internal coordination and coordination with the Host Country). Provision of updates on the WRC preparation process to member states through Council reports and other suitable channels. Participation in meetings organized by regional telecommunication organizations to assist in detailed preparations and coordination between regions, as well as with the preparation of proposals. Provision of support and training for WRC Chair elect. Timely preparation and submission of Secretariat documents to WRC. Organization of WRC-27 with adequate and timely delivery of key products and services (including registration, translation, document, and facility management). Provision of secretarial support for the WRC Plenary and Committees. Publication of the provisional Final Acts of WRC-27. |
| To convene the 2nd and 3rd ITU Inter-Regional Information Session (IRIS) on WRC-27 Preparation | In accordance with Resolution 72 (Rev.WRC-19), organization of these two events planned respectively in December 2026 (prior to CPM27-2) and August 2027 (after CPM27-2) to provide ITU membership with additional opportunities to exchange on the most challenging WRC-27 agenda items and issues as well as of the draft preliminary views and positions. |

2027-2030 human resources allocation

Work/months

| Grade | 2027 | 2028 | 2029 | 2030 |
| --- | --- | --- | --- | --- |
| E2 | 1.8 | 1.8 | 0.6 | 0.6 |
| D1 | 3.1 | 2.1 | 1.6 | 1.2 |
| D2 | 1.1 | 1.2 | 0.0 | 0.6 |
| P5 | 13.8 | 16.1 | 10.1 | 10.4 |
| P4 | 24.2 | 15.2 | 7.5 | 9.8 |
| P3 | 24.5 | 3.2 | 2.4 | 9.7 |
| P2 | 3.6 | 1.4 | 1.0 | 1.3 |
| P1 | 1.6 | 1.6 | 1.6 | 1.6 |
| G7 | 8.0 | 4.9 | 2.0 | 2.0 |
| G6 | 22.5 | 21.7 | 2.8 | 6.1 |
| G5 | 1.8 | 7.2 | 1.8 | 0.8 |
| G4 | 0.7 | 2.5 | 0.7 | 0.4 |
| TOTAL | 106.9 | 78.9 | 32.2 | 44.5 |

## 2.4	CPM’s output (CPM Report)

Description

In accordance with Resolution ITU-R 2-9, the Conference Preparatory Meeting (CPM) shall prepare a Report to the World Radiocommunication Conferences (WRC) on the ITU-R preparatory studies and possible solutions to the WRC agenda items, to be used in support of the work of WRC.

At the end of December 2023, immediately following WRC-23, the first session of the CPM for WRC-27 (CPM27-1) took place to organize the ITU-R preparatory studies for WRC-27. The CPM27-1 results have been disseminated at the beginning of 2024 (see CA/270 of 26 January 2024) to indicate the allocation of ITU-R preparatory work for WRC-27 as well as other important elements for the preparation of the Report of the CPM to WRC-27. As a result of the CPM-27 Steering Committee meeting held on 24 June 2024, the deadline for the submission of the draft CPM texts by the ITU-R working parties responsible for the WRC-27 agenda items, was set to 23 October 2026 and communicated to the membership in Addendum 1 to CA/270 of 15 July 2024. The CPM-27 Management Team meeting was planned for 11 and 12 November 2026. As a result of the CPM-27 Steering Committee meeting held on 3 December 2024, some additional amendments to the allocation of ITU-R preparatory work for WRC-27 were made and the deadline for the submission of materials on criteria, characteristics and methodologies for the WRC-27 preparatory studies was extended to 1 July 2025 (see Corrigendum 1 to Addendum 1 of CA/270 dated 12 December 2024).

2025 performance report

2025 Statement of achieved results

| Expected results | Achieved results | Key performance indicators | Measurement / performance data |
| --- | --- | --- | --- |
| Follow-up on the work program set by CPM27-1. Organization of the CPM-27 Steering Committee meetings. Availability of a preliminary version of the CPI webtool for WRC-27. Regular updates of the ITU webpages on ITU-R preparatory studies for WRC-27 and preliminary studies for WRC-31. | Two meetings of the CPM-27 Steering Committee to review the progress and address potential issues were successfully held on 3 July and 5 December 2025. Based on the 2024 Edition of the Radio Regulations, a preliminary version of the CPI webtool for WRC-27 was developed and made available in January 2025. The webpages on ITU-R preparatory studies for WRC-27 and preliminary studies for WRC-31 were updated after each meeting of the responsible ITU-R working parties. | Implementation of CPM27-1 decisions Adequate level of planning undertaken. | Satisfaction of delegations. Actions undertaken in a timely manner |

2027 Statement of expected results

2027 Statement of expected results

| Expected results | Key performance indicators |
| --- | --- |
| Preparation and organization of CPM27-2. Continue the work program set by CPM27-1 and the timely preparation of the draft CPM Report to WRC-27. Dissemination of information. Publication of the draft CPM Report and of the final CPM Report to WRC-27 in accordance with Resolution ITU-R 2. | Documents available on-line as soon as practicable; increased information content on CPM web page. Organization of CPM27-2, including the preparation, logistics, internal coordination and coordination with CICG. Participation in meetings organized by various regional telecommunication organizations to assist in detailed preparations and coordination between regions and prepared for the 3rd IRIS on WRC-27 Preparation. |
| Preparation and organization of CPM31-1. | Organization of CPM31-1, including the preparation, logistics, internal coordination and coordination with host country. |

2027-2030 human resources allocation

Work/months

| Grade | 2027 | 2028 | 2029 | 2030 |
| --- | --- | --- | --- | --- |
| E2 | 1.2 | 0.0 | 0.6 | 0.6 |
| D1 | 1.2 | 1.2 | 1.2 | 0.9 |
| D2 | 0.0 | 0.0 | 0.0 | 0.6 |
| P5 | 21.6 | 6.9 | 7.3 | 5.4 |
| P4 | 4.2 | 2.1 | 2.1 | 5.1 |
| P3 | 4.9 | 2.4 | 2.4 | 5.1 |
| P2 | 1.2 | 1.2 | 1.2 | 1.4 |
| P1 | 0.0 | 0.0 | 0.0 | 0.0 |
| G7 | 5.0 | 1.4 | 2.0 | 1.9 |
| G6 | 18.0 | 4.5 | 5.0 | 3.7 |
| G5 | 5.4 | 3.0 | 3.0 | 1.4 |
| G4 | 0.6 | 0.6 | 0.6 | 1.0 |
| TOTAL | 63.3 | 23.3 | 25.4 | 27.1 |

## 2.5	RRB’s outputs (Rules of Procedure and Decisions)

Description

The Radiocommunication Bureau provides support for the RRB including preparation and circulation of draft Rules of Procedure and other documents for its consideration, implementation of its decisions and support for the conduct of its meetings. The tasks of the Board involve regular consideration of difficulties encountered by the Bureau in administering the provisions of the Radio Regulations, any submissions to it by administrations, cases of harmful interference referred to the RRB and regular maintenance of Rules of Procedure.

2025 performance report

2025 Statement of achieved results

| Expected results | Achieved results | Key performance indicators | Measurement / performance data |
| --- | --- | --- | --- |
| The RRB undertook the ongoing review of the Rules of Procedure, pursuant to RR Article 13, consideration of the cases of harmful interference and any other issues submitted by administrations. A total of 3 meetings were heled in 2025 | Requests for review were resolved at the first available meeting after receiving submissions from Member States. The revision of the RoP were approved by the RRB and the Edition of 2025 was published. | Timely consideration of cases and issues submitted by administrations | No complaints from administrations and appropriate consideration of cases/issues submitted for decisions |

2027 Statement of expected results

2027 Statement of expected results

| Expected results | Key performance indicators |
| --- | --- |
| The Radiocommunication Bureau provides support for the RRB including preparation and circulation of draft Rules of Procedure and other documents for its consideration, implementation of its decisions and support for the conduct of its meetings. The tasks of the Board involve regular consideration of difficulties encountered by the Bureau in administering the provisions of the Radio Regulations, any submissions to it by administrations, cases of harmful interference referred to the RRB and regular maintenance of Rules of Procedure. A total of 3 meetings is foreseen in 2027 | Consideration of Rules of Procedure and follow up. Expeditious resolution of requests for review after receiving submissions from Member States. Bureau convening bilateral or multilateral meetings to resolve continuing difficulties between administrations in relation to the use of spectrum. Administration’s satisfaction and timeliness of actions |

2027-2030 human resources allocation

Work/months

| Grade | 2027 | 2028 | 2029 | 2030 |
| --- | --- | --- | --- | --- |
| E2 | 0.6 | 1.2 | 1.2 | 1.2 |
| D1 | 2.1 | 2.1 | 2.1 | 0.9 |
| D2 | 1.1 | 0.6 | 0.6 | 1.2 |
| P5 | 12.5 | 12.0 | 12.0 | 8.8 |
| P4 | 4.3 | 4.7 | 4.7 | 4.7 |
| P3 | 1.2 | 2.6 | 2.6 | 1.9 |
| P2 | 1.5 | 1.9 | 1.9 | 1.8 |
| P1 | 0.0 | 0.0 | 0.0 | 0.0 |
| G7 | 1.5 | 2.1 | 2.1 | 2.2 |
| G6 | 8.8 | 6.5 | 6.5 | 8.7 |
| G5 | 0.0 | 0.0 | 0.0 | 0.5 |
| G4 | 0.6 | 0.6 | 0.6 | 0.5 |
| TOTAL | 34.2 | 34.4 | 34.4 | 32.5 |

## 2.6	Software (not related to Processing of notices, e.g. RR Article 5 TFA software, Radio Navigation Tool search engine etc)

Description

The RR5 TFA software tool, designed to conduct a detailed search and analysis of the Table of Frequency Allocations in Article 5 of the Radio Regulations, enables filtering and reformatting by frequency range, service, category of service, footnote, country, etc. The tool has been updated based on the outcomes of the WRC-23 and the RR 2024 Edition to introduce the changes in the frequency allocations, country footnotes, and related references to associated Resolutions and Recommendations. It also includes links to the relevant ITU-R Recommendations referenced in RR5, as well as the latest version of the relevant Rules of Procedure and other relevant Articles of the RR. The package is also equipped with a utility to extract the National Table of Frequency Allocations for a specific country as it results from combining the various provisions of RR5. The most recent release of the package is available for purchase at the ITU sales website since October 2024. All software and data updates will be provided regularly and freely to the subscribers until the release of the new version, based on WRC-27 decisions.

The RR Navigation tool provides one-stop access to the Radio Regulations, the Rules of Procedure (RoP), ITU-R Recommendations cited but not included in the RR, ITU Constitution and Convention. It helps users to navigate over 15,000 references including articles, provisions, and annexes. The update of the tool to conform to the 2024 edition of the Radio Regulations and other relevant texts (Rules of Procedure, Basic texts) was completed. The updated software (free for all users) was released in August 2025.

The Bureau finalized the modernization of its terrestrial frequency notifications processing system. As a consequence of this work, and in accordance with the access policy, access to the current terrestrial BR IFIC is now freely available online to Member States Administrations, at Terrestrial BR IFIC, since March 2025, including access to previous terrestrial BR IFICs published during the current year. Various query and export tools were also made available online.

The Terrestrial Services Department (TSD) develops and enhances eTerrestrial web platform, which provides to ITU Members online tools related to terrestrial services (e.g. eMIFR, eValidation, WISFAT, eBroadcasting, eFXM (Fixed/Mobile), ePropagation and eHFBC). Geospatial activities for the implementation of BR Geospatial platform have progressed and the BR Geoportal is ready for a preview production deployment.

TSD released the final version of the new online platform for treatment of the reports of harmful interference and infringements, concerning terrestrial services (HITS).

TSD enhances the maritime service publications user’s experience. The online sales platform, the desktop application containing the digital publications and mobile application for ship inspectors are in production.

2025 performance report

2025 Statement of achieved results

| Expected results | Achieved results | Key performance indicators | Measurement / performance data |
| --- | --- | --- | --- |
| Development, maintenance and enhancement of web tools and their functions under eTerrestrial web platform. Development of ePubFXM under eFXM to consult FXM Special Sections RR9.21 and GE06L. Development of WEB tool for calculations based on ITU‐R P.452 propagation model. Enhancement of the Web interface for the submission of terrestrial frequency assignments (WISFAT) to the BR Development of HITS (Harmful Interference to Terrestrial Services) web platform | Continuous improvement of eHFBC component in eBroadcasting. New features include additional calculation options, management tools and integration of maps and antenna diagrams. Development of ePubFXM under eFXM to consult FXM Special Sections RR9.21 and GE06L was finalized WEB tool development for calculations based on ITU‐R P.452 propagation model (point to point) completed. Implementation in ePropagation of multipoint-to-point calculations based on ITU-R P.1546 propagation model. Development of WISFAT 2.0 completed. The final version of HITS has been released for Member States. Development of a map template library to ensure a consistent look and feel of maps in BR web applications and speed up map development. Integration of this template in several screens. | Timely implementation and user satisfaction. | Appropriate consideration of feedback received and satisfaction of users. Number of users and number of administrations using the web tools |
| Enhancement of the maritime service publications user’s experience | The creation of a Sales Platform, the development of the Desktop Application and the Inspector application are completed |  |  |

2027 Statement of expected results

2027 Statement of expected results

| Expected results | Key performance indicators |
| --- | --- |
| Implementation of software tools based on user’s requirements. | Timely completion and user’s satisfaction. Target dates, acceptance criteria. |

2027-2030 human resources allocation

Work/months

| Grade | 2027 | 2028 | 2029 | 2030 |
| --- | --- | --- | --- | --- |
| E2 | 0.6 | 0.6 | 0.6 | 0.6 |
| D1 | 1.3 | 1.3 | 1.3 | 1.7 |
| D2 | 0.0 | 0.6 | 0.0 | 0.6 |
| P5 | 16.1 | 16.1 | 16.1 | 21.2 |
| P4 | 138.9 | 142.6 | 142.6 | 205.9 |
| P3 | 67.8 | 73.8 | 73.8 | 128.2 |
| P2 | 34.5 | 34.5 | 34.5 | 45.8 |
| P1 | 0.0 | 0.0 | 0.0 | 0.0 |
| G7 | 1.6 | 1.6 | 1.6 | 1.6 |
| G6 | 12.5 | 17.3 | 16.7 | 23.6 |
| G5 | 0.0 | 0.0 | 0.0 | 0.7 |
| G4 | 0.0 | 0.0 | 0.0 | 0.0 |
| TOTAL | 273.3 | 288.3 | 287.1 | 429.8 |

## 2.7	ITU-R publications (not covered under ITU-R study groups, e.g. Maritime Manual, List IV, List V)

Description

TSD, in accordance with Article 20 of the RR, issues the following maritime and monitoring-related service publications: List IV (biannually), List V (annually), Maritime Manual (every four years) and the List of International Monitoring Stations - List VIII (every three years).

2025 performance report

2025 Statement of achieved results

| Expected results | Achieved results | Key performance indicators | Measurement / performance data |
| --- | --- | --- | --- |
| Production of: Ship stations (List V) and List of Coast Stations and Special Service Stations (List IV) | List V and List IV were produced | Timely preparation of these publications | Publications prepared and produced on time. Level of revenue consistent with budget forecast |

2027 Statement of expected results

2027 Statement of expected results

| Expected results | Key performance indicators |
| --- | --- |
| Timely preparation and production of Ship stations (List V) and List of Coast Stations and Special Service Stations (List IV | Publications to be prepared and produced on time. Level of sales of publications revenue consistent with budgeted revenue |

2027-2030 human resources allocation

Work/months

| Grade | 2027 | 2028 | 2029 | 2030 |
| --- | --- | --- | --- | --- |
| E2 | 0.6 | 0.6 | 0.6 | 0.6 |
| D1 | 0.5 | 0.6 | 0.5 | 0.6 |
| D2 | 1.1 | 0.6 | 0.6 | 0.6 |
| P5 | 2.8 | 1.7 | 1.7 | 2.7 |
| P4 | 9.0 | 10.2 | 10.2 | 9.0 |
| P3 | 13.7 | 13.1 | 13.1 | 13.2 |
| P2 | 0.9 | 0.9 | 0.9 | 0.9 |
| P1 | 1.4 | 1.4 | 1.4 | 1.4 |
| G7 | 1.5 | 1.5 | 1.5 | 1.5 |
| G6 | 14.1 | 14.8 | 14.8 | 11.5 |
| G5 | 6.0 | 6.0 | 6.0 | 6.0 |
| G4 | 2.4 | 2.4 | 2.4 | 1.9 |
| TOTAL | 53.9 | 53.8 | 53.7 | 49.8 |

## 2.8	ITU-R study groups’ outputs (ITU-R Recommendations, Reports and Handbooks)

Description

The duties, functions and organization of the Radiocommunication Study Groups are described in Articles 11 and 20 of the Convention, while the working methods of the Study Groups are addressed by Resolution ITU-R 1-9. As approved by RA-23, there are six Study Groups, the Coordination Committee for Vocabulary (CCV) and the Conference Preparatory Meeting (CPM).

The BR provides the necessary support for the above activities, both organizationally and by providing technical guidance in the studies. In addition, it contributes and responds to the work of the RAG in areas concerning Study Groups activities.

2025 performance report

2025 Statement of achieved results

| Expected results | Achieved results | Key performance indicators | Measurement / performance data |
| --- | --- | --- | --- |
| Work programmes in response to: ITU-R Resolutions; work assigned by CPM; work assigned by WRC-23 (not identified by CPM); administrative and logistic support from BR/SGD; necessary information disseminated in administrative circulars (and circular letters); meeting calendars monitored and adjusted in accordance with the progress. | Work programmes executed and completed in accordance with schedules, and information dissemination accomplished on time. Deliverables were made available to membership within expected timescale | Draft Recommendations developed in accordance with Study Groups objectives; draft CPM texts | Outputs available to membership within expected timescale and in the required form |
| Provision of appropriate level of support by BR/SGD for meetings, both technical, administrative and logistic | Adequate level of support with necessary documentation and facilities to allow meetings to run smoothly | Meetings satisfy objectives within the imposed deadlines. | Meetings completed with objectives met. Positive feedback by the membership received on execution of meetings |

2027 Statement of expected results

2027 Statement of expected results

| Expected results | Key performance indicators |
| --- | --- |
| Continuation and completion of work programmes undertaken in response to: - ITU-R Resolutions; - work assigned by CPM27-1; - work assigned by WRC-23 (not identified by CPM27-1); | Work programmes executed in accordance with schedules, and information dissemination accomplished on time; Draft Recommendations; Reports and Handbooks developed in accordance with Study Groups objectives. Deliverables available to membership within expected timescale |
| Provision of appropriate level of support by BR/SGD for meetings, both technical, administrative and logistic | Adequate level of support with necessary documentation and facilities to allow meetings to run smoothly. Meetings satisfy objectives within the imposed deadlines. |
| Documentation associated with meetings processed in accordance with Resolution ITU-R 1 and in accordance with decisions of RA-23; liaison statements and chair’s reports processed in timely manner. Timely and efficient preparation of major deliverables | Document availability before, during and after meetings at required level. Adoption/approval processes effectively implemented, and in accordance with decisions of RA-23. Quality control applied within limits of available resources. Working procedures effectively implemented to enable timely production of major deliverables |

2027-2030 human resources allocation

Work/months

| Grade | 2027 | 2028 | 2029 | 2030 |
| --- | --- | --- | --- | --- |
| E2 | 0.6 | 1.2 | 1.8 | 1.8 |
| D1 | 4.1 | 4.0 | 4.1 | 6.9 |
| D2 | 1.0 | 0.6 | 0.6 | 1.8 |
| P5 | 20.8 | 26.6 | 30.8 | 45.2 |
| P4 | 21.2 | 20.0 | 25.8 | 30.8 |
| P3 | 9.5 | 13.4 | 13.4 | 11.3 |
| P2 | 11.2 | 11.2 | 11.2 | 11.2 |
| P1 | 1.6 | 1.6 | 1.6 | 1.6 |
| G7 | 11.0 | 15.4 | 17.6 | 19.1 |
| G6 | 24.6 | 32.7 | 49.8 | 59.8 |
| G5 | 17.4 | 14.4 | 19.8 | 30.3 |
| G4 | 6.7 | 4.9 | 6.7 | 10.2 |
| TOTAL | 129.6 | 146.0 | 183.3 | 229.9 |

## 2.9	RA outputs (e.g. ITU-R Resolutions)

Description

The principal responsibilities of the Radiocommunication Assembly are to review the results of the previous study period, to define the structure of the Study Groups and establish their work programme for the period up to the next Assembly, to review the ITU-R Resolutions, to approve draft Recommendations, and to nominate chairs/vice-chairs of Study Groups, the CCV, the CPM and the RAG.

The Radiocommunication Bureau is responsible for the planning, management and support of the Assembly, involving the control of documentation and the provision of secretarial support for the Plenary and the Committees. BR also provides appropriate guidance and support to the Study Groups Chairs with respect to the documentation relating to their groups.

The last RA was held in 2023, and the next one is planned to be held in 2027.

2025 performance report

2025 Statement of achieved results

| Expected results | Achieved results | Key performance indicators | Measurement / performance data |
| --- | --- | --- | --- |
| Publication of ITU-R Resolutions approved by RA-23 | Timely publication of the outputs | Adequate level of planning undertaken. | Satisfaction of the membership. Actions undertaken in a timely manner |

2027 Statement of expected results

2027 Statement of expected results

| Expected results | Key performance indicators |
| --- | --- |
| Implementation and follow-up and execution of decisions of RA-23 | Work programs and decisions implemented in timely manner. Satisfaction of the membership. |
| Preparation for RA-27 and follow up of RA-27 decisions | Work programs and decisions implemented in timely manner. Satisfaction of the membership. |

2027-2030 human resources allocation

Work/months

| Grade | 2027 | 2028 | 2029 | 2030 |
| --- | --- | --- | --- | --- |
| E2 | 1.2 | 0.6 | 0.6 | 0.6 |
| D1 | 2.0 | 2.0 | 2.0 | 1.5 |
| D2 | 1.0 | 0.6 | 0.6 | 0.6 |
| P5 | 16.6 | 18.0 | 18.0 | 2.3 |
| P4 | 5.0 | 2.6 | 2.6 | 1.8 |
| P3 | 6.0 | 3.8 | 3.6 | 2.3 |
| P2 | 0.9 | 0.9 | 0.9 | 0.9 |
| P1 | 0.0 | 0.0 | 0.0 | 0.0 |
| G7 | 4.3 | 3.1 | 3.1 | 2.0 |
| G6 | 17.4 | 10.5 | 10.5 | 4.9 |
| G5 | 7.8 | 7.8 | 7.8 | 1.3 |
| G4 | 3.1 | 3.1 | 3.1 | 0.6 |
| TOTAL | 65.3 | 53.1 | 52.9 | 18.8 |

## 2.10	RAG outputs (Advice to BR Director, inputs to RA)

Description

In its advisory capacity, the RAG will continue to review priorities, programmes, operations, financial matters, and strategies related to radiocommunication assemblies, study groups and other groups and the preparation of radiocommunication conferences, and any specific matter as directed by a conference of the Union, a radiocommunication assembly or the Council. In addition, the RAG will review the implementation of the Operational Plan of the preceding period to identify areas in which the Bureau has not achieved or was not able to achieve the objectives laid down in that plan and advise the Director to take the necessary corrective measures. The RAG will continue to recommend measures to foster cooperation and coordination with other standards bodies, with the Telecommunication Standardization Sector, the Telecommunication Development Sector, and the General Secretariat.

2025 performance report

2025 Statement of achieved results

| Expected results | Achieved results | Key performance indicators | Measurement/ performance data |
| --- | --- | --- | --- |
| Administrative actions concerning the convening of 32nd RAG meeting. | Adequate logistical support and provision of secretariat support for the meeting | Logistical support provided, including RAG website up-to-date; invitation letter issued at least 3 months before the meeting, registration; timely processing, translation, and publication of contributions and Secretariat documents; interpretation, captioning, remote participation, etc.; Provision of secretariat support for the meeting. | Meeting completed and actions undertaken in a timely manner. |
| Timely addressing of the relevant issues by RAG | All actions listed in the RAG summary of conclusions were undertaken and completed on time. Progress updates were inserted in the report to the next RAG. | The Draft Summary of Conclusions was approved during the meeting; the Final Summary of Conclusions (in English) was published after the meeting and translated into other languages of the Union | Actions undertaken in a timely manner. |

2027 Statement of expected results

2027 Statement of expected results

| Expected results | Key performance indicators |
| --- | --- |
| Implementation of the advice/guideline provided by the 33rd meeting of the RAG | Timely implementation of the action items as advised by the RAG and recorded in the Summary of Conclusions. As required, status updates are provided on the BR Director’s report to the 34th meeting of the RAG. |
| Administrative actions concerning the convening of the 34th meeting of RAG | Logistical support provided, including RAG website up-to-date; invitation letter issued at least 3 months before the meeting, registration; timely processing, translation, and publication of documents; interpretation, captioning, remote participation, etc.; provision of secretariat support for the meeting. |
| Preparation of Secretariat documents | Timely publication of the BR Director’s Report and Operational Plan to the RAG. |

2027-2030 human resources allocation

Work/months

| Grade | 2027 | 2028 | 2029 | 2030 |
| --- | --- | --- | --- | --- |
| E2 | 0.6 | 0.6 | 0.6 | 0.6 |
| D1 | 1.5 | 1.5 | 1.5 | 1.0 |
| D2 | 1.0 | 1.8 | 1.8 | 0.6 |
| P5 | 7.4 | 6.1 | 6.7 | 4.8 |
| P4 | 2.4 | 1.2 | 1.2 | 1.5 |
| P3 | 4.2 | 4.8 | 4.8 | 4.6 |
| P2 | 0.9 | 0.9 | 0.9 | 0.9 |
| P1 | 0.3 | 0.3 | 0.3 | 0.3 |
| G7 | 3.2 | 4.4 | 4.4 | 3.8 |
| G6 | 7.0 | 9.0 | 9.0 | 6.6 |
| G5 | 1.8 | 1.8 | 1.8 | 0.0 |
| G4 | 0.7 | 0.7 | 0.7 | 0.1 |
| TOTAL | 31.1 | 33.3 | 33.9 | 24.8 |

## 2.11	Technical Assistance (e.g. BR support to regional initiatives)

Description

The Bureau carries a significant number of activities related to telecommunication development. Resolution ITU-R 75 provides a comprehensive framework for liaison and support activities to ITU-D and ITU-T. In particular, the Director of the Bureau continues to cooperate with the Director of BDT in enhancing the ability of the regional and area offices to provide information on their Sector’s activities, as well as the necessary expertise, to strengthen cooperation and coordination with the relevant regional organizations and to facilitate participation of all Member States and Sector Members in the activities of the three Sectors of the Union.

The work programme of the ITU-R Study Groups aims to keep in mind the requirements of developing countries and, where appropriate, to orient its work accordingly. This involves: (i) stimulating the development of draft Recommendations which provides direct assistance in the development and implementation of systems; (ii) the production of handbooks, providing material of a tutorial nature; (iii) offering advice, from Study Groups participants and BR, on issues such as national spectrum management, wireless access, IMT (International Mobile Telecommunication), satellite systems (including LEO, MEO and GEO systems), digital broadcasting, science services and radio-wave propagation.

The objective of the programme is for the professional staff of the BR to provide such assistance through: (i) participation in ITU-D/ITU-T meetings and events and liaise with BDT/TSB staff; (ii) promoting the development of handbooks within ITU-R; (iii) providing direct assistance on specific problems in a country or region, e.g. spectrum management, prevailing propagation conditions and propagation measurements; transition to digital TV and digital dividend; (iv) lecturing at seminars/workshops organized for developing countries, e.g. information meetings.

BR experts assist the BDT in the development and implementation of the spectrum management system for developing countries. Finally, the Bureau organizes meetings aimed at designing standard spectrum management frameworks suitable for administrations of developing countries.

2025 performance report

2025 Statement of achieved results

| Expected results | Achieved results | Key performance indicators | Measurement / performance data |
| --- | --- | --- | --- |
| Participation of ITU-R and/or BR experts in workshops / seminars organized by other ITU Sectors. Assist developing countries and BDT on aspects of mutual interest, such as spectrum management techniques | Trainings on Spectrum Management provided in seminars and workshops. Development of self-paced trainings | Satisfaction expressed by participants; increased awareness of developing countries in the work of ITU-R | Satisfaction of the participants. |

2027 Statement of expected results

2027 Statement of expected results

| Expected results | Key performance indicators |
| --- | --- |
| Participation of ITU-R and/or BR experts in workshops/seminars organized by other Sectors and organizations | Participants benefit from ITU-R and BR expertise. Satisfaction expressed by participants; increased awareness of developing countries of work of ITU-R |
| Assist developing countries and other ITU Sectors on aspects of mutual interest, such as spectrum management techniques | As above |

2027-2030 human resources allocation

Work/months

| Grade | 2027 | 2028 | 2029 | 2030 |
| --- | --- | --- | --- | --- |
| E2 | 0.6 | 0.6 | 0.6 | 0.6 |
| D1 | 1.2 | 1.2 | 1.2 | 2.2 |
| D2 | 1.0 | 0.6 | 0.6 | 0.6 |
| P5 | 11.2 | 9.8 | 10.2 | 13.9 |
| P4 | 20.2 | 14.8 | 14.8 | 24.2 |
| P3 | 19.8 | 13.2 | 13.2 | 17.0 |
| P2 | 2.3 | 2.3 | 2.3 | 5.5 |
| P1 | 0.5 | 0.5 | 0.5 | 0.5 |
| G7 | 1.8 | 1.8 | 1.8 | 1.8 |
| G6 | 5.6 | 4.0 | 4.0 | 6.0 |
| G5 | 0.0 | 0.0 | 0.0 | 0.0 |
| G4 | 0.0 | 0.0 | 0.0 | 0.0 |
| TOTAL | 64.2 | 48.8 | 49.2 | 72.3 |

## 2.12	ITU-R Seminars (e.g. WRS, RRS)

Description

The Radiocommunication Bureau organizes, in Geneva, seminars on radiocommunication matters, for the entire ITU membership, as well as regional seminars that are held outside Geneva and hosted by different ITU Member States, whose program puts emphasis on the implementation of the provisions of the Radio Regulations and other spectrum management issues. These seminars normally comprise presentations from BR staff and from Member States’ staff, as well as interactive workshops, with an emphasis on spectrum management and on the preparation of major spectrum decisions, such as transition to digital terrestrial television broadcasting or allocation of the digital dividend.

The Bureau organizes information sessions to assist administrations in their preparation for radiocommunication conferences.

2025 performance report

2025 Statement of achieved results

| Expected results | Achieved results | Key performance indicators | Measurement/ performance data |
| --- | --- | --- | --- |
| Organize 3 regional seminars during the period. | 3 regional seminars were held: RRS-25-Africa, RRS-25-Americas and RRS-25 Asia-Pacific. | Establishment of the team delivering the seminar, timely preparation of the documentation, planning, logistics, presentations and workshops | Preparation, documentation on time,participants satisfaction |

2027 Statement of expected results

2027 Statement of expected results

| Expected results | Key performance indicators |
| --- | --- |
| Organize 2 regional seminars during the period: RRS Arab States, RRS Africa | Timely preparation (documentation and logistic) and participants’ satisfaction |

2027-2030 human resources allocation

Work/months

| Grade | 2027 | 2028 | 2029 | 2030 |
| --- | --- | --- | --- | --- |
| E2 | 0.6 | 0.6 | 0.6 | 0.6 |
| D1 | 1.8 | 1.8 | 1.8 | 2.0 |
| D2 | 1.0 | 1.8 | 1.8 | 0.6 |
| P5 | 13.8 | 14.0 | 14.1 | 17.6 |
| P4 | 31.1 | 27.5 | 27.5 | 26.2 |
| P3 | 15.9 | 18.3 | 18.3 | 12.9 |
| P2 | 5.9 | 5.9 | 5.9 | 5.7 |
| P1 | 1.1 | 1.1 | 1.1 | 1.1 |
| G7 | 1.9 | 3.1 | 3.1 | 2.7 |
| G6 | 6.2 | 11.3 | 11.3 | 7.3 |
| G5 | 1.8 | 1.8 | 1.8 | 4.1 |
| G4 | 0.7 | 0.7 | 0.7 | 0.5 |
| TOTAL | 81.7 | 87.8 | 87.9 | 81.3 |

# 3.	Risk Assessment

| Objectives | Risk description | Impact | Likely-hood | Mitigation measures in place | Mitigation planned/in progress | Potential cause | Potential consequences |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Processing of space and terrestrial notice (OP R1, R2) | •Delays in processing satellite and terrestrial filings beyond the regulatory time limits •Number and complexity of filings generate peak workloads and bottlenecks respectively •Records and registers frequency assignments for space or terrestrial systems, as well as invoice/payment issues (error, fraud) •Cost of activities, notably for all related Satellite Network Filing, is materially higher than the cost allocations methodology outlined in Council Decision 535. | 7 | 8 | •Revision of Decision 482 enters into force on 1st January 2026 •Data integrity checks and public accessibility of payment status for cost recovery invoices, validation software, review systems, and regulatory controls •Semi-annual reporting with KPIs •Focus and user groups for suggestions and complaints •Updating skills and training in new technologies | •Appropriate level of resources allocated for various steps of the processes through budget process with member states' approval. •Ensuring adequate staffing lever with required skills. | •Critical lack of resources, notably personnel with the required skills. | •Delay in processing leads to a reduction in cost-recovery revenues •Some companies require an IFIC publication prior to the launch •Longer overall coordination periods •Some Administrations require an IFIC publication before granting licensing rights which can delay service provision |
| Software upgrade for processing frequency notifications (OP. R6) | •Insufficient software modernization •Insufficient software testing and validation •Delay in implementing software resulting from WRC decisions prior to the date of entry into force of the resulting new edition of the Radio Regulations | 7 | 8 | •Suite of software and applications supporting and automating registry function steps for SNF (e.g. eSubmission, eCommunication, SNTrack, BRSIS-Cost recovery Module) •Roadmap for SW modernization is being implemented, but is limited due to the current resources •BR managers oversee the advancement of SW development Projects •Council approved 500 KCHF/year for the modernization of BR SW | •Continuous modernization of BR software •Investment in additional manual and automated testing •Investment in adequate hardware (laptops, VMs, servers etc.) whether on premise or in the cloud | •Lack of resources to undertake all required software development resulting from WRCs decisions. •Lack of resources to undertake software modernization. •Lack of resources fully dedicated to software testing and validation. •Lack of necessary physical resources (servers) and capacity. •Lack of a clear ITU Cloud strategy. | •Security risk in running SW with legacy technology •Delays in processing satellite and terrestrial filings beyond the regulatory time limits •Administrations refrain from installing the BR necessary software •Software usability is compromised •Increased time to run simulations and process filings •"Qualified" favourable findings are provided |
| Integrity of MIFR, frequency Plans and availability of BR key Information, digital assets and systems. (R1, R2, R3, R4, R7, R8) | •Total or partial loss or corruption or unavailability of MIFR, or in any Plans •Loss, corruption, unavailability of data, correspondence and other information submitted by member states •Inadvertent deletion of important physical records deemed too old •Disruption to system software and applications necessary for critical BR registry functions or for membership to access key information. •Loss of files systems and backups affecting work of study groups | 9 | 3 | •Daily data backup (resp. ISD) •Systematic archiving activities of relevant older documents in collaboration with Library section. •Corrective: Activity Recovery Plans for IAP (TAS/SAS), TSD, SSD and SGD are in place for business continuity following significant disruption, to facilitate recovery within the relevant Maximum Tolerable Period of Disruption (MTPD) and Recovery Time Objective (RTO) (joint resp. ISD/BR) | •Enforcement of high data security program and procedures (joint efforts ISD/BR) | Data confidentiality, integrity, and availability issues. | •Inadequate protection of the rights of administrations to use spectrum and orbit resources. •Delays in recognition of the rights of administrations in using spectrum and orbit resources. •BR is unable to assist in resolving cases of frequency coord. and/or harmful interference •Delays and difficulties in conducting important Study Groups meetings. |
| Support to Radiotelecommunication Conference (WRC), Assembly (RA) (OP R3, R9) | • Delay in signing the Host Country Agreement (HCA). • Failure to forecast requirements; forestall and respond to event organizational problems. • Disruption prior or during the Conference to key products and services delivery (e.g. translation, document, ICT services, and facility management) • Effective provision of secretarial support for the RA/WRC Plenary and Committees. • Failure to meet the deadline for Secretariat document publishing or to process input documents (contributions and proposals). • Failure to achieve consensus during WRC. • Failure to publish in the 6 languages of the Union on the last day of the conference the provisional final acts. • Failure to implement WRC decisions. | 9 | 3 | • Negotiation with the HC on the provisions included in the HCA. • Close and advanced coordination with the Host Country, including site visits. • Close internal coordination with ITU functional support department for Secretariat documents, interpretation & translation (C&P), information and document management system (ISD), safety and security (SSRD), etc. • Update of RoP RR 4.4 regarding responsibilities for implementation outside the RR framework. •Regional preparations and WRC informal coordination group. | • Future budget process allocation activities and approval by member states • Provide updates on the WRC preparation process to member states through Council reports and other suitable channels. • Provide ITU Secretariat and delegates advance training (eg. on proposal management) | •Host Country limitations •Geopolitical environment for negotiations •Lack of resources | • Unavailability of documents prior to the events disrupts the membership preparation process. • Decision-making is unduly affected, including with final text not being adopted at the event. • Lack of awareness of RR and their revisions lead to industry/ policymakers’ dissatisfaction leading ITU memberships looking for alternative non-RR solutions |

| Support to Meetings (e.g. CPMs, RAGs), and seminars (OP R4, R5, R10) | • Failure to forecast requirements; forestall and respond to event organizational problems. • Failure to meet the deadline for document submissions to, and process/provide output documents, as well as to implement decisions (e.g. from RRB). • Shortage of meeting room facilities at the ITU and during the demolition of Varembé building (business continuity). • Disruption to key products and services delivery (e.g. translation, document and facility management) . • Failure to organize and properly focus seminars and related information events to increase the membership knowledge of Radio Regulations (RR) and their revisions | 6 | 3 | •Close internal coordination with ITU functional support department and unit for Secretariat documents, interpretation & translation (C&P), information and document management system (ISD), safety and security (SSRD), etc. •Regular world and regional ITU-R seminars and outreach program to further raise awareness of RR •Allocation of sufficient resources through budget process with MS approval | Future budget process allocation activities and approval by member states | •Lack of resources •Lack of provision for business continuity during the construction of the new building. •Increase in the number of ITU events/meetings, and consequential increase in demand for meeting rooms | •Lack of awareness of RR and their revisions can lead to industry/ policymakers’ dissatisfaction and the search for alternative non-RR solutions. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Organizational and technical support to the Radio Regulations Board, six Study Groups and CCV. (OP R5, R8) | •Subpar quality of final texts (e.g. draft Rules and Procedures, ITU-R recommendations, Reports, Handbooks) and inadequate product and services (e.g. technical expertise) to properly support the work of RRB (e.g. cases of harmful interference), Study Groups and the CCV. | 6 | 3 | •Continual efforts to allocate sufficient resources | Future budget process allocation activities and approval by member states | •Lack of resources, including timely retaining external technical expertise were needed, combined with unexpected increase in workload | •Lack of awareness of RR and revisions to the related documentation (ITU-R texts) lead to industry/ policymakers’ dissatisfaction leading ITU memberships looking for alternative non-RR solutions. |
| ITU-R publications (RR Article 20 Maritime Manual, Lists IV, V, VIII) (OP R7) | •Reduced membership interest for these publications, despite List V being a mandatory publication for the maritime sector •Cancellation of the RR requirements for mandatory carriage by a WRC | 8 | 3 | •Anticipated the level of demand for publication. Monitoring of sales, finding reasons in case of sales reductions and rectifying the reasons •Ongoing content improvement and support/media delivery, including digital formats and web access | •Development of a mobile application to assist port inspectors in controlling carriage requirements | •Alternative cost-effective/free access to the related information, leading to pressure for publication not to be mandatory | •Decrease in cost-recovery revenues |
| Qualified personnel | •Disruptions from the departure of senior managers holding key strategic or operational positions •Critical functions with mandatory regulatory responsibilities lack backup personnel •Protracted critical staff absence due to health reasons, conflicting plans or other disrupting events | 8 | 3 | •External expertise obtained by temporary/permanent recruitment •Recruitment of retired staff as SSAs | •Training of staff as a temporary replacement for critical functions •Recruitment of young, qualified staff •Continued re-pyramidization process •Service recovery plans for those functions without backup personnel •Handover and Succession plan covering the likely departure of senior staff in the next 4 years | •Limited human resources with required expertise for critical positions •Retirement | •Disruption in the development of critical BR Software •Difficulties in planning and organizing BR Conferences |

_______________________

____________________

The tables covering the 2027-2029 human resources allocation are based on time survey data and have been normalised to 220 working days, in accordance with the methodology applied in previous Operational Plans; consequently, no Level of Effort (LoE) is reflected above this threshold for those three years. The projections for 2030 are derived from the new Operational Plan methodology and, therefore, reflect more realistic levels of engagement that are not subject to the same normalisation convention.