RESOLUTION com5/1

Intersessional activities relating to the accomplishment of the required planning exercises as requested by the first session of the Regional 
Radiocommunication Conference (Geneva, 2004)

The first session of the Regional Radiocommunication Conference (Geneva, 2004),

considering

a)	that it has adopted planning principles, planning methods, planning parameters and criteria and network configurations, to be used for the establishment of the digital terrestrial broadcasting service in the planning area referred to in Council Resolution 1185 (modified, 2003);

b)	that it has also established inter-service and intraservice sharing in the frequency bands 174-230 MHz and 470-862 MHz;

c)	that administrations need to provide their digital broadcasting requirements before the established deadlines (see Annex 2) using the format developed in accordance with the decisions of this session;

d) 	that administrations need to provide requirements related to their existing and planned broadcasting service and data related to other primary services before the established deadlines (see Annex 2),

noting

that there is a need to carry out necessary planning activities between the two sessions of the conference based on the information referred to in considering a), b), c) and d) above, in accordance with the time schedule in Annex 2,

further noting

a)	that the planning software will be developed by administrations and regional organizations and provided to the Radiocommunication Bureau (BR) prior to 1 September 2004;

b)	that BR needs to examine and test this software before integrating into its software package,

recognizing

a)	that resolves 5 of Council Resolution 1185 (modified, 2003) provides for the establishment of a planning project team (PPT) to carry out the planning activities;

b)	that, pursuant to No. 159E of Article 28 of the ITU Constitution, expenses incurred by regional conferences referred to in No. 43 of the Constitution shall be borne by all Member States of the region concerned in accordance with their class of contribution,

resolves

1	to establish an intersessional planning group (IPG)1, open to participation on the same basis as the Regional Radiocommunication Conference (RRC) with the following terms of reference:

a)	to monitor the intersessional activities in respect of the development of the draft plan and supervise the activities of the planning exercise team (composed of BR assisted by experts nominated by the respective groups);

b)	to take into account the results of bilateral and multilateral negotiations carried out by administrations, when submitted to IPG;

c) 	to review the result of the planning exercise and the draft plan and, where appropriate, give instructions to the planning exercise team to make the necessary adjustments2 for carrying out subsequent activities;

d)	to take into account the results of ITU-R studies as requested by the first session of RRC (see Resolutions COM4/2, COM4/3, COM4/4, COM4/5, COM4/6 and COM4/7), if available, with a view to their implementation for the improvement of the planning exercise process;

e)	to prepare a report after each IPG meeting, including the results of the planning exercise and the draft plan, to be dispatched to administrations for comment and feedback as soon as it becomes available; the report should also contain suggestions to administrations on any appropriate action that may be necessary to achieve the objectives of the planning exercise;

f)	to review and revise, if appropriate the time schedule and scope of intersessional activities set out in Annex 2, taking into account the work carried out by IPG and the planning exercise team, provided that these changes in no way affect the overall schedule of the intersessional activities and the right of administrations in terms of the date of submission of information (requirements and data) to be taken into account;

2	that IPG will be chaired by an expert representing a Member State of the Union from the planning area assisted by four vice-chairmen each representing a regional group;

3	that IPG will work in accordance with the working methods contained in Annex 1;

4	that IPG will work in close cooperation with the Regulatory/Procedural Group (RPG);

5	that the estimated costs of CHF 738 100 incurred by IPG will be included in the intersessional activities budget,

instructs the Secretary-General

1	to bring this resolution to the attention of the Member States of the Union and ITU-R Sector Members indicating that for outside the planning area it is for information only;

2	to submit the final output of IPG including the draft plans to the second session of RRC,

further instructs the Secretary-General

1	to bring this resolution to the attention of the Council at its 2004 session for necessary action, as appropriate;

2	to provide the administrations and IPG with information every three months on ITU expenses incurred in the intersessional work;

3	to ensure that the information, if available, is based on a transparent and open time recording process

instructs the Director of the Radiocommunication Bureau

1	to make the necessary arrangements for convening the meetings of IPG and to provide it with the necessary facilities and information;

2	to establish a Planning exercise team3 (see Annex 3) composed of BR officials assisted by experts nominated by the respective groups4;

3	to provide, if possible, one fellowship per least-developed country administration, for their participation at the IPG meetings, within the available resources in the budget envisaged for the intersessional work;

4	to provide to administrations, in particular those of developing countries and countries with economies in transition, assistance necessary for their preparation for the second session, within the available resources in the budget envisaged for the intersessional work;

5	to dispatch to the Member States of the Union within the planning area, the reports referred to in resolves 1e) above as soon as they become available, including the final report, at least two months before the commencement of the second session of RRC, for their consideration and required action, as appropriate;

6	to make the necessary arrangements for organizing regional information meetings/workshops to provide assistance to the administrations in their preparations during the intersessional period and for the second session of RRC,

invites the Director of the Telecommunication Development Bureau

to make the necessary arrangements for organizing regional information meetings/workshops to provide assistance to the administrations in their preparations during the intersessional period and for the second session of RRC,

invites

1	the administrations of the Member States and ITU-R Sector Members belonging to the planning area of RRC to actively participate in the meeting of IPG;

2	the administrations of Member States to nominate one point of contact for the work of IPG (see Annex 2).

ANNEX 1

Working methods for the Intersessional Planning Group (IPG)

Steering group

An IPG “steering group” composed of a chairman and four vice-chairman will be established.

The leader of the planning exercise team will participate in the meetings of the steering group.

The steering group will meet as necessary.

The steering group will work in one language only.

The first meeting of the steering group will take place in the fourth quarter of 2004.

IPG meetings

IPG will hold two meetings5 as indicated in Annex 2.

The meetings of IPG will take place in the following periods:

July 2005

February 2006

The meetings of IPG will be with interpretation in the five relevant working languages of the Union. The documentation will be in the five relevant working languages of the Union.

IPG will meet for a maximum of 10 working days. This period will be appropriately distributed between the two meetings, depending on the scope and volume of the work to be carried out at each meeting.

The participants are encouraged to work electronically.

Contributions

The deadline for submission of contributions to IPG shall be in accordance with the time-limits in Resolution ITU-R 1.

ANNEX 2

The following schedule is based on the assumption that the second session of RRC will begin in May 2006:

| Activity/event | Duration | Deadline | Action by |  |
| --- | --- | --- | --- | --- |
| End of the first session of RRC |  | 28.05.2004 |  |  |
| Preparatory phase |  |  |  |  |
| Development and distribution of: – electronic form for input data(1) – data capture software(2) | 1 month 3 months | 30.06.2004 01.09.2004 | BR |  |
| Planning software to be provided to BR | – | 01.09.2004 | Administrations and regional organizations |  |
| Planning software implementation and verification using test data(3) | 6 months |  | BR assisted by the experts |  |
| Information/workshop regional meetings |  |  | BR and BDT |  |
| Meeting of the IPG Steering Group for review of implementation and test runs of the planning software before launch of the next phase |  | Mid January 2005 | IPG Steering Group |  |
| First planning exercise |  |  |  |  |
| Preparation and submission of initial input data(1) |  | 28.02.2005 | Administrations |  |
| Validation, correction and publication of input data | 3 months | 31.05.2005 | BR and administrations |  |
| First planning exercise | 1.5 month |  | BR assisted by the experts | See resolves 1 |
| Meeting of IPG |  | Mid July 2005 | IPG |  |
| Publication of the results of the first planning exercise |  | 15.07.2005 | BR |  |
| Analysis of the results by administrations and preparation of input data for production of the draft plan | 3.5 months |  | Administrations |  |

| Activity/event | Duration | Deadline | Action by |  |
| --- | --- | --- | --- | --- |
| Production of the draft Plan |  |  |  |  |
| Reference situation date(4) |  | 31.10.2005 | Administrations |  |
| Last submission of input data(1) prior to the second session of RRC |  | 31.10.2005 | Administrations |  |
| Validation, correction and publication of input data | 3 months | 31.01.2006 | BR and administrations |  |
| Production of the draft plan | 1 month |  | BR assisted by the experts | See resolves 1a) |
| Meeting of the IPG; submission of the draft plan to the second session of RRC |  | February 2006 | IPG |  |
| Publication of the draft plan |  | 28.02.2006 | BR |  |
| Analysis of the draft plan by administrations | 2 months6 |  | Administrations |  |
| Beginning of the second session of RRC |  | May 20067 |  |  |
| (1) Input data to the planning exercises and production of the draft plan consist of: – Requirements for digital broadcasting assignments and/or allotments (data shall be provided by the administrations and not generated by BR), including existing or planned digital assignments/allotments. – Data for: – existing and planned analogue broadcasting assignments; and – existing and planned assignments of other primary services shall be retrieved from the relevant files as indicated in § 1.7. Attention is drawn to the fact that administrations which intend to update their data should complete relevant procedures prior to the reference situation date. Administrations shall indicate: – those existing and planned broadcasting assignments/allotments that are not to be taken into account in the planning process; and – those existing and planned assignments of other primary services that are to be taken into account in the planning process. Information on existing digital assignments in ST61 or GE89 Plans shall be submitted in the new form for requirements. Requirements for digital broadcasting shall be submitted to BR in an electronic form. Submission of input data for the draft plan may include a complete set of input data or modification to the previously submitted input data. There is no priority attached to input data with regard to date of submission, provided that input data are received by BR by the deadline as indicated in the time schedule, in a complete form. For administrations that have not submitted data, it is assumed that all the existing and planned broadcasting or other services assignments, according to the definition provided in § 1.7, shall be protected in the planning process. |  |  |  |  |

(2) Development and distribution of form for input data and data capture software. – form of input data, including electronic data format, should be made available to the administrations as soon as it is developed, but not later than one month after the end of the first session of RRC. It will allow preparation of initial input data to begin immediately after publication of the form of requirements; – data capture software should be developed and distributed to administrations not later than three months after the end of the first session of RRC. (3) Test data will be generated by BR and the experts and will consist of: – digital broadcasting assignments and/or allotments – existing and planned broadcasting assignments – existing and planned assignments of other primary services, these data shall be retrieved from the relevant existing BR files. (4) The reference situation contains the existing and planned assignments and allotments of the broadcasting service and the existing and planned assignments of the other primary service to be taken into account for the development of the Plan(s). NOTE – In order to facilitate the exchange of information between administrations and BR, each administration shall nominate a contact person. Full contact details (name, title, postal address, telephone and telefax numbers, e-mail …) shall be supplied to BR.

ANNEX 3

Planning exercise team

–	The planning exercise team will be composed of BR officials assisted by experts nominated by the respective groups. There will be up to two experts each from EBU, CEPT, ATU, RCC and the League of Arab States, and one from the Islamic Republic of Iran.

–	The cost of participation of the nominated experts will be borne by their respective administrations or regional organizations, as appropriate.

–	The leader of the planning exercise team will be nominated by the Director of the Radiocommunication Bureau.

–	The planning exercise team will meet as appropriate.

–	The planning exercise team will work electronically as far as possible.

–	The overall responsibility for the planning exercise activities lies with the Director of the Radiocommunication Bureau.

Any clarification regarding the working methods of this team can be coordinated with the IPG steering group as required.

______________

1 	This constitutes the PPT mentioned in Council Resolution 1185 (modified, 2003).

2 	This adjustment excludes any change to the requirements of administrations without their prior agreement.

3 	The cost of participation of the nominated experts will be borne by their respective administrations or regional organizations as appropriate.

4 	The leader of the planning exercise team will be nominated by the Director of the Radiocommunication Bureau.

5 	Due to limited capacity of the meeting rooms it may be necessary to limit the number of participants from each administration and Sector Member.

6 	Irrespective of the date of the second session, which will be decided by the Council, the two months foreseen for the analysis of the draft plan shall not be reduced to less than two months.

7 	To be decided by the Council.