# Doc. CNG1/28

Activities related to corrections of 4th iteration and final complementary analysis

|  | Date and time | Activity | Comments |
| --- | --- | --- | --- |
| 1 (9) |  | Definitive publication of the Administrative Declarations for the fourth iteration as soon as they are validated by the DPT |  |
| 2 (10) |  | Conduct of the fourth iteration |  |
| 3 (11) | Saturday, 10 June 2006, 1200 hours/1600 hours | Distribution of the results of the fourth iteration to the CNGs | Results will be available on the computers in CNGs’ rooms and in CICG at 1200 hours, on CD-ROM at 1600 hours. |
| 4 (12) |  | Examination of the results of the fourth iteration in the CNGs | Delegations to verify that all their entries in the Plan are in accordance with the submitted input requirements and Administrative Declarations. Any identified errors and/or omissions are to be notified to the relevant CNG. |
| 4 bis | Saturday, 10 June 2006 19h00-22h00 (Sub CNGs Meetings) | Examination of the results of the fourth iteration by administrations in order to identify possible errors. | Sub CNGs to agree on the necessary corrections to the results of the fourth iteration due to omissions or processing errors and notify in writing CNG1. For this purpose special forms will be used. The forms will be published on CNG1 Web site (both ITU and ERO) as soon as they are agreed on Steering group of COM4. |
| 5 (13) | Saturday, 10 June 2006, 2000 hours | Distribution of the results of the complementary analysis for the fourth iteration to the CNGs |  |
| 6 (14) |  | Preparation of Administrative Declarations based on the complementary analysis results (digital-to-analogue only) |  |
| 7 | Sunday, 11 June 2006, 1040-1200 hours (CNG1 Meeting) | Consideration of the results of the fourth iteration and the complementary analysis within CNG1. Establishment of the final list of corrections (e.g. omissions or processing errors). | CNG1 to agree on the necessary corrections to the results of the fourth iteration due to omissions or processing errors and notify in writing to COM 4. |
| 8 (16) | Sunday, 11 June 2006, 1400-1700 hours | Approval of the results of the fourth iteration in COM 4. Validation of the list of corrections (e.g. omissions or processing errors). |  |
| 9 (17) | Sunday, 11 June 2006, 1700-2100 hours | Notification of corrections from COM 4 to the DPT Submission of the Administrative Declarations (digital-to-analogue only) for the final complementary analysis |  |
| 10 (18) |  | Processing of the corrections to the digital Plan and conduct of the final calculations regarding the digital Plan (limited to the corrections submitted by COM 4) Processing of the Administrative Declarations for the final complementary analysis (digital-to-analogue only) |  |
| 11 (19) | Monday, 12 June 2006, 0800 hours | Publication of the results of the corrected Plan | The results will be published only on the computers in CNGs’ rooms and in CICG. |
| 12 (20) | Monday, 12 June 2006, 0900 hours | Initial publication of the Administrative Declarations (digital-to-analogue only), as received from delegations for the final complementary analysis. | Delegations will have four hours for the final check of the Administrative Declarations files (digital-to-analogue only) and corrections, if any. |
| 13 (21) | Monday, 12 June 2006, 1300 hours | Deadline for submission of corrections to Administrative Declarations (digital-to-analogue only) |  |
| 14 (22) | Monday, 12 June 2006, 1500 hours | Definitive publication of the Administrative Declarations for the final complementary analysis (digital-to-analogue only), as validated by DPT. |  |
| 15 (23) |  | Conduct of the final complementary analysis |  |
| 16 (24) | Tuesday, 13 June 2006, 0800 hours | Publication of the results of the final complementary analysis | Results of the final complementary analysis will be available on the computers in CNGs’ rooms and in CICG. |