## Slide 1: Process and timetable for The elaboration of the ITU STRATEGIC and financial PLANs for 2020-2023 2nd Meeting of the Council Working Group for Strategic and Financial Plans for 2020-2023
11-12 September 2017
Revision 1 to Document CWG-SFP-2/7-E 12 September 2017 Original: English

## Slide 2: Process for the 2020-2023 strategic plan
CWG-SFP
C17
C18
PP18
SG provides input to Council
(No.74A, Constitution)
Council shall initiate the
preparation of a draft SP
(e.g. by creating a CWG)
(No. 62A, Convention)
Draft
SP
CWG coordinates the elaboration of the
draft SP
(Res. 1384 / C17)
Final
Draft
SP
Member States
Sector Members
Advisory Groups
Provide input for the preparation of a draft SP
(No. 62A, Convention)
SG coordinates the Implementation of the SP
(No.86A c) bis, Convention)
Strategic
Plan
2020-2023
Adopts the
Strategic Plan for
the Union
(No.51, Convention)
Secretariat
Secretariat
WTDC-17 contribution
Open and public consultations
Notes: Council 2017 initiated the process for the preparation of the new draft Strategic Plan, by establishing the CWG for the elaboration of the Strategic and Financial Plans 2020-2023
The process is similar to the process followed for the elaboration of the current (2016-2019) plans
The CWG is open to Member States and Sector Members as well –and will receive inputs also from the Sector Advisory Groups and WTDC-17, as well as open and public consultation (as per the previous cycle)
The First Public Consultation and a Staff Survey have already taken place –we will present more details in this presentation. We propose to have Public Consultations at every step of the process.
Following the work of the CWG, the Draft Strategic Plan will be submitted to the 2018 Session of Council, which will review and forward to PP-18
It is a membership driven, open and transparent process to which Member States, Sector Members, regional organizations, etc. are invited to contribute at all stages.

## Slide 3: Timetable for the elaboration of the 2020-2023 strategic and financial plans
Date | Milestone
2017 Session of Council | Establishment of the CWG-SFP
23 May 2017 | 1st meeting of CWG-SFP
Jun – Aug 2017 | Preparation of the secretariat’s input, including: - Public consultation of the CWG-SFP on the strategic priorities - Strategic planning workshops within the ITU secretariat
11-12 Sep 2017 | 2nd meeting of CWG-SFP
9-20 October 2017 | WTDC-17 contribution to the ITU Strategic Plan
October / November 2017 | Public consultation of the proposed draft strategic framework
15-16 Jan 2018 | 3rd meeting of CWG-SFP Draft Strategic and Financial Plans presented / draft revised Res. 71, 72, 151
March 2018 | Public consultation on the draft strategic plan
Q1-Q2 2018 (tbc) | RAG / TSAG / TDAG
16 April 2018 | 4th meeting (before the 2018 Session of Council)
17-27 April 2018 | Council 2018
End of June 2018 | Final draft Strategic and Financial Plans submitted to PP-18
29 Oct – 16 Nov 2018 | Adoption of the Strategic and Financial Plans by PP-18

## Slide 4: Alternatives for the 2nd Public Consultation
Scenario 1
Draft Objectives are posted to the 2nd public consultation but final form to be discussed at the 3rd CWG-SFP, with all inputs from the public consultation
The 3rd CWG meeting will also discuss WTDC input
Public consultation to start independently from WTDC. Possible timeline:
September 11-12: CWG meeting
September 20: End of preparation of the material for the public consultation
September 27: Public consultation documents approved and signed and the documents are translated
September 28-29: Launch of the public consultation
October 30: End of the public consultation
November 14: Report on the second public consultation
November 27 or December 4: All documents submitted for the 3rd CWG-SFP meeting
Scenario 2
Decision to wait for the consolidation of the WTDC input to then conduct the 2nd public consultation of CWG-SFP.
Possible timeline:
October 20: End of WTDC
October 27: End of preparation of the material for the public consultation
November 1: The public consultation documents are approved and signed and the documents are translated
November 3: Launch of the public consultation
December 4: End of public consultation
December 11: Report on the second public consultation
December 15: All documents submitted for the 3rd CWG-SFP meeting (on time for the one month deadline before the meeting)

## Slide 5: Subject for the 2nd Public Consultation
Participants in the 2nd Public Consultation will be invited to provide inputs on the following elements of the preliminary/draft proposed ITU strategic framework* for 2020-2023:
  Situational / strategic analysis
  ITU Vision, Mission, Values, Strategic Goals
  Proposed Targets
  Strategic Risk management analysis
  Linkage with the SDG framework
  Preliminary/draft ITU results framework
    Objectives/Outcomes and Outputs
  * As per the preliminary/draft presentation to CWG-SFP and the changes discussed and proposed by the Group