| Council Working Group on Financial and Human Resources Twelfth meeting – Virtual, 25-26 January 2021 |  |
| --- | --- |
|  | Document CWG-FHR-12/7 |
|  | 18 December 2020 |
|  | English only |

Contribution by the Secretariat

REPORT ON the implementation of the risk management action plan

Summary This document presents a final report for the implementation of the Action Plan to strengthen the ITU Risk Management Framework, as a follow-up to the progress reports presented to CWG-FHR (Doc. CWG-FHR-11/12) and to the Virtual Consultation of Councillors (Doc. C20/61 Rev.1). Action required The Council Working Group is invited to note this report. ____________ References Document CWG-FHR-11/12 (Progress report on Strengthening ITU Risk Management Framework: action plan); Council documents C17/74 (ITU Risk management policy); C17/73 (ITU Risk appetite statement) Document C20/61 Rev.1

## 1	Final report on the implementation of the Action plan to strengthen ITU risk management framework

1.1.	Since the endorsement of the Action plan by CWG-FHR in February 2020, HLCM released in March 2020 a Guidance Note on Embedding Risk Management (CEB/2020/HLCM/4) and JIU released in September 2020 a report on approaches and uses of Enterprise Risk Management in UN system organizations (JIU/REP/2020/5). Both reports have been taken into consideration while implementing the plan. In addition, the project has been supported by an external senior consultant to gain quality and assurance that the implementation of the action plan would capitalize on best risk management strategies experienced by other organisations.

| Action item / progress achieved | Timeline |
| --- | --- |
| - All organizational and operational entities to be involved in Risk Management - Kick-off meetings, introducing the objectives of the Action plan and its deliverables both by Council 2020 and by end of 2020, have been conducted with more than 20 key stakeholders incl. Focal points (Bureaux, Regional Offices, Depts. of the General Secretariat, including Finance, HR, IS, Internal Audit). Comments and suggestions from the participants have been taken into consideration. - Proposed revised documents were sent (notably regarding actions #2, #3, #5 and #6 below), requesting feedback from stakeholders. - Two workshops, delivered in eight distinct sessions in November and December, have included more than 40 distinct participants from all organizational and operational ITU entities. - Action #1 completed as of December 18th, 2020. | End of 2020 |
| - Risk registers to be developed for the whole organization and have those risks assessed and rated - Preliminary risk registers and mitigation plans were obtained from organizational entities. - A new risk register template has been developed, which integrates cause and consequences of a risk, as well as the inclusion of controls in place and the confidence in controls effectiveness. - The risk register template and the related operational details of managing risks are part of a new Risk Management and Internal Control Manual which has been finalized. This manual has been essential to support the training activities included in actions #4 and #8 below. - Risks have been identified and assessed as of December 2020 using the new risk registers(overview of risks identified by December 18th presented in Appendix A). - Action #2 completed as of December 18th, 2020 -acknowledging that the assessment of the risks is a continuous process. | End of 2020 / Continuous assessment of risks |
| - Set up an internal risk governance structure - Based on the best practices found in HLCM Risk Management Task Force survey results (March 2019) conducted among 25 UN Organisations, as well as the feedback gathered from the key stakeholders (cf. action #1 above), it was recommended to strengthen the risk governance structure. This enhancement is centered around the integration of a Risk and Internal Control function to oversee the implementation of risk management with a second line of defence accountability. Fully dedicated to Risk management and Internal controls, this function is responsible for coordinating the risk and control management processes, as well as their ongoing improvement including Risk management framework, policies and manual. - Considering the responsibilities assigned to the Risk and Internal Control function and the current structure for dealing with risk management within the organization, the role of the Inter-Sectoral Coordination Task Force (ISC-TF) was aligned accordingly to consult on the recommendations provided by the Risk and Internal Control function. On one hand and based on proposals made by the Risk and Internal Control function, ISC-TF would review risk management framework, policies and manual and prepare recommendations for approval by the Coordination Committee (CoCo) through the Management Coordination Group (MCG). On the other hand, it will review cross-sector moderate level risks on a regular basis, whereas single Sector risks would remain at the Bureau level. - Finally, MCG/CoCo would review high level risks on a regular basis and take decisions related to risk management, ensuring a clear tone at the top to promote a culture of responsible and effective risk management. - All of these competencies and monitoring activities are described in the risk management policy and further detailed in the risk management manual. - Action #3 completed as of December 18th, 2020. | Council 2020 |
| - Aim to improve staff accountability at all levels for managing risks - Trainings and workshops on how to integrate risk management and internal controls in the business processes of the organization were conducted. Two rounds of workshops have been prepared and duly delivered, using the new Risk register and the new Risk Management manual as guidance. The workshops were aligned with the on-going process to revise the overall ITU accountability and transparency framework. In addition continuous training and support have been provided to Focal points along the whole project duration. - Action #4 completed as of December 18th, 2020. | End of 2020 |
| - Establish a more systematic risk management process - The Risk Management Policy and Risk Appetite Statement have been reviewed to ensure a more systematic process to identify, assess and manage risks. They have been focused to their key-principles, and all operational details of managing risks are part of the new Risk Management and Internal Control Manual. The manual is structured on a 6-step sequence to help mainly Risk Owners, Focal points and Risk and Internal Control function manage and / or coordinate the risk management process, with reference to 2017 COSO ERM key-principles whenever relevant. These improvements enable ITU: - To have unity in the approach and methodology used for risk management (Results-based management, project management, business continuity management, crisis management) and operations (including through a common Risk Register). - To foster opportunity management, foresight, and innovation, rather than an approach that focuses only on avoiding harm and reacting to issues as they arise. - To ensure a greater alignment between risk appetite, categories and impact, ensuring risk management go hand-in-hand with ITU’s perspectives and its willingness to accept risk in key areas. - To systematically integrate risk reporting to the highest level of the organization for decision-making. - To ensure alignment with accountability framework of the organization (current framework presented in Doc. C20/43). - To rely on a solid ground for risk management and governance thanks to the “Three Lines” model introduced in the risk management policy. - Action #5 completed as of December 18th, 2020. | Council 2020 |
| - Review the effectiveness of the internal controls - A new risk register template has been developed, which integrates controls in place and their effectiveness to assess risk. In addition, confidence in control effectiveness is being rated and used for determining monitoring periodicity. The related modalities of how to use existing controls to assess risk and how to rate confidence in control effectiveness are described in the manual. - Action #6 completed as of December 18th, 2020 - acknowledging that the assessment of the effectiveness of internal controls is a continuous process. | Council 2020 / Continuous assessment of the effectiveness of internal controls |
| - Develop a risk management dashboard utilizing the new risk register - A risk management dashboard has been implemented (using business intelligence tools) to monitor and communicate information related to risk management, providing a visual interface to navigate the risk registers of the organization. - The dashboard contains a set of interactive pages that provide snapshot views of key risk management indicators (risk score heat map, risk monitoring map, risks by risk owner, mitigation measures by risk response owner, etc.). - The dashboard is easily accessible through MS-Teams and can be further customized to each sector / department needs. - Action #7 completed as of December 18th, 2020. | Q4 2020 |
| - Strengthen the capacity of staff to manage risks - Action item has been implemented in combination with point 4 above, leveraging training and risk management workshops to raise awareness and strengthen the capacity of managers to manage risks. - Action #8 fully completed as of December 18th, 2020. | End of 2020 |
| - Aim to embed risk management in the staff performance management system - Developing integrated processes, systems and tools that enable the operational teams to feel empowered and in control of their risks supports embedding risk management into the organisation. - As part of the project implementation, discussions were held with HRMD on options on how to best integrate risk management in the staff performance management. Risk accountability and the ability to factor risk management into day-to-day decision-making in operations have been recalled to be a core aspect of all individual performance management processes. - The necessary amendments to the job descriptions and to ePMDS objective setting were presented during the workshops, to be implemented in the next performance management cycle. - Action #9 completed as of December 18th, 2020 in terms of the current project. Final implementation to be coordinated by HRMD by June 2021. | End of 2020 |
| - Systematically communicate and report on risk information to membership - The secretariat will continue reporting on risk management arrangements to CWG-FHR, while reports on the updated risk register and the risk management dashboard will continue to be presented regularly to membership. - Concretely, this final action plan status is reported to CWG-FHR, including an overview of the current snapshot of the ITU risk management dashboard (Annex: Overview of ITU Risk Management Dashboard). - Action #10 completed as of December 18th, 2020 | Ongoing – Council 2020 |

ANNEX: Overview of the itu RIsk management dashboard

An overview of the risk management dashboard with a snapshot of the latest data included in the ITU-wide risk register will be added to the presentation to CWG-FHR.

____________________

____________________