| Agenda item: PL-3 | Document C26/6-E |
| --- | --- |
|  | 27 March 2026 |
|  | Original: English |
| Report by the Secretary-General |  |
| PREPARATIONS FOR THE 2027 RADIOCOMMUNICATION ASSEMBLY (RA-27) AND THE 2027 WORLD RADIOCOMMUNICATION CONFERENCE (WRC-27) |  |
| Purpose This document reports on the ongoing preparations for the Radiocommunication Assembly 2027 (RA-27), the World Radiocommunication Conference 2027 (WRC-27) and the first session of the Conference Preparatory Meeting for WRC-31 (CPM31-1). Action required by the Council The ITU Council is invited to note the progress of preparations for RA-27, WRC-27 and CPM31-1. Relevant link(s) with the Strategic Plan Spectrum use for space and terrestrial services; development and application of the ITU Administrative Regulations; allocation and management of resources. Financial implications Within the allocated budget 2026-2027. _______________ References Council Resolution 1422 (C24); Circular Letter CL-25/45; WRC-27 website; RA-27 website; Inter-Regional Information Sessions on WRC-27 Preparation website; ITU’s Data Protection and Privacy Policy |  |

# 1	Background

The agenda of the 2027 World Radiocommunication Conference (WRC-27) was finalized by ITU Council in Resolution 1422 (C24).

At its 2025 session, the ITU Council decided, as recorded in the Summary Record of the seventh Plenary meeting (Document C25/113), “to accept the invitation from China to host the 2027 Radiocommunication Assembly (RA-27), the 2027 World Radiocommunication Conference (WRC-27) and the first session of the Conference Preparatory Meeting for WRC-31 (CPM31-1) in Shanghai. As a result, and subject to the concurrence of the majority of the Member States of the Union, the 2027 World Radiocommunication Conference will take place in Shanghai, China, preceded by the 2027 Radiocommunication Assembly”,

In accordance with this decision, and pursuant to No. 42 of the ITU Convention, the General Secretariat initiated the Member States consultation on the precise place and exact dates of RA-27 and WRC-27 which received the agreement of the required majority of Member States, as published in Circular Letter CL-25/45. As a result, Member States agreed that the Radiocommunication Assembly 2027 (RA-27) and the World Radiocommunication Conference 2027 (WRC-27) will take place in Shanghai, China, from 11 October to 12 November 2027.

As usually planned, the first session of the Conference Preparatory Meeting for WRC-31 (CPM31-1) will also take place in Shanghai, immediately after WRC-27, on 15 and 16 November 2027.

The RA-27 and WRC-27 websites have also been published and will be updated regularly as new information becomes available.

# 2	Communications from administrations

Following the confirmation of the precise place and exact dates of WRC-27, the Secretary-General received correspondence from a number of administrations presenting views and concerns related to various aspects of the organization of WRC-27 and RA-27. These communications have been duly acknowledged and are being taken into account, as appropriate.

# 3	Host Country Agreement

The draft Host Country Agreement (HCA) has been shared with China. It addresses the necessary requirements for the organization of RA-27, WRC-27 and CPM31-1, including conference facilities, security arrangements, privileges and immunities, visa facilitation, information and communication technology infrastructure and services, and other logistical and operational matters. It also includes provisions related to privileges and immunities in alignment with the 1947 Convention. In addition, the HCA includes cybersecurity and data protection provisions, particularly in light of the adoption of ITU’s Data Protection and Privacy Policy in December 2023.

# 4	Site visit

A first site visit has been conducted by the secretariat in March. The visit enabled an initial assessment of the proposed conference venue, the Shanghai Expo Center, and related facilities, including conference rooms and conference services, information and communication technology infrastructure, and security arrangements. The outcomes of the visit will be used to refine planning assumptions and to identify areas requiring follow-up.

# 5	Internal coordination and coordination with the Host Country

Coordination among the relevant services in the General Secretariat and the Radiocommunication Bureau has already begun in order to ensure the administrative and logistical preparations for RA-27 and WRC-27. This coordination will continue and intensify as preparations progress, including ongoing engagement with the host Country.

# 6	Regional preparations

Taking into account Resolution 80 (Rev. Marrakesh, 2002) of the Plenipotentiary Conference, extensive preparations for RA-27 and WRC-27 are ongoing, in particular through the regional telecommunication organizations, including APT, ASMG, ATU, CEPT, CITEL and RCC. ITU has been assisting with these preparations wherever possible, noting, in particular, Resolution 72 (Rev.WRC-19) of the World Radiocommunication Conference. In this regard, the first ITU inter-regional information session on WRC-27 preparation was held from 3 to 5 December 2025. The second and third ITU inter-regional information sessions are scheduled in the end of 2026 and a few months before WRC-27, respectively.

# 7	Conclusion

The Secretariat considers that the preparations for the Radiocommunication Assembly and the World Radiocommunication Conference in 2027 are progressing in accordance with the decisions of Council 2025 and established ITU procedures. The Council is invited to take note of the related information reported in this document.

______________

____________________