| Agenda item: ADM 1 | Document C26/73-E |
| --- | --- |
|  | 29 March 2026 |
|  | Original: English |
| Report by the Secretary-General |  |
| UPDATE ON IMPLEMENTATION OF ITU’S RESOURCE MOBILIZATION STRATEGY |  |
| Purpose The Plenipotentiary Conference (Bucharest, 2022) instructed the Secretary-General in Decision 5 (Rev. Bucharest, 2022) to develop an ITU-wide resource mobilization strategy and to present it to the ITU Council. The resource mobilization strategy adopted by Council-24 (see Document C24/70) is built upon three main areas of action: strengthen membership; leverage events, products, and services; and increase voluntary contributions. An update on the ongoing implementation was presented at Council-25 (Document C25/67) and at CWG-FHR (Document CWG-FHR-22/16) for comment, review and subsequent submission to Council 2026. Action required by the Council Council is invited to note this document. Relevant link(s) with the Strategic Plan Resource mobilization. Financial implications Potential to increase regular budget and extra-budgetary funding. _______________ References CWG-FHR website; Decision 5 (Rev. Bucharest, 2022) of the Plenipotentiary Conference; Documents C17/67 and C23/INF/12; Kigali Action Plan; Documents C23/62(Rev.1); CWG-FHR-16/11, CWG-FHR-17/3, CWG-FHR-17/INF/9; C24/70 (Resource Mobilization Strategy); C25/67 (Implementation of ITU’s resource mobilization strategy); Circular letter CL-25/36 (Investing in ITU and Our Shared Digital Future); Why ITU matters: ITU’s case for investment; Documents CWG-FHR-22/16 and C-26/47; C26/INF/14 |  |

Background

The Plenipotentiary Conference (Bucharest, 2022) instructed the Secretary-General in Decision 5 (Rev. Bucharest, 2022) to develop an ITU-wide resource mobilization strategy and to present it to the ITU Council for review and guidance on its implementation. The resource mobilization strategy adopted by Council-24 (see Document C24/70) is built upon three main areas of action: strengthen membership; leverage events, products, and services; and increase voluntary contributions. Each of these areas were to be further developed and enhanced through coordinated efforts across the General Secretariat, the Bureaux and the field Offices. In the resource mobilization strategy, 24 action lines across the three main areas of actions were recommended for assessment and implementation where feasible, with the following objectives:

–	Encourage Member States to maintain or increase their unit contributions

–	Strengthen Sector Member engagement and revenues

–	Strengthen overall member engagement

–	Help better leverage events, products and services

–	Increase voluntary contributions.

Out of the 24 action lines, work has started on 18 (75 per cent). Two action lines were identified as high priority and completed in 2025, while the remaining six action lines are targeted for further assessment, with implementation to start and be completed in the period 2026-2028. As a first step towards a roadmap with timelines and milestones, the secretariat has prepared a dashboard (see C26/INF/14) with the status of implementation of each of the action lines.

Priorities for 2025 and 2026 are highlighted below, with summarized information on implementation provided in Annex 1.

Priority areas for immediate action

As about 70 per cent of ITU’s regular budget comes from Member State unit contributions, securing this source has been the top priority of the strategy for 2025, and into 2026, followed by Sector membership which accounts for another 10 per cent. Regarding leveraging events, products, and services, as well as voluntary contributions, there is potential to grow these sources, but they require significant investments in new/reinforced skills, streamlined processes and digital platforms, which are currently being assessed and developed as part of ITU’s transformation roadmap.

# 1	Securing Member State unit revenues

In line with Decision 5 (Rev. Bucharest, 2022), Council-25 fixed the preliminary amount of the contribution unit for the period 2028-2031. Subsequently, the secretariat issued a circular letter (CL-25/36) requesting that Member States announce their provisional class of contribution for the period 2028-2031 before the end of the calendar year 2025. As reported in Document C26/47, 42 responses from Member States have been received with 40 confirming that they will maintain their existing unit contribution level while 2 Member States indicated they intended to decrease their unit contribution level.

In an effort to support Member States in making the case for securing or increasing ITU contributory units within their national administrations, and in line with the Resource Mobilization Strategy, the secretariat prepared an e-brochure entitled “Why ITU matters: The case for investment 2028-2031”, which was shared with Member States in CL-25/36.

# 2	Strengthening Sector membership

The secretariat is reviewing Sector membership benefits and has consulted with the Sector Advisory Groups to ensure that benefits are in alignment with expectations. Sector Members are also being consulted on their priorities. The results of this consultation will help ITU align its offerings to the members’ interests. Cross-selling campaigns are ongoing to encourage existing Sector Members to have memberships across multiple Sectors and Associates to upgrade to full Sector membership.

Under-represented parts of the digital ecosystem and 70 Member States having no Sector Member, Associate and Academia representation have been identified for targeted campaigns to ensure maximum diversity in ITU’s membership. Promotional materials are being reviewed and will be available on the ITU website (here). Campaigns will be planned to raise awareness in all sectors and to promote engagement.

Specific data on Sector membership (Sector Members, Associates, and Academia) at 31 December 2025 is provided in document C26/INF/14.

# 3	Transformation as an enabler of resource mobilization strategy implementation

As part of the transformation road map, new digital and AI-enabled systems are being implemented to support more effective coordinated account management and to improve ITU-wide outreach with members, donors, and partners, with technical configuration to take place from Q1 to Q2 2026, followed by a pilot implementation for the remainder of 2026 to be scaled through 2027. This investment will support action areas 1) strengthen membership and 3) increase voluntary contributions.

Additional transformation efforts to streamline and automate business processes related to recruitment of experts and procurement of services in 2026 will strengthen ITU’s capacity to implement projects on time and on budget, and are therefore essential enablers of action area 3, increase voluntary contributions. Expedited delivery will build confidence among donors and encourage repeat support over longer periods, allowing ITU to scale up resource mobilization. Significant investments in additional digital platforms and building specialized staff capacity and skills are required to implement the recommendations in action area 2) leverage events, products, and services.

Annex: 1

Annex 1

Priorities for 2025 and 2026

| Action item | Milestone | Target |
| --- | --- | --- |
| New executive level briefing and promotional materials that delegates can use when making the case for ITU support within their national administrations. | Completed | Q3 2025 |
| Identify key non-member companies from under-represented parts of the digital ecosystem to join ITU. | Completed | Q3 2025 |
| Review Sector membership benefits and fees in consultation with the Sector Advisory Groups to ensure that benefits are in alignment with expectations, and that Sector membership continues to cover costs. Assess any risks related to potential changes in fees. Among others, consider benefits that would encourage existing Sector Members to have memberships across multiple Sectors and Associates to upgrade to full Sector membership. | Ongoing | Q2 2026 |
| Consider new approaches to promote Sector Member engagement, including promotional material and marketing through digital platforms, and raise awareness in all sectors during major conferences. | Ongoing | Q3 2026 |
| Review potential for new voluntary contributions, leveraging newly approved WTDC-25 Baku Action Plan, as well as partnership initiatives like P2C. | To be started | Q4 2026 |
| Review potential improvements in how ITU recognizes voluntary contributions to align with evolving expectations among donors. | To be started | Q4 2026 |
| Implement new measures and systems to better coordinate account management and improve ITU-wide service to Member States, Sector Members, donors, etc. This includes addressing internal enablers as part of the transformation plan: IT systems, building staff capacity and skills, streamlining, and modernizing financial and administrative rules and processes, etc. | Ongoing | Phase 1: Q2 2026 |

_______________

____________________