|  | Document C26/INF/3-E |
| --- | --- |
|  | 3 March 2026 |
|  | English only |
| Note by the Secretary-General |  |
| PROGRESS ON IMPLEMENTATION OF INFORMATION AND COMMUNICATION TECHNOLOGIES DEVELOPMENT FUND (ICT-DF) FUNDED PROJECTS |  |
| Purpose This information document provides the list of ongoing Projects that received co-funding from the Information and Communication Technologies Development Fund (ICT-DF) as reported in Council Document C26/34. Action required by the Council This document is transmitted to the Council for information. _______________ References Resolution 11 (Rev. Dubai, 2018) of the Plenipotentiary Conference; Final Acts (Part III) and Minutes of the Sixteenth Plenary Meeting (Section 2.3 and 5.2) of the 2022 Plenipotentiary Conference; Council Resolutions 1111, 1338, 1418, 1427 and 1434; Council Documents C23/34, C24/19, C24/34, C25/34, C25/43 and C26/34. |  |

Ongoing ICT-DF projects (Q4 2025) and new ICT-DF projects signed (January 2026)

| Project No. | Title | End date | Region | Partner(s) | Budget signed | Budget remaining (after commitments) |
| --- | --- | --- | --- | --- | --- | --- |
| 7GLO03043 | Rural Telecommunications Development in Least Developed Countries | Dec. 2030 | Multi-regional |  | ICT-DF: Balance (01.01.10): USD 509 035 Additional ICT-DF allocation (15.01.10): USD 1 000 000 Additional ICT-DF allocation (14.11.13): USD 1 000 000 | CHF 701 367 |
| 7OMA13005 | Establishment of a Cybersecurity Innovation Centre for the Arab Region | Sep. 2030 | Arab States | Oman Ministry of Transport, Communications and Information Technology (MTCIT) | MTCIT: USD 2 000 000 ICT-DF: USD 752 500 | USD 146 938 |
| 9GLO21116 | ITU-DAP Promoting effective regulation, greater investment and innovative models for school connectivity in underserved communities and for broader digital inclusion | Mar. 2026 | Multi-regional | United Kingdom Foreign, Commonwealth and Development Office (FCDO) | FCDO: GBP 3 179 361 ICT-DF: USD 276 000 | USD 940 499 |
| 9GLO21112 | Creating a Safe and Prosperous Cyberspace for Children | Dec. 2026 | Multi-regional | Saudi Arabia National Cybersecurity Authority (NCA) | NCA: USD 1 612 500 ICT-DF: USD 400 000 | USD 101 209 |
| 7RAS24076 | Feasibility study: Addressing the special telecommunications/ICT needs of the Pacific Small Island Developing States | Jun. 2026 | Asia-Pacific | Australia Department of Infrastructure, Transport, Regional Development, Communications, Sport and the Arts (DITRDCSA) | DITRDCSA: USD 569 916 ICT-DF: USD 189 972 | USD 197 858 |
| 7RAS23073 | Pathways to Cybersecurity in Pacific | Jun. 2026 | Asia-Pacific | Japan Ministry of Internal Affairs and Communication (MIC Japan) | MIC Japan: USD 150 000 ICT-DF: USD 37 500 | USD 64 499 |
| 7RAS24074 | Enhancing Digital infrastructure and affordable access to ICT services in Asia and the Pacific – Phase 2 | Sep. 2026 | Asia-Pacific | Japan Ministry of Internal Affairs and Communication (MIC Japan) | MIC Japan: USD 150 000 ICT-DF: USD 37 500 | USD 53 845 |
| 7GLO23133 | Boosting digital skills through Digital Transformation Centres (DTCs) – Phase 2 | Jun. 2026 | Multi-regional | Norway Norwegian Agency for Development Cooperation (NORAD) | NORAD: CHF 834 276 ICT-DF: CHF 268 000 | CHF 46 879 |
| 7SUR23017 | National Computer Incident Response Team (CIRT) Implementation – Suriname | Jul. 2027 | Americas | Government of Suriname | Government of Suriname: USD 350 000 ICT-DF: USD 55 000 | USD 244 195 |
| 7GLO23132 | Generation Connect Young Leadership Programme | Apr. 2027 | Multi-regional | Huawei | Huawei: USD 1 255 654 ICT-DF: USD 500 000 | USD 841 384 |
| 7RAS24075 | Creating a Circular Economy for Electronics and Electricals in Thailand and Mongolia | Mar. 2026 | Asia-Pacific | Australia Department of Infrastructure, Transport, Regional Development, Communications, Sport and the Arts (DITRDCSA) | DITRDCSA: USD 256 800 ICT-DF: USD 60 000 | USD 89 880 |
| 7RAF24106 | Cyber resilience for Digital Development in the Least Developed Countries (CRDD-LDCs) | May 2026 | Africa | Czech Republic Ministry of Foreign Affairs (MFA) | MFA: CHF 97 005 ICT-DF: CHF 50 000 | CHF 22 456 |
| 7GLO24144 | Early Warnings for All – ITU funds to support to the implementation of the initiative | Sep. 2027 | Multi-regional | WMO (Funds from Ministry of Foreign Affairs, Denmark) UNDRR (Funds from CREWS - Climate Risk and Early Warning Systems) | WMO, Funds from Ministry of Foreign Affairs, Denmark (9RAF24105): CHF 851 043 UNDRR, Funds from CREWS (9GLO24143): USD 852 212 ICT-DF: USD 600 000 | USD 484 611 |
| 7MNE24002 | Digital Transformation of Local Self-Governments in Montenegro | Apr. 2026 | Europe | Montenegro SDG Acceleration Fund | Montenegro SDG Acceleration Fund: USD 110 210 ICT-DF: USD 55 000 | USD 21 662 |
| 7GLO24139 | Strengthening the capacity for the implementation of the multi-regional EU funded projects | May 2026 | Multi-regional | European Union (EU) | EU: EUR 8 200 000 (9GLO23123, 9GLO23128, 9GLO23129) ICT-DF: CHF 840 000 | CHF 2 434 860 |
| 7CIS25001 | Digital Government Cooperation in the Central Asia and Caucasus countries | Dec. 2026 | Commonwealth of Independent States | Kazakhstan National Information Technologies JSC (NITEC) | NITEC: USD 100 000 ICT-DF: USD 100 000 | CHF 47 999 |
| 7CIS25163 | Satcom Capacity Building | Dec. 2027 | Commonwealth of Independent States | Intersputnik International Organization of Space Communications (Intersputnik) | Intersputnik: USD 60 000 ICT-DF: USD 60 000 | USD 120 000 |
| 7GLO24146 | Cyber for Good (Phase 2) | Dec. 2026 | Multi-regional | Republic of Korea Ministry of Science and ICT (MSIT) | MSIT: USD 150 000 ICT-DF: USD 150 000 | USD 4 933 |
| 7GLO25151 | Her Cyber Tracks (Phase 3) | Feb. 2026 | Multi-regional | Germany Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) | GIZ: EUR 231 125 ICT-DF: EUR 100 800 | CHF 51 963 |
| 7GLO25152 | International Exchange Initiative on Regulating E-waste and Engaging Tech Companies – Creating a Circular Economy for Electronics | Dec. 2026 | Multi-regional | Colombia Presidential Agency for International Cooperation of Colombia (PAICC) | PAICC: USD 150 000 ICT-DF: USD 150 000 | CHF 116 833 |
| 7GLO25156 | Strengthening engagement, compliance and reporting of the EU funded projects | Aug. 2027 | Multi-regional | European Union (EU) | EU: EUR 15 000 000 (9RAF24107) ICT-DF: CHF 970 000 | CHF 11 304 406 |
| 7RAF25157 | Support to the Implementation of GovStack projects in the Africa Region | Jul. 2027 | Africa | WorldBank and Government of the Republic of The Gambia (9RAF25152), Government of the Republic of Guinea‑Bissau (9GNB25158), Government of the Republic of Guinea (9GUI25161) | WorldBank and Governments of the Republic of The Gambia, Republic of Guinea-Bissau and Republic of Guinea: USD 790 985 (USD 536 210 signed, with one additional country pending signature) ICT-DF: USD 260 000 | CHF 378 832 |
| 7RAS25162 | Enhancing the Sustainability of Smart Villages and Smart Islands in the Asia-Pacific | Nov. 2027 | Asia-Pacific | Australia Department of Infrastructure, Transport, Regional Development, Communications, Sport and the Arts (DITRDCSA) | DITRDCSA: USD 503 280 ICT-DF: USD 150 000 | USD 653 280 |
| 9GLO23134 | Assistance to encourage the use of innovative technologies for building a digital shared prosperity society | Jun. 2027 | Multi-regional | Republic of Korea Ministry of Science and ICT (MSIT) | MSIT: USD 226 429 ICT-DF: USD 83 571 | USD 204 910 |
| 9RAS25001 | Artificial Intelligence Technology and standards Capacity Building in Asia-Pacific | Feb. 2026 | Asia-Pacific | Australia Department of Infrastructure, Transport, Regional Development, Communications, Sport and the Arts (DITRDCSA) | DITRDCSA: USD 120 000 ICT-DF: USD 30 000 | USD 45 388 |
| 9RAS25002 | Enhancing Digital infrastructure and affordable access to ICT services in Asia and the Pacific | Nov. 2027 | Asia-Pacific | Japan Ministry of Internal Affairs and Communication (MIC Japan) | MIC Japan: USD 142 923 ICT-DF: USD 35 730 | CHF 154 061 |

More details on projects at www.itu.int/en/ITU-D/Projects.

______________

____________________