|  | Document C26/INF/4 |
| --- | --- |
|  | 10 April 2026 |
|  | Original: English |
| Note by the Secretary-General |  |
| ADDITIONAL INFORMATION ON PROPOSED FRAMEWORK FOR SELECTION PROCESS FOR HOST COUNTRIES OF ITU CONFERENCES AND ASSEMBLIES |  |
| Purpose This document provides supporting information to accompany the proposed framework for a selection process for host countries of ITU conferences and assemblies, submitted to the Council as Document C26/70. Action required by the Council This document is transmitted to the Council for information. _______________ References Council Document C26/70 |  |

Overview

Document C26/70 sets out a proposed framework for a selection process for host countries of ITU conferences and assemblies. The annexes below provide additional information in support of this proposal and include a timeline for the selection process in table format based on a conference planned for 2031 (Annex A); a comparative table of indicative requirements per conference or assembly based on the annexes of the latest signed Host Country Agreement of the respective conference (Annex B); and an example of an assessment table (Annex C).

Annexes: 3

Annex A

Indicative timelines for selection process for a conference or assembly held in October 2031

| T-Minus (months) | Estimated date | Step | Description |
| --- | --- | --- | --- |
| T-60 | October 2026 | Publication of conference list at PP 2026 (Res. 77) | The secretariat publishes, at the Plenipotentiary, the list of conferences and assemblies scheduled for the next eight years, specifying expected periods and providing details on hosts or dates where available. |
| T-52 | June 2027 | Call for proposals | The secretariat issues a Circular Letter inviting Member States to express interest in hosting the 2031 event, outlining submission deadlines for each subsequent stage. |
| T-50 to T-48 | June – August 2027 | Expressions of interest and consultation period | Member States interested in hosting consult with the secretariat and submit official expressions of interest, including supporting rationale. The secretariat provides a model HCA and clarifies budget and facility requirements as needed. |
| T-46 | By December 2027 | Submission of formal proposals | Interested Member States submit formal offers, including a letter of intent with government support, details on facilities, financial guarantees, and compliance with the latest HCA requirements. |
| T-45 | Within 12 days after proposal deadline (January 2028) | Posting of formal proposals | Invitations and information about formal proposals are posted on the ITU Host Country Web Portal. |
| T-45 to T-41 | January – May 2028 | Due diligence and preparation of report for Council 2028 | The secretariat reviews all proposals for compliance with minimum requirements, may conduct site visits, and prepares a due diligence report. The report and proposals are submitted to the Council or PP at least three years before the conference. |
| T-40 to T-37 | June/September 2028 | Selection of Host Country at Council 2028 and confirmation by Member States | The Council confirms or selects the host country, considering the due diligence report and the principle of geographic rotation. ITU Member States’ agreement is then sought by a consultation through Circular Letter. The final decision is then announced by Circular Letter. . |
| T-24 | October 2029 | Draft Host Country Agreement | The draft HCA is shared with the selected host government at least two years before the event. A joint organizing committee is established to oversee venue planning, IT, security, protocol, media and communications, and HCA finalization. |
| T-12 | October 2030 | Signing of HCA | The final HCA is signed by ITU and the host country, preferably one year before the conference. The signed HCA is made available on the ITU Host Country Web Portal and published as a conference document. |
| T-0 | October 2031 | Conference or assembly is held | The event is held in the selected host country, in accordance with the signed HCA and agreed arrangements. |

Annex B

Indicative overview of requirements per conference/assembly based on most recent signed HCAs

Type, number and capacity of rooms

| Category | WTDC-25 | WTSA-24 | WRC-23 | PP-22 |
| --- | --- | --- | --- | --- |
| Main plenary | 1×1 500 | 1×1 500 | 1×2 500 | 1×2 000 |
| Large rooms | 500 | 750 | 900/500 | 800/500/400 |
| Medium rooms | 200 | 2×300 | 2×300 | 200 |
| Small rooms | 100 | 150-200 | 8×100 | 1×75; 2×100 |
| Breakouts | 4×50; 2×30; 4×10-15 | 2×100; 3×50; 2×30; 3×10-20 | 7×50; 10×15-25 | 3×50; 15×10-20 |
| Editorial | 1×30 | 1×30 | 1×30 | 1×30 |

Technical services required

| Category | WTDC-25 | WTSA-24 | WRC-23 | PP-22 |
| --- | --- | --- | --- | --- |
| Interpretation | 6 languages |  |  |  |
| Recording | Digital audio |  |  |  |
| Webcast | 7 channels |  |  |  |
| Networking | BlueLAN1Gb/GreenLAN 2×1Gb links | BlueLAN1Gb/GreenLAN 2×1Gb links | 300Mb+2×1Gb | BlueLAN300Mb/Green1Gb |
| Studios | TV studio (video and podcast) |  |  |  |

Security requirements

| Category | WTDC-25 | WTSA-24 | WRC-23 | PP-22 |
| --- | --- | --- | --- | --- |
| Scope | Full venue and hotels |  |  |  |
| VIP protection | Yes |  |  |  |
| Medical | 24/7 | 24/7 | 18h/day | 24/7 |
| Access control | Yes |  |  |  |

Transport requirements

| Category | WTDC-25 | WTSA-24 | WRC-23 | PP-22 |
| --- | --- | --- | --- | --- |
| Airport transfers | Yes |  |  |  |
| Hotel shuttles | Yes |  |  |  |
| VIP cars | Yes |  |  |  |
| Equipment transport | Yes |  |  |  |

Visa facilitation requirements

| Category | WTDC-25 | WTSA-24 | WRC-23 | PP-22 |
| --- | --- | --- | --- | --- |
| Cost | Free for ITU | Free | Free | Free |
| Processing | ≤3 weeks | ≤2 weeks | ≤3 weeks | ≤3 weeks |

Annex C

Indicative example of assessment table for key requirements 
(non-exhaustive)

| Category | Key selection criteria | Critical requirements | Met (Y/N) | Comments |
| --- | --- | --- | --- | --- |
| Legal & diplomatic | Privileges & immunities | Granting of immunities to ITU staff and delegates; inviolability of the venue. |  |  |
|  | Visa facilitation | Guarantee of non-discriminatory entry and expedited visas for delegates from all 194 Member States. |  |  |
| Venue & infrastructure | Conference & meeting rooms | Large hall for 1 500 to 2 000+ delegates depending on the conference; medium sized conference rooms, large and small meeting rooms; offices for ITU Secretariat. |  |  |
|  | ICT connectivity | High-density, redundant Wi-Fi; 6 language simultaneous interpretation systems; remote participation (Zoom/Webcast). |  |  |
| Logistics | Transport & access | Proximity to international airport; dedicated shuttles for VIPs and delegates and ITU Staff between hotels and venue and airport to hotels. |  |  |
|  | Accommodation | Sufficient block of hotel rooms across various price points |  |  |
| Local staffing | Local support staff | Provision of local staff, IT support, and UN-experienced security personnel. |  |  |
| Safety & security | Safety and security | On-site 24/7 medical service; comprehensive security plan coordinated with UN Department of Safety and Security (UNDSS). |  |  |
| Sustainability | Green event standards | Compliance with "Greening the Meetings" guidelines (e.g., waste reduction, carbon offsetting, paperless policy). |  |  |
| Financial | Host contribution | Commitment to cover of costs for venue rental, AV, shipment, local staff, etc., plus travel/DSA and any other incremental costs for the ITU Secretariat. |  |  |

______________

____________________