|  | World Telecommunication Standardization Assembly (WTSA-16) Hammamet, 25 October - 3 November 2016 |  |  |
| --- | --- | --- | --- |
| PLENARY MEETING |  | Document 35-E |  |
|  |  | September 2016 |  |
|  |  | Original: English |  |
| Director of TSB |  |  |  |
| Action Plan related to the Resolutions and Opinion of WTSA-12 |  |  |  |

| Abstract: | This document contains a WTSA-12 Action Plan which is a monitoring and reporting tool to keep track of the implementation of WTSA-12 Resolutions and Opinion. |
| --- | --- |

WTSA-12 (Dubai, 20-29 November 2012) approved 50 new or revised Resolutions and one new Opinion.  In order to keep track of the implementation of so many Resolutions, a WTSA-12 Action Plan was developed (see http://www.itu.int/en/ITU-T/wtsa12/Pages/default.aspx) as a monitoring and reporting tool by TSB since last Study Period (see WTSA-12 Doc.28 - WTSA-08 Action Plan). It details 234 action items, their associated responsibilities, necessary collaborations, reports and finally status. The WTSA-12 Action Plan was first published on the ITU-T website in June 2013 for TSAG and has gone through five revisions (at the five TSAG meetings respectively) in this Study Period.

This document contains two attachments - a WINWORD document which details the implementation progress report and an EXCEL sheet which illustrates the implementation status of each action item. The WINWORD report is based on TSAG TD547 (18-22 July 2016) which is the final version of the action plan for this study period and updated to include further development until September 2016.

The EXCEL sheet allows all Action Items to be displayed on a single sheet of paper, or sorted by any of the columns, such as all those for TSB action, or all those requiring a report to Council, etc. It also uses colors to visualize the completion status of action items.  The EXCEL sheet illustrates the implementation of action items in figures, in summary:

- The Action Plan contains 234 detailed Action Items for 50 WTSA-12 Resolutions and one Opinion, among which:

  - 40 Resolutions and the Opinion have 143 Action Items for TSB & Director

  - 30 Resolutions have 85 Action Items for SGs

  - 21 Resolutions have 34 Action Items for TSAG/RevCom

  - 23 Resolutions have 53 Action Items on cooperation with other ITU Sectors/General Secretariat

- As of mid September 2016,

  - 45 items are one-time actions with measurable milestone/criteria, and have been completed (19%)

  - 71 items are ongoing by nature with significant progress achieved or periodical goals met for this study period (30%)

  - 102 items are ongoing by nature (44%)

  - 16 items have not yet been completed or not much progressed (74%)

Attachments:

- WTSA-12 Action Plan V6.0 - Progress Report in WINWORD

- WTSA-12 Action Plan V6.0 - EXCEL sheet

_______________