|  | INTERNATIONAL TELECOMMUNICATION UNION TELECOMMUNICATION STANDARDIZATION SECTOR STUDY PERIOD 2017-2020 |  |  | TD 017 |
| --- | --- | --- | --- | --- |
|  |  |  |  | TSAG |
|  |  |  |  | Original: English |
| Question(s): |  | N/A |  | Geneva, 1-4 May 2017 |
| TD (Ref.: SG12 - LS 4 -E) |  |  |  |  |
| Source: |  | ITU-T Study Group 12 |  |  |
| Title: |  | LS on Operational Plan for Implementation of WTSA-16 Resolution 95 (Hammamet, 2016) [from ITU-T SG12] |  |  |
| LIAISON STATEMENT |  |  |  |  |
| For action to: |  |  | ITU-D SG1 |  |
| For comment to: |  |  | ITU-D SG2, TDAG, ITU-T SG2, SG3, SG5, SG9, SG11, SG13, SG15, SG16, SG17, SG20, TSAG |  |
| For information to: |  |  | - |  |
| Approval: |  |  | ITU-T Study Group 12 (Geneva, 19 January 2017) |  |
| Deadline: |  |  | September, 2017 |  |
| Contact: |  |  | Tiago Sousa Prado National Telecommunications Agency Brazil | Tel: +55 61 2312 2617 Fax: +55 61 2312 2793 E-mail: tiago.prado@anatel.gov.br |
| Contact: |  |  | Kwame Baah-Acheamfuor SG12 Chairman Ghana | Tel: +233 24 6375700 E-mail: kwame.baah-acheamfuor@nca.org.gh |

A new liaison statement has been received from SG12.

This liaison statement follows and the original file can be downloaded from the ITU ftp server at http://handle.itu.int/11.1002/ls/sp16-sg12-oLS-00004.docx.

|  | INTERNATIONAL TELECOMMUNICATION UNION TELECOMMUNICATION STANDARDIZATION SECTOR STUDY PERIOD 2017-2020 |  |  |  | COM 12 – LS 4 – E |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Original: English |  |
| Question(s): |  |  | 1/12 |  | Geneva, 10-19 January 2017 |  |
| LS |  |  |  |  |  |  |
| Source: |  |  | ITTU-T Study Group 12 |  |  |  |
| Title: |  |  | LS on Operational Plan for Implementation of WTSA-16 Resolution 95 (Hammamet, 2016) |  |  |  |
| Purpose: |  |  | Action/Comment |  |  |  |
| LIAISON STATEMENT |  |  |  |  |  |  |
| For action to: |  |  |  | ITU-D Study Group 1 |  |  |
| For comment to: |  |  |  | ITU-D Study Group 2, All ITU-T Study Groups, TDAG, TSAG |  |  |
| For information to: |  |  |  | - |  |  |
| Approval: |  |  |  | ITU-T Study Group 12 (Geneva, 19 January 2017) |  |  |
| Deadline: |  |  |  | September, 2017 |  |  |
| Contact: |  | Tiago Sousa Prado National Telecommunications Agency Brazil |  |  |  | Tel: +55 61 2312 2617 Fax: +55 61 2312 2793 E-mail: tiago.prado@anatel.gov.br |
| Contact: |  | Kwame Baah-Acheamfuor SG12 Chairman Ghana |  |  |  | Tel: +233 24 6375700 E-mail: kwame.baah-acheamfuor@nca.org.gh |

| Keywords: | QoS; QoE; regulation, measurement, framework, awareness. |
| --- | --- |
| Abstract: | WTSA Resolution 95 (Hammamet, 2016) on ITU-T initiatives to raise awareness on best practices and policies related to service quality proposes how the studies related with quality regulatory approaches should be conducted by ITU-T, in close collaboration with ITU-D, on the study period 2017-2020. This Liaison Statement informs ITU-D SG 1 on the operational plan for implementing Resolution 95 approved in Question 1/12 of SG 12, seeking collaboration and relevant information from ITU-D on the status of quality regulatory framework deployed by the countries, bottlenecks faced by them as well as capacity-building opportunities available. |

WTSA Resolution 95 (Hammamet, 2016) on ITU-T initiatives to raise awareness on best practices and policies related to service quality recognized the importance of the ongoing work on this field being developed on ITU-T. Also, the Resolution proposes how the studies related with quality regulatory approaches should be conducted, in close collaboration with ITU-D, on the next study period, indicating some deliverables to be developed by SG12 and other relevant ITU-T Study Groups.

Among other important provisions, the WTSA-16 Resolution 95 indicated as important topics to be studied in the next study period:

- guidelines and best practices for establishment of national quality measurement frameworks suitable to perform QoS and QoE measurement, especially in developing countries, identifying human and institutional capacity-building necessities of these countries;

- strategies to make users informed about the quality of the services offered;

- QoS/QoE evaluation scenarios and testing methodologies;

- sampling methodologies for QoS measurements at a local, national and global level;

- references relating to minimal satisfactory key performance and key quality indicators for evaluating the quality of services;

- promoting participation of regulators, operators and suppliers in wider operational and regulatory discussions about new strategies to deliver better QoS and QoE to users.

Furthermore, the Resolution instructs the Director of TSB, in close collaboration with ITU-D:

- to assist developing and least developed countries in identifying human and institutional capacity-building opportunities for establishing national quality measurement frameworks;

- to conduct activities in each region in order to identify and prioritize the problems faced by developing and least developed countries related to the provision of acceptable service quality to users;

- to assist developing and least developed countries in elaborating and implementing actions to improve service quality and keep users informed.

The full text of the referred WTSA Resolution 95 (Hammamet, 2016) can be found in the link below: https://www.itu.int/pub/T-RES-T.95-2016.

Based on the clear directions given by WTSA Resolution 95 (Hammamet, 2016), SG12 has approved an Operational Plan for implementation of this Resolution (see Annex 1), identifying the operative provisions, what would be the deliverables, who would be responsible for developing them and reasonable deadlines for all the work.

Request for action:

Given the background information on WTSA Resolution 95 (Hammamet – 2016) and the necessity of collaboration between ITU-T and ITU-D on initiatives to raise awareness on best practices and policies related to service quality, ITU-T SG12 would appreciate ITU-D SG 1 collaboration and relevant information that surely will be useful to accomplish the aforementioned challenges.

Valuable inputs on the status of quality regulatory framework deployed by the countries, bottlenecks faced by them, strategies for collecting data on QoS/QoE among the countries, examples of questionnaires already disseminated on QoS/QoE matters, focal points on quality matters already identified among the countries (mainly from regulatory bodies) as well as capacity-building opportunities available for developing and least developed countries would be really welcomed.

ANNEX I

Operational Plan for Implementation of WTSA Resolution 95 (Hammamet, 2016)

| ID |  | Directives | References (Res 95) | Activities | Responsabilities | Time Plan | Status (Jan/2017) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Level 1 | Level 2 |  |  |  |  |  |  |
| 1 | 1.1 | Promote wider participation of regulators, operators and suppliers in the international debate on service quality | Resolves (4) Instructs ITU-T SGs (5) | Conduct outreach activities, e.g., workshops | SG12, QSDG, SG12 RG-AFR | continued | QSDG workshops being conducted. More open events needed. |
|  | 1.2 |  |  | Produce publication/advertisement material for SG 12 | TSB | Sep - 2017 | Actions needed |
| 2 | 2.1 | Raise awareness on the importance of deploying QoS and QoE measurements and also keeping users informed about the results | Resolve (2 and 4) | Recommendations on strategies to give transparency on quality measurements to end users | QALL (with inputs from QSDG, SG12 RG-AFR, ITU-D) | 2017-2018 | Y.FMIPQoS and E.QMME highlight the importance of giving tranparency on the measurement results. Further material needed. |
|  | 2.2 |  |  | Training material | ITU-D | Sep 2017 | LS sent to ITU-D SG 1 asking information on traning material already available |
|  | 2.3 |  |  | Publication material | TSB | continued | On demand |
| 3 | 3.1 | Identify and prioritize problems faced by developing and least developed countries related to the provision of acceptable service quality to users; | Instructs TSB (2) | Questionnaire on status of QoS, QoE and user satisfaction regulatory approaches | Q1/12 | Sep-2017 | First draft discussed |
|  | 3.2 |  |  | List focal points on quality matters among countries | LS Rapporteur on Res 95 | Sep-2017 | LS sent to Regional Offices |
|  | 3.3 |  |  | Disseminate questionnaire and follow up through BDT and Regional Offices | SG12, QSDG, SG12 RG-AFR, ITU-D, TSB, BDT | Sep-2017 | Waiting questionnaire approval |

| ID |  | Directives | References (Res 95) | Activities | Responsabilities | Time Plan | Status (Jan/2017) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Level 1 | Level 2 |  |  |  |  |  |  |
| 4 | 4.1 | Assist developing and least developed countries in establishing a national quality measurement framework suitable to perform QoS and QoE measurement | Resolves (3) Instructs TSB (1 and 3) Instructs SGs (1, 2, 3 and 4) | Handbook with countries' experiences in establishing a national quality measurement framework | Q2/12 | TBD | Being done |
|  | 4.2 |  |  | Recommendations on strategies to establish national quality measurement framework suitable to perform QoS and QoE measurement; | QALL | 2017-2020 | Actions needed |
|  | 4.3 |  |  | Recommendations on sampling methodologies for QoS measurement | QALL | 2017-2020 | Actions needed |
|  | 4.4 |  |  | Recommendations with minimal satisfactory key performance and key quality indicators for evaluating the quality of services | QALL | 2017-2020 | Actions needed |
|  | 4.5 |  |  | Recommendations on QoS and QoE evaluation scenarios and testing tools | QALL | 2017-2020 | Actions needed |
|  | 4.6 |  |  | Identify capacity-building opportunities | ITU-D | Sep-2017 | LS sent to ITU-D SG 1 asking information on traning material already available |

_________________