|  | INTERNATIONAL TELECOMMUNICATION UNION TELECOMMUNICATION STANDARDIZATION SECTOR STUDY PERIOD 2017-2020 |  |  | TD 025 Rev.1 |
| --- | --- | --- | --- | --- |
|  |  |  |  | TSAG |
|  |  |  |  | Original: English |
| Question(s): |  |  | N/A | Geneva, 1-4 May 2017 |
| TD |  |  |  |  |
| Source: |  |  | Director, TSB |  |
| Title: |  |  | Action plan related to the Resolutions and Opinion of WTSA-16 |  |
| Purpose: |  |  | Discussion |  |
| Contact: |  | Martin Euchner TSB |  | Tel: +41 22 730 5866 Fax: +41 22 730 5853 E-mail: martin.euchner@itu.int |

| Keywords: | WTSA-16 Action Plan |
| --- | --- |
| Abstract: | This document contains the initial WTSA-16 Action Plan which is a monitoring and reporting tool to keep track of the implementation of WTSA-16 Resolutions and Opinion. |

Action:	TSAG is invited to discuss the initial WTSA-16 Action Plan.

WTSA-16 (Hammamet, 25 October – 3 November 2016) approved 61 new or revised Resolutions.

In order to keep track of the implementation of so many Resolutions, TSB developed and maintained a WTSA Action Plan (see https://www.itu.int/en/ITU-T/wtsa16/Documents/WTSA-Action-Plan/WTSA-ActionPlan-201609.zip) as a monitoring and reporting tool during the last 2013-2016 Study Period (see WTSA-16 Doc.35 - WTSA-12 Action Plan).

This document develops the initial action plan for the WTSA-16 Resolutions to be maintained and progressed through this study period.

It details 363 action items, their associated responsibilities, necessary collaborations, reports and current status.

Action items from the fomer WTSA-12 Action Plan, which were obsolete or were considered completed at WTSA-16, are no longer listed in this Action Plan; they are:

- 07-02;

- 22-01, 22-02, 22-03 (action item numbers reused);

- 31-01;

- 33-02, 33-03, 33-04; (Resolution 33 suppressed)

- 35-01 (but provision still exists in Resolution);

- 43-01, 43-02, 43-03 (but provision still exists in Resolution);

- 44-04, 44-06, 44-08, 44-09, 44-10, 44-16, 44-17, 44-18, 44-22 (still exists);

- 54-02;

- 55-05 (new action item);

- 65-03 (but provision still exists in Resolution);

- 67-04;

- 69-02, 69-04 (but provision still exists in Resolution);

- 70-02 and 70-09 (but provision still exists in Resolution);

- 71-01;

- 74-01;

- 76-11;

- 77-01, 77-02, 77-03 and 77-05 (but provision still exists in Resolution);

- 81-01, 81-02, 81-03 (Resolution 81 was suppressed);

- 82-01, 82-02, 82-03 (Resolution 82 was suppressed);

- OP-01-02.

This document contains two attachments

- a WORD document which details the implementation progress report

- and an EXCEL sheet which illustrates the implementation status of each action item.

The WORD report is based on WTSA-16 C 0035 which was the final version of the action plan for the study period 2013-2016 as provided to WTSA-16, and has been updated to include further development since September 2016, in particular outcomes of Study Groups (SG12 and SG16 in January 2017, SG11 and SG13 in February 2017, SG17 and SG20 in March 2017, SG2 and SG3 in April 2017) meetings.

The EXCEL sheet allows all Action Items to be displayed on a single sheet of paper, or sorted by any of the columns, such as all those for TSB action, or all those requiring a report to Council, etc. It also uses colors to visualize the completion status of action items. The EXCEL sheet illustrates the implementation of action items in figures, in summary:

- In summary, this Action Plan contains 363 detailed Action Items for the 61 WTSA-16 Resolutions and one Opinion, among which:

  - 56 Resolutions and the Opinion have 216 Action Items for TSB & Director;

  - 47 Resolutions have 153 Action Items for Study Groups;

  - 19 Resolutions have 30 Action Items for TSAG;

  - 5 Resolutions have 5 Action Items for the General Secretariat;

  - 10 Resolutions have 13 Action Items on cooperation with the General Secretariat and regional Offices;

  - 26 Resolutions have 62 Action Items on cooperation with BDT/ITU-D/TDAG;

  - 14 Resolutions have 29 Action Items on cooperation with BR/ITU-R/RAG.

Preliminary assessment of the implementation of WTSA resolutions

WSTA-16 Resolution 83 instructs the TSB Director to assess the implementation of WTSA resolutions by all parties concerned. As not all study groups have yet met, this document just attempts to convey a preliminary assessment of the resolutions against the action item as per April 2017 where some progress reporting has been achieved.

The action plan categorizes the action items into four types depending on progress:

- Complete: The action item is considered complete and met its goals.

- Ongoing by nature with periodic goals met: The action item has progressing well according to its reported achievement.

- Ongoing: The action item typically is under consideration, but needs more time and efforts for its progression.

- No action / needs attention: The action item has not made any necessary progress and deserves attention.

As of mid April 2017

  - Five action items are one-time actions with measurable milestone/criteria, and have already been fully implemented and can be considered complete (1% of all; i.e., 02-01, 11-02, 18-05, 67-08, and 92-11).

  - 235 action items are ongoing by nature with certain/some/significant progress achieved or periodical goals met (65%).

  - 121 action items are ongoing by nature (33%).

  - 2 action items are identified not to have had any activity so far (1%; i.e. 48-01, 50-15).

It is planned to further maintain this action plan throughout this 2017-2020 study period and to provide updates at each forthcoming TSAG meeting.

Observations and Advisory to TSAG:

- For action item 48-01 >> SG16, and other relevant SGs, considering input contributions, to study internationalized (multilingual) domain names (i. SG16)<< it is reported that only one contribution was submitted in the study period 2009-2012 to ITU-T SG16, which resulted in an exchange of Liaison Statements with relevant external organizations. Feedback provided and lack of further activity (including in the current study period) suggests that perhaps the work is complete.

TSAG is invited to consider closing this action item.

- For action item 50-15 >>All ITU-T SGs to ensure that security aspects are considered throughout the ITU-T standards development process (resolves 9)<< it is reported that SG13 took a decision sometime in 2002 that each of its Recommendations will have an obligatory clause on security considerations. This practice was closely followed since 2002.

TSAG should consider to recommend this approach to all SGs.

Attachments: 2

- WTSA-16 Action Plan V0.2 - Progress Report in WINWORD

- WTSA-16 Action Plan V0.2 - EXCEL sheet.

_______

_______________