|  | INTERNATIONAL TELECOMMUNICATION UNION TELECOMMUNICATION STANDARDIZATION SECTOR STUDY PERIOD 2017-2020 |  |  | TSAG-TD292 |
| --- | --- | --- | --- | --- |
|  |  |  |  | TSAG |
|  |  |  |  | Original: English |
| Question(s): |  |  | N/A | Geneva, 10 – 14 December 2018 |
| TD |  |  |  |  |
| Source: |  |  | Director, TSB |  |
| Title: |  |  | Action plan related to the Resolutions and Opinion of WTSA-16 |  |
| Purpose: |  |  | Discussion |  |
| Contact: |  | Martin Euchner TSB |  | Tel: +41 22 730 5866 Fax: +41 22 730 5853 E-mail: martin.euchner@itu.int |

| Keywords: | WTSA-16 Action Plan; |
| --- | --- |
| Abstract: | The WTSA-16 Action Plan is a monitoring and reporting tool to keep track of the implementation of WTSA-16 Resolutions and Opinion. This document contains the WTSA-16 Action Plan that has been updated since March 2018. |

Action:	TSAG is invited to discuss the WTSA-16 Action Plan.

WTSA-16 (Hammamet, 25 October – 3 November 2016) approved 61 new or revised Resolutions.

In order to keep track of the implementation of so many Resolutions, TSB developed and maintained a WTSA Action Plan (see https://www.itu.int/en/ITU-T/wtsa16/Documents/WTSA-Action-Plan/WTSA-ActionPlan-201609.zip) as a monitoring and reporting tool during the last 2013-2016 Study Period (see WTSA-16 Doc.35 - WTSA-12 Action Plan).

This document further updates the initial action plan for the WTSA-16 Resolutions (from March 2018 TSAG-TD139r1) to be maintained and progressed through this study period.

The Action Plan details 362 action items, their associated responsibilities, necessary collaborations, reports and current status.

This document contains two attachments

- a WORD document which details the implementation progress report;

- and an EXCEL sheet which illustrates the implementation status of each action item.

The WORD report is based on WTSA-16 C 0035 which was the final version of the action plan for the study period 2013-2016 as provided to WTSA-16, and has been updated to include further developments since September 2016, in particular outcomes of Study Groups (SG12 and SG16 in January 2017, SG11 and SG13 in February 2017, SG17 and SG20 in March 2017, SG2 and SG3 in April 2017) meetings.

The EXCEL sheet allows all Action Items to be displayed on a single sheet of paper, or sorted by any of the columns, such as all those for TSB action, or all those requiring a report to Council, etc. It also uses colors to visualize the completion status of action items. The EXCEL sheet illustrates the implementation of action items in figures, in summary:

- In summary, this Action Plan contains 362 detailed Action Items for the 61 WTSA-16 Resolutions and one Opinion, among which:

  - 56 Resolutions and the Opinion have 217 Action Items for TSB & Director;

  - 47 Resolutions have 153 Action Items for Study Groups;

  - 19 Resolutions have 30 Action Items for TSAG;

  - 5 Resolutions have 5 Action Items for the General Secretariat;

  - 10 Resolutions have 13 Action Items on cooperation with the General Secretariat and regional Offices;

  - 26 Resolutions have 62 Action Items on cooperation with BDT/ITU-D/TDAG;

  - 14 Resolutions have 29 Action Items on cooperation with BR/ITU-R/RAG.

Assessment of the implementation of WTSA resolutions

WSTA-16 Resolution 83 instructs the TSB Director to assess the implementation of WTSA resolutions by all parties concerned.

The action plan categorizes the action items into four types depending on progress:

- Complete: The action item is considered complete and met its goals.

- Ongoing by nature with periodic goals met: The action item has been progressing well according to its reported achievement.

- Ongoing: The action item typically is under consideration, but needs more time and efforts for its progression; or is waiting to be started.

- No action / needs attention: The action item has not made any necessary progress and deserves attention.

As of 3 December 2018

  - 11 action items are one-time actions with measurable milestone/criteria, and have already been fully implemented and can be considered complete (3% of all).

  - 298 action items are ongoing by nature with certain/some/significant progress achieved or periodical goals met (82%).

  - 13 action items are ongoing/pending by nature (3%).

  - 40 action items are identified not to have had any activity so far or require attention (11%).

It is planned to further maintain this action plan throughout this 2017-2020 study period and to provide updates at each forthcoming TSAG meeting.

Attachments: 2

- WTSA-16 Action Plan V0.5 - Progress Report in WINWORD

- WTSA-16 Action Plan V0.4 - EXCEL sheet.

Appendix

Action items from the fomer WTSA-12 Action Plan, which were obsolete or were considered completed at WTSA-16, are no longer listed in this Action Plan; they are:

- 07-02;

- 22-01, 22-02, 22-03 (action item numbers reused);

- 31-01;

- 33-02, 33-03, 33-04; (Resolution 33 suppressed)

- 35-01 (but provision still exists in Resolution);

- 43-01, 43-02, 43-03 (but provision still exists in Resolution);

- 44-04, 44-06, 44-08, 44-09, 44-10, 44-16, 44-17, 44-18, 44-22 (still exists);

- 54-02;

- 55-05 (new action item);

- 65-03 (but provision still exists in Resolution);

- 67-04;

- 69-02, 69-04 (but provision still exists in Resolution);

- 70-02 and 70-09 (but provision still exists in Resolution);

- 71-01;

- 74-01;

- 76-11;

- 77-01, 77-02, 77-03 and 77-05 (but provision still exists in Resolution);

- 81-01, 81-02, 81-03 (Resolution 81 was suppressed);

- 82-01, 82-02, 82-03 (Resolution 82 was suppressed);

- OP-01-02.

___________________

_______________