|  | INTERNATIONAL TELECOMMUNICATION UNION TELECOMMUNICATION STANDARDIZATION SECTOR STUDY PERIOD 2022-2024 |  |  | TSAG-TD410 |
| --- | --- | --- | --- | --- |
|  |  |  |  | TSAG |
|  |  |  |  | Original: English |
| Question(s): |  |  | N/A | Geneva, 22 - 26 January 2024 |
| TD (Ref. TD191R3) |  |  |  |  |
| Source: |  |  | Director, TSB |  |
| Title: |  |  | Action plan related to the Resolutions and Opinion of WTSA |  |
| Contact: |  | Xiaoya Yang TSB, Secretary of RG-WTSA |  | Tel: +41 22 730 6206 E-mail: xiaoya.yang@itu.int |

| Abstract: | The WTSA-20 Action Plan is a monitoring and reporting tool to keep track of the implementation of WTSA Resolutions and Opinion. This document contains the updated WTSA-20 Action Plan from its last revision in May 2023 for last TSAG meeting. |
| --- | --- |

Action:	TSAG is invited to take note of the WTSA-20 Action Plan, especially those 4% ‘needs attention’ action items marked in red in attachment 2 of this document.

# Background

As an outcome of WTSA-20 (Geneva, 1 – 9 March 2022) 58 new or revised Resolutions are in force.

In support of CV §197H, and of Rec. ITU-T A.1 clause 1.3.1, and in order to keep track of the implementation of so many Resolutions, TSB continued the established practice initiated after WTSA 2008 (ref. WTSA-12 DOC28, WTSA-16 DOC35, WTSA-20 DOC34) and developed and maintained a new WTSA-20 action plan as a monitoring and reporting tool for the 2022-2024 Study Period.

# Executive summary

This WTSA-20 Action Plan for the 2022-2024 Study Period details 409 action items, their associated responsibilities, necessary collaborations, reports and current status.

This document contains two attachments

- a WORD document which details the implementation progress report;

- and an EXCEL sheet which illustrates the implementation status of each action item, and statistics.

The WORD document is developed based on WTSA-20 C34, the final version of the WTSA-16 Action Plan for the study period (2017-2021) before WTSA-20. Following the precedence of its Appendix I, a new Appendix II was added which identifies 30 action items which are obsolete or were considered completed at WTSA-20, and consequently, their implementation are no longer been included in the attachments of this reporting tool.

This WORD document has been updated to include further developments since December 2022 in each TSAG meeting.

The EXCEL sheet allows all action items to be displayed on a single sheet, or sorted by any of the columns, such as all those for TSB action, or all those requiring a report to Council, etc. It also uses colours to visualize the completion status of action items. The EXCEL sheet illustrates the implementation of action items in figures:

- In summary, this action plan contains 409 detailed action items for the 58 WTSA Resolutions in force.

- TSB/TSBDir is responsible for 230 action items, and Membership is responsible for 179 action items.

# Assessment of the implementation of WTSA resolutions

WTSA Resolution 83 (Hammamet, 2016) instructs the TSB Director to assess the implementation of WTSA resolutions by all parties concerned.

The action plan categorizes the status of the action items into four types depending on progress:

| Complete | The action item is considered complete and met its goals. |
| --- | --- |
| Ongoing by nature with periodic goals met | Ongoing by nature with periodic goals met: The action item has been progressing well according to its reported achievement. |
| Ongoing/Pending | The action item typically is under consideration but needs more time and efforts for its progression or its reporting; or is waiting to be started. |
| No action / needs attention | The action item has no progress reported and deserves attention. |

As of 18 January 2024

- 14 action items (3% of all) are either one-time actions with measurable milestone/criteria or have already been fully implemented and can be considered complete.

- 273 action items (67%) are ongoing by nature with certain/some/significant progress achieved or periodical goals met.

- 105 action items (26%) need more time and efforts for its progression or its reporting; or wait to be started.

- 18 action items (4%) are identified not to have had any activity so far or require attention.

Note that the attached Excel sheet provides more detailed statistics for the status of the action items with respect to the responsibilities of TSB/TSBDir and Membership.

TSB will be maintaining and updating this action plan, reporting through future TSAG meetings to WTSA-24.

# Attachments: 2

1.	WTSA-20 Action Plan V0.3 - Progress Report in WINWORD (18 January 2024)

2.	WTSA-20 Action Plan V0.3– EXCEL sheet (18 January 2024).

________________

_______________