TSAG-TD410 (2024-01) Att.1

WTSA-20 Action Plan, V0.3

(18 January 2024)

Contents

Section I - List of WTSA-20 Resolutions and Opinion, and executive summary of action plan for implementation	6

Section II - Progress reports on implementation of the WTSA-20 Resolutions and Opinion	18

1.	Resolution 1 - Rules of procedure of the ITU Telecommunication Standardization Sector	18

2.	Resolution 2 - ITU Telecommunication Standardization Sector Study Group responsibility and mandates	21

3.	Resolution 7 - Collaboration with the International Organization for Standardization and the International Electrotechnical Commission	22

4.	Resolution 11 - Collaboration with the Postal Operations Council of the Universal Postal Union in the study of services concerning both the postal and the telecommunication sectors	26

5.	Resolution 18 - Principles and procedures for the allocation of work to, and strengthening coordination and cooperation among, ITU Radiocommunication, ITU Telecommunication Standardization and ITU Telecommunication Development Sectors	27

6.	Resolution 20 - Procedures for allocation and management of international telecommunication numbering, naming, addressing and identification resources	30

7.	Resolution 22 - Authorization for Telecommunication Standardization Advisory Group to act between world telecommunication standardization assemblies	31

8.	Resolution 29 - Alternative calling procedures on international telecommunication networks	40

9.	Resolution 31 - Admission of entities or organizations to participate as Associates in the work of the ITU-T Telecommunication Standardization Sector	42

10.	Resolution 32 - Strengthening electronic working methods for the work of the ITU-T Telecommunication Standardization Sector	43

11.	Resolution 34 - Voluntary contributions	47

12.	Resolution 40 - Regulatory and policy aspects of work of the ITU Telecommunication Standardization Sector	48

13.	Resolution 43 - Regional preparations for world telecommunication standardization assemblies	49

14.	Resolution 44 - Bridging the standardization gap between developing and developed countries	50

15.	Resolution 47 - Country code top-level domain names	63

16.	Resolution 48 - Internationalized (multilingual) domain names	63

17.	Resolution 49 - ENUM	64

18.	Resolution 50 - Cybersecurity	65

19.	Resolution 52 - Countering and combating spam	72

20.	Resolution 54 – Regional groups of study groups of the ITU Telecommunication Standardization Sector	75

21.	Resolution 55 – Promoting gender equality in ITU Telecommunication Standardization Sector activities	79

22.	Resolution 58 – Encourage the creation of national computer incident response teams, particularly for developing countries	83

23.	Resolution 60 – Responding to the challenges of the evolution of the identification/numbering system and its convergence with IP-based systems / networks	84

24.	Resolution 61 – Countering and combating misappropriation and misuse of international telecommunication numbering resources	86

25.	Resolution 62 - Dispute settlement	87

26.	Resolution 64 - IP address allocation and facilitating the transition to and deployment of IPv6	88

27.	Resolution 65 - Calling party number delivery, calling line identification and origin identification information	90

28.	Resolution 67 – Use in the ITU Telecommunication Standardization Sector of the languages of the Union on an equal footing and the Standardization Committee for Vocabulary	92

29.	Resolution 68 - Evolving role of industry in the ITU Telecommunication Standardization Sector	95

30.	Resolution 69 - Non discriminatory access and use of Internet resources and telecommunications/information and communication technologies	97

31.	Resolution 70 - Telecommunication/ information and communication technology accessibility for persons with disabilities and persons with specific needs	98

32.	Resolution 72 - Measurement and assessment concerns related to human exposure to electromagnetic fields	103

33.	Resolution 73 - Information and communications technologies, environment, climate change and circular economy	108

34.	Resolution 74 - Enhancing participation of Sector Members* from developing countries in the work of the ITU Telecommunication Standardization Sector	117

35.	Resolution 75 - The ITU Telecommunication Standardization Sector's contribution in implementing the outcomes of the World Summit on the Information Society, taking into account the 2030 Agenda for Sustainable Development	117

36.	Resolution 76 - Studies related to conformance and interoperability testing, assistance to developing countries, and a possible future ITU mark programme	120

37.	Resolution 77 – Enhancing the standardization work in the ITU Telecommunication Standardization Sector for software-defined networking	125

38.	Resolution 78 – Information and communication technology applications and standards for improved access to e-health services	128

39.	Resolution 79 – The role of telecommunications/ information and communication technology in handling and controlling e-waste from telecommunication and information technology equipment and methods of treating it	131

40.	Resolution 80 – Acknowledging the active involvement of the membership in the development of ITU Telecommunication Standardization Sector deliverables	133

41.	Resolution 83 – Evaluation of the implementation of resolutions of the World Telecommunication Standardization Assembly	135

42.	Resolution 84 – Studies concerning the protection of users of telecommunication/information and communication technology services	136

43.	Resolution 86 - Facilitating the implementation of the Smart Africa Manifesto	139

44.	Resolution 87 - Participation of the ITU Telecommunication Standardization Sector in the periodic review and revision of the International Telecommunication Regulations	141

45.	Resolution 88 - International mobile roaming	142

46.	Resolution 89 - Promoting the use of information and communication technologies to bridge the financial inclusion gap	143

47.	Resolution 90 - Open source in the ITU Telecommunication Standardization Sector	149

48.	Resolution 91 - Enhancing access to an electronic repository of information on numbering plans published by the ITU Telecommunication Standardization Sector	151

49.	Resolution 92 - Enhancing the standardization activities in the ITU Telecommunication Standardization Sector related to non-radio aspects of international mobile telecommunications	152

50.	Resolution 93 - Interconnection of 4G, IMT-2020 networks and beyond	159

51.	Resolution 94 - Standardization work in the ITU Telecommunication Standardization Sector for cloud-based event data technology	162

52.	Resolution 95 - ITU Telecommunication Standardization Sector initiatives to raise awareness on best practices and policies related to service quality	164

53.	Resolution 96 - ITU Telecommunication Standardization Sector studies for combating counterfeit telecommunication/information and communication technology devices	168

54.	Resolution 97 - Combating mobile telecommunication device theft	173

55.	Resolution 98 - Enhancing the standardization of Internet of things and smart cities and communities for global development	177

56.	Resolution 99 - Consideration of organizational reform of the ITU Telecommunication Standardization Sector study groups	186

57.	Resolution 100 - A common emergency number for Africa	188

58.	Opinion 1 - Practical application of network externality premium	189

Appendix I – Obsolete action items from WTSA-12 Action Plan	190

Appendix II – Obsolete action items from WTSA-16 Action Plan	191

# Section I - List of WTSA-20 Resolutions and Opinion, and executive summary of action plan for implementation

Table 1
List of WTSA-20 Resolutions and Opinion, and executive summary of action plan for implementation of WTSA-20 Resolutions

| Resolution - Title** | Action by |  |  |  |  |  | Collaboration with |  |  | Report to |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | SGs | TSAG | TSB | Membership | Council | GenSec | GenSec | BDT ITU-D | BR ITU-R | TSAG | Council | WTSA | PP |
| Resolution 1 – Rules of procedure of the ITU Telecommunication Standardization Sector | All | X | X |  |  |  |  |  |  | X |  | X |  |
| Resolution 2 – ITU Telecommunication Standardization Sector study group responsibility and mandates | All |  | X |  |  |  |  | X |  | X |  |  |  |
| Resolution 7 – Collaboration with the International Organization for Standardization and the International Electrotechnical Commission | All | X | X | MSs |  |  |  |  |  | X |  |  |  |
| Resolution 11 – Collaboration with the Postal Operations Council of the Universal Postal Union in the study of services concerning both the postal and the telecommunication sectors | SG3, SG12, SG17 |  | X |  |  |  |  |  |  |  |  |  |  |
| Resolution 18 – Principles and procedures for the allocation of work to, and strengthening coordination and cooperation among, the ITU Radiocommunication, ITU Telecommunication Standardization and ITU Telecommunication Development Sectors | All SGs | X | X |  |  |  | ISCG, ICG, IRG | TDAG | RAG | ISCG, ISC-TF |  |  |  |
| Resolution 20 – Procedures for allocation and management of international telecommunication numbering, naming, addressing and identification resources | SG2 |  | X |  |  |  | Council |  |  |  | X |  |  |
| Resolution 22 – Authorization for Telecommunication Standardization Advisory Group to act between world telecommunication standardization assemblies |  | X | X |  |  |  |  | X | X | X |  | X | X |
| Resolution 29 – Alternative calling procedures on international telecommunication networks | SG2, SG3, SG12 |  | X | MSs |  |  |  | X |  |  |  |  |  |
| Resolution 31 – Admission of entities or organizations to participate as Associates in the work of the ITU Telecommunication Standardization Sector |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Resolution 32 – Strengthening electronic working methods for the work of the ITU Telecommunication Standardization Sector |  | X | X | MSs, SMs, Associates |  |  |  | X |  | X |  |  |  |
| Resolution 34 – Voluntary contributions |  |  | X | MSs, SMs, Associates |  |  |  |  |  |  |  |  |  |
| Resolution 40 – Regulatory and policy aspects of the work of the ITU Telecommunication Standardization Sector | SGs | X |  | MSs |  |  |  |  |  | X |  | X |  |
| Resolution 43 – Regional preparations for world telecommunication standardization assemblies |  |  | X | MS |  | SecGen | SecGen, RTOs, MSs | X | X |  | X |  |  |
| Resolution 44 – Bridging the standardization gap between developing and developed countries | All SGs, regional groups | X | X ITU regional offices | MSs, SMs | X |  |  | X, ITU Academy | X | X | X | X | X |
| Resolution 47 – Country code top-level domain names | SG2 |  | X | MSs |  |  |  |  |  |  | X |  |  |
| Resolution 48 – Internationalized (multilingual) domain names | SG16, regional groups |  | X | MSs, SMs |  |  |  |  |  |  | X |  |  |
| Resolution 49 – ENUM | SG2 |  | X | MSs |  |  |  |  |  |  | X |  |  |
| Resolution 50 – Cybersecurity | All SGs, SG17 |  | X | MSs, SMs, Associates, academia |  | SecGen | GCA | ITU-D Question 3/2 | X | X | X |  |  |
| Resolution 52 – Countering and combating spam | SGs, SG17 |  | X | MSs, SMs, Associates, academia |  |  | GCA | X |  | X |  |  |  |
| Resolution 54 – Regional groups of study groups of the ITU Telecommunication Standardization Sector | all SGs, regional groups | X | X | Regions, MSs |  |  |  | X |  | X |  |  |  |
| Resolution 55 – Promoting a gender equality in ITU Telecommunication Standardization Sector activities | WISE |  | X | MSs, SMs |  | SecGen | SecGen |  |  | X |  | X |  |
| Resolution 58 – Encourage the creation of national Computer Incident Response Teams, particularly for developing countries | SG17 |  | X | MSs, SMs |  |  |  | X |  |  |  |  |  |
| Resolution 60 – Responding to the challenges of the evolution of the identification/numbering system and its convergence with IP-based systems / networks | SG2, SG13 |  |  | MSs, SMs |  |  |  |  |  |  |  |  |  |
| Resolution 61 – Countering and combating misappropriation and misuse of international telecommunication numbering resources | SG2, SG3 |  |  | MSs |  |  |  |  |  |  |  |  |  |
| Resolution 62 – Dispute settlement | SG3 |  | X | MSs |  |  |  |  |  |  | X |  |  |
| Resolution 64 – IP address allocation and facilitating the transition to and deployment of IPv6 | SG2, SG3 |  | X | MSs, SMs |  |  |  | X |  |  | X | X |  |
| Resolution 65 – Calling party number delivery, calling line identification and origin identification information | SG2, SG3, SG11, SG17 |  | X | MSs |  |  |  |  |  |  |  | X |  |
| Resolution 67 – Use in the ITU Telecommunication Standardization Sector of the languages of the Union on an equal footing and the Standardization Committee for Vocabulary | All SGs | X | X |  |  | CCV, SCV | CCV, SCV | X | X | X |  | X |  |
| Resolution 68 – Evolving role of industry in the ITU Telecommunication Standardization Sector |  |  | X | SMs |  |  | X |  |  | X |  | X |  |
| Resolution 69 – Non-discriminatory access and use of Internet resources and telecommunications/information and communication technologies |  |  | X | MSs, SMs, Associates, academia |  |  | SecGen | X | X | X | X | X |  |
| Resolution 70 – Telecommunication/information and communication technology accessibility for persons with disabilities and persons with specific needs | All SGs, SG16, JCA-AHF | X | X | MSs, SMs |  |  |  | X | X |  | X |  |  |
| Resolution 72 – Measurement and assessment concerns related to human exposure to electromagnetic fields | SG5 |  | X | MSs, SMs |  |  |  | X | X |  |  | X |  |
| Resolution 73 – Information and communications technologies, environment, climate change and circular economy | All SGs, SG5 | X | X | MSs, SMs, Associates |  | SecGen | SecGen | X | X | X | X | X |  |
| Resolution 74 – Enhancing participation of Sector Members from developing countries in the work of the ITU Telecommunication Standardization Sector |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Resolution 75 – The ITU Telecommunication Standardization Sector's contribution in implementing the outcomes of the World Summit on the Information Society, taking into account the 2030 Agenda for Sustainable Development | All SGs |  | X | MSs, SMs, Associates, academia |  |  | SecGen, CWG-WSIS& SDG, CWG-Internet |  |  |  | X |  |  |
| Resolution 76 – Studies related to conformance and interoperability testing, assistance to developing countries, and a possible future ITU mark programme | All SGs, SG11, ITU-T CASC |  | X | MSs, SMs | X |  |  | X |  |  | X |  |  |
| Resolution 77 – Enhancing the standardization work in the ITU Telecommunication Standardization Sector for software-defined networking | All SGs, SG13, JCA-SDN | X | X | MSs, SMs, Associates, academia |  |  |  |  |  |  |  |  |  |
| Resolution 78 – Information and communication technology applications and standards for improved access to e-health services | SG11, SG16, SG17, SG20 |  | X | MSs, SMs, academia |  |  |  | X | X |  |  |  |  |
| Resolution 79 – The role of telecommunications/ information and communication technologies in handling and controlling e-waste from telecommunication and information technology equipment and methods of treating it | SG5 |  | X | MSs, SMs, academia |  |  |  | X |  |  |  |  |  |
| Resolution 80 – Acknowledging the active involvement of the membership in the development of ITU Telecommunication Standardization Sector deliverables | All SGs | X | X | MSs |  |  |  |  |  |  |  |  |  |
| Resolution 83 – Evaluation of the implementation of resolutions of the World Telecommunication Standardization Assembly |  |  | X | MSs, SMs |  |  |  | X | X | X |  |  |  |
| Resolution 84 – Studies concerning the protection of users of telecommunication/information and communication technology services | All SGs, SG3, SG12, SG17 |  | X | MSs, SMs, Associates, academia |  |  |  | ITU-D SG1 |  |  |  |  |  |
| Resolution 85 – Strengthening and diversifying the resources of the ITU Telecommunication Standardization Sector |  |  | X |  |  |  |  |  |  |  | X |  |  |
| Resolution 86 – Facilitating the implementation of the Smart Africa Manifesto | All SGs |  | X |  |  |  |  | X |  |  |  |  |  |
| Resolution 87 – Participation of the ITU Telecommunication Standardization Sector in the periodic review and revision of the International Telecommunication Regulations |  | X | X | MSs, SMs |  |  |  |  |  |  | X |  |  |
| Resolution 88 – International mobile roaming | SG3 |  | X | MSs |  |  |  | X |  |  |  |  |  |
| Resolution 89 – Promoting the use of information and communication technologies to bridge the financial inclusion gap | All SGs |  | X | MSs, SMs, Associates |  | SecGen | SecGen | X | X |  | X | X |  |
| Resolution 90 – Open source in the ITU Telecommunication Standardization Sector | All SGs | X | X | MSs, SMs, Associates, academia |  |  |  |  |  | X |  |  |  |
| Resolution 91 – Enhancing access to an electronic repository of information on numbering plans published by the ITU Telecommunication Standardization Sector | SG2 |  | X | MSs, SMs, Associates, academia |  |  |  |  |  |  |  |  |  |
| Resolution 92 – Enhancing the standardization activities in the ITU Telecommunication Standardization Sector related to non-radio aspects of international mobile telecommunications | All SGs, SG3, SG5, SG11, SG12, SG13, SG15, SG17, JCA-IMT2020 | X | X | MSs, SMs, Associates, academia |  |  |  | X | X |  |  |  |  |
| Resolution 93 – Interconnection of 4G, IMT-2020 networks and beyond | SG2, SG3, SG11, SG13, SG17, |  | X | MSs, SMs |  |  |  |  |  |  | X |  |  |
| Resolution 94 – Standardization work in the ITU Telecommunication Standardization Sector for cloud-based event data technology | SG13, SG16, SG17, SG20 | X | X | MSs, SMs, Associates, academia |  |  |  |  |  |  |  |  |  |
| Resolution 95 – ITU Telecommunication Standardization Sector initiatives to raise awareness on best practices and policies related to service quality | All SGs, SG12, QSDG |  | X | MSs, SMs, Associates, academia |  |  | Regional offices | X |  |  |  |  |  |
| Resolution 96 – ITU Telecommunication Standardization Sector studies for combating counterfeit telecommunication/information and communication technology devices | All SGs, SG2, SG11, SG17, SG20 |  | X | MSs, SMs, Associates, academia |  |  |  | X | X |  | X |  |  |
| Resolution 97 – Combating mobile telecommunication device theft | All SGs, SG11, SG17 |  | X | MSs, SMs |  |  |  | X | X |  |  |  |  |
| Resolution 98 – Enhancing the standardization of Internet of things and Smart Cities and Communities for global development | SG20, JCA-IoT and SC&C), |  | X | membership |  |  | JCA-IoT and SC&C, U4SSC | X | X |  |  | X |  |
| Resolution 99 – Consideration of organizational reform of the ITU Telecommunication Standardization Sector study groups | SGs | X | X | MSs, SMs |  |  |  |  |  | X |  | X |  |
| Resolution 100 – A common emergency number for Africa |  |  | X | MSs |  |  |  | X |  |  |  | X |  |
| Opinion 1 – Practical application of network externality premium | SG3 |  |  | MSs |  |  |  |  |  |  |  |  |  |

Legend:

*	Numbers in the Resolution Number column are hyperlinked to the full texts of the published Resolutions

**	The Resolution titles are hyperlinked to the status reports in this document below

GCA		: Global Cybersecurity Agenda

GenSec	: General Secretariat

ICG		: intersector coordination group

IRG		: intersector rapporteur group

ISCG		: Inter-Sector Coordination Group

ISC-TF	: Inter-Sector Coordination Task Force

MS		: Member States

PP			: Plenipotentiary Conference

RTO		: Regional Telecommunication Organization

SecGen	: ITU Secretary-General

SG		: Study Group

SM		: Sector Member

The Action Plan for WTSA-20 Resolutions and Opinion includes references and linkages ITU-T documents and activities, and also to documents and activities of Council, Plenipotentiary Conference and the other Sectors. These references and links are updated with each update to the Action Plan.

» Top

# Section II - Progress reports on implementation of the WTSA-20 Resolutions and Opinion

This section of the report shows the name of each WTSA-20 Resolution/Opinion, followed by the text of the "operative" portion of the Resolution, i.e., the resolves, calls upon, instructs, etc., a listing of the Action Items and due dates, with a column that indicates if a particular Action Item is ongoing by nature that has met periodic goals, and another column that indicates if a particular Action Item has been completed. Further on in each section, detailed information on the status of each Action Item is/will be provided. The section remains empty in case, where no (new) information is available, or nothing could be reported.

# Resolution 1 - Rules of procedure of the ITU Telecommunication Standardization Sector

resolves

that the provisions referred to in considering e) to l) above shall be further elaborated by the provisions of this resolution and the resolutions to which they refer, bearing in mind that, in the case of inconsistency, the Constitution, the Convention, the ITRs and the General Rules of conferences, assemblies and meetings of the Union (in that order) shall prevail over this resolution.

5.17	The Director shall foster cooperation and coordination with the other standardization organizations for the benefit of all members and report to TSAG on these efforts.

7.4.1.3	Notification of the result [concerning Deletion of a Question between WTSAs] will be given in a circular, and TSAG shall be informed by the Director. In addition, the Director shall publish a list of deleted Questions whenever appropriate, but at least once by the middle of a study period.

9.8.2.2	Notification of the result [ref. Deletion of Recommendations between WTSAs] shall be included in another circular, and TSAG shall be informed by a report from the Director. In addition, the Director shall publish a list of deleted Recommendations whenever appropriate, but at least once by the middle of a study period.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 01-01 | TSB to prepare agreement with host country for WTSA-24 (resolves) | One year before WTSA-24 | √ | √ |
|  | PP-22 decided that WTSA-24 will be hosted by India. Host country agreement was announced in ITU Council July 2023. |  |  |  |
| 01-02 | TSBDir to prepare proposal for organization and structure of WTSA-24 (resolves) | 3 months before WTSA-24 |  |  |
| 01-03 | TSBDir to prepare report to WTSA-24 (§1.1 h), 5.7, 5.8, 5.9, 5.10, 6.1) | WTSA-24 |  |  |
| 01-04 | All lead study groups shall inform TSAG on the progress of the work as defined in the scope of the lead study group activity. (Section 2.1.6) | TSAG 2024 | √ |  |
|  | - SG2 (eight LSG roles): SG2 sent its LSG reports to TSAG (ref. TSAG TDs 29, 199, 331). - SG3 (three LSG roles): SG3 sent its LSG reports to TSAG (ref. TSAG TDs 30, 200, 332). - SG5 (five LSG roles): SG5 sent its LSG reports to TSAG (ref. TSAG-TDs 31, 333). - SG9 (two LSG role): SG9 sent its LSG reports to TSAG (ref. TSAG TDs 32, 201, 334). - SG11 (four LSG roles): SG11 sent its LSG reports to TSAG (ref. TSAG TDs 33, 202, 335). - SG12 (three LSG roles): SG12 sent its LSG reports to TSAG (ref. TSAG TDs 34, 203, 336). - SG13 (four LSG roles): SG13 sent its LSG reports to TSAG (ref. TSAG-TDs 35, 204, 337). - SG15 (three LSG roles): SG15 sent its LSG reports (ref. TSAG TDs 36, 205, 338). - SG16 (seven LSG roles): SG16 sent its LSG reports (ref. TSAG TDs 346, 345, 339). - SG17 (three LSG roles): SG17 sent its LSG reports to TSAG (ref. TSAG-TDs 38, 206, 340). - SG20 (four LSG roles): SG20 sent its LSG reports to TSAG (ref. TSAG-TDs 39, 207, 341). |  |  |  |
| 01-05 | TSBDir to report on fostered cooperation and coordination with the other standardization organizations (clause 5.17) | TSAG 2024 | √ |  |
|  | - The IEC – IEC – ITU-T joint Smart City Task Force (J-SCTF) continues its coordination activities on smart cities. - The IEC – IEC – ITU-T Standards Programme Coordination group (SPCG) continues its coordination activities. - Many workshops are organized in collaboration with other SDOs. - Regional standards organizations (such as CEN-CENELEC, COPANT, PASC, ARSO and GSO, have been inviting ITU-T/TSB to present activities at their governance bodies and have invited TSB official to join some initiatives. - The African Organization for Standardization (ARSO) and the GCC Standardization Organization have joined ITU-T membership since 2021. - SG5 is exchanging liaisons with many organizations. Additionally, ITU-T SG5 develops technically aligned standards with ETSI TC Environmental Engineering. Furthermore, many of the SG5 experts attend other organizations’ meetings for better coordination and collaboration. - SG12 is exchanging liaisons with many organizations. In addition, many of the SG12 experts attend other organizations’ meetings for better coordination and collaboration. - SG13 exchanges liaison statements and regularly informs other SDOs about the start of the new work (to name few, 3GPP, ETSI, IETF, ISO/IEC JTC 1, BBF and MEF) JCA-IMT2020 and JCA-ML contribute to coordination of IMT-2020 and Beyond studies and those in the machine leaning area. SDO representatives are invited with talks to the workshops, organized by SG13 and the groups reporting to it. - SG15 is exchanging liaisons with many organizations. In addition, many of the SG15 experts attend other organizations’ meetings for better coordination and collaboration. |  |  |  |
| 01-06 | TSBDir to inform TSAG upon deleted Questions (clauses 7.5.1.3 and 9.8.2.2) | TSAG 2024 |  |  |
| 01-07 | TSBDir shall provide to WTSA (for information) a summary of the accounts for the years which have elapsed since the preceding WTSA, and the estimated expenses of ITU‑T to cover its financial requirements until the next WTSA for the subsequent biennial budgets and financial plan, as appropriate, taking into account the pertinent results of WTSA, including priorities. (clause 5.7) | WTSA-24 |  |  |
| 01-08 | TSBDir shall submit for preliminary examination by the Budget Control Committee, and thereafter for approval by WTSA, the accounts for expenses incurred for the current WTSA. (clause 5.8) | WTSA-24 |  |  |
| 01-09 | ITU-T study groups to submit their report (Part I, Part II) to WTSA no later than 35 calendar days before the opening of WTSA. (clause 2.4.1) | WTSA-24 |  |  |
| 01-10 | TSBDir shall submit to WTSA a report on the proposals that have been received from TSAG (see 4.9) concerning the organization, terms of reference and work programme of study groups and other groups for the next study period, as well as proposals on ways and means to increase ITU resources through ITU‑T. TSBDir may give views on these proposals (clause 5.9) | WTSA-24 |  |  |
| 01-11 | TSBDir shall supply administrations of Member States and Sector Members and other duly authorized entities taking part in the activities of ITU-T with a list of the study groups and other groups set up by WTSA, indicating the general areas of responsibility and the Questions that have been referred to the various groups for study (clause 5.12) | 2022 | √ | √ |
|  | Done with TSB Circular 1. |  |  |  |

» Top

# Resolution 2 - ITU Telecommunication Standardization Sector Study Group responsibility and mandates

resolves

1	that the mandate of each study group, which it shall use as the basis for organizing its study programme, taking into account recognizing a), b), c), and d) above, shall consist of:

–	a general area of responsibility, as set out in Annex A, within which the study group may amend existing Recommendations, in collaboration with other groups, as appropriate;

–	a set of Questions related to particular areas of study, which are compatible with the general area of responsibility and which should be results-oriented (refer to Section 7 of Resolution 1 (Rev. Geneva, 2022) of this assembly);

2	to encourage the study groups to consider collocation (e.g. of study group plenaries, working parties or rapporteur meetings) as a means to improve cooperation in some areas of work; the study groups involved will need to identify the areas in which they need to cooperate, based on their mandates, and keep TSAG and TSB informed;

3	to encourage ITU-T study groups to conduct work on how to ensure wider implementation of ITU-T Recommendations at the national level in collaboration with the ITU Telecommunication Development Sector (ITU-D) study groups;

instructs the Telecommunication Standardization Bureau

to support and facilitate the operational aspects of such collocation.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 02-01 | TSB Counsellors to insert pointer on Resolution 2 webpage to location of updated SG structure, mandate or Annex C information within one month of change. | 2022 |  | √ |
|  | An updated Annex C is available on the ITU-T website here: https://www.itu.int/en/ITU-T/about/Pages/res2-annexc-sp16.aspx. Updates are recorded on this page shortly after approval. Changes in mandate and lead SG roles are recorded directly under the "Mandate and lead roles" sub-page under each individual study group, http://itu.int/en/ITU-T/studygroups/2022-2024/xx/Pages/mandate.aspx, where xx=02, 03, 05, 09, 11, 12, 13, 15, 16, 17, 20. |  |  |  |
| 02-02 | Study groups to consider collocation (e.g. of study group plenaries, working parties or rapporteur meetings) as a means to improve cooperation in some areas of work; the study groups involved will need to identify the areas in which they need to cooperate, based on their mandates, and keep TSAG and TSB informed (resolves 2) | Ongoing | √ |  |
|  | - Q15/17 held collocated RG meetings on Quantum based security with Q16/13. |  |  |  |

» Top

# Resolution 7 - Collaboration with the International Organization for Standardization and the International Electrotechnical Commission

resolves

1	to request the Director of the Telecommunication Standardization Bureau (TSB) to report regularly to the Telecommunication Standardization Advisory Group (TSAG) on the status of collaboration with ISO and IEC;

2	to continue inviting ISO and IEC to examine, through TSAG, the ITU-T study programme in the early stages of its studies and vice versa, and to further examine such programmes to take into account ongoing changes, in order to identify subjects where coordination seems desirable for common and complementary work, and which would benefit the membership, and to inform the Director of TSB;

3	to request the Director of TSB, after consultation with the study group management team concerned, to reply, and to furnish any additional information requested by ISO and IEC, as it becomes available;

4	to invite the Director of TSB, at the request of Member States and Sector Members, in consultation with TSAG, to review the agreement between ISO/IEC and ITU-T, with a view to exploring options for accessing and publishing common texts, with a possible unified approach;

5	to request the Director of TSB to examine and update the programme of cooperation and priority of the study items among ITU-T, ISO and IEC and highlight this information on the ITU-T website on a regular basis;

6	to request the Director of TSB, the study groups and TSAG, as appropriate, to consider and propose further improvements to the procedures for cooperation between ITU-T and ISO and IEC;

7	that the necessary contacts with ISO and/or IEC (including ISO/IEC JTC 1) at the appropriate levels and coordination methods should be mutually agreed and regular coordination events arranged:

•	for work where text should be drawn up mutually and kept aligned, procedures in accordance with Recommendation ITU-T A.23 and the Guidelines for Cooperation therein apply;

•	for other activities where coordination between ITU-T and ISO and IEC is required (for example in relation to any mutual agreements, such as the Memorandum of Understanding on standardization in the field of electronic business), clear means of coordination shall be established and regular coordination contacts made;

8	to request the chairmen of study groups to take into account the related work programmes and the progress of projects in ISO, IEC and ISO/IEC JTC 1; further, to cooperate with these organizations as widely as possible and by appropriate and balanced means, in order to:

•	ensure that the specifications which have been jointly drawn up remain aligned;

•	collaborate in drawing up other specifications in fields of shared interest;

9	that, for reasons of economy, any necessary collaborative meetings take place to the extent possible in association with other relevant meetings;

10	that the report concerning such coordination indicate the status of alignment and compatibility of draft texts on points of shared interest, in particular identifying cases where cross-referencing would be helpful to users of published International Standards and Recommendations;

11	to invite administrations to contribute significantly to the coordination between ITU-T on the one hand and ISO and IEC (including ISO/IEC JTC 1) on the other by ensuring adequate coordination of national activities associated with the three organizations.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 07-01 | TSBDir to consult with ISO and IEC on work programmes and follow through with study group management team. (resolves 2, 3, 5) | Ongoing | √ |  |
|  | The World Standards Cooperation (WSC) meets annually in the February timeframe. In addition, the TSB Director, ISO Secretary General and IEC General Secretary meet periodically (two-three times a year) to discuss cooperation topics. - WSC meetings: - The 21st meeting of the IEC/ISO/ITU World Standards Cooperation took place on 25 February 2022, virtual. - World Standards Day - The theme of World Standards Day 2022 (14 October 2022) was “Shared vision for a better world”. - Academia - The Joint IEC-ISO-ITU Smart Cities Task Force (J-SCTF) has held the following meetings: - Virtual, 10 and 12 May 2022 - Korea, 28-30 November 2022 - Geneva, 27-28 January 2023 - Geneva, 27-28 March 2023 - Virtual, 10-11 July 2023 - Virtual, 2-3 November 2023 - During COP28, within the ITU Green Digital Action track the WSC organized a session on The WSC’s session on International Standards for sustainable digital tech. This session aimed to spotlight how sustainability principles inform the design of international standards for digital tech. The session concluded with a joint statement by World Standards Cooperation on the importance of sustainability being built into technical standards’ development by design, and standards helping the world to reach net-zero emissions and achieve a resource-efficient circular and low-carbon economy. - SG5 continues to liaise with IEC and ISO. - SG12 is regularly exchanging liaisons with IEC and ISO/IEC JTC 1. - SG13 regularly exchanges liaison statements with ISO/IEC JTC 1 and receives the reports about the ISO/IEC JTC 1 work progress from its Liaison Rapporteur. - SG15 appointed liaison rapporteurs to IEC TC86. SG15 is regularly exchanging liaisons with IEC and ISO/IEC JTC 1. - SG17 continues to work jointly with several ISO TCs, IEC TCs and ISO/IEC JTC 1/SCs on work items of common interest. SG17 appointed liaison rapporteurs to IEC TCs 25 and 57; ISO TCs 12, 204, 215, 292 and 307; ISO/IEC JTC 1/SCs 6, 7, 17, 25, 27, 31, 37, 38, 41 and 42. - SG20 continues to liaise with IEC, ISO and ISO/IEC JTC 1. |  |  |  |
| 07-03 | TSB, in consultation with the study groups, to update programme of cooperation and priority among ITU-T, ISO and IEC, and update website (resolves 2, 5) | Ongoing | √ |  |
|  | The work programme database is regularly updated. |  |  |  |
| 07-05 | TSBDir to review the agreement between ISO/IEC and ITU-T, with a view to exploring options for accessing and publishing common texts, including a possible unified approach (only upon request of a Member State) (resolves 4) | Ongoing | √ |  |
|  | No such requests have been received so far. |  |  |  |
| 07-06 | TSBDir, the study groups and TSAG to consider and propose further improvements to the procedures for cooperation between ITU-T and ISO and IEC (resolves 6) | Ongoing | √ |  |
|  | WTSA-20 revised Resolution 7 (Rev, Geneva 2022), which yields improved cooperation with IEC and ISO. Annex A to Recommendation ITU-T A.23 is implemented by SG17. SG17 expects its work on registration authorities will be useful to TSAG in updating Annex A of ITU-T A.23. |  |  |  |
| 07-07 | TSB to establish/maintain the necessary contacts with ISO and/or IEC should be at the appropriate levels and coordination methods should be mutually agreed and regular coordination events arranged (resolves 7) | Ongoing | √ |  |
|  | World Standards Collaboration (WSC) meetings, IEC-ISO-ITU-T Standards Programme Coordination Group (SPCG), IEC-ISO-ITU Joint Task Force on Smart Cities (J-SCTF), and regular meetings of the ISO/IEC/ITU/UNECE MoU/MG on e-business facilitate coordination and allow to establish necessary contacts among the secretariats and groups. A liaison officer is appointed from TSAG to ISO/IEC JTC 1. TSAG delegated Mr Olivier DUBUISSON(Orange) as ITU-T Liaison Officer to IEC/SMB/SG12 “Digital Transformation and Systems Approach”. He is also the ITU-T representative in the IEC-ISO-ITU-T-UNECE MoU on electronic business. |  |  |  |
| 07-08 | The chairmen of study groups to take into account the related work programmes and the progress of projects in ISO, IEC and ISO/IEC JTC 1; further, to cooperate with these organizations as widely as possible and by appropriate means (resolves 8) | Ongoing | √ |  |
|  | SG5 continues to liaise with ISO and IEC through sharing information on relevant work items. SG12 is regularly exchanging liaisons with IEC and ISO/IEC JTC 1. SG13 has dedicated Liaison Rapporteurs for four committees and working groups of ISO/IEC JTC 1. It reviews the reports on progress in these committees upon submission. SG15 appointed liaison rapporteurs to IEC TC86. SG15 is regularly exchanging liaisons with IEC and ISO/IEC JTC 1. SG17 liaises with many groups in ISO, IEC and ISO/IEC JTC 1. The SG17 Chairman and other leaders participate in ISO/IEC JTC 1/SC27 and other groups. SG17 has many approved common text Recommendations with ISO/IEC. SG20 continues to liaise with ISO, IEC and ISO/IEC JTC 1 through sharing information on relevant work items. |  |  |  |
| 07-09 | SGs, for reasons of economy, any necessary collaborative meetings to take place to the extent possible in association with other relevant meetings (resolves 9) | Ongoing | √ |  |
|  | Q11/17 meets collaboratively with ISO/IEC JTC 1/SC 6/WG10. |  |  |  |
| 07-10 | TSBDir to report regularly to TSAG on the status of collaboration with ISO and IEC (resolves 1) | TSAG 2024 | √ |  |
|  | Done through reports to TSAG by - IEC – ISO – ITU-T Standards Programme Coordinate Group (SPCG) in TSAG-TD43, - IEC – ISO – ITU-T Joint Task Force on Smart Cities (J-SCTF) in TSAG-TD46, - Reports by the ITU-T Lead study groups (where applicable, e.g., SG17). - TSB Director activity report (TSAG-TD20). |  |  |  |

» Top

# Resolution 11 - Collaboration with the Postal Operations Council of the Universal Postal Union in the study of services concerning both the postal and the telecommunication sectors

resolves

that the relevant study groups of the ITU Telecommunication Standardization Sector (ITU-T) should continue to collaborate with the Postal Operations Council (POC) committees as necessary, on a reciprocal basis and with a minimum of formality, in particular by investigating issues of common interest such as quality of service (QoS), quality of experience (QoE), electronic services and security, digital financial services and transaction costs of mobile payment,

instructs the Director of the Telecommunication Standardization Bureau

1	to encourage and assist this collaboration between the two organs;

2	to consult with UPU on the establishment of a joint working group between ITU and UPU on digital financial services to share lessons learned through the implementation of projects in the area of digital financial inclusion in order to drive standardization activities in both organizations.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 11-01 | ITU-T SGs to collaborate with the UPU POC committees on issues of common interest (resolves) | Ongoing | √ |  |
|  | Collaboration between UPU and ITU-T takes place at the secretariat-level: - UPU participates in the annual MoU/MG on e-business. - In May 2022, UPU and ITU Secretary Generals met. - At a meeting with UPU Secretariat in 2016 to discuss the setting up of the working group on Digital Financial services, it was mentioned by UPU that the POC is composed of Member States and it would not be feasible to have such a working group with ITU. It was then agreed that ITU and UPU secretariats would meet regularly (quarterly) to discuss and coordinate on digital financial services activities. These quarterly meetings are held with ITU and UPU to discuss different activities on digital financial services and are ongoing. - In 2023, ITU DFS Security Lab had three meetings with UPU to share information about the DFS Security Lab facilities and the security tests that could be undertaken for mobile payment apps used by Posts for mobile money services. A DFS Security Clinic was conducted by the DFS Security Lab team for UPU Secretariat on 19 June 2023. A plan of work for conducting tests on mobile payment apps used by Posts for mobile money services and investigating use of blockchain secure authentication for posts mobile money services are planned in 2024. |  |  |  |

» Top

# Resolution 18 - Principles and procedures for the allocation of work to, and strengthening coordination and cooperation among, ITU Radiocommunication, ITU Telecommunication Standardization and ITU Telecommunication Development Sectors

resolves

1	that the Radiocommunication Advisory Group (RAG), TSAG and the Telecommunication Development Advisory Group (TDAG), meeting jointly as necessary, shall continue the review of new and existing work and its distribution among ITU-R, ITU-T and ITU-D, for approval by Member States in accordance with the procedures laid down for the approval of new and/or revised Questions;

2	that, if considerable responsibilities in any two or all Sectors in a particular subject are identified:

i)	the procedure given in Annex A to this resolution should be applied; or

ii)	the matter should be studied by relevant study groups of the Sectors involved, with appropriate coordination and matching of relevant Question topics of interest to the study groups in ITU-T, ITU-D and ITU-R (see Annexes B and C to this resolution); or

iii)	a joint meeting may be arranged by the Directors of the Bureaux involved.

invites

1	RAG, TSAG and TDAG to continue to assist ISCG in the identification of subjects of mutual interest to the three Sectors and mechanisms to enhance their cooperation and collaboration;

2	the Directors of the Radiocommunication (BR), Telecommunication Standardization (TSB) and Telecommunication Development (BDT) Bureaux and ISC-TF to report to ISCG and the respective Sector advisory groups on options for improving cooperation at the secretariat level to ensure that close coordination is maximized,

instructs

1	the ITU-T study groups to continue cooperation with the study groups of the other two Sectors so as to avoid duplication of effort and proactively make use of the results of work done by the study groups of those two Sectors;

2	the Director of TSB to report annually to TSAG on the results of the implementation of this resolution.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 18-01 | TSAG to continue to review work and its distribution and possible coordination between ITU-T, ITU-D, and ITU-R (resolves 1) | Ongoing | √ |  |
|  | The updated Inter-Sector mapping tables (ITU-T – ITU-R, ITU-D – ITU-T) are found on the ISCG web page for ongoing review and updating by the Secretariats and respective study groups. |  |  |  |
| 18-02 | TSAG to continue to assist ISCG in the identification of subjects common to the three Sectors and mechanisms to enhance their cooperation and collaboration. (invites 1) | Ongoing | √ |  |
|  | See 18-01, 18-03. The inter-Sector coordination group (ISCG) on issues of mutual interest is composed by representatives of all three advisory groups, and works to identify subjects common to the three Sectors. It also seeks to identify the necessary mechanisms to strengthen the cooperation and joint activity among the three Sectors, with particular emphasis on the interests of developing countries. In addition, the ITU Inter-Sectoral Coordination Task Force (ISC-TF) is coordinating activities among the three Bureaux. TSAG, through its appointed new team of representatives to ISCG, assists in actively conducting ITU Inter-Sector coordination. The appointed TSAG representatives to ISCG are: Mr Abdurahman AL HASSAN (TSAG Chairman), Mr Dominique WÜRGES (ITU-T SG5 Chairman), and Mr Noah LUO (ITU-T SG16 Chairman); Mr Phil RUSHTON is the TSAG Representative to ITU Inter-Sector Coordination Group (ISCG) on remote participation. |  |  |  |
| 18-03 | ITU-T SGs to continue cooperation with the study groups of the other two Sectors so as to avoid duplication of effort and proactively make use of the results of work done by the study groups of those two Sectors. (instructs 1) | Ongoing | √ |  |
|  | Collaboration with ITU-R and with ITU-D is a standing agenda point of TSAG, where TSAG examines existing methods and approaches to collaboration and/or cooperation with other sectors, with the view to encouraging ITU-T to work more collaboratively and/or cooperatively in a reciprocal manner, and review is performed on a regular basis based on information received. Three inter-Sector Rapporteur groups (IRGs) were created to work on items of interests to various ITU-T and ITU-R study groups. - IRG-AVA: Intersector Rapporteur Group Audiovisual Media Accessibility, amongst ITU-T SG9, ITU-T SG16 and ITU-R SG6; - IRG-AVQA: Intersector Rapporteur Group Audiovisual Quality Assessment, amongst ITU-T SG12 and ITU-R SG6; - IRG-IBB: Intersector Rapporteur Group Integrated Broadcast-Broadband, between ITU-T SG9, ITU-T SG16 and ITU-R WP 6B. NOTE: IRG-IBB decided to terminate its mandate at the end of this Study Period, the collaboration on IBB topics will continue with usual liaison exchanges between ITU-T SG9, SG16 and ITU-R SG6. - SG3 collaborates with ITU-D Study Groups 1 and 2 as appropriate. - SG5 continues to send liaison statements to ITU-D and ITU-R related to new and existing work items. - SG13 works closely with ITU-R WP 5D on IMT-2030 related issues, it exchanges liaison statements with ITU-R SG4 (on fixed, mobile and satellite convergence issues), ITU-D SGs 1 and 2. - SG15 and SG17 liaise with ITU-R SGs and ITU-D SGs as appropriate. - SG20 continues to send liaison statements to ITU-D and ITU-R related to new work items and other matters. |  |  |  |
| 18-04 | TSBDir to report annually to TSAG on the results of the implementation of this resolution. (instructs 2) | Ongoing | √ |  |
|  | Accomplished through this document. |  |  |  |
| 18-05 | This resolution should also be brought to the attention of the ITU Radiocommunication and Telecommunication Development Sectors (footnote). | 2022 |  | √ |
|  | BDT and BR were informed. |  |  |  |
| 18-06 | TSAG shall continue to consider current and new activities and their distribution among ITU-R, ITU-T and ITU-D for approval by the ITU Member States in accordance with the procedures for approval of new and revised questions, meeting jointly as necessary (PP-22 Res.191 resolves 1). | Ongoing | √ |  |
|  | TSAG sent liaison reply (in TSAG-OLS07) to ITU-T SG13 on new Question 10/13. SG13 acted accordingly. TSAG undertook the revision of mapping ITU-R, ITU-D Questions to those of ITU-T. Each SG contributed to this review. |  |  |  |
| 18-07 | TSAG to continue to assist ISCG in identifying subjects of mutual interest to the three Sectors and mechanisms to enhance their cooperation and collaboration paying particular attention to the interests of the developing countries (PP-22 Res.191 invites). | Ongoing | √ |  |
|  | TSAG sent OLS3 on updated guidelines for remote participation and appointment of representative to ISCG. The ISCG inter-Sector mapping tables were updated. |  |  |  |

» Top

# Resolution 20 - Procedures for allocation and management of international telecommunication numbering, naming, addressing and identification resources

resolves to instruct

1	the Director of TSB, before assigning, reassigning and/or reclaiming international telecommunication NNAI resources, to consult:

i)	the chairman of Study Group 2, in liaison with the chairmen of the other relevant study groups, or if needed the chairman's delegated representative to resolve requirements as specified in relevant ITU-T Recommendations; and

ii)	the relevant administration(s); and/or

iii)	the authorized applicant/assignee when direct communication with TSB is required in order to perform its responsibilities.

in the Director's deliberations and consultations, the Director will consider the general principles for the allocation of NNAI resources, and the provisions of the relevant Recommendations in the ITU-T E-, ITU-T F-, ITU-T Q-, ITU-T X- and ITU-T Y-series, and those to be further adopted;

2	Study Group 2, in liaison the other relevant study groups, to provide to the Director of TSB advice on technical, functional and operational aspects in the assignment, reassignment and/or reclamation of international telecommunication NNAI resources in accordance with the relevant Recommendations, taking into account the results of any ongoing studies, information and guidance in cases of reported complaints about misuse of international telecommunication NNAI resources;

3	the Director of TSB, in close collaboration with Study Group 2, and any other relevant study groups, to follow up with the administrations involved on the misuse of any international telecommunication NNAI resources and inform the ITU Council accordingly;

4	the Director of TSB to encourage all relevant study groups to study the impact of new and emerging telecommunications/ICTs on the allocation and management of international telecommunication NNAI resources;

5	the Director of TSB to take the appropriate measures and actions where Study Group 2, in liaison with the other relevant study groups, has provided information, advice and guidance in accordance with resolves to instruct 2 and 3 above;

6	Study Group 2 to continue to study necessary action to ensure that the sovereignty of ITU Member States with regard to country code NNAI plans is fully maintained, including ENUM as enshrined in Recommendation ITU-T E.164 and other relevant Recommendations and procedures; this shall cover ways and means to address and counter any misuse of any international telecommunication NNAI resources.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 20-01 | TSBDir to use procedures in relevant Recommendations upon receipt of new numbering, naming, addressing and identification resource requests (resolves 1) | Ongoing | √ |  |
|  | The Director has been following the relevant Recommendations in his deliberations and consultations for assigning, reassigning and/or reclaiming international NNAI. |  |  |  |
| 20-02 | SG2, in liaison with the other relevant SGs, to provide TSBDir with advice and guidance related to Resolution 20 (resolves 2) | Ongoing | √ |  |
|  | The Director has been advised by SG2 experts and by the Numbering Coordination Team on matters related to the allocation and management of international numbering resources. |  |  |  |
| 20-03 | TSBDir, in close collaboration with SG2 and other relevant study groups, to follow-up with the administrations involved on misuse of international telecommunication NNAI resources and inform Council accordingly (resolves 3) | Council 2024 | √ |  |
|  | See 61-02. |  |  |  |
| 20-04 | SG2 to continue to study necessary action to ensure sovereignty of ITU Member States with regard to international telecommunication country code NNAI plans is maintained, including ENUM (resolves 5) | Ongoing | √ |  |
|  | Notifications of national numbering/identification plan update and assignment or reclamation of national numbering/identification resources were received and published in the ITU Operational Bulletin and ITU website. The ITU Operational Bulletin is published in the six official languages of the Union. |  |  |  |
| 20-05 | TSBDir to encourage all relevant study groups to study the impact of new and emerging telecommunications/ICTs on the allocation and management of international telecommunication NNAI resources (resolves 4) | Ongoing |  |  |

» Top

# Resolution 22 - Authorization for Telecommunication Standardization Advisory Group to act between world telecommunication standardization assemblies

resolves

1	to assign to TSAG the following specific matters within its competence between this assembly and the next assembly to act in the following areas in consultation with the Director of TSB:

a)	maintain and provide up-to-date, efficient and flexible working guidelines;

b)	promote high-priority standardization activities related to technical, operating and tariff questions on the basis of contributions submitted by the membership from a global viewpoint and to coordinate among ITU-T study groups in this regard;

c)	assume responsibility, including development and submission for approval under appropriate procedures, for the ITU-T A-series Recommendations;

d)	restructure and establish ITU-T study groups, taking into account the needs of the ITU-T membership and in response to changes in the telecommunication/ICT marketplace, and assign chairmen and vice-chairmen to act until the next WTSA in accordance with Resolution 208 (Dubai, 2018) of the Plenipotentiary Conference;

e)	issue advice on study group schedules to meet standardization priorities;

f)	while recognizing the primacy of the study groups in carrying out the activities of ITU-T, create, terminate or maintain other groups, including focus groups, appoint their chairmen and vice-chairmen, and establish their terms of reference with a defined duration, in accordance with Nos. 191A and 191B of the Convention, in order to enhance and improve the effectiveness of ITU-T's work as well as promoting flexibility in responding rapidly to high-priority issues; such groups shall not adopt Questions or Recommendations, in accordance with Article 14A of the Convention, but work on a specific mandate;

g)	identify changing requirements and provide advice on appropriate changes to be made to the priority of work in ITU-T study groups, planning and allocation of work between study groups, having due regard for the cost and availability of resources;

h)	take an active role in ensuring coordination among ITU-T activities, particularly on standardization issues that are being studied in more than one group;

i)	review reports of and consider appropriate proposals made by coordination groups and other groups, and implement those that are agreed;

j)	identify requirements and provide determination on appropriate changes to be made where overlapping issues arise, which includes, but is not limited to, assignment of a mandate to a study group to lead on coordination work;

k)	establish the appropriate mechanism and encourage the utilization, for example, of coordination groups or other groups, to address key topics of work which span several study groups, with a view to ensuring effective coordination of standardization topics in order to achieve suitable global solutions;

l)	review progress in the implementation of the ITU-T work programme, including fostering coordination and collaboration with other relevant bodies such as standardization organizations, forums and consortia outside of ITU;

m)	cooperate and coordinate with ITU-R and ITU-D and with other, external, standardization bodies;

n)	advise the Director of TSB on financial and other matters;

o)	approve the programme of work arising from the review of existing and new Questions and determine the priority, urgency, estimated financial implications and time-scale for the completion of their study;

p)	group, as far as practicable, Questions of interest to developing countries, including the least developed countries, small island developing states, landlocked developing countries and countries with economies in transition, in order to facilitate their participation in these studies;

q)	address other specific matters within the competence of WTSA, subject to the approval of Member States, using the approval procedure contained in Resolution 1 (Rev. Geneva, 2022) of this assembly, Section 9;

r)	take into account the interests of developing countries and encourage and facilitate their involvement in these activities,

2	that TSAG examine implementation of the actions and achievement of the goals as reflected in the annual ITU-T operational plan and in the WTSA-20 Action Plan, which includes the WTSA resolutions, for the purpose of identifying possible difficulties and possible strategies for implementing key elements, and recommending solutions to the Director of TSB regarding them;

3	that revisions to the relevant procedures for the adoption of Questions and Recommendations by study groups, other than those referred to in Nos. 246D, 246F and 246H of the Convention, may be initiated by TSAG for approval by Member States between WTSAs, using the approval procedure contained in Resolution 1 (Rev. Geneva, 2022) of this assembly, Section 9;

4	that TSAG provide liaison on its activities to relevant organizations outside ITU in consultation with the Director of TSB, as appropriate;

5	that TSAG consider the implications, for ITU-T, of market needs and new and emerging technologies that have not yet been considered for standardization by ITU-T, establish an appropriate mechanism to facilitate the examination of their consideration, for example assigning Questions, coordinating the work of study groups or establishing coordination groups or other groups, and appoint their chairmen and vice-chairmen;

6	that TSAG review and coordinate standardization strategies for ITU-T by identifying the main technological trends and market, economic and policy needs in the fields of activity relevant to the mandate of ITU-T, and identify possible topics and issues for consideration in ITU-T's standardization strategies;

7	that TSAG establish an appropriate mechanism to facilitate standardization strategies, for example assigning Questions, coordinating the work of study groups or establishing coordination groups or other groups, and appoint their chairmen and vice-chairmen;

8	that TSAG consider the result of this assembly concerning GSS and take follow-up actions, as appropriate;

9	that a report on the above TSAG activities shall be submitted to the next WTSA.

instructs the Director of the Telecommunication Standardization Bureau

1	to take into consideration the advice and guidance of TSAG in order to improve the effectiveness and efficiency of ITU-T;

2	to provide to each TSAG meeting a report on:

-	the implementation of WTSA resolutions and actions to be undertaken pursuant to their operative paragraphs;

-	the progress of the ITU-T annual operational plan and WTSA-20 Action Plan, identifying difficulties, if any, that hinder the progress, and possible solutions;

3	to provide information about any work item that has not given rise to any contribution in the time interval of the previous two study group meetings through his or her report about study group activity;

4	to report to TSAG on the experience in the implementation of the A-series Recommendations for consideration by the ITU-T membership.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 22-01 | TSAG to consider results of WTSA concerning GSS, for appropriate action (resolves 8) | TSAG 2024 | √ |  |
|  | The WTSA-20 conclusions of the fourth Global Standards Symposium (GSS-20), which was held prior to WTSA-20 are contained in WTSA-20 C43 for further consideration. More information is available here. TSAG took note of the report (in TSAG-D022) of the Global Standards Symposium (GSS-20) and the World Telecommunication Standardization Assembly (WTSA-20). |  |  |  |
| 22-02 | TSAG to establish an appropriate mechanism to examine and coordinate work on new and emerging technologies (resolves 5) | TSAG2022 |  | √ |
|  | An Associate Rapporteur (Mr Arnaud TADDEI) on emerging technologies was appointed under the TSAG Rapporteur Group Industry Engagement, Metrics (RG-IEM) with the objective to examine and coordinate work on new and emerging technologies. A study was started and proposed in RG-IEM. |  |  |  |
| 22-03 | TSAG report on its activities to WTSA-24 (resolves 9) | Last TSAG before WTSA-24 WTSA-24 |  |  |
| 22-04 | TSAG to examine implementation of the actions and achievement of the goals as reflected in the annual ITU-T operational plan and in the WTSA-20 Action Plan (resolves 2) | TSAG 2024 | √ |  |
|  | Continuously done through this action plan document. In addition, a specific TSAG action plan for the 2022-2024 study period was developed in TSAG-TD65-R1. |  |  |  |
| 22-05 | TSAG to review and coordinate standardization strategies for ITU-T by identifying the main technological trends and market, economic and policy needs in the fields of activity relevant to the mandate of ITU-T, and identify possible topics and issues for consideration in ITU-T’s standardization strategies (resolves 6) | TSAG 2024 | √ |  |
|  | This instruction was given to RG-IEM as action 3 as a package with resolve 5 and 7 under the purview of M. Arnaud Taddei. As the study started, in the meantime a TSAG Rapporteur on Strategic & Operational Plan (R-SOP) (Mr Víctor MARTÍNEZ VANEGAS, Mexico) was appointed, to collect and provide appropriate input from TSAG for consideration of the Council Working Group for the elaboration of the draft strategic plan. Also, TSAG established a Rapporteur Group on Industry Engagement, Metrics (RG-IEM) to review and analyse outcomes of former RG-StdsStrat (e.g. metrics, statistics), and to develop a plan to attract intensive industry participation in order to take account of latest technical trends and market needs. TSAG 2022 called for contributions. The ITU Focus Group on metaverse (FG-MV) has been established under the Telecommunication Standardization Advisory Group (TSAG) on 16 December 2022. The FG-MV lays the groundwork for international standards for the metaverse. The group will analyse the technical requirements of the metaverse to identify fundamental enabling technologies in areas from multimedia and network optimization to digital currencies, Internet of Things, digital twins, and environmental sustainability. The following meetings took place: - Riyadh, 8-9 March 2023 - Shanghai, 4-6 July 2023 - Geneva, 3-5 October 2023 ​ - Geneva, 4-7 December 2023 The FG-MV established nine Working Groups, ranging from General, Applications & Services, Architecture & Infrastructure, Virtual/Real World Integration, Interoperability, Security, Data & Personally identifiable information Protection, Economic, Regulatory & Competition Aspects, to Sustainability, Accessibility & Inclusion and Collaboration. The workplan is available HERE. The list of completed deliverables is available HERE. |  |  |  |
| 22-06 | TSAG to establish an appropriate mechanism to facilitate standardization strategies, for example assigning Questions, coordinating the work of study groups or establishing coordination groups or other groups, and appoint their chairmen and vice-chairmen (resolves 7) | TSAG 2024 | √ |  |
|  | See 22-05. This instruction was given to RG-IEM as action 3 as a package with resolve 5 and 7 under the purview of M. Arnaud Taddei. As the study started, in the meantime TSAG RG-WPR is reviewing the lead study group reports, and is assisting in coordination among the Questions of the ITU-T study groups. TSAG, at its first meeting, endorsed the continuation of the JCAs, and established new ITU-T Joint Coordination Activity on Quantum Key Distribution Network (ITU-T JCA-QKDN) with JCA-QKDN leadership, with TSAG as parent. |  |  |  |
| 22-07 | TSBDir to provide to each TSAG meeting a report on the implementation of WTSA resolutions and actions to be undertaken pursuant to their operative paragraphs, and on the progress of the ITU-T annual operational plan and WTSA-20 Action Plan, identifying difficulties, if any, that hinder the progress, and possible solutions (instructs TSBDir 2) | TSAG 2024 | √ |  |
|  | This document is tracking progress in the implementation of the operational parts within all WTSA-20 Resolutions. TSAG-TD24, TSAG-TD191were presented at the TSAG 2022, 2023 meetings. TSAG-TD410 will be presented to the TSAG 2024 meeting. |  |  |  |
| 22-08 | TSBDir to provide information about any work item that has not given rise to any contribution in the time interval of the previous two study group meetings through his or her report about study group activity (instructs TSBDir 3) | TSAG 2024 | √ |  |
|  | Study Groups monitor the list of stale work items based on a report provided by the SG secretariat at each study group meeting, or on request of the SG management. TSAG sent OLS 006 to all study groups reminding their duties to follow-up on stale work items. TSAG compiles the statistics of the ITU-T study groups which includes the report on the stale work items (TSAG-TD25, TSAG-TD193, TSAG-TD411). |  |  |  |
| 22-09 | TSBDir to report to TSAG on the experience in the implementation of the A-series Recommendations for consideration by the ITU-T membership (instructs TSBDir 4) | TSAG 2024 |  |  |
| 22-14 | TSBDir to bring draft new Resolution [IAP-3], Use of in-person and virtual options on an equal footing in the activities of the ITU Telecommunication Standardization Sector, to the attention of the TSAG AHG-GME, to the Council, and to the Plenipotentiary Conference. | TSAG2022, Council 2022, PP22 |  | √ |
|  | Council 2022 was informed in C22/24-R1. PP-22 received C-71. TSAG AHG-GME received DOC26. |  |  |  |
| 22-15 | ITU-T Study Group 3 to consider the proposed new Question on OTTs (in AFCP/35A33/1). | Ongoing |  | √ |
|  | The May 2022 SG3 meeting considered this proposal (SG3-C2, and SG3-C15). The conclusions are reflected in SG3-R1. |  |  |  |
| 22-16 | WTSA-20 invites TSAG to continue studying ITU-T A.7 related issues. | Ongoing | √ |  |
|  | TSAG (within RG-WM) is studying matters related to the ITU-T A-series texts within RG-WM. |  |  |  |
| 22-17 | WTSA-20 included the text of the draft new Resolution on pandemic (see Annex 1) into the final WTSA report, and invited the Plenipotentiary Conference to consider the text in Annex 1 and take any necessary actions on this matter, as appropriate. (WTSA-20 Action 1) | PP22 |  | √ |
|  | C-43 was submitted and submitted to PP-22. PP-22 results are reflected in Resolution 167 (Rev., Bucharest 2022) (C-198) and in COM5 recommendation#2 (C-189). |  |  |  |
| 22-18 | TSBDir is instructed to inform the Directors of the other two Bureaux on the above request in 22-17 to the Plenipotentiary Conference for necessary coordination. (WTSA-20 Action 2) | 2022 |  | √ |
|  | C-43 was coordinated through the ITU GBS. |  |  |  |
| 22-19 | WTSA-20 to forward the text on “SMART Submarine Cable Systems” to TSAG for coordination and to the relevant study groups for action, as appropriate. (WTSA-20 Action 3) | TSAG2022 Ongoing |  | √ |
|  | A TSAG-TD114 was submitted to the TSAG2022 meeting. TSAG took note of the closure of WTSA Action plan Action 3 related to Smart Cables – TD114 (action WP2-3). |  |  |  |
| 22-20 | ITU-T SGs to study the concept of SMART cables and encourage further consideration of related issues that impact the feasibility of related projects and the deployment of SMART cables, invites the study groups to report on their activities to TSAG as part of their regular reporting. (WTSA-20 Action 4) | Ongoing | √ |  |
|  | SG15 established a work item on SMART cables in Q8/15 in April 2021 and is developing Recommendations. TSAG2022 (WP2) took note on ongoing WTSA-20 Action 4 for Smart Cables from the WTSA Action plan – TSAG-TD114 (action WP2-4). SG5 established a work item on SMART cables (draft Recommendation ITU-T L.SMART “Impact assessment framework for evaluating how ICT-based subsea infrastructure could support climate, environmental and biodiversity monitoring in the oceans”) in Q12/5 in June 2023 |  |  |  |
| 22-21 | TSBDir to liaise with the Joint Task Force (JTF) SMART Cables, other standards development organizations (SDOs), research institutes and other organizations and stakeholders to exploit synergies and avoid duplication of efforts among such organizations. (WTSA-20 Action 5) | Ongoing | √ |  |
|  | The TSB Director participated in the workshops on SMART cables in January 2022, and in January 2023 and gave opening remarks. |  |  |  |
| 22-22 | Secretary-General is invited to continue to cooperate and collaborate with other entities within the United Nations in formulating future international efforts related to SMART cables as they contribute to the achievement of the goals of the 2030 Agenda for Sustainable Development. (WTSA-20 Action 6) | Ongoing | √ |  |
|  | The Chairman of the JTF on SMART cables participated in the UN Ocean conference in June 2022. |  |  |  |
| 22-23 | TSAG to conduct, with the support and contributions from its members, to take necessary measures to review Resolution 11 (Rev. Hammamet, 2016) and its implementation and to provide a proposal for the way forward for its modification and/or any other suggestion. (WTSA-20 Action 9) | TSAG 2024 | √ |  |
|  | This Resolution 11 is being considered by Rapporteur Group "WTSA Preparations (RG-WTSA)", and a call for contributions was made. |  |  |  |
| 22-24 | TSAG to consider the issue of industry engagement discussed at WTSA-20, including Resolution 68 (Rev. Hammamet, 2016) or draft revised Resolution 68. (WTSA-20 Action 10) | TSAG 2024 | √ |  |
|  | TSAG is considering matters of industry engagement by Working Party 2 "Industry Engagement, Work Programme, Restructuring (WP-IEWPR)" and further by Rapporteur Group "Industry Engagement, Metrics (RG-IEM)". |  |  |  |
| 22-25 | TSAG to review annually the use of all official languages of the Union on an equal footing in ITU publications and on ITU websites. (PP Res.167 instructs the Sector advisory groups) | TSAG 2024 |  |  |
| 22-26 | TSAG to further evaluate of the use of fully virtual meetings and physical meetings with remote participation, including the legal aspects. (PP Res.167 instructs the Secretary-General) | TSAG 2024 | √ |  |
|  | TSAG AHG on Governance and Management of E-meetings (AHG-GME) his identifies an initial set of issues that will form the basis for future studies with respect to detailing the governance and management of e-meetings. The activities of AHG-GME (now closed) are continued within TSAG RG-WM through the Associate Rapporteur on e-meetings; TSAG sent OLS3 on updated guidelines for remote participation and appointment of representatives to the ISCG. The 2022 TSAG meeting approved revised ITU-T A.Suppl.4, Supplement 4 to the ITU-T A-series Recommendations: Guidelines for remote participation, which specifies guidelines on the organization and handling of meetings of ITU-T groups with remote participation. |  |  |  |
| 22-27 | In acknowledging the limitations imposed by the current requirements in recognizing e) of Resolution 167, the 2022 Plenipotentiary Conference recognizes the importance of ITU Members as well chairmen of Study Group meetings which have remote participation, by considering the positions and proposals of remote participants in regard to the issues being discussed in the meeting and the importance of stable technical facilities. (PP-22 COM5 recommendation 2) | Ongoing | √ |  |
|  | In scope of TSAG AHG-GME/TSAG RG-WM; see also 22-26. |  |  |  |
| 22-28 | TSAG, study group or other group shall be made aware of the non-attendance of chairmen and vice-chairmen at their respective groups and raise the issue through the Director of the relevant Bureau with the members concerned in an attempt to encourage and facilitate participation in these roles. (PP Res.191 resolves 7) | Ongoing | √ |  |
|  | The TSB Director report (TSAG-TD020, TSAG-TD189, TSAG-TD409) lists the non-attendance of Chairmen/Vice Chairmen. |  |  |  |

» Top

# Resolution 29 - Alternative calling procedures on international telecommunication networks

resolves

1	to continue identifying and defining all forms of alternative calling procedures, to study their impact on all parties, and to develop appropriate Recommendations concerning alternative calling procedures;

2	that administrations and international telecommunication operators or operating agencies authorized by Member States should take, to the furthest extent practicable, all measures to suspend the methods and practices of any form of alternative calling procedures which seriously degrade the QoS and QoE of telecommunication networks, or prevent the delivery of CLI or OI information;

3	that administrations and international telecommunication operators or operating agencies authorized by Member States should take a cooperative approach to respect the national sovereignty of others, and suggested guidelines for this collaboration are attached;

4	to instruct ITU-T Study Group 2 to study other aspects, forms and definition of alternative calling procedures, including those associated with the interworking of legacy and IP-based infrastructures, and the consequent instances of hindrance, obscuring or spoofing of OI or CLI information, and the evolution of alternative calling procedures, including the use of over-the-top telephone applications that use telephone numbers, that may give rise to instances of fraudulent practices, and to develop appropriate Recommendations and guidelines;

5	to instruct ITU-T Study Group 3 to continue studying the economic effects of alternative calling procedures, origin non-identification or spoofing and over-the-top telephone applications, on the effort of developing countries for sound development of their local telecommunication networks and services, and to develop the appropriate Recommendations and guidelines;

6	to instruct ITU-T Study Group 12 to develop guidelines regarding the minimum QoS and QoE threshold to be fulfilled during the use of alternative calling procedures;

7	to instruct ITU-T Study Groups 2, 3 and 12 to continue the ongoing collaboration in studying issues related to alternative calling procedures,

instructs the Director of the Telecommunication Standardization Bureau

to continue to cooperate with the Director of the Telecommunication Development Bureau in order to facilitate the participation of developing countries in these studies and to make use of the results of the studies, and in the implementation of this resolution.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 29-01 | SG2 to study other aspects, forms and definition of alternative calling procedures, including those associated with the interworking of legacy and IP-based infrastructures, and the consequent instances of hindrance, obscuring or spoofing of OI or CLI information, and the evolution of alternative calling procedures, including the use of over-the-top telephone applications that use telephone numbers, that may give rise to instances of fraudulent practices, and to develop appropriate Recommendations and guidelines (resolves 4) | Ongoing | √ |  |
|  | Draft new E.ACP, “Alternative Calling Procedures”, is under study in SG2 to define ACP and related terminology. Latest draft in SG2-TD300R1/PLEN. |  |  |  |
| 29-02 | SG3 to continue studying the economic effects of alternative calling procedures, origin non-identification or spoofing and over-the-top telephone applications, etc. on the effort of developing countries for sound development of their local telecommunication networks and services, and to develop appropriate Recommendations and guidelines (resolves 5) | Ongoing | √ | X |
|  | Work items D.SIMBOX (Economic impact of SIMBOX bypass) and STUDY_ACPMIS (Alternative Calling Procedures, and misappropriation and misuse of facilities and services) have not received contributions over a prolonged period of time and have been discontinued from the SG3 work programme. |  |  |  |
| 29-03 | TSBDir to facilitate developing countries' participation and make use of the work/studies of SG2 and SG3 on alternative calling procedures (instructs TSBDir) | Ongoing | √ |  |
|  | Fellowships are provided to support interested developing countries in the works of SG2, and SG3. |  |  |  |
| 29-04 | SG12 to develop guidelines regarding the minimum QoS and QoE threshold to be fulfilled during the use of alternative calling procedures (resolves 6) | Completed |  | √ |
|  | ITU-T G.1010 includes performance targets for conversational voice. |  |  |  |
| 29-05 | ITU-T SGs 2, 3 and 12 to continue the ongoing collaboration in studying issues related to alternative calling procedures (resolves 7) | Ongoing | √ |  |
|  | The collaboration continues based on contributions and progress on related work. |  |  |  |

» Top

# Resolution 31 - Admission of entities or organizations to participate as Associates in the work of the ITU-T Telecommunication Standardization Sector

resolves

1	that an interested entity or organization may join ITU-T as an Associate and be entitled to take part in the work of a selected single study group;

2	that Associates are limited to the study group roles described below and excluded from all others:

•	Associates may take part in the process of preparing Recommendations within a study group, including the following roles: meeting participant, contribution submitter, Recommendation editor, and, during the alternative approval process, provider of comments during the last-call period (but not during the additional review period);

•	Associates may have access to documentation required for their work;

•	an Associate may serve as rapporteur, responsible for directing the studies for the relevant study Question within the selected study group, except for taking part in any decision-making or liaison activities which are to be handled separately, in accordance with No. 248B of the Convention;

3	that the amount of the financial contribution for Associates be based upon the contributory unit for Sector Members as determined by Council for any particular biennial budgetary period,

requests

1	the Secretary-General to admit entities or organizations to participate as Associates in the work of a given study group or subgroups thereof following the principles set out in Nos. 241B, 241C, 241D and 241E of the Convention;

2	the Telecommunication Standardization Advisory Group to review on an ongoing basis the conditions governing the participation (including financial impact on the Sector budget) of Associates based on the experience gained within ITU-T,

instructs the Director of the Telecommunication Standardization Bureau

to prepare the necessary logistics for the participation of Associates in the work of ITU-T, including possible impacts of study group reorganization.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 31-02 | TSBDir to continue to provide necessary logistics for participation of Associates | Ongoing | √ |  |
|  | All necessary logistics are being provided. The current list of Associates may be found at https://www.itu.int/en/myitu/Membership/ITU-Members/SMEs/Associates. |  |  |  |

» Top

# Resolution 32 - Strengthening electronic working methods for the work of the ITU-T Telecommunication Standardization Sector

resolves

1	that the principal EWM objectives of ITU-T are:

•	that collaboration between members on development of Recommendations should be by electronic means;

•	that TSB, in close collaboration with the ITU Telecommunication Development Bureau (BDT), should provide facilities and capabilities for EWM at ITU-T meetings, workshops and training courses, particularly to assist developing countries that have bandwidth limitations and other constraints, including remote participation and electronic access, such as via LINUX-based platforms;

•	to encourage electronic participation of developing countries in ITU-T meetings, by providing simplified facilities and guidelines, and by waiving any expenses for those participants, other than the local call or Internet connectivity charges;

•	that TSB, in close collaboration with BDT, should provide facilities and capabilities for EWM at ITU-T meetings, workshops and training courses, and encourage participation of developing countries, by waiving, within the credits that the Council is empowered to authorize, any expenses for those participants, other than the local call or Internet connectivity charges;

•	that TSB should provide all members of ITU-T with appropriate and ready access to electronic documentation for their work, including a global, unified and consolidated view of document traceability;

•	that TSB should provide appropriate systems and facilities to support the conduct of ITU-T's work by electronic means;

•	that all activities, procedures, studies and reports of ITU-T study groups be posted on the ITU-T website so as to facilitate navigation to find all relevant information,

•	to consider developing a mobile-friendly version of the ITU-T website to facilitate easy access by smart mobile devices to information; and

•	to simplify and facilitate enhanced searching for documents and/or information;

2	that these objectives should be systematically addressed in an EWM Action Plan, including individual action items identified by the ITU-T membership or TSB, and prioritized and managed by TSB with the advice of the Telecommunication Standardization Advisory Group (TSAG),

instructs

1	the Director of TSB to:

•	maintain the EWM Action Plan to address the practical and physical aspects of increasing the EWM capability of ITU-T;

•	identify and review costs and benefits of the action items on a regular basis;

•	report to each meeting of TSAG on the status of the Action Plan, including the results of the cost and benefit reviews described above;

•	provide the executive authority, budget within TSB, and resources to execute the Action Plan with all possible speed;

•	develop and disseminate guidelines for the use of ITU-T EWM facilities and capabilities;

•	take action, in order to provide appropriate electronic participation or observation facilities (e.g. webcast, audioconference, web conference/document sharing, videoconference, etc.) in ITU-T meetings, workshops and training courses for delegates unable to attend events in person, and coordinate with BDT to assist in the provision of such facilities; and

•	provide an ITU-T website that is easy to navigate to find all relevant information, and in particular a classification mechanism and an enhanced search engine to extract documents and/or information that are related to a specific subject, topic or issue; and

•	provide a mobile-friendly version of the ITU-T website;

2	TSAG to continue to:

•	act as the point of contact between the ITU-T membership and TSB on EWM matters, in particular providing feedback and advice on the contents, prioritization and implementation of the Action Plan;

•	identify user needs and plan the introduction of suitable measures through appropriate subgroups and pilot programmes;

•	request study group chairmen to identify EWM liaisons;

•	encourage participation by all participants in the work of ITU-T, especially EWM experts from TSAG, the study groups, TSB and appropriate ITU Bureaux and departments;

•	continue its work electronically outside TSAG meetings as necessary to carry out its objectives.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 32-01 | TSB to maintain EWM Action Plan to address the practical and physical aspects of increasing the EWM capability of ITU-T (instructs TSBDir 1) | Ongoing | √ |  |
|  | The EWM Action Plan is being maintained. Progress reports by EWM are regularly provided to TSAG. See the Electronic Working Methods services and database applications reports (TSAG-TD28, TSAG-TD195, TSAG-TD414). |  |  |  |
| 32-02 | TSB to review and recommend new and revised capabilities of ITU-T tools and applications, and TSBDir report status of EWM Action Plan to each meeting of TSAG | TSAG 2024, Ongoing | √ |  |
|  | See the Electronic Working Methods services and database applications reports (TSAG-TD28, TSAG-TD195, TSAG-TD414). JCA-IMT2020 group delegates expressed appreciation to the ITU-T standardization landscape online database developed and maintained by TSB. |  |  |  |
| 32-03 | TSBDir to develop budget estimate to implement EWM Action Plan and include it in budget request to Council; and identify and review costs and benefits of the action items on a regular basis; and to report to each meeting of TSAG on the status of the Action Plan, including the results of the cost and benefit reviews; and provide the executive authority, budget within TSB, and resources to execute the Action Plan with all possible speed (instructs TSBDir 1) | Council 2024, TSAG 2024, Ongoing |  |  |
| 32-04 | TSB to develop and disseminate guidelines for use of ITU-T EWM facilities and capabilities; with appropriate and ready access to electronic documentation for their work, including a global, unified and consolidated view of document traceability (resolves 1) | Ongoing | √ |  |
|  | See the Electronic Working Methods services and database applications reports (TSAG-TD28, TSAG-TD195, TSAG-TD414). |  |  |  |
| 32-05 | TSAG to act as the point of contact between the ITU-T membership and TSB on EWM matters, in particular providing feedback and advice on the contents, prioritization and implementation of the Action Plan (resolves 2) | Ongoing | √ |  |
|  | TSAG RG-WM is handling matters concerning electronic working methods. TSAG is considering contributions from membership and feedback from ITU-T study groups on EWM. |  |  |  |
| 32-06 | TSBDir to provide a mobile-friendly version of the ITU-T website; and to simplify and facilitate enhanced searching for documents and/or information, and in particular a classification mechanism and an enhanced search engine to extract documents and/or information that are related to a specific subject, topic or issue (resolves 1, instructs TSBDir 1) | Ongoing | √ |  |
|  | See the Electronic Working Methods services and database applications reports (TSAG-TD28, TSAG-TD195, TSAG-TD414). |  |  |  |
| 32-07 | TSB, in close collaboration with the ITU Telecommunication Development Bureau (BDT), should provide facilities and capabilities for EWM at ITU-T meetings, workshops and training courses, particularly to assist developing countries that have bandwidth limitations and other constraints, including remote participation and electronic access, such as via LINUX-based platforms; and encourage participation of developing countries, by waiving, within the credits that the Council is empowered to authorize, any expenses for those participants, other than the local call or Internet connectivity charges (resolves 1) | Ongoing | √ |  |
|  | See the Electronic Working Methods services and database applications reports (TSAG-TD28, TSAG-TD195, TSAG-TD414). |  |  |  |
| 32-08 | ITU-T study groups to post all activities, procedures, studies and ITU-T SG reports on the ITU-T website so as to facilitate navigation to find all relevant information (resolves 1) | Ongoing | √ |  |
|  | All ITU-T study groups regularly post their activities, reports on their respective websites. SG17 webpage contains a wealth of easily accessible information on its work available to the public, especially on common ITU-T¦ISO/IEC standards, ICT security standardization roadmap and SG17’s ASN.1 and OID projects and SG17 action plan on 5G and DLT security. Information on ITU-T, Digital Transformation for People-Centred Cities activities is available here. Information on United for Smart Sustainable Cities (U4SSC) initiative is available here. Information on metaverse activities is available here. |  |  |  |
| 32-09 | TSAG to identify user needs and plan the introduction of suitable measures through appropriate subgroups and pilot programmes (resolves 2) | TSAG 2024 | √ |  |
|  | TSB, when developing and piloting EWM tools and providing EWM services, is considering diverse user needs; see also 32-01, 32-02, 32-06, and 32-07; TSB does not see any additional needs for TSAG to create additional subgroups. TSAG AHG on Governance and Management of E-meetings (AHG-GME) is identifying an initial set of issues that will form the basis for future studies with respect to detailing the governance and management of e-meetings. The activities of AHG-GME will be continued within TSAG RG-WM through the Associate Rapporteur on e-meetings. |  |  |  |
| 32-10 | TSAG to request study group chairmen to identify EWM liaisons (resolves 2) | TSAG 2024 | √ |  |
|  | - SG13 appointed SG13 EWM liaison rapporteur. - SG15 EWM team meets regularly at every SG15 meeting and sends a Liaison to TSAG to report its activities. SG15 appointed three EWM coordinators (one for each WP). - SG20 has appointed a EWM liaison rapporteur. |  |  |  |

» Top

# Resolution 34 - Voluntary contributions

resolves

1	to encourage the financing of specific projects, focus groups, regional groups of ITU-T study groups or other new initiatives, including any activities which help achieve the objectives of Resolution 44 (Rev. Geneva, 2022) of this assembly, on bridging the standardization gap, by voluntary contributions;

2	to invite Sector Members and Associates to finance voluntarily the participation of developing countries, and in particular remote participation using electronic working methods, in ITU-T meetings and workshops;

3	to invite Member States, Sector Members and Associates from both developing and developed countries to make voluntary contributions and to submit to the Director of the Telecommunication Standardization Bureau projects and other initiatives of interest for ITU-T to be financed under voluntary contributions.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 34-01 | TSB to solicit voluntary contributions for specific activities, e.g., projects, meetings, workshops, EWM | Ongoing |  |  |
| 34-02 | TSB presentations at workshops, regional meetings and other promotional events to include encouragement of voluntary contributions to fund new initiatives (also see Resolution 44) | Ongoing | √ |  |
|  | TSB prepared a slide on encouragement of voluntary contributions; this slide is included in the TSB workshop package since August 2018. |  |  |  |

» Top

# Resolution 40 - Regulatory and policy aspects of work of the ITU Telecommunication Standardization Sector

resolves

1	that, when determining whether all New Work Items, Questions or Recommendations have policy or regulatory implications study groups shall more generally consider possible topics such as:

–	the right of the public to correspond;

–	protection of telecommunication channels and installations;

–	use of the limited numbering and addressing resources;

–	naming and identification;

–	secrecy and authenticity of telecommunications;

–	safety of life;

–	practices applicable to competitive markets;

–	misuse of numbering resources; and

–	any other relevant matters, including those identified by a decision of Member States, or recommended by TSAG, or Questions or Recommendations where there is any doubt about their scope;

2	to instruct TSAG to study and identify the operational and technical areas related to quality of service/quality of experience (QoS/QoE) of telecommunications/information and communication technologies that might have policy and regulatory nature, taking into account the studies being carried out by the relevant study groups, and report that to the next WTSA,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 40-01 | SGs to consider the Resolution when determining whether New Work Items, Questions or Recommendations have policy or regulatory implications (resolves 1) | First SG meeting, Ongoing | √ |  |
|  | - SG3 uses TAP as the default approval process for normative texts. - SG12 uses AAP as the default, but uses TAP if appropriate. - While the agreed default approval procedure in SG13 is AAP, Resolution 40 is considered for some particular cases per Members' requests. - SG15 uses AAP as the default, but uses TAP if appropriate. - SG17 at its first meeting of 2022-2024 study period reviewed and assigned a default approval process for each Question. In addition, the approval process of each Recommendation is assigned when each new work item is established. - SG20 uses the AAP as the default process but uses TAP as appropriate. |  |  |  |

» Top

# Resolution 43 - Regional preparations for world telecommunication standardization assemblies

resolves to instruct the Director of the Telecommunication Standardization Bureau

to maintain the organization, within the financial limitations established by the Plenipotentiary Conference, of at least one regional preparatory meeting per region, in close coordination with relevant regional organizations, with the assistance of regional offices when necessary, covering all Member States from ITU without exception, even if they do not belong to any of the six regional telecommunication organizations; the regional preparatory meetings should be the closest in time possible to the next WTSA, followed by an informal meeting of the chairmen and vice-chairmen of the regional preparatory meetings and other interested parties, to be held not earlier than six months prior to WTSA,

invites the Secretary-General, in cooperation with the Directors of the Bureaux of the three Sectors

1	to consult with Member States and regional and subregional telecommunication organizations on the means by which assistance can be provided in support of their preparations for future WTSAs, including support for the organization of a "Bridging the Standardization Gap Forum" per region to address major issues of the next WTSA of interest to developing countries1;

2	on the basis of such consultations, to assist Member States and regional and subregional telecommunication organizations in such areas as:

i)	the organization of informal regional and interregional preparatory meetings, and formal regional preparatory meetings if a region so requests;

ii)	the identification of major issues to be resolved by the next WTSA;

iii)	the development of coordination methods;

iv)	the organization of information sessions on expected work for WTSA;

3	to submit, no later than the session of the ITU Council following WTSA, a report on feedback from Member States concerning WTSA regional preparatory meetings, their results and the application of this resolution,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 43-01 | TSBDir to organize, at the request of the region, at least one regional preparatory meeting per region six months prior to WTSA-24 (resolves) | 2023/2024 | √ |  |
|  | First inter-regional meeting on WTSA-24 preparation was held on 18 January 2024. Second meeting is planned on 25 July 2024. |  |  |  |
| 43-02 | TSBDir to invite Secretary General to consult Member States and regional telecommunication organizations on the means by which their preparations for WTSA-24 can be supported, including support for a Bridging the Standardization Gap Forum per region. | 2023/2024 |  |  |
| 43-03 | SecGen to submit, no later than the session of the ITU Council following WTSA, a report on feedback from Member States concerning WTSA regional preparatory meetings, their results and the application of this resolution. (invites SecGen 3) | 2022/2023 |  |  |

» Top

# Resolution 44 - Bridging the standardization gap between developing and developed countries

resolves

1	that the action plan annexed to this resolution, having the objective of bridging the standardization gap between developed and developing countries, should be continued and be reviewed on an annual basis to take into account the requirements of developing countries;

2	that ITU-T, in collaboration with the other Sectors, especially the ITU Telecommunication Development Sector (ITU-D), as appropriate, shall develop a programme to:

i)	assist developing countries in developing strategies and methods that facilitate the process of linking their challenges and innovations to the standardization process in support of the digital transformation of society;

ii)	assist developing countries in developing means to align their national industrial and innovation strategies towards the goal of achieving highest impact on their socio-economic ecosystems;

iii)	assist developing countries to develop strategies for establishing test laboratories which are nationally, regionally and internationally recognized for emerging technologies;

3	that, subject to Council approval, there should be free online access to the manuals, handbooks, directives and other ITU material related to understanding and implementation of ITU-T Recommendations, particularly in the area of developing planning, operation and maintenance of telecommunication equipment and networks;

4	to support, within available or otherwise contributed resources, and on a case-by-case basis, the coordinated creation of regional groups of ITU-T study groups, according to approval or procedures set forth in Resolution 54 (Rev. Geneva, 2022) of this assembly, and encourage cooperation and collaboration of these groups with other regional standardization entities;

5	to maintain in the annual budget of the Union a separate expenditure line item for bridging the standardization gap activities, while at the same time voluntary contributions should be further encouraged;

6	that interpretation shall be provided, based on the requests of participants, at all study group and working party plenary meetings and the entire meeting of TSAG;

7	to encourage the participation of members, particularly Academia, from developing countries in ITU-T standardization activities,

resolves further that ITU regional offices

1	be engaged in the activities assigned by TSAG in order to further enhance the implementation of the action plan annexed to this resolution, promoting and coordinating standardization activities in their regions, including raising awareness among prospective Sector Members, Associates and academia from developing countries and providing the necessary assistance to the regional groups of ITU-T study groups;

2	assist, within the offices' budgets, the vice-chairmen of TSAG and ITU-T study groups appointed with specific responsibilities, including, among others, the following:

i)	closely work with ITU members in the region in order to mobilize them to participate in ITU standardization activities to assist in bridging the standardization gap;

ii)	make mobilization and participation reports to the ITU body concerning the region;

iii)	prepare and submit a mobilization programme for the regions that they represent at the first meeting of TSAG or a study group and send a report to TSAG;

iv)	inform ITU members of programmes and initiatives within ITU-D that could assist in bridging the standardization gap;

3	organize and coordinate the activities of the regional groups of ITU-T study groups,

invites the Council

1	in view of the above resolves, in particular resolves 6, to increase the ITU-T budgetary provisions for fellowships, interpretation and translation of documents for meetings of TSAG, ITU-T study groups and regional groups of ITU-T study groups;

2	to consider the exemption from payment of the membership fees for a limited time of up to one full study period for new Academia members from developing countries in order to encourage them to get involved in ITU-T activities and the standardization process,

instructs the Director of the Telecommunication Standardization Bureau, in collaboration with the Directors of the Radiocommunication Bureau and the Telecommunication Development Bureau

within available resources

1	to continue implementing the objectives of the action plan annexed to this resolution;

2	to encourage the formation of partnerships under the patronage of ITU-T as one of the means for financing and implementing the objectives of the action plan annexed to this resolution;

3	to consider, whenever possible, holding workshops concurrently with the meetings of their respective regional groups of ITU-T study groups, or organizing other workshops or events in coordination and collaboration with the Director of BDT and ITU regional offices alongside these meetings;

4	to assist developing countries with their studies, particularly in respect of their priority questions and towards developing and implementing ITU-T Recommendations;

5	to continue the activities of the implementation group established within TSB to organize, mobilize resources, coordinate efforts and monitor work related to this resolution and the associated action plan;

6	to continue to carry out the necessary studies on the role of innovation management and innovation stimulation programmes on bridging the standardization gap between the developed and developing countries;

7	to include in the TSB budget proposal to the Council funds identified for the implementation of this resolution, taking into account financial constraints and existing and planned BDT activities;

8	to report on the implementation of this plan to future world telecommunication standardization assemblies and plenipotentiary conferences, with a view to reviewing this resolution and introducing the appropriate amendments in the light of implementation outcomes, as well as the budgetary adjustments needed;

9	to provide support and assistance to developing countries, if requested, in drafting/developing a set of guidelines on the application of ITUT- Recommendations at the national level in order to enhance their participation in ITU-T study groups, with the assistance of the ITU regional offices, for bridging the standardization gap;

10	to enhance the use of electronic channels such as webinars or e-learning for education and training on the implementation of ITU-T Recommendations, in close collaboration with the ITU Academy and other capacity-building initiatives of BDT;

11	to provide support and all necessary measures for creating and ensuring the smooth functioning of the regional groups and to facilitate the organization of regional group meetings and workshops for disseminating information and increasing understanding of new Recommendations, in particular for developing countries;

12	to report on the effectiveness of the regional groups of ITU-T study groups to the Council;

13	to conduct workshops and seminars, as appropriate, for disseminating information and increasing understanding of new ITU-T Recommendations and implementation guidelines for Recommendations, in particular for developing countries;

14	to ensure equal access to the ITU electronic meetings to the maximum extent possible and to provide remote participation, where possible, for more ITU-T workshops, seminars and forums, encouraging greater participation by developing countries;

15	to leverage existing ITU-D tools in order for developing countries to have greater involvement in ITU-T's standardization work;

16	to study the possibility of generating additional revenue for ITU-T activities on bridging the standardization gap, through identifying new financial resources not related to the voluntary contributions mentioned above,

instructs study groups of the ITU Telecommunication Standardization Sector and the Telecommunication Standardization Advisory Group

1	to be actively involved in the implementation of the programmes set forth in the action plan annexed to this resolution;

2	to consider including implementation guidelines for ITU-T Recommendations where these could provide advice to assist developing countries in adopting them, with emphasis on Recommendations having regulatory and policy implications;

3	to coordinate joint meetings of regional groups of ITU-T study groups,

further instructs the study groups

1	to take account of the specific characteristics of the telecommunication/ICT environment of the developing countries in establishing standards in the fields of planning, services, systems, operation, tariffs and maintenance, and to provide solutions relevant to developing countries wherever possible;

2	to take appropriate steps to have studies carried out on questions connected with standardization which are identified by WTDCs or which are identified via specific studies or surveys targeting developing countries carried out by other ITU-T study groups;

3	to continue liaising with ITU-D study groups, where appropriate, when developing new or revised ITU-T Recommendations, on the specific needs and requirements of developing countries, in order to broaden the appeal and applicability of the Recommendations in those countries;

4	to identify the challenges that developing countries are facing with a view to bridging the standardization gap among Member States,

invites the Director of the Telecommunication Standardization Bureau

1	to work closely with the Directors of BDT and the Radiocommunication Bureau (BR) in order to encourage the formation of partnerships under the patronage of ITU-T as one of the means for financing the action plan;

2	to encourage Sector Members from the developed countries to promote the participation in ITU-T activities of their subsidiaries based in developing countries;

3	to develop mechanisms to support the effective participation by members, including telecommunication operators, from developing countries in standardization activities

4	to consider, whenever possible, holding meetings of ITU-T study groups in developing countries,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 44-01 | TSB to continue maintaining the BSG action plan in annex of Res. 44 and be reviewed by TSAG on an annual basis (resolves 1) | TSAG 2024, Ongoing | √ |  |
|  | The intersectoral task force is working on monitoring progress of implementation of Action Plan in Resolution 44. |  |  |  |
| 44-02 | TSB to develop a programme to assist developing countries to develop methods, strategies, and means to link national innovations to standardization process in support of the digital transformation of society (resolves 2i) | Ongoing | √ |  |
|  | New BSG program is under the development and improvement of tools (see TD422). |  |  |  |
| 44-03 | TSBDir to assist developing countries to develop strategies for establishing test laboratories for emerging technologies which are nationally, regionally and internationally recognized for emerging technologies (resolves 2, iii) | Ongoing |  |  |
|  | The Conformity Assessment Steering Committee , which works under auspices of SG11, has developed an ITU Testing Laboratories recognition procedure in close collaboration with the International Laboratory Accreditation Cooperation (ILAC). Under this recognition procedure, all laboratories with a scope covering ITU standards accredited by ILAC Mutual Recognition Arrangement signatories may be recognized by ITU. In October 2023, TSB organized tutorial on TL recognition procedure which provided detailed information on how to apply for such recognition. The event was attended by 89 representatives of many developing countries. |  |  |  |
| 44-05 | TSB further encourage voluntary contributions to the bridging the standardization gap fund (see also Resolution 34) (resolves 5) | Ongoing | √ |  |
|  | MIC, Japan, supported New BSG program with the fund (TD422), while encouraging other voluntary contributions to the BSG Fund. |  |  |  |
| 44-11 | SGs to take account of specific characteristics of telecommunication/ICT environment in developing countries, and provide solutions relevant to developing countries wherever possible. (further instructs SGs 1) | Ongoing | √ |  |
|  | Study groups review contributions from developing countries and derive requirements and/or studies based on the inputs received. - SG2 RG-AFR was organized in Abidjan, Côte d'Ivoire, 21-22 September 2023, where BSG traing was co-organized. - SG3, through its five regional groups, is addressing the needs of developing countries within its mandate. As per Section 9.2 of WTSA Resolution 1, one regional Recommendation (ref. ITU-T D.608R) was approved. - SG5, through its four regional groups (SG5RG-AFR, SG5RG-ARB, SG5RG-LATAM and SGRG-AP), is addressing the needs of developing countries within its mandate. - SG5RG-AFR was organized in Kampala, Uganda from 15-17 May 2023. A BSG training was organized. SG5 RG-AP was organized in Bangkok, Thailand, 11-12 September 2023, when BSG training was co-organized in close coordination and collabroation with Regional Development Forum of BDT. - SG11 was organized in Geneva, 10-20 October 2023, when New BSG program with updated training and Quiz was co-organized for optimizing resource and results. - SG12, through its regional groups, is addressing the needs of developing countries within its mandate. - SG13 has a Question dedicated to address the needs of developing countries (Q5/13 "Applying Future Networks and innovation in developing countries"). SG13RG-AFR and SG13RG-EECAT brought standardization priorities of these regions to the SG13 meetings. - SG15 informs regularly ITU-D of received contributions from developing countries for their consideration for providing assistance, etc. - SG17 created the SG17 RG-AFR on 17 April 2015 in 2013-2016 study period and created the SG17 RG-ARB on 30 March 2017 in 2017-2020 study period. A gathering of delegates from Africa was organized by SG17 RG-AFR Chairman during SG17 virtual meeting from 10-20 May 2022, during SG17 meeting from 23 August to 2 September 2022, and during SG17 meeting from 21 February to 3 March 2023. A gathering of delegates SG17 RG-ARB was organized by SG17RG-ARB Acting Chairman during SG17 meeting from 21 February to 3 March 2023, when there was a joint meeting of Q3/17 and SG17 RG-AFR. SG17RG-AFR and Regional Cybersecurity Summit were organized for Africa, Kampala, Uganda, 20-23 November 2023, when BSG training was co-organized. - SG20 regularly organizes a Bridging the Standardization Gap training. SG20, through its five regional groups, is addressing the needs of developing countries within its mandate. SG20 developed Recommendation ITU-T Y.4218 “IoT and ICT requirements for deployment of smart services in rural communities”. SG20 is also working on draft Recommendation ITU-T Y.dt-IWCS “Requirements and capability framework of digital twin for intelligent water conservancy system” and draft Recommendation ITU-T Y.4222 (ex Y.smart-evacuation) “ Framework of smart evacuation in a disaster or emergency in smart cities and communities”. |  |  |  |
| 44-12 | SGs to continue liaise with ITU-D SGs, to assist developing countries with their priority questions for studies, such as identified by WTDC or which are identified via specific studies or surveys targeting developing countries carried out by other ITU-T study groups. (further instructs SGs 2) | Ongoing | √ |  |
|  | - SG3 liaised with ITU-D SG1 and SG2 on an appointed SG3 Representative to ITU-D and topics of common interest. - SG5 regularly liaises with ITU-D on activities related to Human Exposure to EMF, Environment, Climate Change and Circular Economy - SG13 maintains the communication channel with ITU-D SGs 1 and 2. - SG20 regularly liaises with ITU-D on activities and information related to Internet of things (IoT) and smart cities & communities. |  |  |  |
| 44-13 | SGs and TSAG to consider including implementation guidelines for ITU-T Recommendations where these could provide advice to assist developing countries in adopting them, with emphasis on Recommendations having regulatory and policy implications. (instructs TSBDir 9, instructs 2 SGs + TSAG) | TSAG 2024, Ongoing | √ |  |
|  | Study groups will develop implementation guidelines for new ITU-T Recommendations to enable developing countries to adopt them, based on received contributions. The ITU has developed guidelines for developing countries to establish standardization secretariats to better interface with ITU-T study groups to enhance their contributions to the ITU-T standardization process. Implemented in the context of Action Item 44-28 below. - TSAG WP1 on Working Methods and related WTSA preparations (WP-WMW) is considering implementation guidelines for ITU-T Recommendations. - SG12 regularly publishes informative material (technical papers, technical reports, supplements, implementer’s guides) to provide information to implementers, etc. - SG15 regularly publishes informative material (technical papers, technical reports, supplements, flyers) to provide information to implementers, etc. - SG17 has agreed Supplements to its Recommendations on implementation guidelines. - SG20 developed Y.Suppl.78 “Use Cases on implemented or evaluated SSC solutions based on ITU-T Y.4900 Recommendation Series”. SG20 develops and publishes Supplements and technical reports to facilitate implementation. |  |  |  |
| 44-14 | SGs and TSAG to coordinate joint meetings of regional groups. (instructs SGs + TSAG 3) | Ongoing | √ |  |
|  | The following regional group meetings were organized in the reporting period: - SG20 Regional Group for Africa (SG20RG-AFR), Sharm El-Sheikh, Egypt, 8 June 2023 - SG3 Regional Group for the Arab Region (SG3RG-ARB), E-meeting, 20 June 2023 - SG20 Regional Group for Asia and the Pacific (SG20RG-AP), E-meeting, 25-26 July 2023 - SG20 Regional Group for the Arab Region (SG20 RG-ARB), E-meeting, 1 August 2023 - SG3 Regional Group for Latin America and the Caribbean (SG3RG-LAC), San José, Costa Rica, 28-29 September 2023 - SG3 Regional Group for Asia and Oceania (SG3RG-AO), Bangkok, Thailand 11-12 September 2023 - SG5 Regional Group for Asia and the Pacific (SG5RG-AP), Bangkok, Thailand 11-12 September 2023 - SG11 Regional Group for Africa (SG11RG-AFR), 13-15 September 2023 - SG13 Regional Group for Africa (SG13RG-AFR), Abidjan, Côte d'Ivoire, 21-22 September 2023 - SG2 Regional Group for Africa (SG2RG-AFR), Abidjan, Côte d'Ivoire, 21-22 September 2023 - SG17 Regional Group for Africa (SG17RG-AFR), 23 November 2023 |  |  |  |
| 44-15 | TSBDir to continue the activities of the Bridging the Standardization Gap (BSG) implementation group within TSB. (instructs TSBDir 5) | Ongoing | √ |  |
|  | TSB Director led New BSG program (see TD422). |  |  |  |
| 44-19 | TSB to assist requested developing countries to draft/develop a set of guidelines on the application of ITU-T Recommendations at the national level in order to enhance their participation in ITU-T SGs. (instructs TSBDir 9) | Ongoing |  |  |
| 44-20 | TSB to enhance the use of electronic channels such as webinars or e-learning for education and training on implementation of ITU-T Recommendations in close collaboration with the ITU Academy and other capacity-building initiatives of BDT. (instructs TBSDir 10) | Ongoing | √ |  |
|  | The e-learning course hosted on the ITU Academy platform about ITU-T Working Methods and Mechanisms was revised and updated under the New BSG program in 2023. The main objectives of the e-learning course are to introduce the structures, management, coordination mechanisms and operating procedures of ITU-T study groups as defined in Recommendation ITU-T A.1. Recommendation ITU-T A.1 describes general working methods for ITU-T study groups. It provides guidelines related to work methods, such as the conduct of meetings, preparation of studies, management of study groups, the role of Rapporteurs and the processing of ITU-T contributions and temporary documents. The course is intended for delegates participating in ITU-T study group meetings, especially new participants. Online video primers have also been developed and available on the BSG website at www.itu.int/go/bridging. |  |  |  |
| 44-21 | TSB to provide support and all necessary measures for creation, organization of meetings and workshops of the regional groups to ensure their smooth functioning. (instructs TSBDir 11) | Ongoing | √ |  |
|  | Implemented in the context of Action Item 44-24 (see below). The ITU-T SG13 9th Regional Workshop for Africa "Standardization of Future Networks and Emerging Network Technologies: African perspectives " was held in Abidjan, Cote D'Ivoire on 19 – 20 September 2023. SG17 organized a Regional Cybersecurity Summit for Africa, Kampala, Uganda, 20-23 November 2023. |  |  |  |
| 44-23 | TSBDir to work closely with BRDIR and BDTDir, to encourage partnership under the patronage of ITU-T as one of the means for financing the BSG action plan. (invites TSBDir 2) | Ongoing | √ |  |
|  | BDT and BR are represented in the intersectoral Force as well as the Directors of the ITU Regional Offices. |  |  |  |
| 44-24 | TSBDir to develop mechanisms to support the effective participation by members, including telecommunication operators, from developing countries in standardization activities, and to encourage Sector Members from the developed countries to promote the participation in ITU-T activities of their subsidiaries based in developing countries (invites TSBDir 2, 3) | Ongoing | √ |  |
|  | The strategy for the Standardization Forums was adopted under the BSG programme. These are now fully in line with the priorities of our study groups, and are mainly held in coordination with our regional groups. The Standardization Forums are also contributing in raising awareness of standards activities through the participation of key decision makers. In 2022 the following Forums were held: - ITU Regional Standardization Forum (RSF) on “Regulatory and Policy aspects of Telecommunications/ICTs”, New Delhi, India, 8 August 2022. Further the following events were held: ITU Workshop "Economic and fiscal incentives to accelerate digital transformation of data and applications over telecommunication infrastructure", 3-4 November 2022, Geneva. |  |  |  |
| 44-28 | TSBDir, in close collaboration with BDT and BR, providing training courses on standardization to developing countries. (instructs TSBDir 13, 14) | Ongoing | √ |  |
|  | The hands-on trainings revised and updated under the New BSG Program are geared towards assisting member states, developing countries in particular, in acquiring the right skills and capabilities for international standards-making and to draft contributions for ITU-T meetings. The sessions focus on the development of practical skills to maximize the effectiveness of developing countries' participation in the ITU-T standardization process, covering topics including relevant terms related to study group meetings, strategies for participation in study groups, drafting Contributions, presenting proposals, collaborative working methods and means of gaining support and building consensus. In 2023, 12 hands-on trainings in coordination with SGs and regional groups were organized to train 338 delegates, while on-line course on ITU-T Working Methods attracted 208 delegates. |  |  |  |
| 44-29 | Organizing in-depth tutorials on implementation of ITU-T Recommendations. (Programme 3 instructs TSBDir 13) | Ongoing | √ |  |
|  | A structured training course has been developed by TSB to provide guidelines on submitting effective proposals to Study Groups and navigating the international standards-making process. A tutorial was developed providing an Overview and comparison of AAP vs TAP. - SG17 maintains Technical Report XSTR-SUSS on the successful use of security standards. SG17 organizes a set of tutorials at each of its meetings with a variety of presenters both inside and outside the ITU. SG17 organized a series of ITU workshops on security aspects of new emerging technologies and applications, such as 1st and 2nd X.509 day event (9 May 2022 & 2023), Security for 5G and beyond (Aug 2022). SG17 held an ITU workshop on “DLT security, identity management and privacy” on 20 February 2023. SG17 organized Regional Cybersecurity Summit for Africa, Kampala, Uganda, 20-23 November 2023 introduced ITU-T X.1060 cyber defence center and X.1352 on IoT security. The Toolkit on Digital Transformation for People-Oriented Cities and Communities supports strategizing and planning the digital transformation of cities and communities to promote sustainable, inclusive, resilient and improved quality of life for residents in cities and communities. The resources contained in the Toolkit include international standards and guidance, the latest research and projections, and cutting-edge reports on a variety of timely topics relevant to the digital transformation of cities and communities. The toolkit is available at: https://toolkit-dt4c.itu.int/ ​ The information session on the “Toolkit on Digital Transformation for People-oriented Cities and Communities” was organized by the Telecommunication Standardization Bureau (TSB) of the ITU with the support of the ITU Office for Europe, and took place virtually on 21 June 2022. The objective of the information session was to provide an overview of the Toolkit, its functionalities, and stakeholders that can benefit from it. |  |  |  |
| 44-30 | Provision, by the TSB, of fellowships to eligible countries to attend relevant ITU-T meetings. (Programme 3) | Ongoing | √ |  |
|  | In 2023, 422 fellowship requests were received, out of which 152 were granted (see TD422) in comparison with177 requested and 101 granted in 2022. |  |  |  |
| 44-31 | TSB to provide interpretation on request of participants to all SG and WP plenary meetings and the entire meeting of TSAG. (resolves 6) | Ongoing | √ |  |
|  | - Over the period January to November 2022 interpretation was provided to: IRM, TSAG (2 days), GSS-20 and WTSA-20. ITU-T Study Group 3 (every day) and closing plenaries of SG11, SG12, SG16 and SG17 ITU-T SG3RG-AFR, SG3RG-LAC and ITU-T Workshops at WSIS Forum Sign language interpretation was provided to some sessions of TSAG and SG16. - Over the period December 2022 to March 2023 interpretation was provided to: TSAG (2 days) ITU-T SG3 (every day) and closing plenaries of SG12, SG20 and SG17. ITU-T SG5RG-AFR |  |  |  |
| 44-32 | TSBDir to ensure equal access to the ITU electronic meetings to the maximum extent possible and to provide remote participation. (instructs TSBDir 14) | Ongoing | √ |  |
|  | See the Electronic Working Methods services and database applications report (TSAG-TD414). |  |  |  |
| 44-33 | TSBDir to leverage existing ITU-D tools. (instructs TSBDir 15) | Ongoing | √ |  |
|  | Ongoing. |  |  |  |
| 44-34 | TSBDir to study the possibility of generating revenue for ITU-T on bridging the standardization gap, through identifying new financial resources not related to voluntary contributions. (instructs TSBDir 16) | Ongoing | √ |  |
|  | TSB is encouraging other voluntary contributions to the BSG Fund. |  |  |  |
| 44-35 | ITU-T SGs to identify the challenges that developing countries are facing with a view to bridging the standardization gap among Member States. (further instructs SGs 4) | Ongoing | √ |  |
|  | - SG3 Terms of Reference of its five Regional Groups include the identification of the challenges that developing countries are facing with a view to bridging the standardization gap. SG3 is considering contributions from developing countries that raise challenges. - SG15 reviews contributions from developing countries in its “Promotion and coordination group meeting” at every SG meeting in addition to usual discussion in Questions. - SG17 created the SG17 RG-AFR on 17 April 2015 in 2013-2016 study period and created the SG17 RG-ARB on 30 March 2017 in 2017-2020 study period. A gathering of delegates from Africa was organized by SG17RG-AFR Chairman during SG17 virtual meeting from 10-20 May 2022, during SG17 meeting from 23 August to 2 September 2022, and during SG17 meeting from 21 February to 3 March 2023. A gathering of delegates SG17 RG-ARB was organized by SG17RG-ARB Acting Chairman during SG17 meeting from 21 February to 3 March 2023. Additionally, there was a joint meeting of Q3/17 and SG17 RG-AFR during SG17 meeting from 21 February to 3 March 2023. |  |  |  |
| 44-36 | TSBDir, in collaboration with the BRDIR and BDTDir, to report on the implementation of this plan to future world telecommunication standardization assemblies and plenipotentiary conferences, with a view to reviewing this resolution and introducing the appropriate amendments in the light of implementation outcomes, as well as the budgetary adjustments needed. (instructs TSBDir 8) | WTSA-24 PP-26 |  |  |
| 44-37 | TSB to be developing guidelines to assist developing countries in their involvement in ITU-T activities, covering, but not limited to, ITU-T working methods, formulating draft Questions and making proposals. (Programme 1: 2) | Ongoing |  |  |
| 44-38 | TSB to be improving procedures and tools for remote participation via electronic means so as to enable experts in developing countries to participate actively in ITU-T meetings (including TSAG, study groups, focus groups, joint coordination activities, global standardization initiatives, among others), workshops and training, from their own countries. (Programme 1: 2) | Ongoing |  |  |
| 44-39 | TSB to be conducting consultancy projects designed to support developing countries in the development of standardization plans, strategies, policies, etc. The outputs should be further transformed into best practices. (Programme 1: 2) | Ongoing |  |  |
| 44-40 | TSB to be developing methods, tools and indicators for accurate measurement of the results and the level of effectiveness of the efforts and activities applied in bridging the standardization gap and providing statistics on the involvement of developing countries in the work and meetings of TSAG, ITU-T focus groups, ITU-T study groups and regional groups in addition to other ITU-T events. (Programme 1: 2) | Ongoing |  |  |
|  | Analytics as a tool was carried out under the New BSG Program to measure the outcome indicators of BSG pursuant to ITU PP Resolution 71 (TD422) in close coordination across TSB and BDT (on fellowship). |  |  |  |
| 44-41 | TSB (with BDT) to be establishing a standardization secretariat to coordinate standardization activities and participation in ITU-T study groups. (Programme 2: 2) | Ongoing |  |  |
| 44-42 | TSB to be compiling and maintaining an up-to-date database with information on new standardized technologies, as well as products that are compliant with ITU-T Recommendations. (Programme 2: 2) | Ongoing |  |  |

» Top

# Resolution 47 - Country code top-level domain names

instructs ITU-T Study Group 2

to continue studies, and to work with Member States and Sector Members, in their respective roles, recognizing the activities of other appropriate entities, to review Member States' ccTLD experiences,

instructs the Director of the Telecommunication Standardization Bureau

to take appropriate action to facilitate the above and to report to the ITU Council annually regarding the progress achieved in this area,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 47-01 | SG2 to review and study contributions regarding MS' ccTLD experiences (instructs SG2) | Ongoing |  |  |
|  | Actions by ITU-T SG2 depend on Contributions, but no such contributions have been received so far. |  |  |  |
| 47-02 | TSBDir to report to Council annually regarding progress in ccTLDs. (instructs TSB Dir) | Council2023 | √ |  |
|  | The TSB Director reports annually in the Council document on "ITU Internet activities: Resolutions 101, 102 and 133, 180, and 206", which includes updates regarding ccTLDs, if any; see S22-CL-C-0033. |  |  |  |

» Top

# Resolution 48 - Internationalized (multilingual) domain names

resolves to instruct ITU-T Study Group 16 and other relevant study groups

to continue to study internationalized (multilingual) domain names, and to continue to liaise and cooperate with appropriate entities, whether intergovernmental or non-governmental, in this area,

instructs the Director of the Telecommunication Standardization Bureau

to take appropriate action to facilitate the above and to report to the ITU Council annually regarding the progress achieved in this area,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 48-02 | TSBDir to report to Council annually regarding progress achieved in internationalized (multilingual) domain names (instructs TSB Dir) | Ongoing, 3 months before Council | √ | √ |
|  | The TSB Director reports annually in the Council document on "ITU Internet activities: Resolutions 101, 102, 133, 180, and 206", which includes updates regarding multilingual domain names, if any; see S22-CL-C-0033. |  |  |  |

» Top

# Resolution 49 - ENUM

resolves to instruct Study Group 2 of the ITU Telecommunication Standardization Sector

1	to study how ITU could have administrative control over changes that could relate to the international telecommunication resources (including naming, numbering, addressing, and routing) used for ENUM;

2	to evaluate the current interim procedure for ENUM delegation, and report back to the Director of the Telecommunication Standardization Bureau,

instructs the Director of the Telecommunication Standardization Bureau

to take appropriate action to facilitate the above and to report to the ITU Council annually regarding the progress achieved in this area, including the continuation of further studies in relation to draft Recommendation ITU-T E.A-ENUM (new version), on principles and procedures for the administration of E.164 country codes for registration into the Domain Name System, and draft Recommendation ITU-T E.A-N/GoC (new version), on administrative procedures for ENUM for E.164 country codes and associated ICs for networks and GICs for groups of countries,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 49-01 | SG2 to study how ITU could have administrative control over changes that could relate to the international telecommunication resources used for ENUM (resolves 1) | Ongoing |  |  |
|  | Actions by ITU-T SG2 depend on Contributions, but no such contributions have been received so far. |  |  |  |
| 49-02 | SG2 to evaluate the current interim procedure for ENUM delegation and report back to TSBDir. (resolves 2) | Ongoing |  |  |
|  | At the meeting of ITU- T SG2 in November 2023, the experts agreed to update the Interim Procedures for Geographic Country Codes in order for the Director of TSB to take action in cases where a Member State does not respond to enquiries related to non-operational CC ENUM delegations under their responsibility (see SG2-TD323/PLEN) |  |  |  |
| 49-03 | TSBDir to report to Council annually regarding progress achieved in ENUM (instructs TSBDir) | Ongoing, 3 months before Council | √ |  |
|  | The TSB Director reports annually in the Council document on "ITU Internet activities: Resolutions 101, 102, 133, 180, and 206", which includes updates regarding ENUM domain names, including information on approved ENUM delegations and ENUM trials, if any; see S22-CL-C-0033. |  |  |  |

» Top

# Resolution 50 - Cybersecurity

resolves

1	to continue to give this work high priority within ITU-T, in accordance with its competencies and expertise, including promoting common understanding among governments and other stakeholders of building confidence and security in the use of ICTs at the national regional and international level;

2	that all ITU-T study groups continue to evaluate existing and evolving Recommendations, with respect to their robustness of design and potential for exploitation by malicious parties, and take into account emerging new services and applications to be supported by the global telecommunication/ICT infrastructure (e.g. including but not limited to cloud computing and IoT, which are based on telecommunication/ICT networks), according to their mandates in Resolution 2 (Rev. Geneva, 2022) of this assembly;

3	that ITU-T continue to raise awareness, within its mandate and competencies, of the need to harden and defend information and telecommunication systems from cyberthreats and malicious cyber activity, and continue to promote cooperation among appropriate international and regional organizations in order to enhance exchange of technical information in the field of information and telecommunication network security;

4	that ITU-T raise global awareness regarding security in ICTs through the development of Recommendations and technical reports which support cybersecurity procedures, technical policies and standards frameworks;

5	that ITU-T should work closely with ITU-D, particularly in the context of ITU-D Question 3/2 (Securing information and communication: Best practices for developing a culture of cybersecurity);

6	that relevant ITU-T study groups should keep pace with the development of the new and emerging technologies, according to their mandates, to develop Recommendations, Supplements and technical reports that help to overcome challenges related to security;

7	that ITU-T continue work on the development and improvement of terms and definitions related to building confidence and security in the use of telecommunications/ICTs, including the term cybersecurity;

8	that global, consistent and interoperable processes for sharing incident-response related information should be promoted;

9	that ITU-T study groups continue to liaise with standards organizations and other bodies active in this field and encourage the engagement of experts in the ITU's activities in the area of building confidence and security in the use of ICTs;

10	that security aspects should be considered throughout the ITU-T standards-development process;

11	that secure, trusted and resilient telecommunication/ICT networks and services should be developed and maintained to enhance confidence in the use of ICT;

12	that ITU-T Study Group 17 needs to develop cooperative security analysis and incident management frameworks;

13	that the resilience of ICT networks and systems should be considered as a priority in network and infrastructure development,

instructs Study Group 17

1	to promote the studies on cybersecurity including security for new services and emerging applications to be supported by the global telecommunication/ICT infrastructure;

2	to support the Director of the Telecommunication Standardization Bureau to maintain the "ICT Security Standards Roadmap", which should include work items to progress standardization work related to security, and share this with relevant groups of ITU-R and ITU-D as the mission of the lead group for security;

3	to promote joint coordination activities on security among all relevant study groups and focus groups in ITU and other SDOs;

4	to collaborate closely with all other ITU-T study groups, to establish an action plan to assess existing, evolving and new ITU -T Recommendations to counter security vulnerabilities, and continue to provide regular reports on security of telecommunications/ICT to the Telecommunication Standardization Advisory Group (TSAG);

5	to define a general/common set of security capabilities for each phase of information systems/networks/applications lifecycle, so that consequently security by design (security capabilities and features available by design) could be achieved for systems/networks/applications from day one;

instructs the Director of the Telecommunication Standardization Bureau

1	to continue to maintain, in building upon the information base associated with the "ICT Security Standards Roadmap" and the ITU-D efforts on cybersecurity, and with the assistance of other relevant organizations, an inventory of national, regional and international initiatives and activities to promote, to the maximum extent possible, the worldwide harmonization of strategies and approaches in this critically important area, including the development of common approaches in the field of cybersecurity;

2	to contribute to annual reports to the ITU Council on building confidence and security in the use of ICTs, as specified in Resolution 130 (Rev. Dubai, 2018);

3	to report to the Council on the progress of the activities on the "ICT Security Standards Roadmap";

4	to continue to recognize the role played by other organizations with experience and expertise in the area of security standards, and coordinate with those organizations as appropriate;

5	to continue the implementation and follow-up of relevant WSIS activities on building confidence and security in the use of ICTs, in collaboration with the other ITU Sectors and in cooperation with relevant stakeholders, as a way to share information on and best practices national, regional and international and non-discriminatory cybersecurity-related initiatives globally;

6	to cooperate with the Secretary-General's GCA and other global or regional cybersecurity projects, as appropriate, in promoting capacity building and developing relationships and partnerships with various regional and international cybersecurity-related organizations and initiatives, as appropriate, and to invite all Member States, particularly developing countries, to take part in these activities and to coordinate and cooperate with these different activities;

7	to support the Director of the Telecommunication Development Bureau in assisting Member States in the establishment of an appropriate framework among developing countries allowing rapid response to major incidents, and to propose an action plan to increase their protection, taking into account mechanisms and partnerships, as appropriate;

8	to support relevant ITU-T study group activities related to strengthening and building confidence and security in the use of ICTs;

9	to disseminate information to all stakeholders related to cybersecurity through the organization of training programmes, forums, workshops, seminars, etc., for policy makers, regulators, operators and other stakeholders, especially from developing countries to raise awareness and identify needs in collaboration with the Director of BDT,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 50-01 | TSBDir to continue to give this work high priority within ITU-T, in accordance with its competencies and expertise, including promoting common understanding among governments and other stakeholders of building confidence and security in the use of ICTs at the national regional and international level. (resolves 1) | Ongoing |  |  |
| 50-02 | All SGs to continue to evaluate existing and evolving new Recommendations for robustness of design and potential for malicious exploitation (e.g. on cloud computing and IoT based on telecommunication networks) (resolves 2). | Ongoing | √ |  |
|  | SG17 has ongoing work to develop security standards for SDN, big data analytics, mobile communication, cloud computing, IoT. SG17 has approved 39 Recommendations on ICT security in this Study Period, as reported to TSAG in TSAG-TDs 38, 206, 340. |  |  |  |
| 50-05 | SG17 to continue develop and improve terms and definitions related to building confidence and security, including the term cybersecurity. (resolves 7) | Ongoing | √ |  |
|  | SG17 sends LS to SCV on intended terms and definitions for action to SCV prior to each SG17 meeting. |  |  |  |
| 50-06 | SG17 to promote global, consistent and interoperable processes for sharing incident-response related information. (resolves 8) | Ongoing |  |  |
|  | SG17 is adopting OASIS STIX Version 2.1 and TAXII Version 2.1 and has draft ITU-T Recommendations X.1221 and X.1222 determined. |  |  |  |
| 50-08 | TSBDir to continue to maintain an inventory of initiatives and activities to promote harmonization of strategies including common approaches in the field of cybersecurity. (instructs TSBDir 1) | Ongoing | √ |  |
|  | SG17 maintains a webpage of Network Forensic and Vulnerability Organizations. |  |  |  |
| 50-09 | TSBDir to report to annual reports to Council on actions taken under Resolution 50, and on ICT Security Standards Roadmap. (instructs TSBDir 2, 3) | Annual, Council 2024 | √ |  |
|  | TSB Director reports on security to Council are contained within S22-CL-C-0018, S23-CL-C-0038. SG17 keeps updating the ICT Security Standards Roadmap database. |  |  |  |
| 50-10 | TSBDir to continue contributing to WSIS security activities. (instructs TSBDir 5) | Ongoing | √ |  |
|  | SG17 work on security standardization contributes to technical measures to implementation WSIS Action Line C5, as reported to annual ITU Council, e.g., S23-CL-C-0061. |  |  |  |
| 50-11 | TSBDir to cooperate with GCA etc to develop relationship/partnership for ITU membership, esp. developing countries. (instructs TSBDir 6) | Ongoing | √ |  |
|  | ITU General secretary is taking lead, see SecGen’s reports to annual ITU Council, e.g., S23-CL-C-0061. |  |  |  |
| 50-13 | TSBDir to support BDTDir in assisting Member States in the establishment of an appropriate framework between developing countries allowing rapid response to major incidents, and to propose an action plan to increase their protection (instructs TSBDir 7) | Ongoing | √ |  |
|  | BDT is taking lead, see SecGen’s reports to annual ITU Council, e.g., S23-CL-C-0061. |  |  |  |
| 50-14 | TSBDir to support relevant ITU-T study group activities related to security (instructs TSBDir 8) | Ongoing | √ |  |
|  | The TSB Director continuously is supporting security activities in the ITU-T study groups such as in SG11, SG17, SG20, and regional groups. |  |  |  |
| 50-15 | All ITU-T SGs to ensure that security aspects are considered throughout the ITU-T standards development process (resolves 9) | Ongoing | √ |  |
|  | SGs are encouraged to follow the same approach when applicable. SG20 is working on Recommendations on cybersecurity and identification. Find the SG20 work programme available here. |  |  |  |
| 50-16 | ITU-T to continue to raise awareness, within its mandate and competencies, of the need to harden and defend information and telecommunication systems from cyberthreats and cyberattacks, and continue to promote cooperation among appropriate international and regional organizations. (resolves 3) | Ongoing |  |  |
| 50-17 | ITU-T study groups should work closely with ITU-D (e.g. ITU-D Q3/2) (resolves 4) | Ongoing |  |  |
| 50-18 | SG17, in close collaboration with all other ITU-T SGs, establish an action plan to assess existing, evolving and new ITU-T Recommendations to counter security vulnerabilities and continue to provide regular reports to TSAG (instructs 4 SG17) | Ongoing Each TSAG meeting | √ |  |
|  | SG17 maintains and keeps updating an ICT security standards roadmap since 2006 which includes 2600+ existing and ongoing ICT security standards in major SDOs, such as 3GPP, ETSI, FIDO Alliance, IEEE, IETF, ISO/IEC JTC 1/SC 27, OASIS, etc. SG17 reports on its LSG functions to each TSAG . |  |  |  |
| 50-20 | TSBDir to continue to recognize the role played by other organizations with experience and expertise in the area of security standards, and coordinate with those organizations as appropriate (instructs TSBDir 4) | Ongoing | √ |  |
|  | SG17 maintains and keeps updating an ICT security standards roadmap since 2006 which includes 2600+ existing and ongoing ICT security standards in major SDOs, such as 3GPP, ETSI, FIDO Alliance, IEEE, IETF, ISO/IEC JTC 1/SC 27, OASIS, etc. SG17 liaises with relevant organizations as necessary, and developed common/twin texts with ISO/IEC JTC 1/SC 27 and adopted standards from OASIS and FIDO Alliance into ITU-T Recommendations. |  |  |  |
| 50-21 | Relevant ITU-T study groups should keep pace with the development of the new and emerging technologies, according to their mandates, to develop Recommendations, Supplements and technical reports that help to overcome challenges related to security. (resolves 6) | Ongoing | √ |  |
|  | - SG13 convenes tutorial on a particular technical topic alongside its SG meeting. - SG17 organizes workshop on security of new emerging technologies prior to each SG17 meeting. In this study period, SG17 has organized workshops on 5G and beyond, DLT, software supply chain, generative AI. - SG20 is working on the development of Recommendations and Supplements on Security, privacy, trust and identification for IoT and SC&C. Find the list of draft Recommendations and draft Supplements available here. |  |  |  |
| 50-22 | ITU-T SG17 needs to develop cooperative security analysis and incident management frameworks. (resolves 12) | Ongoing |  |  |
| 50-23 | ITU-T SG17 to promote the studies on cybersecurity including security for new services and emerging applications to be supported by the global telecommunication/ICT infrastructure. (instructs 1 SG17) | Ongoing | √ |  |
|  | See SG17 activities reported under 50-21 above. |  |  |  |
| 50-24 | ITU-T SG17 to maintain the "ICT Security Standards Roadmap", which should include work items to progress standardization work related to security, and share this with relevant groups of ITU-R and ITU-D as the mission of the lead group for security. (instructs 2 SG17) | Ongoing | √ |  |
|  | SG17 maintains and keeps updating at every SG17 meeting an ICT security standards roadmap since 2006 which includes 2600+ existing and ongoing ICT security standards in major SDOs, such as 3GPP, ETSI, FIDO Alliance, IEEE, IETF, ISO/IEC JTC 1/SC 27, OASIS, etc, which includes work items to progress standardization work related to security, and share this with relevant groups of ITU-R and ITU-D as the mission of the lead group for security. |  |  |  |
| 50-25 | ITU-T SG17 to promote joint coordination activities on security among all relevant study groups and focus groups in ITU and other SDOs. (instructs 3 SG17) | Ongoing | √ |  |
|  | SG17 has security contacts for coordinating activities on security with other study groups. |  |  |  |
| 50-26 | ITU-T SG17 to define a general/common set of security capabilities for each phase of information systems/networks/applications lifecycle, so that consequently security by design (security capabilities and features available by design) could be achieved for systems/networks/applications from day one. (instructs 5 SG17) | Ongoing | √ |  |
|  | SG17 established a correspondence group CG-SECAPA to develop a work item X.secadef Security capabilities definitions . |  |  |  |
| 50-27 | ITU-T SG17 to design security architecture reference framework(s) with security functional components which could be considered as the basis of security architecture design for various systems/networks/applications in order to improve the quality of recommendations on security. (instructs 6 SG17) | Ongoing | √ |  |
|  | This instruction depends on the Resolve 5 and therefore 50-26 above. Another existing work item X.arch-design needs to be finished too. |  |  |  |
| 50-28 | TSBDir to disseminate information to all stakeholders related to cybersecurity through the organization of training programmes, forums, workshops, seminars, etc., for policy makers, regulators, operators and other stakeholders, especially from developing countries to raise awareness and identify needs in collaboration with the Director of BDT. (instructs TSBDir 9) | Ongoing | √ |  |
|  | See SG17 activities reported under 50-21 above. |  |  |  |

» Top

# Resolution 52 - Countering and combating spam

resolves to instruct the relevant study groups

1	to continue to support ongoing work, in particular in Study Group 17, related to countering spam (e.g. e-mail) and to accelerate their work on spam in order to address existing and future threats within the remit and expertise of ITU-T, as appropriate;

2	to continue collaboration with the ITU-Telecommunication Development Sector (ITU-D) and with the relevant organizations, including other relevant standards organizations (e.g. the Internet Engineering Task Force (IETF)), in order to continue developing, as a matter of urgency, technical Recommendations with a view to exchanging best practices and disseminating information through joint workshops, training sessions, etc.,

further instructs Study Group 17 of the ITU Telecommunication Standardization Sector

1	to report regularly to the Telecommunication Standardization Advisory Group on progress under this resolution;

2	to support ITU-D Study Group 2 on countering and combating spam in its work providing technical training sessions and workshop activities in different regions related to spam policy, regulatory and economic issues and their impact;

3	to continue its work on developing Recommendations, technical papers, and other related publications,

instructs the Director of the Telecommunication Standardization Bureau

1	to provide all necessary assistance with a view to expediting such efforts, working collaboratively with relevant parties that combat spam with a view to identifying opportunities, raising awareness for such activities and identifying possible collaboration, as appropriate;

2	to initiate a study – including sending a questionnaire to the ITU membership –indicating the volume, types (e.g. e-mail spam, SMS spam, spam in IP-based multimedia applications) and features (e.g. different major routes and sources) of spam traffic, in order to help Member States and relevant operating agencies identify such routes, sources and volumes and estimate the amount of investment in facilities and other technical means to counter and combat such spam, taking into account work that has already been carried out;

3	to continue to cooperate with the Secretary-General's initiative on cybersecurity and with the Telecommunication Development Bureau in relation to any item concerning cybersecurity under Resolution 45 (Rev. Dubai, 2014), and to ensure coordination among these different activities;

4	to contribute to the report of the Secretary General to the ITU Council on the implementation of this resolution,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 52-01 | SGs, particular SG17, to accelerate their work on spam (resolves 1) | Ongoing | √ |  |
|  | - The structure of countering spam by technical measures has been established, including five levels: technical strategy level, guideline level, framework level, technology level and supplement level. In this structure, branches of this structure are mainly based on the type of spam: e-mail spam, IP-based multimedia spam, mobile messaging spam, instant messaging spam, etc. - SG17 approved new Recommendations on combating spam are found at https://www.itu.int/itu-t/workprog/wp_search.aspx?isn_sp=8265&isn_status=-1,2&title=spam&details=0&field=acdefghijo. - Ongoing standardization on combating spam are found at: https://www.itu.int/itu-t/workprog/wp_search.aspx?isn_sp=8265&isn_status=-1,1,3&title=spam&details=0&field=acdefghijo |  |  |  |
| 52-02 | SGs to collaborate with ITU-D and with the relevant organizations, including other relevant organizations (i.e. IETF) to develop Recommendations with a view to exchanging best practices; participate in workshops, training sessions, etc. (resolves 2) | Ongoing |  |  |
| 52-03 | SG17 to report on progress of Resolution 52 to each meeting of TSAG (further instructs SG17 1) | TSAG 2024 | √ |  |
|  | SG17 reports on its LSG functions to each TSAG. |  |  |  |
| 52-05 | SG17 to support ITU-D Study Group 2 on countering and combating spam in its work providing technical training sessions and workshop activities in different regions related to spam policy, regulatory and economic issues and their impact. (further instructs SG17 2) | Ongoing | √ |  |
|  | BDT is taking the lead. See action 52-02 SG17 collaboration with ITU-D SG2. |  |  |  |
| 52-06 | SG17 to continue its work on developing Recommendations, technical papers, and other related publications (further instructs SG17 3) | Ongoing | √ |  |
|  | See action also 52-01. SG17 has produced important publications on security work including: - Security Manual - Successful use of security standards. |  |  |  |
| 52-07 | TSBDir to contribute to the report of the Secretary General to the ITU Council on the implementation of this resolution. (instructs TSB Dir 3) | Council 2024 | √ |  |
|  | TSB Director reports to Council are contained within S22-CL-C-0018, S23-CL-C-0038. |  |  |  |
| 52-08 | TSBDir to provide all necessary assistance with a view to expediting such efforts, working collaboratively with relevant parties that combat spam with a view to identifying opportunities, raising awareness for such activities and identifying possible collaboration, as appropriate (instructs TSBDir 1) | Ongoing | √ |  |
|  | TSB Circular 80 containing a Questionnaire on countering spam fraud was prepared by SG17. |  |  |  |
| 52-09 | TSBDir to continue to cooperate with the Secretary-General's initiative on cybersecurity and with BDT in relation to any item concerning cybersecurity under Resolution 45 (Rev. Dubai, 2014), and to ensure coordination among these different activities (instructs TSB Dir 3) | Ongoing | √ |  |
|  | TSB participates in the ITU internal Inter-Sector cybersecurity coordination group. |  |  |  |

» Top

# Resolution 54 – Regional groups of study groups of the ITU Telecommunication Standardization Sector

resolves

1	to support, on a case-by-case basis, to the extent practicable, the coordinated creation of regional groups of ITU-T study groups with at least two supporting members from the region concerned that are committed to contributing actively on the topics assigned to the regional groups;

2	that ITU-T study groups develop terms of reference and working methods for these regional groups and inform TSAG for coordination among study groups;

3	that the composition of regional groups of ITU-T study groups is consistent with considering c), and supported by the regional telecommunications organizations identified under bearing in mind of this resolution;

4	that representatives of Member States and Sector Members who belong to the region concerned may participate fully in the regional groups of ITU-T study groups;

5	that representatives of Associates and Academia that belong to a parent ITU-T study group, and belong to the region concerned, may participate in regional groups of that ITU-T study group, but should not participate in any decision-making or liaison activity, taking into account Resolution 169 (Rev. Dubai, 2018);

6	that meetings of regional groups of other study groups shall, in principle, be limited to delegates and representatives from Member States, Sector Members, Academia and Associates of the study group concerned in the region; however, each regional group may invite other participants to attend all or part of a meeting, to the extent that these other participants would be eligible to attend the meetings of the full study group;

7	to encourage cooperation of regional groups of ITU-T study groups with regional telecommunication standardization entities (regional organizations, regional standardization bodies, and so forth), especially with the regional telecommunication organizations identified under bearing in mind in this resolution, as appropriate, well as the holding of meetings of regional groups of ITU-T study groups jointly with ITU workshops in the region,

invites the regions and their Member States

1	to pursue the creation of regional groups of parent ITU-T study groups in their respective regions, in accordance with resolves of this resolution, and to support meetings and activities of the regional groups, as appropriate, in coordination with the Telecommunication Standardization Bureau;

2	to develop draft terms of reference and working methods for these regional groups, which are to be consistent with and approved by the parent study group, as regards areas of concern to them;

3	to create regional standardization bodies, as appropriate, and encourage joint and coordinated meetings of such bodies with the regional groups of ITU-T study groups in their respective regions, so that these standardization bodies act as an umbrella for such regional group meetings the regional group meetings should be held jointly with thematic ITU workshops being conducted in the region, whenever possible;

4	to propose candidates for regional group chairmanships and vice-chairmanships;

5	to encourage the candidacy of women for the regional group management positions;

6	to encourage eligible ITU-T members from the respective region to participate in the meetings of their regional groups, and to consider terminating a regional group when it is no longer required,

invites the regional groups thus created

1	to disseminate information about telecommunication standardization and encourage the involvement of developing countries in standardization activities in their regions, and to submit written contributions to the parent study group in which they work in accordance with approved terms of reference reflecting the priorities of their respective regions;

2	to cooperate closely with the relevant respective regional telecommunication organizations, standardization bodies and ITU regional offices to create possible synergies and to report on their work in their regions to the relevant parent ITU-T study groups,

instructs study groups and the Telecommunication Standardization Advisory Group

1	to coordinate joint meetings of the regional groups of ITU-T study groups;

2	to consider and identify questions of greatest interest to Member States and Sector Members from developing countries with a view to keeping them updated on the development of international standards in the context of the regional groups of ITU-T study groups,

instructs the Director of the Telecommunication Standardization Bureau, in collaboration with the Director of the Telecommunication Development Bureau

within the allocated or contributed resources that are available

1	to provide all necessary support for creating and ensuring the smooth functioning of the regional groups of the ITU-T study groups;

2	to consider, whenever possible, holding events (workshops, forums, seminars, training, etc.) concurrently with meetings of the ITU-T regional groups, in the relevant regions, and vice versa;

3	to take all necessary measures to facilitate the organization of meetings of the regional groups of ITU-T study groups and workshops in the relevant regions,

calls upon the Director of the Telecommunication Standardization Bureau

1	to cooperate with the Director of the Telecommunication Development Bureau and with the Director of the Radiocommunication Bureau, as appropriate, in order to :

i)	continue to provide specific assistance to regional groups of ITU-T study groups;

ii)	encourage the use of electronic working methods to assist the members of the regional groups;

iii)	take appropriate steps to facilitate meetings of regional groups in order to promote the necessary synergies among the three Sectors and thereby improve the effectiveness and efficiency of the study groups,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 54-01 | TSB to support coordinated creation of regional groups of ITU-T study groups (resolves 1) | Ongoing | √ |  |
|  | The following regional groups have met since WTSA-20: ITU-T Study Group 2 - SG2RG-AFR: Abidjan, Cote D'Ivoire, 21-22 September 2023 co-located with SG13RG-AFR at the same place. ITU-T Study Group 3 - SG3RG-AFR: Fully virtual meeting, 2-5 May 2022. - SG3RG-AFR: Brazzaville, Republic of the Congo, 7-9 February 2023. - SG3RG-AO: New Delhi, India, 9-12 August 2022. - SG3RG-AO: Fully virtual meeting, 23 January 2023. - SG3RG-AO: Bangkok, Thailand, 11-12 September 2023. - SG3RG-ARB: Manama, Bahrain, 30-31 January 2023. - SG3RG-ARB: Fully virtual meeting, 20 June 2023. - SG3RG-LAC: Fully virtual meeting, 6-7 September 2022. - SG3RG-LAC: San Jose, Costa Rica, 28-29 September 2023. ITU-T Study Group 5 - SG5RG-AFR: Kampala, Uganda, 15-17 May 2023 - SG5RG-AP: Fully virtual meeting, 25 May 2023 - SG5RG-AP: Bangkok, Thailand, 11-12 September 2023 ITU-T Study Group 11 ITU-T Study Group 12 - SG12RG-AFR: Banjul, The Gambia, 15-16 March 2023. ITU-T Study Group 13 - SG13RG-AFR: Fully virtual meeting, 20 October 2022. - SG13RG-AFR: Abidjan, Cote D'Ivoire, 21-22 September 2023 co-located with SG2RG-AFR at the same place. ITU-T Study Group 17 - SG17RG-ARB: Cairo, Egypt, 18 May 2023. - SG17RG-AFR: Kampala, Uganda, 23 November 2023 ITU-T Study Group 20 - SG20RG-AFR: Sharm El-Sheik, Egypt, 8 June 2023. - SG20RG-AP: Virtual, 25-26 July 2023. - SG20RG-ARB: Virtual, 1 August 2023. |  |  |  |
| 54-04 (44-14) | SGs and TSAG to coordinate joint meetings of regional groups (instructs SGs 1 + TSAG) | Ongoing | √ |  |
|  | Also, see 54-01. |  |  |  |
| 54-05 (44-21) | TSB to provide all necessary support for creation, organization of meetings and workshops of the regional groups of the ITU-T study groups to ensure their smooth functioning (see also Resolution 44). (instructs TSB Dir 1) | Ongoing | √ |  |
|  | See 44-21. |  |  |  |
| 54-06 (44-24) | TSB to conduct events (workshops, forums, seminars, training, etc.) for developing countries, concurrently with meetings of ITU-T regional groups in the relevant regions and vice versa, in coordination/collaboration with ITU-D (see also Resolution 44). (instructs TSBDir 2) | Ongoing | √ |  |
|  | See 44-24. |  |  |  |
| 54-07 | TSBDir to cooperate with BDTDir and BRDir to continue provide specific assistance to regional groups of ITU-T study groups, encourage the use of electronic working methods to assist the members of the regional group, and take appropriate steps to facilitate meetings of regional groups to improve the effectiveness and efficiency of the SGs (calls upon TSBDir i), ii), iii)) | Ongoing | √ |  |
|  | TSB Director holds monthly coordination meetings with the ITU regional Directors. |  |  |  |
| 54-09 | Regional groups to cooperate closely with the relevant respective regional telecommunication organizations, standardization bodies and ITU regional offices, to create possible synergies and to report on their work in their regions to the relevant parent ITU-T study groups (invites RGs 2). | Ongoing |  |  |

» Top

# Resolution 55 – Promoting gender equality in ITU Telecommunication Standardization Sector activities

resolves

1	that ITU-T continue efforts to ensure that all its policies, work programmes, information dissemination activities, publications, study groups, seminars, courses, assemblies and conferences reflect the commitment to gender equality, and promote gender balance:

i) for posts, including those at the Professional and higher levels in TSB,

ii) in the selection of chairmen, vice- chairmen and rapporteurs of the ITU-T study groups and of TSAG;

2	that a high priority be accorded to gender mainstreaming in the management, staffing and operation of ITU-T, while taking into account geographical representation;

3	that ITU-T continue to support WISE,

instructs the Director of the Telecommunication Standardization Bureau

1	to take the necessary steps to continue implementing the ITU GEM Policy, including, supporting the implementation of recommendations from the Joint Inspection Unit relevant to gender mainstreaming, supporting the Gender Focal Points for ITU-T, and encouraging TSB staff to undertake relevant training;

2	to accelerate the integration of a gender perspective in the work of TSB in accordance with the principles already applied in ITU;

3	to accord high priority to gender mainstreaming in ITU-T management, financial assistance, staffing and operation;

4	to conduct an annual review on progress made in the Sector in advancing gender mainstreaming, including by circulating questionnaires, and by collecting and reviewing statistics on ITU-T standardization activities by and region, in order to identify challenges to women’s participation, and subsequent solutions; gender, and to share findings with TSAG and the next world telecommunication standardization assembly;

5	to encourage the participation of women in all aspects of ITU-T activities, and particularly the opportunity to participate in meetings, and support an increase in the number of women from all regions in ITU-T leadership positions by:

i)	encouraging membership to include women on their delegations, by, inter alia, including in all circulation letters the statement, “The membership is invited to include women on their delegations whenever possible”;

ii)	making the selection of women for TSB positions at the Professional and higher levels a top priority;

iii)	providing training on participation in meetings, writing contributions and chairing meetings;

6	to enhance the ongoing work of WISE to ensure that all women have an opportunity to develop as ITU-T leaders;

7	to continue posting on a public-facing WISE webpage current information on the number of women attending Sector events, including administration or Sector Member affiliation and study group distribution, and identify the study groups in which women hold leadership positions;

7	to include gender balance as a factor in the distribution of financial assistance to attend ITU-T meetings where resources are available;

8	to join the ITU Secretary-General in participating in the Planet 50/50 initiative sponsored by the United Nations High Commissioner for Human Rights to tackle invisible gender bias as a Geneva Gender Champion on behalf of ITU-T,

invites the Secretary-General

1	to comply with the reporting obligations, as required by UNSWAP, on ITU-T activities aimed at promoting gender equality and the empowerment of women;

2	to continue encouraging ITU staff to take account of the gender-neutral guidelines in the ITU English Language Style Guide and to avoid, as much as possible, the use of gender-specific terms,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 55-02 | TSBDir to take the necessary steps to continue implementing the ITU GEM Policy, including, supporting the implementation of recommendations from the Joint Inspection Unit relevant to gender mainstreaming, supporting the Gender Focal Points for ITU-T, and encouraging TSB staff to undertake relevant training (instructs TSBDir 1) | Ongoing | √ |  |
|  | TSB continues to collaborate with the other Bureaux and the General Secretariat to build a framework to move the gender agenda forward, under the umbrella of the ITU Gender Taskforce. All TSB staff are now required to take “I Know Gender” as an ITU wide mandatory training. More importantly, ITU-T experts and staff involved in standards development processes have been invited through ITU Circular 71 to undertake the UNECE training on gender responsive standards with a view to raise their awareness of a gender dimension in standardization as well as ways to incorporation a gender perspective in standards processes. Further, a session on Gender Responsive Standards,” Why a gender lens in ICT standardization matters” was delivered as part of the WSIS Forum on 5 May 2023 to continue to raise awareness on how to incorporate a gender lens in the process of standards development and help ensure that the standards developed are gender responsive. The recording is accessible online. |  |  |  |
| 55-03 | TSBDir to encourage the participation of women in all aspects of ITU-T activities and support an increase in the number of women from all regions in ITU-T leadership positions (encouraging membership to include women on their delegations, selection of women for TSB positions at the Professional and higher levels; selection of chairmen vice chairmen and rapporteurs of ITU-T SGs and of TSAG; and providing training on participation in meetings, writing contributions and chairing meetings (resolves 1, instructs TSBDir 5) | Ongoing | √ |  |
|  | Member States and Sector Members are continually encouraged to support the active participation of women in standardization groups and activities as per this Resolution. Through the Bridging the Standardization Gap programme, TSB provides training on how to write and present contributions. Currently, 51% TSB staff are women. In the professional grade category overall 41% are women while parity has been achieved at P5 level, i.e. 50% are women. Gender parity objectives for WTSA-24 were established, supported by the NOW4WTSA-24 campaign. The campaign encourages Member States to commit to increasing the number of women in ITU-T leadership positions and achieving a 35% female participation target at WTSA-24. A special event “Network of Women Breakfast at TSAG’’ scheduled on 23 January 2024, will mark the launch of NOW4WTSA24. The event will include a panel discussion on ‘’Towards promoting gender equality in standardization’’ with the objective of discussing the enhancement of women's participation in standardization. Member States are encouraged to pledge their support for gender equality in WTSA-24 delegations. TSB plans a series of training for women delegates attending WTSA-24. These sessions will aim to enhance women's knowledge of ITU-T and WTSA leadership, and contribute to reaching the 35% female participation target at WTSA-24. This initiative reinforces TSB's commitment to increased women participation in ITU-T and aligns with the broader ITU effort to offer targeted training for women across key conferences. TSB will be organizing NoW in ITU-T event at WTSA-24 announced for 17 October 2024. Further details will be provided in due course. SG13RG-AFR updated terms of reference recognize and encourage women from Africa involvement into the activities of this regional group. |  |  |  |
| 55-04 | ITU-T to continue WISE; and continue posting WISE web-page (resolves 3, instructs TSBDir 6, 7) | Ongoing | √ |  |
|  | TSAG supported to rename the Women in Standardization Expert Group (WISE) to "Network of Women in ITU-T (NoW)" in ITU-T, and has launched the Network of Women (NoW) in ITU-T; and TSB is joining forces with BDT and BR on corresponding NoW activities.The Terms of Reference outlining the mission, scope, and work plan of the network to promote gender equality in ITU-T activities will be presented at TSAG in January 2024 for comments (see TD 423).TSB has enhanced collaboration with BR and BDT on NoW, leveraging insights and experience throughout ITU. This supports the objective of a "OneITU" approach to gender equality, as outlined in Council-23 C23/76 corr.1, which calls for a new ITU-wide mechanism to coordinate the Network of Women. A new website for NoW in ITU-T has been created, aligning with NoW in ITU-D and NoW in ITU-R. Additionally, a dedicated NoW4WTSA24 page has been created on the WTSA-24 website, with the aim of sharing and promoting upcoming activities. |  |  |  |
| 55-05 | TSBDir to conduct an annual review on progress made in the Sector in advancing gender mainstreaming, including by circulating questionnaires, and by collecting and reviewing statistics on ITU-T standardization activities by gender, and region, in order to identify challenges to women’s participation, and subsequent solutions; and to share findings with TSAG and the next WTSA. (instructs TSBDir 4) | Ongoing; TSAG 2024, WTSA-24 | √ |  |
|  | TSB Circular 70 “Survey on Promoting gender equality in ITU Telecommunication Standardization Sector activities” was issued. Results of the survey which closed on 31 March 2023 were shared with TSAG in June 2023 (TSAG-TD196). TSB is actively implementing actions based on the survey's findings as part of the NoW in ITU-T work plan. |  |  |  |
| 55-06 | Sec-Gen to comply with the UNSWAP reporting obligations on the ITU-T activities aimed at promoting gender equality and the empowerment of women, and encourage ITU staff to avoid as much as possible gender-specific language. (invites SecGen 1, 2) | Ongoing | √ |  |
|  | ITU Sec-Gen has complied with UN SWAP reporting obligations. ITU has been reporting on the United Nations System-Wide Action Plan on Gender Equality and the Empowerment of Women (UN-SWAP) since its endorsement by the CEB in 2012. ITU was commended for implementing new mandatory gender training as well for reporting UN-SWAP results to the Council. ITU continues efforts to incorporate a gender perspective in the work programmes, management approaches, and human resource development of the Union. For example, a gender element has now been incorporated into the staff electronic performance management and development system (ePMDS). TSB staff are invited to conduct a Gender Equality Capacity Assessment to ensure a gender perspective in ITU's work, aligning with the requirements of UN-SWAP (UN System-Wide Action Plan on Gender Equality and the Empowerment of Women). Communications regarding the Council's decision to adopt gender-neutral language were shared with TSB and the relevant Study Groups mailing lists. This follows Council 2023 decided to abrogate Decision 500 of 2000. The Director of TSB, Mr Seizo Onoe , supports the various initiatives to improve gender equality in TSB and ITU-T. |  |  |  |
| 55-07 | TSBDir to join the ITU Secretary General in participating the Planet 50/50 initiative. (instructs TSBDir 9) | Ongoing | √ |  |
|  | Then TSB Director supports the ITU Secretary General’s participation in the Planet 50/50 initiative and continues to encourage gender balanced panels in ITU-T meetings and conferences. |  |  |  |

» Top

# Resolution 58 – Encourage the creation of national computer incident response teams, particularly for developing countries

resolves

to support the creation of national CIRTs in Member States where CIRTs are needed and are currently absent,

instructs the Director of the Telecommunication Standardization Bureau, in collaboration with the Director of the Telecommunication Development Bureau

1	to identify best practices to establish CIRTs in line with the ITU toolkit;

2	to identify where national CIRTs are needed, particularly in developing countries, and encourage their establishment;

3	to collaborate with international experts and bodies to establish national CIRTs;

4	to provide support, as appropriate, within existing budgetary resources;

5	to facilitate collaboration between national CIRTs, such as capacity building and exchange of information, within an appropriate framework;

6	to take necessary action to progress implementation of this resolution,

invites the Member States

1	to consider the creation of a national CIRT as a high priority;

2	to collaborate with other Member States and with Sector Members,

invites Member States and Sector Members

to cooperate closely with ITU-T and ITU-D in this regard.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 58-01 | TSBDir, in collaboration with BDTDir and SG17, to identify best practices to establish CIRTs and identify where CIRTs are needed (instructs TSBDir 1) | Ongoing | √ |  |
|  | BDT is taking the lead. Q3/17 and Q4/17 prepared a global directory of cybersecurity organizations, including CIRTs, which is currently hosted and maintained by the TSB on the SG17 website at: http://www.itu.int/ITU-T/studygroups/com17/nfvo/index.html. This fosters global collaboration among organizations. Q3/17 developed Recommendation ITU-T X.1060, which provides a framework for organizations to build and manage a Cyber Defence Centre (CDC) and indicates CDC security services for those who are responsible for security at the top management level of an organization, such as Chief Security Officer (CSO) and/or Chief Information Security Officer (CISO), and security supervisors who assist the CSO and/or CISO. Q3 conducted cyber defence centre framework survey to Africa with RG-AFR and TSB until the end of March 2022, which was issued in December 2021 as a Circular 365 (Questionnaire on Assessment of Cyber Defence Centres in Africa Using Recommendation ITU-T X.1060: Framework for Creation and Operation of a Cyber Defence Centre). Q3/17 established new work item X.sup-cdc, Supplement to ITU-T X.1060: X.1060 Tutorial material at its September 2022 SG17 meeting. Q4/17 is processing on new work item X.icd-schemas, Security data schemas for integrated cyber defence solutions. |  |  |  |
| 58-02 | TSBDir, in collaboration with BDTDir, to facilitate capacity building and information exchange between national CIRTs (instructs TSBDir 5) | Ongoing | √ |  |
|  | BDT is taking the lead. See Q3/17 work on X.1060 reported under 58-01 above. |  |  |  |
| 58-03 | Q3/17 to continue study the issue of CIRTs creation and possibility to provide a guideline in line with X.1056 (Security incident management for telecommunication organizations), in collaboration with Q4/17 and other relevant Questions and Recommendations (e.g., ITU-T E.409) | Ongoing |  |  |
|  | See Q3/17 work on X.1060 reported under 58-01 above. |  |  |  |

» Top

# Resolution 60 – Responding to the challenges of the evolution of the identification/numbering system and its convergence with IP-based systems / networks

resolves to instruct ITU-T Study Group 2, within the mandate of ITU-T

1	to continue studying, in liaison with the other relevant study groups, the necessary requirements for the structure and maintenance of telecommunication numbering, naming, addressing and identification resources in relation to the deployment of future telecommunications/ICTs including IP-based networks;

2	to ensure continued the development of the administrative requirements for the use of existing numbering, naming, addressing and identification identification/numbering resources management systems;

3	to continue developing guidelines, as well as a framework, for the evolution of the international telecommunication numbering system and its convergence with IP-based systems, in coordination with related study groups and associated regional groups, so that a basis for any new application can be provided,

instructs relevant study groups, and in particular ITU-T Study Group 13

to support the work of Study Group 2, to ensure that such applications are based on appropriate guidelines, as well as a framework, for the evolution of the international telecommunication numbering system and its convergence with IP-based systems, in coordination with related study groups and associated regional groups, so that a basis for any new application can be provided/identification system to meet the needs of emerging telecommunications/ICTs and services to help investigate their impact on the numbering/identification system,

instructs the Director of the Telecommunication Standardization Bureau

1	to take appropriate action to facilitate the foregoing work regarding the evolution of the international telecommunication numbering, naming, addressing and identification system and its applications;

2	to share experiences in relation to this Resolution,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 60-01 | SG2, supported particularly by SG13, to study necessary requirements and related resource management systems regarding telecommunication identification/numbering resources in relation to the deployment of IP-based networks and the transition to NGN and FN, and to develop guidelines for evolution of the international telecommunication numbering system and its convergence with IP-based systems. | Ongoing |  |  |
|  | Actions by ITU-T SG2 depend on Contributions. |  |  |  |
| 60-02 | SGs (in particular SG13) to support SG2 to ensure that such applications are based on appropriate guidelines, as well as a framework, for the evolution of the international telecommunication numbering system and its convergence with IP-based systems, in coordination with related study groups and associated regional groups. | Ongoing |  |  |
| 60-03 | TSBDir to take appropriate action to facilitate the foregoing work regarding the evolution of the international telecommunication numbering, naming, addressing and identification system and its applications, and to share experiences in relation to this Resolution. | Ongoing |  |  |
| 60-04 | SG2 is requested to conduct further research on draft Resolution on hexadecimal numbering for MSISDN and IMSI (RCC/40A18/1) | Ongoing |  |  |

» Top

# Resolution 61 – Countering and combating misappropriation and misuse of international telecommunication numbering resources

resolves to invite Member States

1	to ensure that ITU-T E.164 numbering resources are used only by the assignees and only for the purposes for which they were assigned, and that unassigned resources are not used;

2	to endeavour to ensure that operating agencies authorized by Member States release routing information to duly authorized agencies in cases of fraud or numbering misuse/misappropriation, in accordance with national law;

3	to encourage administrations, operating agencies and national regulators to collaborate and share information on fraudulent activities related to numbering misappropriation and misuse of international numbering resources, and to collaborate to counter and combat such activities;

4	to encourage all international telecommunication operators to enhance the effectiveness of ITU’s role and to give effect to its Recommendations, particularly those of ITU-T Study Group 2, in order to promote a new and more effective basis to counter, combat and address fraudulent activities due to number misappropriation and misuse, which would help mitigate against them and limit the negative effects of these fraudulent activities and the blocking of international calls;

5	to encourage administrations and international telecommunication operators to implement ITU-T Recommendations in order to mitigate the adverse effects of fraudulent number misappropriation and misuse, including blocking of calls to certain countries,

resolves further

1	that administrations and operating agencies authorized by Member States take, to the furthest extent practicable, all reasonable measures to provide information necessary to address issues related to number misappropriation and misuse;

2	that administrations and operating agencies authorized by Member States should take note of and consider, to the furthest extent practicable, the “Suggested guidelines for regulators, administrations and operating agencies authorized by Member States for dealing with number misappropriation”, in accordance with the attachment to this resolution;

3	that Member States and national regulators should take note of instances of activities related to misappropriation and misuse of international numbering resources, in accordance with Recommendation ITU-T E.164 that are notified, through relevant ITU-T resources (e.g. the ITU-T Operational Bulletin) or directly to them;

4	to request Study Group 2 to continue to study all aspects and forms of misappropriation and misuse of numbering resources within its mandate, in particular of international country codes, with a view to amending Recommendation ITU-T E.156 and its supplements and guidelines to identify means to support countering and combating these activities;

5	to request ITU-T Study Group 3, in collaboration with Study Group 2, to develop definitions for inappropriate activities, including inappropriate activities causing loss of revenue, related to misappropriation and misuse of international numbering resources specified in the relevant ITU-T Recommendations, and to continue to study such matters;

6	to request Study Group 3 to continue to study the economic effects resulting from misappropriation and misuse of numbering resources, including call blocking.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 61-02 | SG3 to develop definitions for inappropriate activities related to misappropriation and misuse of international numbering resources specified in ITU-T Recommendations | Ongoing | √ |  |
|  | - An improved misuse web interface has been deployed to ensure alignment with the latest version of Recommendation ITU-T E.156 (2020), “Guidelines for ITU-T action on reported misuse of ITU-T E.164 number resources”. Details can be found in TSB Circular 81, the web interface can be found at: https://www.itu.int/en/ITU-T/inr/misuse/Pages/default.aspx - ITU-T Study Group 3 work items STUDY_ACPMI (Alternative Calling Procedures, and misappropriation and misuse of facilities and services (CLI, CPND and OI)) and D.SIMBOX (Economic impact of SIMBOX bypass) have not received contributions over a prolonged period of time and has been discontinued from the SG3 work programme. |  |  |  |
| 61-03 | SG3 to study the economic effects of misappropriation and misuse of numbering resources, including call blocking | Ongoing | √ | X |
|  | Work item STUDY_ACPMI Alternative Calling Procedures, and misappropriation and misuse of facilities and services (CLI, CPND and OI) has not received contributions over a prolonged period of time and has been discontinued from the SG3 work programme. |  |  |  |

» Top

# Resolution 62 - Dispute settlement

resolves to instruct ITU-T Study Group 3

1	to expedite its work on international connectivity, in order to facilitate the implementation of relevant resolutions;

2	to collect data with respect to the implementation and practical effects of the implementation of relevant resolutions and ITU-T D-series Recommendations,

invites Member States

1	to encourage each party to include in a negotiation or agreement related to, or arising out of, international connectivity matters a dispute settlement clause in such agreements;

2	to encourage all operating agencies domiciled within their territories to implement relevant ITU-T Recommendations;

3	to contribute to ITU-T's further work in the areas mentioned in this resolution,

instructs the Director of the Telecommunication Standardization Bureau

1	to report annually to the ITU Council with respect to the implementation of this resolution;

2	to provide all necessary support, within the existing budget, to Study Group 3 for its further work on this matter.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 62-01 | SG3 to collect data with respect to implementation and practical effects of implementation of relevant resolutions and D-series Recommendations. | Ongoing |  |  |
|  | SG3 is studying in work item Study_DRCI Dispute Resolution Processes and has updated the base text in November 2023. |  |  |  |
| 62-03 | TSBDir to prepare report to Council annually. | Ongoing, 3 months before Council | √ |  |
|  | For the time being, there is nothing else to report to Council than reflected in 62-01. |  |  |  |

» Top

# Resolution 64 - IP address allocation and facilitating the transition to and deployment of IPv6

resolves

1	to instruct Study Groups 2 and 3, each according to its mandate, to analyse statistics for the purpose of assessing the pace and geography of IPv6 address allocation and registration for interested members and, especially, developing countries, in collaboration with all relevant stakeholders;

2	to enhance the exchange of experiences and information with all stakeholders regarding the deployment of IPv6, with the aim of creating opportunities for collaborative efforts and the enhancement of technical skills, and to ensure that feedback exists to enrich ITU efforts to support the transition and deployment of IPv6,

instructs the Director of the Telecommunication Standardization Bureau, in close collaboration with the Director of the Telecommunication Development Bureau

1	to continue the ongoing activities between the Telecommunication Standardization Bureau (TSB) and BDT, taking into consideration the involvement of those partners willing to participate and bring their expertise to assist developing countries with IPv6 migration and deployment, and respond to their regional needs as identified by BDT, taking into account Resolution 63 (Rev. Buenos Aires, 2017);

2	to update and maintain the website which provides information about global activities related to IPv6, in order to facilitate awareness-raising and highlight the importance of IPv6 deployment for all ITU members and interested entities, as well as information related to training events being undertaken by ITU and relevant organizations (e.g. regional Internet registries (RIR), network operator groups and the Internet Society (ISOC));

3	to promote awareness of the importance of IPv6 deployment, facilitate joint training activities, involving appropriate experts from the relevant entities, provide information, including roadmaps and guidelines, and to assist in the continued establishment of IPv6 test-bed laboratories in developing countries in collaboration with appropriate relevant organizations, and to promote awareness of the need for IPv6 deployment with regard to IoT given the substantial demand for IP addresses for IoT devices;

4	to support BDT in relevant IPv6 training for engineers, network operators and content providers, mainly in developing countries, that can enhance their skills and which they can further apply to planning, deployment, and operation at their respective organizations,

further instructs the Director of the Telecommunication Standardization Bureau

to report to the ITU Council and also to the 2024 world telecommunication standardization assembly, regarding the progress on action taken with respect to resolves above,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 64-02 | SG2 (and SG3) to study allocation of IP addresses, and to monitor and evaluate IPv4 allocation for interested members and, especially, developing countries (resolves 1) | Ongoing | √ |  |
|  | - SG2 is working to bring up to date Recommendation ITU-T E.370, “Service principles when public circuit-switched international telecommunication networks interwork with IP-based networks”. Latest draft in SG2-TD178/PLEN. |  |  |  |
| 64-03 | (SG2 and) SG3 to analyse statistics for the purpose of assessing the pace and geography of IPv6 addresses and registration for interested members and, especially for developing countries, in collaboration with all relevant stakeholders (resolves 2). | Ongoing |  |  |
| 64-06 | TSBDir, in collaboration with BDTDir, to continue project to assist developing countries with IPv6 migration and deployment. (instructs TSBDir 1) | Ongoing | √ |  |
|  | Note: The ITU IPv6 project to assist developing countries with IPv6 migration and deployment is led by ITU-D; reports on the ITU IPv6 project are found in the Council document on "ITU Internet activities: Resolutions 101, 102 and 133, 180, and 206", see S22-CL-C-0033, S23-CL-C-0033. |  |  |  |
| 64-07 | TSBDir, in collaboration with BDTDir, to update and maintain the IPv6 portal website that provides information on global activities related to IPv6 and to training events of ITU and relevant orgs. (instructs TSBDir 2) | Ongoing | √ |  |
|  | The ITU-T IPv6 webpage at https://www.itu.int/en/ITU-T/ipv6/Pages/default.aspx is maintained and has been updated. |  |  |  |
| 64-08 | TSBDir, in collaboration with BDTDir, to provide information, including roadmaps and guidelines to assist in the continued establishment of IPv6 test-bed labs in developing countries in collaboration with other orgs; and to promote awareness of the advantages of IPv6 over IPv4 with regard to IoT given the substantial demand for IP addresses for IoT devices. (instructs TSBDir 3) | Ongoing |  |  |
| 64-09 | TSBDir to report to Council and to WTSA-20 (further instructs TSBDir) | Council 2024, WTSA-24 | √ |  |
|  | The TSB Director reports annually in the Council document on "ITU Internet activities: Resolutions 101, 102 and 133, 180, and 206"; see S22-CL-C-0033, S23-CL-C-0033. |  |  |  |
| 64-10 | TSBDir to support BDT in relevant IPv6 training for engineers, network operators and content providers that can enhance their skills and which they can further apply at their respective organizations (instructs TSBDir 4) | Ongoing | √ |  |
|  | TSB has been coordinating and collaborating with BDT; such as in the IPv6 project for its planning and its implementation. |  |  |  |

» Top

# Resolution 65 - Calling party number delivery, calling line identification and origin identification information

resolves

1	that international CPN delivery shall be provided on the basis of the relevant ITU-T Recommendations where technically possible;

2	that international CLI and OI delivery shall be provided on the basis of the relevant ITU-T Recommendations where technically possible;

3	that the delivered CPN should contain at least either the calling party number or the specially allocated number of the operator/service provider responsible for making the call, so that a terminating country can identify the operator/service provider of the outgoing call, or identify the terminal that originates the call, before it is delivered from the originating country to that terminating country;

4	that the delivered CPN and CLI, if delivered, shall include sufficient information to allow proper billing and accounting, for each international call;

5	that the OI information in a heterogeneous networking environment shall, where technically possible, be an identifier assigned to a subscriber by the originating service provider, or be replaced by a default identifier by the originating provider to identify the origin of the call, if specified by the administration;

6	that the CPN, CLI and OI information shall be transmitted transparently by transit networks (including hubs);

7	to encourage operators to make OI information, wherever applicable, CPN and CLI reliable and verifiable in order to combat spoofing and other forms of numbering misuse,

instructs

1	ITU-T Study Group 2, ITU-T Study Group 3 and, where required, ITU-T Study Group 11 and ITU-T Study Group 17 to further study the emerging issues of CPN delivery, CLI and OI information, in particular for a heterogeneous networking environment, including security methods and possible validation techniques;

2	the study groups concerned to expedite work on Recommendations that would provide additional detail and guidance for the implementation of this resolution;

3	the Director of TSB to report on the progress achieved by the study groups in implementing this resolution, which is intended to improve security and minimize fraud, and minimize technical harm as called for by Article 42 of the Constitution;

4	the Director of TSB to share information on country experiences regarding the implementation of this resolution, in a centralized location,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 65-01 | SG2, SG3, SG11 and SG17 to further study emerging issues of CPND, CLI and OI, including security methods and possible validation techniques (instructs 1) | Ongoing | √ |  |
|  | - Work item STUDY_ACPMI Alternative Calling Procedures, and misappropriation and misuse of facilities and services (CLI, CPND and OI) has not received contributions over a prolonged period of time and has been discontinued from the SG3 work programme. - SG11 approved new Recommendation ITU-T Q.3062 “Signalling procedures and protocols for enabling interconnection between trustable network entities in support of existing and emerging networks” and ITU-T Q.3063 “Signalling procedures of calling line identification authentication”. |  |  |  |
| 65-02 | SGs to expedite work on Recommendations that would provide additional detail and guidance for the implementation of this resolution. | Ongoing | √ |  |
|  | - SG11 developed a dedicated webportal which summarizes all activities and achievements related to signalling security (https://itu.int/go/SIG-SECURITY) SG11 organized two webinars on Signalling Security as follows: - Webinar on "Enhancing signalling security and privacy using globally interoperable digital signatures", June 2022, https://itu.int/go/WB-SSP-01. - ITU Webinar Series on Signalling Security - Episode 2: on "Securing legacy telecom network services", November 2022, https://itu.int/go/WB-SSP-02. |  |  |  |
| 65-03 | TSBDir to report [to WTSA-24] on progress achieved by study groups in implementing Resolution 65 (instructs 3) | WTSA-24 |  |  |
| 65-04 | TSBDir to share information on country experiences regarding the implementation of this resolution, in a centralized location (instructs 4) | Ongoing | √ |  |
|  | ITU-T SG11 standardized an approach on incorporating digital signatures (digital certificates) into signalling exchange (e.g. ITU-T Q.3057, Q.3062, Q.3063, etc.) in order to combat with spoofing numbers and other types of attacks on ICT infrastructure. During the ITU Workshop in 2021 it was noted that there is a need global authority, which will issue such digital certificates. During ITU Webinar in 2022, the best practice security mitigations for these attacks were shared. Moreover, during this webinar it was highlighted that “… the trust anchor for the trust model for those tokens definitely can be ITU as UN specialized agency which is responsible for International Numbering Resources and it is globally trusted organization.” (see Q&A transcript, of ITU webinar, 2022). |  |  |  |

» Top

# Resolution 67 – Use in the ITU Telecommunication Standardization Sector of the languages of the Union on an equal footing and the Standardization Committee for Vocabulary

resolves

1	that the ITU-T study groups, within their terms of reference, should continue their work on technical and operational terms and their definitions in English only;

2	that the work of standardizing vocabulary within ITU-T shall be based on the proposals made by the study groups in the English language, with the consideration and adoption of the translation into the other official languages as proposed by the General Secretariat, and that this shall be ensured by ITU CCT, which is composed of experts fluent in the official languages from all ITU Sectors, and persons designated by interested organizations and other participants in the work of ITU, in close collaboration with the ITU General Secretariat and the Telecommunication Standardization Bureau (TSB) editor for the English language;

3	that, when proposing terms and definitions, the ITU-T study groups shall use the guidelines given in Annex B to the "Author's guide for drafting ITU-T Recommendations";

4	that, where more than one ITU-T study group is defining the same terms and/or concept, efforts should be made to select a single term and a single definition which is acceptable to all of the ITUT- study groups concerned;

5	that, when selecting terms and preparing definitions, the ITU-T study groups shall take into account the established use of terms and existing definitions in ITU, in particular those appearing in the online ITU Terms and Definitions database;

6	that the TSB should collect all new terms and definitions which are proposed by the ITU-T study groups in consultation with ITU CCT, enter them in the online ITU Terms and Definitions database, and provide a search mechanism based on time ranges;

7	that the chairman and six vice-chairmen of SCV, each representing one of the official languages, should be nominated by the WTSA;

8	that the terms of reference of ITU-T SCV are given in the annex to this resolution,

instructs the Director of the Telecommunication Standardization Bureau

1	to continue to translate all Recommendations approved under the traditional approval process (TAP) in all the official languages of the Union;

2	to translate all reports of the Telecommunication Standardization Advisory Group (TSAG), and the reports of study group plenary meetings, in all the official languages of the Union;

3	to translate all ITU-T A-series Recommendations (ITU-T working methods) in all the official languages of the Union;

4	to translate all ITU-T guidelines on intellectual property rights;

5	to translate documents relating to the mandates and working methods of the Director of TSB's ad-hoc groups;

6	to include in the circular that announces the approval of a Recommendation an indication of whether it will be translated;

7	to continue the practice of translating ITUT- Recommendations approved under the alternative approval process (AAP) up to 2 000 pages, within the financial resources of the Union;

8	to monitor the quality of translation and associated expenses;

9	to bring this resolution to the attention of the Directors of the Radiocommunication Bureau and the Telecommunication Development Bureau;

10	to continue to explore all possible options for the provision of interpretation and the translation of ITU documentation available, in order to promote the use of the official languages of the Union on an equal footing during official meetings of ITU-T, in particular during study group meetings,

invites the Council

1	to take appropriate measures to ensure that information is posted on the ITU websites in the six official languages of the Union on an equal footing within budgetary limits, consistent with Council Resolution 1372;

2	to consider a review of Resolution 154 (Rev. Busan, 2014) to enable the feasibility of establishing a single working body within ITU to deal with issues of vocabulary and use of all six languages of the Union on an equal footing,

instructs the Telecommunication Standardization Advisory Group

1	to consider the best mechanism for deciding which Recommendations approved under AAP shall be translated, in light of the relevant Council decisions;

2	to continue consideration on use of all the official languages of the Union on an equal footing in ITU publications and sites.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 67-01 | SGs to follow the guidelines on the use of language and coordination on terms and definitions in this Resolution (resolves 1, 2, 3, 4, 5) | Ongoing | √ |  |
|  | All the ITU-T study groups have appointed their liaison rapporteur for SCV and submit their new terms and definitions to the SCV for harmonization in accordance with resolves 1-5 of this Resolution. |  |  |  |
| 67-02 | TSB to enter all new terms and definitions in the online ITU Terms and Definitions database, and provide a search mechanism based on time ranges (resolves 6) | Ongoing | √ |  |
|  | TSB continues to systematically enter new terms, definitions and abbreviations approved by the membership in ITU-T Recommendations into the online ITU Terms and Definitions database. |  |  |  |
| 67-03 | TSBDir to continue translate TAP Recs, TSAG reports, all SG plenary reports, and all ITU-T A-series Recs, all ITU IPR guidelines, and documents related to mandates and working methods related to TSBDir ad-hoc groups in all official languages of the Union, indicate in approval announcement whether a Rec will be translated (instructs TSBDir 1, 2, 3, 4, 5) | Ongoing | √ |  |
|  | TSB continues to translate all Recommendations approved under the traditional approval process (TAP), as well as all TSAG reports in all the languages of the Union on an equal footing. The ITU IPR guidelines have been translated and are available online (itu.int/ipr). |  |  |  |
| 67-05 | TSAG to consider the best mechanism to decide which AAP Recs shall be translated, in light of relevant Council decisions, and to continue consideration on use of all the official languages of the Union on an equal footing in ITU publications and sites (instructs 1, 2 TSAG) | Ongoing | √ |  |
|  | AAP Recommendations are translated in accordance with the needs expressed by the linguistic groups and the study groups |  |  |  |
| 67-06 | TSBDir to continue the practice of translating ITU-T Recommendations approved under AAP up to 2 000 pages, within the financial resources of the Union (instructs TSBDir 7) | Ongoing | √ |  |
|  | AAP Recommendations are translated in accordance with the needs expressed by the linguistic groups and the study groups, and within budget constraints. |  |  |  |
| 67-07 | TSBDir to monitor the quality of translation and associated expenses (instructs TSBDir 8) | Ongoing | √ |  |
|  | Activities are ongoing within Decision 5 of PP-18/PP-22. |  |  |  |
| 67-08 | TSBDir to bring this resolution to the attention of the BRDir and to the BDTDir (instructs TSBDir 9) | 2022 |  | √ |
|  | BR and BDT were informed. |  |  |  |
| 67-09 | SCV to inform TSAG at least once per year of its activities and to report its results to the next WTSA (ToR #3) | TSAG 2024, WTSA-24 | √ |  |
|  | The SCV reported on its activities and status to TSAG in TSAG-TD435. |  |  |  |

» Top

# Resolution 68 - Evolving role of industry in the ITU Telecommunication Standardization Sector

resolves to instruct the Director of the Telecommunication Standardization Bureau

1	to continue to organize meetings for industry executives, e.g. CTO group meetings, in order to assist in identifying and coordinating standardization priorities and subjects;

2	to bring the needs of developing countries to those meetings by consulting them prior to the meetings and to encourage the participation of local industry representatives;

3	to encourage participation in the CTO group of a wide representation of industry, from the ITU-T Sector Members from all regions;

4	to develop effective mechanisms to organize participation by industry representatives in those meetings (for example, having a stable composition and regular participation in the group by the CTO or alternate);

5	to continue to include the conclusions of the CTO group meetings in an official ITU-T communiqué;

6	to take the conclusions of the CTO group into account in ITU-T work, especially in the strategy function of TSAG and in the ITU-T study groups as appropriate;

7	to produce a regular report to TSAG on the follow-up of the CTO conclusions;

8	to produce a report to the next WTSA assessing the outcomes of the CTO group over the period and examining the need to continue or enhance its activities,

encourages Sector Members from developing countries

to participate at the level of their executives in the CTO meetings, and to raise proposals in regard to their priority standardization areas as well as standardization priorities and needs of developing countries.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 68-01 | TSBDir to organize CTO group meetings (resolves 1) | Ongoing | √ |  |
|  | Two CxO meetings took place on 6 December 2022 and 5 December 2023, Dubai, United Arab Emirates. |  |  |  |
| 68-02 | TSBDir to develop effective mechanisms to attract industry executives and promote ITU-T membership (resolves 3, 4) | Ongoing | √ |  |
|  | TSAG RG-IEM, per its ToR, is mandated to perform a review of the CXO/CTO coordination process. TSAG-RG-IEM also developed (in TSAG-TD153-R2) an action plan for industry engagement. See also 68-01. |  |  |  |
| 68-03 | TSBDir to bring the needs of developing countries to those CTO meetings by consulting them prior to the meetings (resolves 2) | Ongoing |  |  |
| 68-04 | TSBDir to report on outcomes and follow-up of the CTO conclusions of the CTO group to TSAG and WTSA-20 (resolves 7, 8) | TSAG 2024, WTSA-24 | √ |  |
|  | TSAG WP2, per its ToR, is mandated to consider the CXO/CTO recommendations. The December 2022 TSAG WP2 meeting considered TSAG-TD069, which contains the Communiqué of the TSB Director CxO consultation meeting, 6 December 2022, Dubai, United Arab Emirates. The January 2024 TSAG WP2 meeting considered TSAG-TD398, which contains the Communiqué of the TSB Director CxO consultation meeting, 5 December 2023, Dubai, United Arab Emirates. |  |  |  |
| 68-05 | TSBDir to include the conclusions of the CTO group meetings in an official ITU-T communiqué. (resolves 5) | Ongoing | √ |  |
|  | The outcomes of the CxO group meetings are published as ITU-T communiqués on the ITU-T CTO/CxO meeting web-page. See action item 68-01. |  |  |  |
| 68-06 | The Secretary-General and the Director of the Bureau continue to encourage the enhanced participation of entities and organizations in the activities of the Union, in accordance with all relevant provisions of the ITU Constitution and Convention. The Plenipotentiary Conference further invites the Director of Bureau to bring this topic to the attention of TSAG, as appropriate. (PP-22 COM5 Recommendation 5) | Ongoing | √ |  |
|  | TSB informs ITU-T Sector Members through a variety of communication channels, such TSB Circulars, Collective Letters, AAP announcements etc. about study group meetings and planned or taken decisions. Under the guidance of the TSB Director, the TSB Secretariat, in coordination with the General Secretariat, is taking the necessary and appropriate steps to implement Res. 209 (Bucharest, 2022). The TSB Secretariat continues to encourage Academia to actively participate in the work of ITU-T including TSAG. In addition, the TSB Secretariat is engaging Academia in global and regional conferences, workshops and other activities of ITU-T such as Focus Groups and submitting research to our academic publications (ITU Journal on Future and Evolving Technologies). TSAG is informed in (TSAG-TD112) about the Outcome of PP-22 concerning a draft new Resolution on industry participation. |  |  |  |

» Top

# Resolution 69 - Non discriminatory access and use of Internet resources and telecommunications/information and communication technologies

resolves to invite Member States

1	to refrain from taking any unilateral and/or discriminatory actions that could impede another Member State from accessing public Internet sites and using resources, within the spirit of Article 1 of the Constitution and the WSIS principles;

2	to report to the Director of the Telecommunication Standardization Bureau (TSB) on any incident of the kind referred to in resolves 1 above,

instructs the Director of the Telecommunication Standardization Bureau

1	to integrate and analyse the information on incidents reported from Member States;

2	to report this information to Member States, through an appropriate mechanism;

3	to report to the Telecommunication Standardization Advisory Group (TSAG) on progress on this resolution, in order for TSAG to evaluate the effectiveness of its implementation;

4	to report on progress on this resolution to the next world telecommunication standardization assembly,

instructs the Secretary-General

to report annually to the ITU Council on progress on this resolution,

invites the Directors of the Telecommunication Standardization Bureau, Radiocommunication Bureau and Telecommunication Development Bureau

to contribute to the report on progress on this resolution,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 69-01 | TSBDir to integrate and analyse incident reports from Member States; and to report this information to Member States, through an appropriate mechanism (instructs TSBDir 1, 2) | Ongoing | √ |  |
|  | Resolution 69 (Rev. Hammamet, 2016) since its first adoption in WTSA-08 aims to refrain Member States from taking any unilateral and/or discriminatory actions that could impede another Member State from accessing public Internet sites and using resources, within the spirit of Article 1 of the Constitution and the WSIS principles. TSB has implemented a platform and tool since 2009 by which Member States can report and submit an incident related to this Resolution and raise that incident to the attention of the TSB Director, such that the TSB Director would take appropriate and necessary action on any such reported incidents. All Resolution 69 related reports and any replies for ITU TIES users’ access are maintained at: https://www.itu.int/net/ITU-T/res69/secured/notifications.aspx. TSB has not received any incident reports since 2017. All Resolution 69 related reports and any replies for ITU TIES users’ access are maintained at: https://www.itu.int/net/ITU-T/res69/secured/notifications.aspx. |  |  |  |
| 69-03 | TSBDir to submit progress report to TSAG, for TSAG to evaluate the effectiveness of its implementation. (instructs TSBDir 3) | TSAG 2024 |  |  |
|  | This document. |  |  |  |
| 69-04 | TSBDir to report on progress on this resolution to WTSA-24 (instructs TSBDir 4) | WTSA-24 |  |  |
| 69-05 | ITU Secretary General to report annually to Council (instructs Sec-Gen) | Council meetings | √ |  |
|  | The TSB Director reports annually in the Council document on "ITU Internet activities: Resolutions 101, 102 and 133, 180, and 206", about updates regarding WTSA Resolution 69, if any, see S22-CL-C-0033, S23-CL-C-0033. |  |  |  |

» Top

# Resolution 70 - Telecommunication/ information and communication technology accessibility for persons with disabilities and persons with specific needs

resolves

1	that ITU-T Study Group 16 shall continue giving high priority to work on the relevant Questions, Recommendation ITU-T F.790, the guide for ITU-T study groups on telecommunication accessibility guidelines for older persons and persons with disabilities, and Recommendation ITU-T F.791 on accessibility terms and definitions;

2	that ITU study groups should consider aspects of universal design in their work, including the drafting of non-discriminatory standards, service regulations and measures for all persons, including persons with disabilities and older persons, with cross-cutting user-protection actions;

3	that all ITU-T study groups utilize the Telecommunications Accessibility Checklist, which makes it possible to incorporate the principles of universal design and accessibility;

4	that ITU workshops be held to inform about the progress in the work and the results achieved by the study groups in charge of ICT accessibility before the next world telecommunication standardization assembly,

instructs the Director of the Telecommunication Standardization Bureau

1	to report to the ITU Council on the implementation of this resolution;

2	to contribute to the development of an ITU-wide internship programme for persons with disabilities who have expertise in the field of ICTs, so as to build capacity among persons with disabilities in the standards-making process and to raise awareness within ITU-T of the needs of persons with disabilities;

3	that ITU-T employ the technical papers FSTP-AM "Guidelines for accessible meetings" and FSTP-ACC-RemPart "Guidelines for supporting remote participation for all", as appropriate, to make it possible for persons with disabilities to be able to attend ITU meetings and events,

invites the Director of the Telecommunication Standardization Bureau

1	to work collaboratively on accessibility-related activities with the Directors of the Radiocommunication Bureau (BR) and the Telecommunication Development Bureau (BDT), taking into account JCA-AHF, in particular concerning awareness and mainstreaming of telecommunication/ICT accessibility standards, reporting findings to the Council as appropriate;

2	to work collaboratively on accessibility-related activities with ITU-D, in particular developing programmes that enable developing countries to introduce services that allow persons with disabilities to utilize telecommunication services effectively;

3	to work collaboratively and cooperatively with other standardization organizations and entities, in particular, in the interest of ensuring that ongoing work in the field of accessibility is taken into account, in order to avoid duplication;

4	to work collaboratively and cooperatively with disability organizations in all regions to ensure that the needs of the disabled community are taken into account in all standardization matters;

5	to continue JCA-AHF, and any other accessibility coordination functions and advisory function within ITU-T, in order to assist the Director of TSB in reporting the findings of the review of ITU-T services and facilities;

6	to consider using accessibility resources in the meetings organized by ITU-T in order to encourage the participation of persons with disabilities and persons with specific needs in the standardization process;

7	to consider the possibility of organizing, jointly with ITU-D and with the involvement of other standardization organizations and entities, coaching and training for developing countries on working with disability organizations;

8	to identify and document examples of best and good practices for accessibility in the field of telecommunications/ICT for dissemination among ITU Member States and Sector Members;

9	to review the accessibility of ITU-T services and facilities, and consider making changes, where appropriate, pursuant to UNGA Resolution 61/106, in the Convention on the Rights of Persons with Disabilities, and report to the Council on these matters,

instructs the Telecommunication Standardization Advisory Group

1	to revise the guide for ITU study groups – "Considering end-user needs in developing Recommendations",

2	to consider how study groups facilitate, in their respective work, the implementation of new software, services and proposals enabling all persons with disabilities and persons with specific needs with age-related disabilities, to effectively use telecommunication/ICT services, and relevant guidelines for end-user needs, in order specifically to include the needs of persons with disabilities and persons with specific needs, and to update this guide on a regular basis, based on contributions from Member States and Sector Members as well as the ITU-T study groups, as appropriate.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 70-01 | SG16 to continue work on accessibility with high priority. (resolves 1) | Ongoing | √ |  |
|  | Meeting organized in July 2023 with captioning for all plenary sessions and some expert sessions. BSL interpretation provided for Q26/16 sessions, as well as IRG-AVA hosted under SG16 and the JCA-AHF. Live captioning provided to plenary sessions as well as in sessions where accessibility was discussed. New work continued on a conformance testing procedure for ITU-T F.780.2 on use cases and requirements for accessible telehealth services, on revised technical paper ITU-T FSTP.ACC-WebVRI (V2) "Guideline on web-based remote sign language interpretation or video remote interpretation (VRI) system". Work completed on new Technical Paper FSTP-ACC-Rural "Use cases of accessibility to multimedia systems in rural and out-of-home environments". Cooperation continues with ISO/IEC JTC 1/SC35 "User interfaces" for two joint texts. |  |  |  |
| 70-02 | TSB to hold ITU workshops on progress and achievement of ITU-T SGs on ICT accessibility before WTSA-24 (resolves 4) | Before WTSA-24 |  |  |
|  | In preparation |  |  |  |
| 70-03 | TSBDir to report to Council (instructs TSBDir 1) | Council 2024 | √ |  |
| 70-06 | TSBDir to work collaboratively with other Directors, taking into account JCA-AHF, on accessibility activities on ITU wide awareness and mainstreaming of telecommunication/ICT Accessibility Standards, reporting findings to Council as appropriate (invites TSBDir 1) | Ongoing, Council 2024 | √ |  |
|  | The ITU-T Joint Coordination Activity on Accessibility and Human Factors (JCA-AHF) serves as a useful coordination mechanism across ITU sectors and external SDOs and disability groups. The Intersector Rapporteur Group Audiovisual Media Accessibility (IRG-AVA) studies topics related to audiovisual media accessibility, aiming at development of Recommendations, and other non-normative materials as appropriate. It addresses matters contributing to the coordination of the standardization work of the involved ITU-T and ITU-R groups and collaborates with other SDOs and other audiovisual media organizations (e.g., forums and consortia, research institutes and academia). TSB participates and contributes actively to the Inter-Sectoral Coordination Task Force (ISC-TF) on the area of accessibility. |  |  |  |
| 70-07 | TSBDir, in collaboration with BDT Director, in developing programmes to enable developing countries to introduce services to enable persons with disabilities to use ICT services effectively (invites TSBDir 2) | Ongoing | √ |  |
|  | The ITU-T JCA-AHF serves as a useful coordination mechanism across ITU sectors and external SDOs and disability groups, with representatives of ITU-D delegates and BDT. TSB contributes to and participates in Accessible Americas and Accessible Europe, led by the Regional Office for the Americas and the Regional Office for Europe respectively. |  |  |  |
| 70-08 | TSBDir to work collaboratively and cooperatively with other SDOs to avoid duplication, and with disability orgs to ensure accessibility needs are taken into account in standardization (invites TSBDir 3) | Ongoing | √ |  |
|  | Cooperation continues with ISO/IEC JTC 1/SC35 "User interfaces" on joint texts. |  |  |  |
| 70-09 | TSBDir to contribute to the development of an ITU-wide internship programme to involve persons with disabilities and ICT expertise. (instructs TSBDir 2) | Ongoing |  |  |
|  | In preparation |  |  |  |
| 70-10 | TSBDir to continue JCA-AHF and the disability coordination and advisory function within ITU-T. (invites TSBDir 5) | Ongoing | √ |  |
|  | The ITU-T JCA-AHF serves as a useful coordination mechanism across ITU sectors and external SDOs and disability groups. One meeting held with SG16 in October 2022. TSAG 2022 endorsed the continuation of JCA-AHF. |  |  |  |
| 70-11 | TSBDir to consider using accessibility resource to encourage participation of persons with disabilities (invites TSBDir 6) | Ongoing | √ |  |
|  | In addition to real time captioning at selected meetings, sign language interpretation has been provided within the TSB budget for delegates that requested these accessibility accommodations. Some experts had participation facilitated by TSB to participate in discussions of accessibility and human factor studies. Experimentation was made with remote provisioning of sign language interpretation as a response to COVID-19 pandemic. Real-time captioning in meetings was provided on-demand and subject to availability of resources to various meetings. |  |  |  |
| 70-12 | TSAG to revise the guide for ITU study groups – 'considering end-user needs in developing Recommendations', and consider how SGs to implement this guide (instructs TSAG 1, 2) | Ongoing | √ |  |
|  | TSAG will consider updating the revision of the Guide for ITU-T Study Groups Considering End-User Needs in developing Recommendations, now that ISO/IEC Guide 71/ITU-T Supplement 17 Guide for addressing accessibility in standard has been adopted. |  |  |  |
| 70-13 | TSBDir to employ the technical papers FSTP-AM "Guidelines for accessible meetings" and FSTP-ACC-RemPart "Guidelines for supporting remote participation for all", as appropriate, to make it possible for persons with disabilities to be able to attend ITU meetings and events (instructs TSBDir 3) | Ongoing | √ |  |
|  | Accessibility of ITU-T meetings has been improving over the recent years, and more experience is gained as the existing guidelines are more deployed. With experiences gained, work is ongoing at SG16 to update both guidelines, FSTP-AM and FSTP-ACC-RemPart. The next edition of the accessible remote meetings is planned as a Recommendation under ITU-T SG16, rather than Technical Paper. |  |  |  |
| 70-14 | ITU-T study groups to consider aspects of universal design in their work, including the drafting of non-discriminatory standards, service regulations and measures for all persons (resolves 2) | Ongoing | √ |  |
|  | ITU-T standards and other deliverables are developed following the universal design principles. |  |  |  |
| 70-15 | TSBDir to identify and document examples of best and good practices for accessibility in the field of telecommunications/ICT for dissemination among ITU Member States and Sector Members (invites TSBDir 8) | Ongoing | √ |  |
|  | FSTP-ACC-Rural (07/2023) “Use cases of accessibility to multimedia systems in rural and out-of-home environments” is the first Technical report approved origin from Mozambique and Southern Africa. |  |  |  |
| 70-16 | TSBDir to review the accessibility of ITU-T services and facilities, and consider making changes, where appropriate, pursuant to UNGA Resolution 61/106, in the Convention on the Rights of Persons with Disabilities, and report to the Council on these matters (invites TSBDir 9) | Ongoing Council 2024 | √ |  |
|  | Accessibility accommodations offered for ITU-T meetings on a regular basis, upon request and availability of resources. |  |  |  |

» Top

# Resolution 72 - Measurement and assessment concerns related to human exposure to electromagnetic fields

resolves

to invite ITU-T, in particular Study Group 5, to expand and continue its work and support in this domain, including, but not limited to:

i)	developing new and/or updating existing reports and Recommendations, taking into account the advancements in wireless technologies, advances in measurement/assessment methodologies and best practices, in close coordination with other ITU Sectors and relevant specialized organizations in this field;

ii)	publishing and disseminating its technical reports, as well as developing ITU-T Recommendations to address these issues;

iii)	developing, promoting and disseminating information and training resources related to this topic through the organization of training programmes, workshops, forums and seminars for regulators, operators and any interested stakeholders from developing countries;

iv)	studying EMF exposure assessment from both intentional and unintentional or ambient (such as wireless power transfer) sources associated with new and emerging technologies, including Internet of Things (IoT) and International Mobile Telecommunications (IMT) systems, as well as the results of measurement, evaluation, monitoring, calculations and overview of the impact on EMF levels;

v)	continuing to cooperate and collaborate with other organizations working on this topic and to leverage their work (ICNIRP 2020, IEEE C95.1, 2019), in particular with a view to assisting the developing countries in the establishment of standards and in monitoring compliance with these standards, especially on telecommunication installations and terminals;

vi)	collaborating with ICT experts, the research community and other relevant stakeholders to study the EMF aspects of telecommunications/ICTs, including emerging ones, potentially also using emerging ICT technologies to study these EMF aspects;

vii)	cooperating on these issues with ITU-R Study Groups, and with ITU-D Study Group 2 in the framework of EMF measurements to assess human exposure and other relevant issues;

viii)	coordinating and cooperating with various international organizations specialized in health matters, SDOs and organizations recognized by United Nations agencies dealing with the harmonization of exposure guidelines in order to generate consistent protocols for assessing exposure to RF-EMF;

ix)	strengthening coordination and cooperation with WHO, ICNIRP, IEEE, ISO/IEC and other relevant organizations on guidelines and limits of human exposure to EMF so that any publications relating to human exposure to EMF are circulated to Member States as soon as they are issued,

instructs the Director of the Telecommunication Standardization Bureau, in close collaboration with the Directors of the other two Bureaux

within the available financial resources

1	to support the development of reports identifying the needs of developing countries on the issue of assessing human exposure to EMF, and to submit the reports as soon as possible to ITU-T Study Group 5 for its consideration and action in accordance with its mandate;

2	to regularly update the ITU-T portal on EMF activities including, but not limited to, the ITU EMF Guide, its mobile application, links to websites, the global portal on ICTs and the environment and flyers;

3	to hold workshops in developing countries with presentations and training on the use of equipment employed in assessing human exposure to RF energy;

4	to appoint experts in the field of assessment and measurement of exposure to EMF to assist developing countries in the formulation of their strategies in this area;

5	to extend support for developing countries while they establish their national and/or regional centres equipped with test benches for continuous monitoring of EMF levels, especially in selected areas where the public has concerns, and transparently provide the data to the general public by using, among other things, the modalities listed in Resolutions 44 (Rev. Geneva, 2022) and 76 (Rev. Geneva, 2022) of this assembly, and of Resolution 177 (Rev. Dubai, 2018) of the Plenipotentiary Conference in the context of the development of regional test centres;

6	to invite Study Group 5 to coordinate and cooperate with various international organizations such as WHO, ICNIRP, IEC, IEEE and other relevant international and regional organizations in the harmonization of exposure thresholds globally and to generate consistent measurement protocols;

7	to report to the next world telecommunication standardization assembly on measures taken to implement this resolution,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 72-01 | SG5 to develop new or updating existing reports and Recommendations, promote and disseminate information and training resources related to EMF through organizing training programmes, workshops, forums and seminars for regulators, operators etc and any interested stakeholders from developing countries, and in close coordination with other ITU Sectors and relevant specialized organizations in this field (resolves i, ii) | Ongoing | √ |  |
|  | ITU-T SG5 has developed the following ITU-T Supplements: - K.Suppl.29: Electromagnetic field strength inside and outside of electric vehicle using wireless power transfer (WPT) - K.Suppl.16 “Electromagnetic field compliance assessments for 5G wireless networks” - K.Suppl.32 "Case Studies of RF-EMF assessments" The 14th Symposium on ICT, Environment, Climate Change and Circular Economy took place on 25 October 2022 and a session was dedicated to 5G and beyond: EMF considerations for a Sustainable Digital Transformation. A Workshop on Human Exposure to Electromagnetic Fields and Electromagnetic Compatibility took place on 18 May 2023 in Kampala, Uganda, within the framework of the Sustainable Digital Transformation Week for Africa Region 2023. |  |  |  |
| 72-02 | SG5 to coordinate with WHO, ICNIRP, IEEE, ISO/IEC and other relevant organizations on guidelines and limits of human exposure to EMF so that fact sheets relating to human exposure to electromagnetic fields is circulated to Member States as soon as it is issued (resolves ix) | Ongoing | √ |  |
|  | ITU participates in WHO meetings and WHO provides an overview of their updates during SG5 meetings. |  |  |  |
| 72-03 | TSBDir, in collaboration with other Directors, to support the development of reports identifying needs of developing countries for consideration by ITU-T SG5 (instructs TSBDir 1) | Ongoing | √ |  |
|  | All Reports on ICTs, EMF, environment and climate change are available at: https://www.itu.int/en/ITU-T/climatechange/Pages/publications.aspx |  |  |  |
| 72-04 | TSBDir, in collaboration with other Directors, to extend support for developing countries to establish national and/or regional centres equipped with test benches for continuous monitoring of EMF levels, and transparently provide the data to the general public (see also Resolution 76) in the context of the development of regional test centres. (instructs TSBDir 5) | Ongoing |  |  |
| 72-06 | SG5 to cooperate with ITU-R SGs, and with ITU-D SG 2 in the framework of EMF measurements to assess human exposure and other relevant issues. (resolves vii) | Ongoing | √ |  |
|  | SG5 submits regular liaison statements to ITU-R SGs and ITU-D SG2 on the work related to EMF. |  |  |  |
| 72-07 | TSBDir to regularly update the ITU-T portal on EMF activities including, but not limited to, the ITU EMF Guide, its mobile application, links to websites, the global portal on ICTs and the environment and flyers (instructs TSBDir 2) | Ongoing | √ |  |
|  | The EMF website is kept up to date and is available at: https://www.itu.int/en/ITU-T/emf/Pages/default.aspx. Additionally, the page on “What is new on ITU-T Activities on EMF?” is kept up to date. |  |  |  |
| 72-08 | TSBDir to report to the next WTSA on measures taken to implement this resolution (instructs TSBDir 7) | WTSA-24 |  |  |
| 72-09 | SG5 to study EMF exposure assessment from both intentional and unintentional or ambient (such as wireless power transfer) sources associated with new and emerging technologies, including IoT and IMT systems, as well as the results of measurement, evaluation, monitoring, calculations and overview of the impact on EMF levels. (resolves iv) | Ongoing | √ |  |
|  | ITU-T SG5 has developed the following ITU-T Recommendations and Supplements: - K.153: ​Guidance on Determining the Compliance Boundaries (the exclusion zone) of radio transmitter installation - K Suppl. 29: Electromagnetic field strength inside and outside of electric vehicle using wireless power transfer (WPT). ITU-T SG5 has revised the following Recommendations to keep them up to date with new developments: - K.83: Monitoring of the electromagnetic field levels - K.91: Guidance for assessment, evaluation and monitoring of human exposure to radio frequency electromagnetic fields |  |  |  |
| 72-10 | SG5 to collaborate with ICT experts, the research community and other relevant stakeholders to study the EMF aspects of telecommunications/ICTs, including emerging ones, potentially also using emerging ICT technologies to study these EMF aspects, and coordinating and cooperating with various international organizations specialized in health matters, SDOs and organizations recognized by United Nations agencies dealing with the harmonization of exposure guidelines in order to generate consistent protocols for assessing exposure to RF-EMF (resolves vi, viii) | Ongoing |  |  |
|  | ITU-T SG5 collaborates with WHO and other SDOs |  |  |  |
| 72-11 | TSBDir to appoint experts in the field of assessment and measurement of exposure to EMF to assist developing countries in the formulation of their strategies in this area (instructs 4 TSBDir) | Ongoing |  |  |
| 72-12 | SG5 to coordinate and cooperate with various international organizations such as WHO, ICNIRP, IEC, IEEE and other relevant international and regional organizations in the harmonization of exposure thresholds globally and to generate consistent measurement protocols; (instructs 6 TSBDir) | Ongoing |  |  |
|  | ITU-T SG5 collaborates with WHO, ICNIRP, IEC and IEEE and sends liaison statement updating on the ongoing work and approved standards. |  |  |  |

» Top

# Resolution 73 - Information and communications technologies, environment, climate change and circular economy

resolves

1	to continue and further develop the ITU-T work programme initially launched in December 2007 on ICTs, climate change and circular economy, as a high priority, in order to contribute to the wider global efforts to moderate climate change, as part of the United Nations processes;

2	to take into account the progress already made in the international symposia on ICTs, environment, climate change and circular economy, held in various parts of the world2, by distributing their outcomes as widely as possible;

3	to continue to maintain and update the ITU-T Global Portal on ICTs, environment, climate change and circular economy, extending its features by developing an electronic and interactive forum to share information and to disseminate ideas, standards and best practices on the relationships between ICTs and environmental sustainability, experiences and practices for disclosure, labelling schemes and recycling facilities;

4	to promote the development and adoption of Recommendations for enhancing the use of ICTs to serve as a potent and cross-cutting tool to assess and reduce greenhouse gas (GHG) emissions, optimize energy and water consumption, minimize e-waste and improve its management across economic and social activities;

5	to increase awareness and promote information sharing on the role of ICTs in enhancing environmental sustainability, in particular by promoting the use of more energy-efficient3 devices and networks and more efficient working methods, as well as ICTs that can be used to replace or displace higher energy consuming technologies/uses;

6	to work towards the reductions in emissions of GHGs arising from the use of ICTs that are necessary to meet the goals of the United Nations Framework Convention on Climate Change (UNFCCC);

7	to work towards a reduction of the adverse environmental impact of environmentally unfriendly materials used in ICT products;

8	to bridge the standardization gap by providing technical assistance to countries to develop their national green ICT action plans, and develop a reporting mechanism in order to support countries in implementing their plan;

9	to set up e-learning programmes on Recommendations related to ICTs, the environment, climate change and circular economy;

10	to work towards supporting cities and the ICT sector in harnessing ICTs to combat climate change and reach net zero;

11	to work towards identifying the environmental protection requirements of ICTs and developing strategic frameworks for assessing their environmental impacts;

12	to support using ICTs to facilitate climate-change mitigation and adaptation efforts as well as building climate resilient infrastructures;

13	to work towards the implementation of circular economy in cities and human settlements to enhance their sustainability,

instructs the Telecommunication Standardization Advisory Group

1	to coordinate the activities of ITU-T study groups in relation to their review of relevant standardization activities of other standards development organizations (SDOs) and facilitate collaboration between ITU and those SDOs in order to avoid duplication of, or overlap in, international standards;

2	to ensure that study groups carry out a review of all future Recommendations in order to assess their implications and the application of best practices in the light of protection of the environment, and climate change and circular economy;

3	to consider further possible changes to working procedures in order to meet the objective of this resolution, including extending the use of electronic working methods to reduce the climate-change impact, such as paperless meetings, virtual conferencing, teleworking, etc.,

instructs all study groups of the ITU Telecommunication Standardization Sector

1	to cooperate with Study Group 5 to develop appropriate Recommendations on ICTs, the environment and climate-change issues within the mandate and competency of ITU-T, including telecommunication networks used for monitoring and adapting to climate change, for example disaster preparedness, signalling and quality of service issues, taking into account any economic impact on all countries and in particular on developing countries;

2	to identify best practices and opportunities for new applications using ICTs to foster environmental sustainability, and to identify appropriate actions;

to identify and promote best practices towards implementing environmentally-friendly policies and practices, and to share use cases and key success factors;

4	to identify initiatives which support consistently successful and sustainable approaches that will result in cost-effective application;

5	to identify and promote successful new energy-efficient technologies using renewable energy or alternative energy sources that are proven to work for both urban and rural telecommunication sites;

6	to liaise with the relevant ITU-R and ITU-D study groups and promote liaison with other SDOs and forums in order to avoid duplication of work, optimize the use of resources and accelerate the availability of global standards,

instructs the Director of the Telecommunication Standardization Bureau, in collaboration with the Directors of the other Bureaux

1	to report on progress on the application of this resolution annually to the Council and to the next world telecommunication standardization assembly;

2	to keep up to date the calendar of events relevant to ICTs, the environment, climate change and circular economy, based on proposals by the Telecommunication Standardization Advisory Group and in close collaboration with the other two Sectors;

3	to launch pilot projects, aimed at bridging the standardization gap, on environmental sustainability issues, in particular in developing countries;

4	to support the development of reports on ICTs, the environment, climate change and circular economy, taking into consideration relevant studies, in particular the ongoing work of Study Group 5, including issues related to, inter alia, circular economy, green data centres, smart buildings, green ICT procurement, cloud computing, energy efficiency, smart transportation, smart logistics, smart grids, water management, adaptation to climate change and disaster preparedness, and how the ICT sector contributes to annual reductions in GHG emissions, and submit the reports as soon as possible to Study Group 5 for its consideration;

5	to organize forums, workshops and seminars for developing countries in order to raise awareness and identify their particular needs and challenges in regard to environment, climate-change and circular economy issues;

6	to develop, promote and disseminate information and training programmes on ICTs, climate change, environment and circular economy;

7	to report on progress of the ITU/WMO/UNESCO IOC Joint Task Force to investigate the potential of using submarine telecommunication cables for ocean and climate monitoring and disaster warning;

8	to promote the ITU-T Global Portal on ICTs, environment, climate change and circular economy and its use as an electronic forum for the exchange and dissemination of ideas, experience and best practices on ICTs, the environment, climate change and circular economy;

9	to assist countries that are vulnerable to climate-change impact, with specific emphasis on developing countries:

i) located along coastal areas and those surrounded by oceans and seas, as well as inland areas that are susceptible to wildfire and drought;

ii) whose economies rely on agricultural investments;

iii) with weak capacity or lack of infrastructure and technical systems of meteorological support for the mitigation of climate-change effects,

invites the Secretary-General

to continue to cooperate and collaborate with other entities within the United Nations in formulating future international efforts to address protection of the environment and climate change, and support vulnerable countries in projects towards mitigation, adaptation and resilience efforts as well as climate-change preparedness plans, contributing to the achievement of the goals of the 2030 Agenda for Sustainable Development,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 73-01 | TSBDir to continue and develop the ITU-T ICT and Climate Change and circular economy work programme (resolves 1) | Ongoing | √ |  |
|  | TSB is continuing to maintain the Global Portal on Environment , which reflects the ITU-T Climate Change work programme and provide a wealth of information and resource materials, and an overview of activities. |  |  |  |
| 73-02 | TSB to continue maintain, update, develop and promote the ITU-T Global Portal on ICTs, environment, climate change and circular economy (resolves 2, 3) | Ongoing | √ |  |
|  | The ITU-T Global Portal on Environment is kept up to date and is available at: https://www.itu.int/en/ITU-T/climatechange/resources/Pages/env-and-ssc.aspx |  |  |  |
| 73-03 | TSB to promote the development and adoption of ITU-T Recs as a potent and cross-cutting tool to assess and reduce GHG emission, optimize energy and water consumption, minimize e-waste, etc., increase awareness on the role of ICTs in enhancing environmental sustainability (resolves 4) | Ongoing | √ |  |
|  | The ITU-T Global Portal on Environment provides and promotes material on past and current activities such as: - Green ICT Standards and Supplements. - Toolkit on Environmental Sustainability for the ICT Sector. - ICTs and Climate Change Adaptation, ICTs and Climate Change Mitigation. - ITU-T Reports and publications, surveys, and other external studies on the subject matter areas. - Events such as ITU Green Standards Week and Symposium on ICT, Environment and Climate Change. - Smart Water Management. - Greening the ICT Supply Chain, Smart Logistics and Green ICT Procurement. In addition, TSB promotional activities occur through publication of news stories, in blogs, in interviews, and through speeches. |  |  |  |
| 73-04 | TSB to provide technical assistance to develop national green ICT action plan, and develop a reporting mechanism to support countries in implementing their plans (resolves 8) | Ongoing |  |  |
| 73-05 | TSB to setup e-learning programmes on Recommendations related to ICTs, environment, climate change and circular economy (resolves 9) | Ongoing | √ |  |
|  | The ITU-T Global Portal on Environment and Smart Sustainable Cities, provides a wealth of information and resource materials for self-learning. Training materials relating to ICTs and climate change are currently being developed. |  |  |  |
| 73-06 | TSAG to coordinate the activities of ITU-T study groups in relation to their review of relevant standardization activities of other standards development organizations (SDOs) and facilitate collaboration between ITU and those SDOs in order to avoid duplication of, or overlap in, international standards (instructs TSAG 1) | TSAG 2024 |  |  |
|  | ITU-T SG5 participates in the Intersector Coordination Group related to the activities on Environment, Climate Change and Circular Economy. |  |  |  |
| 73-07 | TSAG to consider revision of working methods to reduce climate change impact (instructs TSAG 3) | TSAG 2024 | √ |  |
|  | The practice of carrying out virtual ITU-T meeting has a direct impact in travelling and has helped to reduce the impact to climate change. |  |  |  |
| 73-08 | Study Groups, especially SG5, to develop Recommendations on ICTs, environment and climate change (instructs SGs 1) | Ongoing | √ |  |
|  | SG5 continues working on the development of standards on environment, climate change and circular economy such as: - ITU-T L.1023: ​Assessment method for circular scoring - ITU-T L.1471: Guidance and criteria for information and communication technology organizations on setting Net Zero targets and strategies - ITU-T L.1326: ​Requirements and use cases of liquid cooling solutions and high energy efficiency solutions for 5G BBU in Centralized-RAN mode - ITU-T L.1027: Assessment of material efficiency of ICT network infrastructure goods (circular economy) part 5- server and data storage product disassembly and disassembly instruction” - ITU-T L.1070: Global digital sustainable product passport opportunities to achieve a circular economy - ITU-T L.1241: Methodologies for evaluating the functionality and performance of power supply unit configured for servers​ - ITU-T L.1631: Reference model of firefighting infrastructure management system for buildings in sustainable cities - ITU-T L.1362: ​Power management capabilities of the future energy telecommunication fixed network nodes. Enhanced Interface for power management in Network Function Virtualization (NFV) environments​ - ITU-T L.1031: ​Guideline for the development of an e-waste management system and achieving the e waste targets of the Connect 2030 Agenda - ITU-T L.1307: Energy Efficiency in Micro Data Centre for Edge Computing - ITU-T L.1640: Methodology for dynamic monitoring and analysis of greenhouse gas emissions in city - ITU-T L.1508: Framework for climate change adaptation in coastal cities using ICT and digital technologies - ITU-T L.1391: Specifications of 5G network sharing and co-construction adapting to climate change mitigation​ SG15 has developed some Recommendations with “power saving mode” in access and home networking technical fields. SG20 is working on draft Recommendations on energy management, IoT-based smart aquaculture and IoT-based soil environmental protection. Please see the SG20 work programme available at: https://www.itu.int/ITU-T/workprog/wp_search.aspx?sg=20 |  |  |  |
| 73-09 | TSBDir, in collaboration with other Directors, to keep update the calendar of events relevant to ICTs, environment, climate change and circular economy (instructs TSBDir 2) | Ongoing | √ |  |
|  | The calendar of events relevant to ICTs, environment and climate change is kept up to date and is available at: https://www.itu.int/en/ITU-T/climatechange/resources/Pages/env-and-ssc.aspx |  |  |  |
| 73-11 | TSBDir, in collaboration with other Directors, to support development of reports on ICTs, environment, climate change and circular economy, particularly relevant to ongoing work of SG5, and submit the reports as soon as possible to Study Group 5 for its consideration (instructs TSBDir 4) | Ongoing | √ |  |
|  | All Reports on ICTs, environment and climate change are available at: https://www.itu.int/en/ITU-T/climatechange/Pages/publications.aspx |  |  |  |
| 73-12 | TSBDir, in collaboration with other Directors, to organize forums, workshops and seminars for developing countries to raise awareness and identify needs. (instructs TSBDir 5) | Ongoing | √ |  |
|  | - The 14th Symposium on ICT, Environment, Climate Change and Circular Economy took place on 25 October 2022. - A WSIS Session on Enabling the Net Zero Transition – Harnessing ICT solutions to reduce GHG emissions took place on 17 March 2023. - An Episode #23: STI Forum Side event on Building the pathway to sustainable digital transformation took place on 2 May 2023. - The Sustainable Digital Transformation week for Africa region took place from 15-19 May 2023 in Kampala, Uganda. - WSIS virtual event: Embracing Biodiversity – How the ICT sector can go beyond COP 15, 22 May 2023. - WSIS virtual event: Sustainable Batteries - The building blocks of a circular economy, 26 May 2023. - Global Symposium for Regulators – Session 8: Going Green with the Digital Transformation, 8 June 2023. - Workshop on “Shaping a Sustainable and Digital Future - Pathway towards the Green Standards Week”, Virtual, 15 June 2023. - Workshop on “Reducing your carbon footprint – A guide to Scope 3 GHG reporting for telecommunication operators”, Virtual, 11 July 2023. - Workshop on “Working together towards a better future – A guide to Scope 3 emissions reporting”, Virtual, 14 September 2023 (morning and afternoon session). - Workshop on “the Role of ICTs in Standards on Circular Economy and GHG Emissions Reduction”, Virtual, 9 November 2023. During COP28, ITU launched the Green Digital Action to enhance collaboration, fast-track industry-wide commitments to addressing climate challenges, and put digital solutions at the forefront of climate action. The GDA involved over 40 partners, including industry associations, UN agencies, governments and businesses. The collective contribution led to a rich Green Digital Action programme at COP28, and the efforts resulted in nine concrete commitments/outcomes across four thematic pillars – ICT industry GHG emissions, standards, e-waste and Early Warnings for All. ITU-T and ITU-T SG5 participated and contributed in COP28 and the Green Digital Action through a broad range of activities, including: - Leverage ICT's positive impacts on the climate (2 December 2023) - Reducing ICT sector GHG emissions (3 December 2023) - From commitment to action: Implementing standards for a sustainable future (4 December 2023) - The WSC's session on International Standards for sustainable digital tech (4 December 2023) - Climate classroom – “Digital Solutions for Climate Action” (6 December 2023) - Climate classroom – “Greening Data Centres” (11 December 2023) |  |  |  |
| 73-13 | TSBDir to report (to TSAG) progress of ITU/WMO/UNESCO IOC Joint Task Force to investigate the potential of using submarine telecom cables for ocean and climate monitoring and disaster warning (instructs TSBDir 7) | TSAG 2024 | √ |  |
|  | See also the TSB Director's Reports to TSAG. Information on this Task Force including publications and workshop information is available at its web page at http://www.itu.int/en/ITU-T/climatechange/task-force-sc/Pages/default.aspx. |  |  |  |
| 73-14 | ITU Secretary-General to continue cooperation and collaboration with other United Nations entities contributing to the achievement of the goals of the 2030 Agenda for Sustainable Development (invites SecGen) | Ongoing | √ |  |
|  | The ITU Secretary-General is cooperating with UNFCCC, UNEP and WMO in the context of climate change and SDGs. ITU organized the Green Digital Action track from 1 to 12 December 2023 at UNFCCC COP28. See also 73-12. |  |  |  |
| 73-15 | TSBDir to assist countries that are vulnerable to climate-change impact, with specific emphasis on developing countries (instructs TSBDir 9) | Ongoing | √ |  |
|  | See TSB Director's reports to TSAG. |  |  |  |
| 73-16 | TSB to work towards the reductions in emissions of GHGs arising from the use of ICTs, and to work towards a reduction of the adverse environmental impact of environmentally unfriendly materials used in ICT products (resolves 6 ,7) | Ongoing | √ |  |
|  | - SG5 is working on the development of several standards such as: - L.VirtualMeetings “Methodology for estimating GHG emissions in the frame of virtual meetings and events”. - L.Database: Guidance for the creation of an ITU database on GHG emissions of the global ICT sector - L.Database_countries: Criteria for the development and maintenance of databases on national ICT sector GHG emissions - L.SimplifiedLCA: Guidance on simplified life cycle assessments of Information and Communication Technologies - L.D4PI: An information model for digital product information on sustainability and circularity - L.Env.PerSmartphone: Method for environmental performance scoring of smartphones |  |  |  |
| 73-17 | TSAG to ensure that study groups carry out a review of both the appropriate existing ITU-T Recommendations and all future Recommendations in order to assess their implications and the application of best practices in the light of protection of the environment, climate change and circular economy (instructs TSAG 2) | Ongoing |  |  |
| 73-18 | SGs to identify and promote best practices, initiatives and opportunities for new applications using ICTs to foster environmental sustainability, and to identify appropriate actions (instructs SGs 2, 3, 4, 5) | Ongoing | √ |  |
|  | - SG15 has developed some Recommendations with “power saving mode” in access and home networking technical fields. - SG20 approved Recommendation ITU-T Y.4482 “Requirements and framework for smart livestock farming based on the Internet of things” and Recommendation ITU-T Y.4490 “Framework of monitoring of water system for smart fire protection”. SG20 is working on draft Recommendation ITU-T Y.CL-EDM “Energy data model for city-level energy management platform”, draft Recommendation ITU-T Y.energy-data “Framework of city-level energy data sharing and analytics among buildings” and draft Supplement ITU-T Y.Sup.SmartAgri-usecases “Use cases of IoT based smart agriculture". |  |  |  |
| 73-19 | Study groups to liaise with the relevant ITU-R and ITU-D study groups and promote liaison with other SDOs and forums in order to avoid duplication of work, optimize the use of resources and accelerate the availability of global standards (instructs SGs 6) | Ongoing | √ |  |
|  | - SG5 liaises regularly with ITU-R and ITU-D Study Groups and also other relevant organizations. - SG20 liaises with relevant organizations as necessary. |  |  |  |
| 73-20 | TSBDir to report on progress on the application of this resolution annually to the ITU Council and to the next WTSA (instructs TSBDir 1) | Council 2024 WTSA-24 |  |  |
| 73-21 | TSBDir to develop, promote and disseminate information and training programmes on ICTs, climate change, environment and circular economy (instructs TSBDir 6) | Ongoing | √ |  |
|  | The ITU-T Global Portal on Environment and Smart Sustainable Cities, provides a wealth of information and resource materials for self-learning. Training materials relating to ICTs, smart sustainable cities and climate actions are currently being developed; see also 73-05. The Toolkit on Digital Transformation for People-Oriented Cities and Communities contains international standards and guidance, the latest research and projections, and cutting-edge reports on a variety of timely topics relevant to the digital transformation of cities and communities. The toolkit is available at: https://toolkit-dt4c.itu.int/ ​ The Digital Transformation Resource Hub has been launched in February 2023. The Hub provides a wide range of quality publications on digital transformation topics, including smart sustainable cities, cities’ actions to tackle COVID-19, artificial intelligence, Internet of things, blockchain, digital twin, metaverse and digital transformation trends. All resources are freely available to all and is available at: https://www.itu.int/cities/dt-resource-hub/ |  |  |  |

» Top

# Resolution 74 - Enhancing participation of Sector Members* from developing countries in the work of the ITU Telecommunication Standardization Sector

resolves

1	to encourage the adoption of the necessary measures and mechanisms to enable new Sector members from developing countries to join ITU-T and to be entitled to take part in the work of the ITU-T study groups and other groups within ITU-T;

2	encourage Sector Members from the developed countries to promote the participation in ITU-T activities of their subsidiaries established in developing countries,

* Such Sector Members from developing countries shall not be affiliated in any way to any Sector Member of a developed country, and shall be limited to those Sector Members of developing countries (including the least developed countries, small island developing states, landlocked developing countries and countries with economies in transition) having an income per capita according to the United Nations Development Programme not exceeding a threshold to be determined.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 74-02 | TSBDir encourage the adoption of the necessary measures to enable new members from developing countries to join ITU-T and to be entitled to take part in the work of the ITU-T study groups and other groups within ITU-T. | Ongoing |  |  |

» Top

# Resolution 75 - The ITU Telecommunication Standardization Sector's contribution in implementing the outcomes of the World Summit on the Information Society, taking into account the 2030 Agenda for Sustainable Development

resolves

1	to continue ITU-T's work on the implementation of WSIS outcomes and the WSIS Vision beyond 2015 and follow-up activities within its mandate;

2	that ITU-T should contribute to achievement of the objectives of the 2030 Agenda for Sustainable Development, through and in harmony with the WSIS framework;

3	that ITU-T should carry out the activities under resolves 1 and 2 above in cooperation with other relevant stakeholders, as appropriate;

3	that the relevant ITU-T study groups should consider in their studies the output of CWG-WSIS&SDG and CWG-Internet,

instructs the Director of the Telecommunication Standardization Bureau

1	to provide CWG-WSIS&SDG with a comprehensive summary of ITU-T activities on implementation of the WSIS outcomes, taking into account the 2030 Agenda for Sustainable Development;

2	to ensure that concrete objectives and deadlines for activities in connection with WSIS outcomes, taking into account the 2030 Agenda for Sustainable Development, are developed and reflected in the operational plans of ITU-T in accordance with Resolution 140 (Rev. Dubai, 2018) and Council 2019 Resolution 1332;

3	in implementing the WSIS outcomes, taking into account the 2030 Agenda for Sustainable Development, within the mandate of ITU-T, to pay special attention to the needs of the developing countries;

4	to provide information on emerging trends based on ITU-T activities;

5	to take appropriate action to facilitate the activities for implementation of this resolution;

6	to submit contributions to the relevant annual reports of the ITU Secretary-General on these activities,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 75-01 | Study groups carry out activities to implement WSIS outcome and consider in their studies the output of CWG-WSIS&SDG and CWG-Internet (resolves 4) | Ongoing | √ |  |
|  | ITU-T's work contributes to the implementation of these ITU mandates. ITU-T Study Groups continue their developments and activities in line with the relevant WSIS Action Lines and SDGs and are following the roadmap for ITU’s activities to help achieve the 2030 Agenda for Sustainable Development. For the entire set of ITU-T study group Questions that came into force at WTSA-20, ITU-T study groups provided assignments of the Questions to the WSIS Action Lines, and to the UN Sustainable Development Goals. WSIS Action Lines C2 (I&C infrastructure), C5 (ICT confidence and security), and C6 (e-environment) are the main WSIS Actions Lines for ITU-T study groups, addressing subjects such as ICTs, security and cybersecurity for building confidence and security in the use of ICTs, conformance and interoperability, accessibility, ICT infrastructure, and enabling environment, while some study group activities and results exist also for other WSIS Action Lines, among them C4 (e-learning and capacity building), C7 (e-health, environmental aspects, ICT applications) and C9 (media). Detailed results are contained in the annual reports of the “ITU Contribution to the Implementation of WSIS Outcomes, taking into account the 2030 Agenda for Sustainable Development”, at https://www.itu.int/en/itu-wsis/Pages/Contribution.aspx. See also 75-02 below. |  |  |  |
| 75-02 | TSBDir to provide CWG-WSIS&SDG a comprehensive summary of ITU-T activities on implementation of the WSIS outcome (instructs TSBDir 1) | Council 2024 | √ |  |
|  | The following activities were organized at WSIS Forum 2023: - ICTs and Clean Technologies for Climate Change special track: Sustainable Batteries - The building blocks of a circular economy - Embracing Biodiversity – How the ICT sector can go beyond COP 15 - Part Session 1: General aspects of standards and standardization work of ITU-T Study Group 15 - Part Session 2: ITU-T Study Group 15 relevant standards for the fibre optic broadband network infrastructure - Part Session 3: ITU-T Study Group 15 relevant standards for the optical transport network, architecture and synchronization aspects - Digital Agriculture - Climate Change and how to promote DRR (Disaster risk reduction) - Gender Responsive Standard The Director of TSB supported and participated in additional session including ‘Enabling the Net Zero Transition – Harnessing ICT solutions to reduce GHG emissions’ and the ‘Mayors High-Level Presentations’ in which Mayors around the world shared scalable best practices and challenges of digital solutions for climate change adaptation and energy transition |  |  |  |
| 75-03 | TSBDir to ensure concrete objectives and deadlines for activities in connection with WSIS outcomes, taking into account the 2030 Agenda for Sustainable Development in ITU-T operational plan. (instructs TSBDir 2) | Ongoing | √ |  |
|  | The ITU Strategic plan 2024-2027 approved by PP-22 takes into account the 2030 agenda for SDGs. |  |  |  |
| 75-04 | ITU-T study groups and TSB to contribute to achievement of the objectives of the 2030 Agenda for Sustainable Development | Ongoing | √ |  |
|  | See 75-01. |  |  |  |
| 75-05 | TSBDir to provide information on emerging trends based on ITU-T activities (instructs 4 TSBDir). | Ongoing | √ |  |
|  | TSB organizes a wealth of ITU Workshops, seminars, webinars each year, that address emerging technologies and trends; see https://www.itu.int/en/ITU-T/Workshops-and-Seminars. Other related activities are ITU AI Summits, and ITU-T Focus Groups that investigate new trends. The activities are reported regularly in the TSB Director activities report to TSAG. |  |  |  |

» Top

# Resolution 76 - Studies related to conformance and interoperability testing, assistance to developing countries, and a possible future ITU mark programme

resolves

1	to continue working on the pilot projects that encourage conformity to ITU-T Recommendations to gain experience identify requirements and methodology in the development of test suites;

2	that Study Group 11 continues to coordinate the Sector's activities related to the ITU C&I programme across all study groups;

3	that Study Group 11 continues to undertake activities within the C&I programme, including pilot projects on conformance/interoperability testing;

4	to continue working with accreditation bodies to recognize testing laboratories with competence to test in accordance with ITU-T Recommendations;

5	to encourage collaboration between ITU-T and ITU-D on the four pillars of the ITU C&I programme, each according to its responsibilities;

6	that conformance testing requirements shall provide for verification of the parameters defined in the current and future ITU-T Recommendations as determined by the study groups developing the Recommendations, and for interoperability testing to take into account user needs and consider the market demand, as appropriate;

7	to continue to develop a set of methodologies and procedures for remote testing using virtual laboratories;

8	that ITU-T could hold interoperability testing events as needed to promote the interoperability of equipment conforming to ITU-T Recommendations;

9	that ITU, being a world standardization body, can address the impediments to harmonization and growth of worldwide telecommunications and promote the visibility of ITU standards (ensure interoperability), by means of having an ITU testing mark regime, taking into account the technical and legal implications, if any, and/or any revenue-generating possibilities, taking into consideration recognizing f),

instructs the Director of the Telecommunication Standardization Bureau

1	to continue consultations and assessment studies in all regions, taking into consideration the needs of each region, on implementation of the action plan endorsed by the ITU Council, including, in collaboration with the Director of the Telecommunication Development Bureau (BDT), and assistance in the establishment of test facilities in developing countries;

2	to implement the action plan agreed by the Council at its 2012 session and revised by the Council at its 2014 session, in cooperation with the Director of BDT;

3	considering resolves 9, to accelerate the implementation of Pillar 1, so as to ensure gradual and smooth accomplishment of the other three pillars and the possible implementation of the ITU Mark;

4	to continue implementing the ITU C&I programme including the testing laboratory database and informative pilot conformity product database, identifying product conformance and origin, in cooperation with the Director of BDT, and in consultation with each region;

5	to publish an annual plan of C&I activities which could attract more members' participation;

6	to facilitate the development and implementation of an ITU-T C&I test laboratory recognition procedure;

7	to involve experts and external entities as appropriate;

8	to provide progress reports on the activities carried out under the action plan to the Council for its consideration and required actions;

9	to facilitate the interoperability testing events in order to achieve the interoperability of equipment conforming to ITU-T Recommendations,

instructs the study groups

1	to accelerate accomplishing the pilot projects started by ITU-T study groups and to continue to identify possible existing ITU-T Recommendations that are candidates for C&I testing, taking into account the needs of the membership and that are capable of providing end-to-end interoperable services on a global scale, adding to their content, if necessary, specific requirements within their scope;

2	to prepare the ITU-T Recommendations identified in instructs the study groups 1 above, with a view to conducting C&I tests as appropriate;

3	to continue and enhance cooperation, as appropriate, with interested stakeholders, including other standards development organizations (SDOs), forums and consortia, in order to optimize studies to prepare test specifications taking into account user needs and in consideration of the market demand for a conformity assessment programme;

4	to submit to CASC a list of ITU-T Recommendations which could be candidates for the certification scheme, taking into account market needs,

instructs the ITU Telecommunication Standardization Sector Conformity Assessment Steering Committee

to study and define an ITU procedure to recognize testing laboratories that are competent to test according to ITU-T Recommendations, in collaboration with existing accreditation bodies,

invites the ITU Council

to consider the Director's report referred to in instructs the Director of the Telecommunication Standardization Bureau 8 above,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 76-01 | ITU-T SGs to continue working on the pilot projects that encourage conformity to ITU-T Recommendations to gain experience identify requirements and methodology in the development of test suites (resolves 1) | Ongoing | √ |  |
|  | - SG11 updated its C&I action plan which require TSB to maintain the list of pilot projects for conformity assessment against ITU-T Recommendations based on inputs provided by all SGs. The list is up to date and it is made available on ITU C&I Portal, https://itu.int/go/citest. - SG15 is liaising regularly with SG11. |  |  |  |
| 76-02 | ITU-T SGs accelerate accomplishing the pilot projects started by ITU-T study groups and to continue to identify existing ITU-T Recommendations that are candidates for C&I testing (instructs SGs 1) | Ongoing | √ |  |
|  | - SG11 updated its C&I action plan which require TSB to maintain the reference table of standards suitable for C&I assessment based on inputs provided by all SGs. The updated list is available on ITU C&I Portal, https://itu.int/go/citest - SG15 is liaising regularly with SG11. |  |  |  |
| 76-03 | ITU-T SGs, in continued and enhanced cooperation with other entities as appropriate, to prepare test specifications for those key technologies identified by 76-02 (instructs SGs 2) | Ongoing | √ |  |
|  | - SG5, SG9, SG11, SG12, SG15, SG16, SG20: see 76-02. |  |  |  |
| 76-04 | SG11 continues to coordinate the Sector’s activities related to the ITU C&I programme across all SGs (resolves 2) | Ongoing | √ |  |
|  | - SG11 is in charge of developing test specifications for different types of networks, technologies and services. SG11 updated its C&I action plan which provides guidance on populating reference table and list of pilot projects based on inputs provided by all SGs. Also, Conformity Assessment Steering Committee, which works under auspice of SG11, coordinates activities related to TL recognition procedure and appointment of ITU-T Technical experts in collaboration with all SGs. All achievements are highlighted on ITU C&I Portal, https://itu.int/go/citest and CASC webpage, https://itu.int/go/casc. |  |  |  |
| 76-05 | TSBDir, in cooperation with BR and BDT Directors, to continue consultations and assessment studies in all regions, taking into consideration the needs of each region, on implementation of the action plan endorsed by the ITU Council, and assistance in the establishment of test facilities in developing countries. (instructs TSBDir 1) | Ongoing | √ |  |
|  | The SG11RG-EECAT is to be conducted in Tashkent (Uzbekistan) from 23-25 May 2023. It is collocated with regional ITU Forum on Future networks and ITU C&I training. TSB will give an overview about the ongoing activities related to implementation of C&I action plan endorsed by ITU Council as well as participates in the interactive session on C&I issues to be organized during the above-mentioned events. |  |  |  |
| 76-06 | TSBDir to implement the action plan agreed by the Council at its 2012 session and revised by the Council at its 2014 session, in cooperation with the Director of BDT; (instructs TSBDir 2) | Ongoing | √ |  |
|  | TSB continues implementing the C&I Action plan agreed by Council-12. |  |  |  |
| 76-07 | TSBDir to continue implementing the ITU C&I programme including the testing laboratory database and informative pilot conformity product database, identifying product conformance and origin, in cooperation with the Director of BDT, and in consultation with each region (instructs TSBDir 4) | Ongoing | √ |  |
|  | The ITU Product Conformity Database (https://itu.int/go/tcdb), endorsed by PP Resolution 177 to provide industry with a means to publicize the conformance of ICT products and services with ITU-T’s international standards was launched on 18 December 2014. The “ICT Product Conformity Database” enables industry to publicize the conformance of ICT products and services to ITU-T Recommendations, assisting users in their efforts to select standards-compliant products. The database contains more than 500 entries. Five categories of products and services have been registered in the database as follows (e-Health, mobile phones, Ethernet services, IPTV, MNP). This database might be used for increasing customer’s awareness on ITU-T Recommendations implemented in ICT equipment. ITU started recognition of the testing laboratories (TLs) which have competence to test product against ITU-T Recommendations (see TSB Circular 368). This activity goes in close collaboration with the International Laboratory Accreditation Cooperation (ILAC, https://ilac.org/). The Memorandum of Understanding between ITU-T, the International Laboratory Accreditation Cooperation (ILAC) and the International Accreditation Forum (IAF) was updated and signed in August 2022. See newslog. The description of the procedure and recognition criteria are defined in the ITU-T Guideline on Testing Laboratory Recognition procedure which was updated by ITU-T SG11 in July 2022. As of April 2023, 11 Testing Laboratories are registered in ITU Testing Laboratories Database (https://itu.int/go/tldb). The recognized TLs are also listed in ITU Operational Bulletins (OB.1253, OB.1256, OB.1263 and OB.1266). ITU/TSB keeps receiving new request and will proceed them accordingly. |  |  |  |
| 76-08 | TSBDir to identify and involve experts and external entities (instructs TSBDir 7) | Ongoing | √ |  |
|  | TSB collaborates with the International Laboratory Accreditation Cooperation (ILAC) and the International Accreditation Forum (IAF) on C&I issues. The updated MoU was signed on 24 August 2022. |  |  |  |
| 76-11 | TSBDir provide progress reports on C&I activities carried out under the action plan to Council (instructs TSBDir 8) | Ongoing Council 2024 | √ |  |
|  | The updates are highlighted in TSB Director progress report. |  |  |  |
| 76-12 | TSBDir to accelerate the implementation of Pillar 1 (instructs TSBDir 3) | Ongoing | √ |  |
|  | ITU-T maintains the Product Conformity Database and list of mobile phones. ITU assisted companies on conducting relevant test events (e.g. pilot projects). Following establishment of ITU TL Recognition procedure (see 76-07), all ICT products tested against ITU-T Recommendation by TLs recognized by ITU may be registered in the ITU Product Conformity Database, based on the request. The relevant requests need to be submitted via online form accordingly. |  |  |  |
| 76-13 | TSBDir to publish an annual plan of C&I activities which could attract more members’ participation (instructs TSBDir 5) | Ongoing | √ |  |
|  | All information about C&I activities is available on the ITU C&I portal (https://itu.int/go/citest). |  |  |  |
| 76-14 | TSBDir to facilitate the development and implementation of an ITU-T C&I test laboratory recognition procedure (instructs TSBDir 6) | Ongoing | √ |  |
|  | TSB collaborates with ILAC/IAF on testing laboratory recognition procedures. The updated MoU was signed on 24 August 2022. According to the ITU recognition criteria which are defined in the ITU-T Guideline on Testing Laboratory Recognition procedure (July 2022), in order to be recognized by the ITU, testing laboratories shall: - have ITU-T Recommendations in the TL's scope of accreditation; - be accredited by Accreditation Body (AB) that is a signatory to the ILAC MRA (https://ilac.org/ilac-mra-and-signatories/) for testing (using ISO/IEC 17025). TSB invited TLs which fulfil the above-mentioned criteria to apply for ITU recognition. 11 TLs are registered in ITU TL Database (https://itu.int/go/tldb) from July 2022 until April 2023. |  |  |  |
| 76-15 | ITU-T SGs to submit to CASC a list of ITU-T Recommendations which could be candidates for the certification scheme, taking into account market needs (instructs SGs 4) | Ongoing | √ |  |
|  | SG15 is liaising with SG11 and informing SG11 of candidate Recommendations regularly. |  |  |  |
| 76-16 | ITU-T CASC to study and define an ITU procedure a procedure to recognize testing laboratories that are competent to test according to ITU-T Recommendations, in collaboration with existing accreditation bodies. (instructs ITU CASC) | Ongoing | √ |  |
|  | ITU-T CASC revised its ToR and updated ITU-T Guideline on Testing Laboratory Recognition procedure in July 2022. This guideline is currently used for populating ITU Testing Laboratories Database. |  |  |  |
| 76-18 | ITU-T to continue to develop a set of methodologies and procedures for remote testing using virtual laboratories (resolves 7) | Ongoing | √ |  |
|  | SG11 created a new Focus Group on testbed federations for IMT-2020 and beyond (FG-TBFxG). Among FG objectives are to define a set of use cases for Federated Testbeds and associated APIs, such as “Testbed-as-a Service” (TaaS) and develop the required application program interfaces (APIs) aligned with the Testbeds Federations Reference Model defined in Recommendation ITU-T Q.4068. |  |  |  |
| 76-19 | TSBDir to facilitate the interoperability testing events in order to achieve the interoperability of equipment conforming to ITU-T Recommendations. (instructs 7 TSBDir) | Ongoing | √ |  |
|  | TSAG approved revised Supplement 2 to ITU-T A-series Recommendations, Guidelines on interoperability experiments and proof-of-concept events, which relate to interoperability experiments and proof-of-concept events to be performed outside of ITU-T. The guidelines have been prepared in order to encourage such experiments and events to be performed, and to facilitate information exchange between ITU-T and parties participating in such experiments. |  |  |  |

» Top

# Resolution 77 – Enhancing the standardization work in the ITU Telecommunication Standardization Sector for software-defined networking

resolves to instruct study groups of the ITU Telecommunication Standardization Sector

1	to continue and enhance collaboration and cooperation with different standards development organizations (SDOs), industry forums, and open-source software projects on SDN, as appropriate, taking into account the outcome of TSAG work on open source;

2	to continue to expand and accelerate the work on SDN standardization, especially carrier SDN;

3	to research the advancement of emerging technology such as NFV container/docker to evolve the SDN technology;

4	to continue to develop the ITU-T SDN standards to enhance interoperability between the controller products;

5	to consider the potential implications of the SDN orchestrator layer for ITU-T operation supporting system (OSS) related work,

instructs Study Group 13

to continue the JCA-SDN work, to coordinate and help plan the work so as to ensure that ITU-T SDN standardization is progressed in a well-coordinated manner and more efficiently among relevant study groups, to study the SDN-related work programmes (including NFV, programmable networks and network as a service) in ITU-T study groups, as well as in other SDOs, forums and consortia, for use in its coordination function, and to provide information on this work for use by the relevant study groups in planning their work,

instructs the Telecommunication Standardization Advisory Group

to examine the matter, consider the input of study groups and take the necessary actions, as appropriate, with a view to deciding on the necessary SDN standardization activities in ITU-T, with the following actions:

•	to continue coordination and assistance in SDN standardization across different ITU-T study groups effectively and efficiently;

•	to continue collaboration with other SDN-related standards bodies and forums;

•	to coordinate the work on technical issues of SDN across the study groups according to their areas of expertise;

•	to define a clear strategic vision for SDN standardization and an important active role that ITU-T should play,

instructs the Director of the Telecommunication Standardization Bureau

1	to provide the necessary assistance with a view to expediting such efforts, in particular using any opportunity within the allocated budget to exchange opinions with the telecommunication/ICT industry, including through the chief technology officer (CTO) meetings under Resolution 68 (Rev. Hammamet, 2016) of this assembly and in particular to promote participation of the industry in SDN standardization work in ITU-T;

2	to conduct workshops, with other relevant organizations, for capacity building on SDN, so that the gap in technology adoption in developing countries may be bridged at the early stages of implementation of SDN-based networks, and to organize the annual SDN&NFV workshop with open source solutions representation to share the progress in SDN/NFV standards and real experience in the current carrier network,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 77-01 | SGs to continue to expand and accelerate work on SDN standardization, especially carrier SDN (resolves SG 2) | Ongoing | √ |  |
|  | - SG13 has a dedicated Question, dealing with SDN and network softwarization issues, Q21/13 "Networks beyond IMT-2020: Network softwarization". It has currently (by January 2024) 10 ongoing work items. SG13 approved 6 Recommendations related to SDN topic in this study period. The IMT-2020 standardization roadmap, maintained by the JCA-IMT2020, has a separate branch to keep deliverables on SDN. - SG15, in particular, Q12/15 and Q14/15 are working on SDN and liaising with other organizations. - SG17 collaborates with SG13 on SDN security. |  |  |  |
| 77-04 | TSBDir to assist the exchange of opinions in CTO meetings and to promote SDN standardization work in ITU-T (instructs TSBDir 1) | Ongoing |  |  |
| 77-06 | SGs to continue and enhance collaboration and cooperation with different standards development organizations (SDOs), industry forums, and open-source software projects on SDN, as appropriate, taking into account the outcome of TSAG work on open source (resolves SGs 1) | Ongoing | √ |  |
|  | - SG13 regularly liaise with ETSI NFV and other SDOs active in the SDN and network softwarization domain.JCA-IMT2020 meeting in March 2023 enjoyed the TM Forum presentation on their work on intent implementation in networks, April 2023 JCA-IMT-2020 meeting witnessed the ONAP presentation, SDN and intend-based network work were part of it. In October 2023 SG15 delivered presentation on transport network support for IMT-2020 and the evolution towards IMT-2030. - SG15, in particular, Q12/15 and Q14/15 are working on SDN and liaising with other organizations. - SG17 collaborates with SG13 on SDN security. |  |  |  |
| 77-07 | SGs to research the advancement of emerging technology such as NFV container/docker to evolve the SDN technology (resolves SGs 3) | Ongoing | √ |  |
|  | - Within the remits of its mandate, SG13 explores the new emerging networking technologies. It started at the end of the last study period its work on intent-based network scenarios and requirement as well as on digital twin network. ITU-T SG13 FG-AN convened the workshop on Advances in Autonomous Networks: 2023 and beyond on 24 October 2023 in Geneva. - SG15, in particular, Q12/15 and Q14/15 are working on SDN and liaising with other organizations. |  |  |  |
| 77-08 | SGs to continue to develop the ITU-T SDN standards to enhance interoperability between the controller products (resolves SG 4) | Ongoing | √ |  |
|  | - SG15, in particular, Q12/15 and Q14/15 are working on SDN and liaising with other organizations. |  |  |  |
| 77-09 | SGs to consider the potential implications of the SDN orchestrator layer for ITU-T operation supporting system (OSS) related work (resolves SG 5) | Ongoing |  |  |
| 77-11 | TSBDir to conduct workshops, with other relevant organizations, for capacity building on SDN; and to organize the annual SDN&NFV workshop with open source solutions representation to share the progress in SDN/NFV standards and real experience in the current carrier network (instructs TSB Dir 2) | Ongoing | √ |  |
|  | SG13 IMT-2030 part of the workshop in July 2023 touched base on network softwarization. |  |  |  |

» Top

# Resolution 78 – Information and communication technology applications and standards for improved access to e-health services

resolves to instruct the Director of the Telecommunication Standardization Bureau, in collaboration with the Director of the Telecommunication Development Bureau and the Director of the Radiocommunication Bureau

1	to consider with priority the enhancement of telecommunication/ICT initiatives in e-health and to coordinate their related standardization activities;

2	to continue and further develop ITU activities on telecommunication/ICT applications for e-health in order to contribute to the wider global efforts concerning e-health;

3	to work collaboratively with WHO, academia and other relevant organizations on activities related to e-health in general and to this resolution in particular;

4	to organize seminars and workshops on e-health for developing countries and gauge the needs of the developing countries, which are the countries with the greatest need for e-health applications,

instructs Study Groups 16 and 20 of the ITU Telecommunication Standardization Sector, in collaboration with the relevant study groups, particularly Study Groups 11 and 17 of the ITU Telecommunication Standardization Sector

1	to identify and document examples of best practice for e-health in the field of telecommunications/ICT, for dissemination among ITU Member States and Sector Members;

2	to coordinate activities and studies relating to e-health among the relevant study groups, focus groups and other relevant groups in ITU-T, the ITU Radiocommunication Sector (ITU-R) and ITU-D, in order in particular to foster awareness of telecommunication/ICT standards pertaining to e-health;

3	for ensuring the broad deployment of e-health services in diverse operating conditions, to study communication protocols relating to e-health, especially among heterogeneous networks;

4	within the current mandate of the ITU-T study groups, to give priority to the study of security standards (e.g. for communications, services, network aspects and service scenarios for databases and record handling, identification, integrity and authentication) relating to e-health, taking into account recognizing e),

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 78-01 | TSBDir, in collaboration with BDT and BR Directors, to develop ITU e-health activities (resolves TSBDir 1, 2, 3) | Ongoing | √ |  |
|  | Regular Health track on the AI for Good online events. |  |  |  |
| 78-03 | TSBDir, in collaboration with BDTDir and BRDir, to organize e-health seminars and workshops for developing countries and gauge their needs for e-health (resolves TSBDir 4) | Ongoing |  |  |
| 78-04 | SG16 and SG20, in collaboration with relevant SGs, particular SG11 and SG17, to identify, document and disseminate e-health best practices for ITU membership (instructs SGs16+20 1) | Ongoing | √ |  |
|  | - Following adoption by both ITU and World Health Organization (WHO) of ITU-T F.780.2 on use cases and requirements for accessible telehealth services, SG16 started new work to define a conformity testing specification to enable verification that implementations meet the necessary requirements. Following approval of the 2nd edition of ITU-T H.870 "Guidelines for safe listening devices/systems", which is a joint standard of ITU and WHO, work started on a revised version of the conformity testing specification for the joint ITU & WHO standard. Maintenance work for the Continua Design Guidelines of the H.810 series continued with revised ITU-T H.845.10 "Conformance of ITU-T H.810 personal health system: Personal Health Devices interface Part 5J: Insulin pump". Two other new Recommendations and one new Technical Paper were also completed: ITU-T F.760.1 "Requirements and reference framework for emergency rescue systems", ITU-T F.780.3 "Use cases and requirements for ultra-high-definition teleconsulting system" and Technical paper ITU-T FSTP-CONF-F780.1 "Conformance test specification for F.780.1" - Q10/17 works in collaboration with SG16, ITU-D, ISO TC 12, IEC TC 25 and WHO to identify and document examples of best practice for e-health in the field of telecommunication/ICT. Q10/17 collaborates with relevant study groups, focus groups and other relevant groups in ITU-T, the ITU-R and ITU-D, in order to foster awareness of telecommunication/ICT standards pertaining to e-health. - SG13 has ongoing new work on "Quality of service assurance requirements and framework for smart healthcare supported by IMT-2020 and beyond". - SG20 approved Recommendation ITU-T Y.4484 “Framework to support Web of Objects ontology based semantic data interoperability of eHealth services”. Q2/20 is currently working on draft Recommendation ITU-T Y.FSPH “Framework for smart public health emergency management in smart and sustainable cities”. Q3/20 is currently working on draft Recommendation ITU-T Y.4496 (ex Y.RA-PHE) “Requirements and reference architecture of smart service for public health emergency”. A joint ITU and PAHO report on “The Role of Digital Technologies in Aging and Health” has been published in April 2023. |  |  |  |
| 78-05 | SG16 and SG20, in collaboration with relevant SGs, particular SG11 and SG17, for ensuring the broad deployment of e-health services in diverse operating conditions, to study communication protocols relating to e-health, especially among heterogeneous networks (instructs SGs 16+20 3) | Ongoing | √ |  |
|  | See 78-04. - Q10/17 collaborates with SG11 to study communication protocols relating to e-health, especially among heterogeneous networks, to ensure the broad deployment of e-health services in diverse operating conditions. - TSAG established Joint Coordination Activity on Digital COVID Certificate (JCA-DCC) in 2022 to coordinate standardization work on DCCs among relevant ITU-T Study Groups, external organizations and forums. |  |  |  |
| 78-06 | SG16 and SG20, in collaboration with relevant SGs, particular SG11 and SG17, to give priority to study of security standards relating to e-health (i. SGs 16+20 4) | Ongoing | √ |  |
|  | See 78-04. - Q10/17 develops Recommendations related to security of e-health services, (e.g., for communications, services, network aspects and service scenarios of databases and record handling, identification, integrity and authentication) relating to e-health, taking into account the importance of safeguarding patients’ rights and privacy. |  |  |  |
| 78-07 | SG16 and SG20, in collaboration with relevant SGs, particular SG11 and SG17, to coordinate activities and studies relating to e-health among the relevant study groups, focus groups and other relevant groups in ITU-T, the ITU Radiocommunication Sector (ITU-R) and ITU-D, in order in particular to foster awareness of telecommunication/ICT standards pertaining to e-health (instructs SGs 16+20 2) | Ongoing | √ |  |
|  | - SG13 is developing Recommendation on QoS requirements for smart healthcare supported by IMT-2020, Y.IMT2020-qos-req-sh. - Work completed in SG16 on ITU-T F.760.1 "Requirements and reference framework for emergency rescue systems". - SG20 through the JCA on IoT and SC&C provides a platform for information sharing and coordination of the standardization work on digital health and relevant IoT aspects. As part of the Digital Transformation Dialogues, the following webinars took place, Episode on Emergency responses in smart cities: Driving resilience in the post-pandemic era (22 November 2022), Episode on Decade of healthy aging: role of digital technologies (22 August 2023), Episode on Digital transformation in the pharma Industry (14 November 2023) and Fireside Chat on Prospects for Surgical Advances (18 January 2024). |  |  |  |

» Top

# Resolution 79 – The role of telecommunications/ information and communication technology in handling and controlling e-waste from telecommunication and information technology equipment and methods of treating it

resolves to instruct the Director of the Telecommunication Standardization Bureau, in collaboration with the Director of the Telecommunication Development Bureau

1	to pursue and strengthen the development of ITU activities in regard to handling and controlling e-waste from telecommunication and information technology equipment and methods of treating it;

2	to assist developing countries to undertake proper assessment of the size/quantity of e-waste generated in a harmonized manner;

3	to address the handling and controlling of e-waste and to contribute to global efforts designed to deal with the increasing hazards which arise therefrom;

4	to work in collaboration with the relevant stakeholders, including academia and relevant organizations, and to coordinate activities relating to e-waste among the ITU study groups, focus groups and other relevant groups;

5	to organize seminars and workshops to enhance awareness of the hazards and sustainable management of e-waste, particularly in developing countries, and gauge the needs of the developing countries, which are the countries that suffer most from the hazards of e-waste

6	to assist and facilitate developing countries in the implementation of circular economy principles,

instructs ITU-T Study Group 5, in collaboration with the relevant ITU study groups

1	to develop and document examples of best practice for handling and controlling e-waste resulting from telecommunications/ICT and methods of treating and recycling it, for dissemination among ITU Member States and Sector Members;

2	to develop Recommendations, methodologies and other publications relating to sustainable management of e-waste resulting from telecommunications/ICT equipment and products, and appropriate guidelines on implementation awareness of these Recommendations;

3	to study the impact of used telecommunication/ICT equipment and products brought into developing countries and give appropriate guidance, taking into account recognizing further above, to assist developing countries,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 79-01 | TSBDir, in collaboration with BDTDir, to develop ITU activities to handle, control and treat e-waste of telecommunication and IT equipment (resolves 1) | Ongoing | √ |  |
|  | The ITU-T, Environment, Climate Change and Circular Economy portal features reports, events such as the Green Standards Week, material for training, and activities on e-waste and circular economy. ITU-T SG5 collaborates with ITU-D SG2, Q6/2 on topics related to E-waste. ITU-T SG5 collaborates with BDT Environmental programme on topics related to e-waste. |  |  |  |
| 79-02 | TSBDir, in collaboration with BDTDir, to assist developing countries to undertake proper assessment of the size/quantity of e-waste generated in a harmonized manner (resolves 2) | Ongoing |  |  |
| 79-03 | TSBDir, in collaboration with BDTDir, to organize seminars and workshops for developing countries and gauge their needs for e-waste (resolves 5) | Ongoing | √ |  |
|  | - A Workshop on "Accelerating Circular and Sustainable Public Procurement of ICT" was held on 14 February 2023. - The Sustainable Digital Transformation week for Africa region took place from 15-19 May 2023 in Kampala, Uganda. - WSIS virtual event: Sustainable Batteries - The building blocks of a circular economy, 26 May 2023. - Global Symposium for Regulators – Session 8: Going Green with the Digital Transformation, 8 June 2023. - Workshop on “Shaping a Sustainable and Digital Future - Pathway towards the Green Standards Week”, Virtual, 15 June 2023. - Workshop on “the Role of ICTs in Standards on Circular Economy and GHG Emissions Reduction”, Virtual, 9 November 2023. |  |  |  |
| 79-04 | SG5, in collaboration with relevant SGs, to identify, document and disseminate e-waste best practices for ITU membership (instructs SG5 1) | Ongoing |  |  |
| 79-05 | SG5, in collaboration with relevant SGs, to develop Recommendations, methodologies and other publications relating to sustainable management of e-waste resulting from telecommunications/ICT equipment and products, and appropriate guidelines on implementation awareness of these Recommendations (instructs SG5 2) | Ongoing | √ |  |
|  | See TSAG-TD333 – ITU-T SG5 Lead Study Group report. See TSAG-TD31 – ITU-T SG5 Lead Study Group report. |  |  |  |
| 79-06 | SG5, in collaboration with relevant SGs, to study the impact of telecom/ICT e-waste to developing countries and give guidance to assist developing countries (instructs SG5 3) | Ongoing |  |  |
|  | See 79-04. |  |  |  |
| 79-07 | TSBDir, in collaboration with BDTDir, to assist and facilitate developing countries in the implementation of circular economy principles. (resolves 6) | Ongoing |  |  |
|  | See 79-04. ITU-T SG5 has developed ​Questionnaire on the best practices for​ implementing the circular economy for ITU-T membership. |  |  |  |

» Top

# Resolution 80 – Acknowledging the active involvement of the membership in the development of ITU Telecommunication Standardization Sector deliverables

resolves

that it is important to acknowledge significant contributors to the work of ITU-T,

instructs the Director of the Telecommunication Standardization Bureau

to acknowledge the value of active participation of the membership, in particular academia, universities and their associated research establishments, in the standardization activities of ITU, by collaborating closely with Member States and their respective bodies that formulate public policies in areas such as education, science, technology, industry and commerce in order to highlight the importance of contribution to ITU-T study group deliverables,

instructs the Telecommunication Standardization Advisory Group

to establish criteria that guide study groups to clearly acknowledge contributors to the development of study group deliverables;

instructs the study groups of the ITU Telecommunication Standardization Sector

to acknowledge contributors to the development of study group deliverables, in particular those from academia, universities and associated research establishments, based on the criteria established by the Telecommunication Standardization Advisory Group (TSAG),

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 80-01 | TSBDir to collaborate with Member States to acknowledge the value of active membership participation and contribution to ITU-T SG deliverables (instructs TSBDir) | Ongoing | √ |  |
|  | At WTSA-12, Resolution 80 was approved with the aim of stimulating further participation of academia, universities and their associated research establishments in the work of ITU-T through the acknowledgment of their contributions to the development of ITU-T deliverables. The rationale behind this was that the performance of academics is evaluated on their publications (books, papers, patents, etc.), courses taught, thesis advisory roles, and research projects accomplished, while the efforts applied to writing, editing or presenting contributions to ITU-T, do not count towards grants and career progression for academia members. Incentive mechanisms were thought to be necessary to make key standardization processes, such as authorship of contributions and editorship, more attractive to academia members. Therefore, this Resolution 80 called on ITU-T to modify the publication procedures for its standardization documents, including Recommendations, by acknowledging somewhere in each document detailed information about its editorship and main contributors. However, the ITU Legal Affairs Unit (LAU) clearly stated that ITU solely holds copyrights on its publications (cf. Resolution 66 of Plenipotentiary Conference), and that the so-called “contributors” should not be perceived as co-authors of the texts in question. At its meeting held in June 2013, TSAG agreed to task ITU-T SG9 to explore different mechanisms to implement Resolution 80. Based on ITU-T SG9 analysis, at its meeting in February 2016, TSAG approved a set of options (Guidelines TD 899 (GEN/9): 1. Use of bibliographic references, 2. Lists of participants and contributors per meeting, and 3. Lists of contributors’ names on a given Recommendation’s webpage) to acknowledge contributors to the development of SGs deliverables and encouraged all SGs to implement them. WTSA-16 approved a slightly revised version of Res. 80, strengthening the need to acknowledge contributors to the development of SGs deliverables and to study new criteria. Nonetheless, some legal points were not fully settled and would require further discussion and clarification. In particular, the notion of “significant contribution” is hard to define and poses a constraint in the effective implementation of the Resolution. The collective nature of the ITU standardization process was reiterated by LAU. Hence, no contributors/authors can be acknowledged within the text of the Recommendation itself. This poses the need to redirect efforts towards exploring alternative solutions. For a detailed summary of all actions undertaken with respect to WTSA Resolution 80, please see WTSA-16 Contribution 59. Moreover, in line with option 1 of the guidelines (“Bibliographic references for the purpose of acknowledging input to the content of an ITU-T Recommendation will consist of peer-reviewed publications and/or books that are considered useful for the understanding and/or development of the deliverable”), researchers that are members of the ITU are encouraged to submit their research work to the scientific, peer-reviewed publications of the ITU which are free of charge for both authors and readers: the ITU Kaleidoscope academic conferences Proceedings and the ITU Journal on Future and Evolving Technologies (ITU J-FET). |  |  |  |
| 80-02 | TSAG to establish criteria that guide study groups options on how to clearly acknowledge contributors (instructs TSAG) | TSAG 2024 | √ |  |
|  | See 80-01. |  |  |  |
| 80-04 | ITU-T SGs to acknowledge contributors to the development of study group deliverables, in particular those from academia, universities and associated research establishments, based on the criteria established by the TSAG (instructs SGs) | Ongoing | √ |  |
|  | - The active participation of academia in SG12 is acknowledged in Editor- and Rapporteurships. - The active participation of academia in SG15 is acknowledged and appreciated for activities on SMART cable (Q8/15). - SG17 considered TSAG TD 460 Rev.1 options to acknowledge contributors to the development of study group deliverables; a link was available from the SG17 web page to acknowledge the SG17 management team, SG17 Rapporteurs and Associate Rapporteurs, SG17 editors and contributors. - SG20 actively encourages the participation of Academia in proposing new work items and in contributing to existing work items. |  |  |  |

» Top

# Resolution 83 – Evaluation of the implementation of resolutions of the World Telecommunication Standardization Assembly

instructs the Director of the Telecommunication Standardization Bureau, in collaboration with Directors of the other Bureaux

to take the necessary actions to assess the implementation of WTSA resolutions by all parties concerned,

instructs the Director of the Telecommunication Standardization Bureau

to take account of the implementation of WTSA resolutions and submit an assessment report to TSAG.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 83-01 | TSBDir to take the necessary actions to assess the implementation of WTSA resolutions by all parties concerned (instructs TSBDir) | Ongoing | √ |  |
|  | TSAG Rapporteur Group "WTSA Preparations (RG-WTSA)" was established. TSAG created a new work item ITU-T A.SupWTSAGL for a new Supplement to the ITU-T A-series Recommendations, WTSA preparation guideline on Resolutions. In implementing the instructs part of Resolution 92, SG13 publishes annually the revision to Supplement 59 to Y.3100-series. Last version agreed on 3 November 2023. |  |  |  |
| 83-02 | TSBDir to take account of the implementation of WTSA resolutions and submit an assessment report to TSAG (instructs TSBDir) | TSAG 2024 | √ |  |
|  | Progress on implementation of the WTSA Resolutions is reported in TSAG TDs 24, 191 and 410 (this document) to TSAG. |  |  |  |

» Top

# Resolution 84 – Studies concerning the protection of users of telecommunication/information and communication technology services

resolves

1	to continue developing relevant ITU-T Recommendations in order to provide solutions ensuring and protecting the rights of users/consumers of telecommunication/ICT services, notably in the areas of quality, security and tariff mechanisms;

2	that ITU-T, through its study groups, continue close collaboration with the ITU Telecommunication Development Sector (ITU-D) and its study groups on issues of protection of telecommunication/ICT service users/consumers, as appropriate;

3	that the study groups concerned should expedite work on Recommendations that would provide additional detail and guidance for the implementation of this resolution;

4	that ITU-T Study Group 3, where appropriate with ITU-T Study Groups 2, 11, 12, 17 and 20, within their mandates, should carry out studies, including on standards for the protection and user-centric considerations regarding users/consumers of telecommunication/ICT services;

5	that Study Group 3 should liaise with ITU-D Study Group 1 on the issues of best practices in the field of protection of users/consumers of telecommunication/ICT services,

invites the Director of the Telecommunication Standardization Bureau, in collaboration with the Director of the Telecommunication Development Bureau

1	to make efforts to implement Resolution 196 (Rev. Dubai, 2018);

2	to encourage active participation of developing countries in the relevant ITU-T study groups and to strengthen relations with other standards development organizations involved in resolving issues of protection of telecommunication/ICT service users/consumers;

3	to contribute to the relevant initiatives on the protection of users/consumers, provided that this does not overlap with or duplicate activities of the other Sectors,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 84-01 | SGs (SGs 3, 12, 17) to continue developing relevant ITU-T Recommendations in order to provide solutions ensuring and protecting the rights of users and consumers of telecommunication/ICT services, notably in the areas of quality, security and tariff mechanisms, and to expedite work on those Recommendations that would provide additional detail and guidance for the implementation of this resolution (resolves 1, 3) | Ongoing | √ |  |
|  | - SG12 has revised Recommendation ITU-T E.803 "Quality of service parameters for supporting service aspects". - SG17 works on following areas to protect human rights of users - personal identifiable information (PII) protection - X.1058: Information technology - Security techniques - Code of practice for personally identifiable information protection - X.1171: Threats and requirements for protection of personally identifiable information in applications using tag-based identification - X.1275: Guidelines on protection of personally identifiable information in the application of RFID technology - X.1363: Technical framework of personally identifiable information handling system in Internet of things environment - X.Sup32: Supplement to ITU-T X.1058 on code of practice for personally identifiable information (PII) protection for telecommunication organizations - privacy preserving technologies - X.1770: Technical guidelines for secure multi-party computation - Technical Report on Fully Homomorphic Encryption (FHE) based data aggregation in machine learning - De-identification - X.1148: Framework of de-identification process for telecommunication service providers - X.Supl.39: Supplement to ITU-T X.1148 -Requirements for data de-identification assurance. |  |  |  |
| 84-02 | ITU-T SG3, where appropriate with ITU-T Study Groups 2, 11, 12, 17, and 20, within their mandates, should carry out studies, including on standards for the protection and user-centric considerations regarding users/consumers of telecommunication/ICT services (resolves 4) | Ongoing | √ |  |
|  | - SG11 developed number of Recommendations and conducted several workshops/webinars on protecting customers against different attacks such as telephone spam, spoofing numbers, location tracking, subscriber fraud, intercept calls and messages, DoS, infiltration attacks, routing attacks, etc. All information is available on dedicated webpage https://itu.int/go/SIG-SECURITY. SG11 developed number of Recommendations and non-normative documents related to combating counterfeit and stolen telecommunication/ICT devices, software. All details including references to workshops/webinars are available on dedicated webpage at: https://itu.int/go/CS-ICT. - SG12 has revised Recommendation ITU-T E.803 "Quality of service parameters for supporting service aspects". - SG20 is currently working on draft Recommendation ITU-T Y.4488 (ex Y.IoT-SPWE) “Requirements and functional architecture of data services provided via IoT-based technologies for safety protection of working environments”. SG20 developed Recommendation ITU-T Y.4500.3 “oneM2M – Security solutions”. |  |  |  |
| 84-03 | TSBDir to assist the BDTDir to make efforts to implement Resolution 196 (Rev. Dubai, 2018) (instructs TSBDir 1) | Ongoing |  |  |
| 84-04 | TSBDir to encourage active participation of developing countries1 in the relevant ITU-T study groups and strengthen relations with other standards development organizations involved in resolving issues of protection of telecommunication/ICT service users/consumers (instructs TSBDir 2) | Ongoing | √ |  |
|  | - TSB participates in Coordination Meeting with IGOs Working in the Area of Building Respect for Intellectual Property (IP) and keeps them informed about ongoing activities on combating counterfeiting and mobile device theft. |  |  |  |
| 84-05 | ITU-T, through its study groups, continue close collaboration with the ITU Telecommunication Development Sector (ITU-D) and its study groups on issues of protection of telecommunication/ICT service users/consumers, as appropriate; and Study Group 3 should liaise with ITU-D Study Group 1 on the issues of best practices in the field of protection of users/consumers of telecommunication/ICT services (resolves 2, 5) | Ongoing | √ |  |
|  | SG3 liaises with ITU-D Study Groups on related matters. SG11 informs ITU-D SG2, particularly Q4/2, on all outcomes and ongoing activities related to combating counterfeiting and stolen ICT devices. |  |  |  |
| 84-06 | TSBDir to contribute to the relevant initiatives on the protection of users/consumers, provided that this does not overlap with or duplicate activities of the other Sectors. (invites TSBDir 3) | Ongoing |  |  |

» Top

# Resolution 86 - Facilitating the implementation of the Smart Africa Manifesto

resolves to invite study groups of the ITU Telecommunication Standardization Sector

1	to develop ITU-T Recommendations aimed at implementing emerging technologies, with a special focus on developing countries;

2	to collaborate with the Smart Africa office in regard to standards relating to emerging technologies, with more emphasis on use cases and scenarios for developing countries through regional meetings, forums, workshops, etc.,

instructs the Director of the Telecommunication Standardization Bureau, in collaboration with the Director of the Telecommunication Development Bureau

1	to establish mechanisms for collaboration and cooperation between ITU-T study groups and the Smart Africa office in the development of standards;

2	to continue supporting the Smart Africa Manifesto in accordance with Resolution 195 (Busan, 2014);

3	to provide assistance to Smart Africa and African regional groups from within the assigned budget in order to support pilot projects aimed at speeding up the implementation of ITU standards and Recommendations;

4	to strengthen training and guide Smart Africa member states, partner organizations and industries in their adoption of ITU-T standards.

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 86-01 | All ITU-T SGs to develop ITU-T Recommendations aimed at implementing emerging technologies, with a special focus on developing countries (resolves 1) | Ongoing | √ |  |
|  | See also action item 44-11. - SG13 Q5/13 "Applying Future Networks and innovation in developing countries" has four ongoing Supplements and two Recommendations under development with guidelines/experience for implementing some technologies for developing countries' benefit. - SG20 developed Recommendation ITU-T Y.4484 “Framework to support Web of Objects ontology based semantic data interoperability of eHealth services”, Recommendation ITU-T Y.4218 “IoT and ICT requirements for deployment of smart services in rural communities”. SG20 is also working on draft Recommendation ITU-T Y.4222 (ex Y.smart-evacuation) “Framework of smart evacuation in a disaster or emergency in smart cities and communities”, draft Recommendation ITU-T Y.4496 (ex Y.RA-PHE) “Requirements and reference architecture of smart service for public health emergency” and draft Recommendation ITU-T Y.RemoteEd “Requirements, capabilities and architectural frameworks for e-learning in remote classrooms”. |  |  |  |
| 86-02 | All ITU-T SGs to collaborate with the Smart Africa office in regard to standards relating to emerging technologies, with more emphasis on use cases and scenarios for developing countries through regional meetings, forums, workshops, etc (resolves 2) | Ongoing |  |  |
| 86-03 | TSBDir to establish mechanisms for collaboration and cooperation between ITU-T SGs and the Smart Africa office in the development of standards (instructs TSBDir 1) | Ongoing |  |  |
| 86-04 | TSBDir to continue supporting the Smart Africa Manifesto in accordance with Resolution 195 (Busan, 2014) (instructs TSBDir 2) | Ongoing |  |  |
| 86-05 | TSBDir to provide assistance to Smart Africa and African regional groups from within the assigned budget in order to support pilot projects aimed at speeding up the implementation of ITU standards and Recommendations (instructs TSBDir 3) | Ongoing | √ |  |
|  | Ongoing. |  |  |  |
| 86-06 | TSBDir to strengthen training and guide Smart Africa member states, partner organizations and industries in their adoption of ITU-T standards (instructs TSBDir 4) | Ongoing | √ |  |
|  | Ongoing. |  |  |  |

» Top

# Resolution 87 - Participation of the ITU Telecommunication Standardization Sector in the periodic review and revision of the International Telecommunication Regulations

resolves to instruct the Director of the Telecommunication Standardization Bureau

1	to undertake the necessary activities within the Director's field of competence in order to fully implement Resolution 146 (Rev. Busan, 2014) and Council Resolution 1379;

2	to submit the result of these activities to EG-ITR,

instructs the Telecommunication Standardization Advisory Group

to provide advice to the Director of the Telecommunication Standardization Bureau consistent with Resolution 146 (Rev. Busan, 2014) and Council Resolution 1379,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 87-01 | TSBDir to undertake the necessary activities within the Director's field of competence in order to fully implement Resolution 146 (Rev. Busan, 2014) and Council Resolution 1379 (resolves TSBDir 1) | Ongoing | √ |  |
|  | TSBDir will be closely following the Council activities for a reconvened EG-ITR in the context of PP-Res.146 (Rev. Bucharest, 2022), and with advice from the relevant advisory group, to contribute to the activities of EG-ITR as appropriate and necessary. |  |  |  |
| 87-02 | TSBDir to submit the result of these activities to EG-ITR (resolves TSBDir 2) | Council 2024 |  |  |
| 87-03 | TSAG to provide advice to the Director of the Telecommunication Standardization Bureau consistent with Resolution 146 (Rev. Busan, 2014) and Council Resolution 1379 (instructs TSAG) | TSAG 2024 |  |  |

» Top

# Resolution 88 - International mobile roaming

resolves

that ITU-T Study Group 3 must continue to study the economic effects of IMR rates,

instructs the Director of the Telecommunication Standardization Bureau

1	to organize initiatives, in collaboration with the Director of the Telecommunication Development Bureau (BDT), to raise awareness of the benefits to the consumer of lowering IMR rates;

2	to propose cooperative approaches to foster the implementation of Recommendations ITU-T D.98 and ITU-T D.97, and to lower IMR rates among the Member States, by promoting capacity-building programmes, workshops and guidelines for international cooperation agreements,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 88-01 | ITU-T SG3 continue to study the economic effects of IMR rates (resolves) | Ongoing | √ |  |
|  | SG3 has adopted a new Technical Report on roaming aspects of IoT and M2M including any related development and tariff principles. SG3 is studying in various work items at international level (D.IoT/M2M Roaming) and regional level (D.502R, D6_R_ROAM, D7_R_ROAM) tariff, economic and policy issues of roaming. SG3 adopted a new Technical Report on regional roaming initiatives. |  |  |  |
| 88-02 | TSBDir to organize initiatives, in collaboration with the Director of the Telecommunication Development Bureau (BDT), to raise awareness of the benefits to the consumer of lowering IMR rates (instructs TSBDir 1) | Ongoing |  |  |
| 88-03 | TSBDir to propose cooperative approaches to foster the implementation of Recommendations ITU-T D.98 and ITU-T D.97, and to lower IMR rates among the Member States, by promoting capacity-building programmes, workshops and guidelines for international cooperation agreements (instructs TSBDir 2) | Ongoing |  |  |
|  | See 44-19. |  |  |  |

» Top

# Resolution 89 - Promoting the use of information and communication technologies to bridge the financial inclusion gap

resolves

1	to continue and further develop the ITU-T work programme, including the ongoing work in relevant ITU-T study groups, in order to contribute to the wider global efforts to enhance financial inclusion, as part of the United Nations processes;

2	to conduct studies and develop standards and guidelines in the areas of interoperability, digitization of payments, consumer protection, quality of service, big data, security of digital financial service transactions, and telecommunications/ICTs related to digital financial services where such studies, standards and guidelines do not duplicate efforts taking place in other institutions and relate to the mandate of the Union;

3	to encourage collaboration between telecommunication regulators and financial services authorities to develop and implement standards and guidelines, including consumer protection guidance;

4	to encourage the use of innovative digital tools and technologies, as appropriate, to advance financial inclusion,

instructs the Director of the Telecommunication Standardization Bureau, in collaboration with the Directors of the other Bureaux

1	to report on progress on the implementation of this resolution annually to the Council, and to the world telecommunication standardization assembly;

2	to support the development of reports and best practices on digital financial inclusion, taking into consideration relevant studies, where clearly within the mandate of the Union and not duplicative of work for which other SDOs and institutions are responsible;

3	to establish a platform or, where possible, connect to those already existing, for peer learning, dialogue and experience-sharing in digital financial services among countries and regions, regulators from telecommunication and financial services sectors, industry experts and international and regional organizations;

4	to organize workshops and seminars for the ITU membership in collaboration with other relevant SDOs, academia and institutions with primary responsibility for financial services standards development, implementation and capacity building, in order to raise awareness and identify regulators' particular needs and challenges in enhancing financial inclusion and in respect of applications of emerging technologies in digital finance, and to share lessons learned from different regions,

instructs the relevant study groups of the ITU Telecommunication Standardization Sector

1	to organize the necessary work and studies in order to expand and accelerate the work on digital financial services, starting with their first meeting in the next study period;

2	to coordinate and collaborate with other relevant SDOs and institutions with primary responsibility for financial services standards development, implementation and capacity-building, and with other groups within ITU,;

3	to develop technical standards and guidelines that will help developing countries take advantage of emerging technologies related to digital financial services;

4	to develop technical standards and guidance for developing countries to assess the security of their digital financial service infrastructure related to telecommunications,

invites the Secretary-General

to continue to cooperate and collaborate with other entities within the United Nations and other relevant entities in formulating future international efforts for effectively addressing financial inclusion,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 89-01 | ITU-T SGs to continue and further develop the ITU-T work programme, including the ongoing work in relevant ITU-T study groups, in order to contribute to the wider global efforts to enhance financial inclusion, as part of the United Nations processes; and to conduct studies and develop standards and guidelines in the areas of interoperability, digitization of payments, consumer protection, quality of service, big data, security of digital financial service transactions and telecommunications/ICTs related to digital financial services, where such studies, standards and guidelines do not duplicate efforts taking place in other institutions and relate to the mandate of the Union; and to organize the necessary work and studies in order to expand and accelerate the work on digital financial services, starting with their first meeting in the next study period (resolves 1, 2, instructs SGs 1) | Ongoing | √ |  |
|  | - SG3 in Question 12/3 is studying Mobile Financial Services. - SG12 in Question 20/12 is studying perceptual and field assessment principles for quality of service (QoS) and quality of experience (QoE) of digital financial services (DFS). - SG17 is working on X.1150, Security assurance framework for digital financial services; X.sgdfs-us Security guidelines for DFS applications based on USSD and STK (developed under the Financial Inclusion Global Initiative) and X.sup-eKYC-dfs: Supplement to ITU-T X.1254: e-KYC use cases in digital financial services |  |  |  |
| 89-02 | ITU-T SGs to encourage collaboration between telecommunication regulators and financial services authorities to develop and implement standards and guidelines, including consumer protection guidance; and to coordinate and collaborate with other relevant SDOs and institutions with primary responsibility for financial services standards development, implementation and capacity-building, and with other groups within ITU (resolves 3, instructs SGs 2) | Ongoing | √ |  |
|  | - SG3 continues its work on this topic (ref. work item TR_DSTR-DFSNPS). |  |  |  |
| 89-03 | ITU-T SGs to encourage the use of innovative digital tools and technologies, as appropriate, to advance financial inclusion (resolves 4) | Ongoing |  |  |
| 89-04 | TSBDir to report on progress on the implementation of this resolution annually to the Council, and to WTSA (instructs TSBDir 1) | Council 2024 WTSA-24 |  |  |
| 89-05 | TSBDir to support the development of reports and best practices on digital financial inclusion, taking into consideration relevant studies, where clearly within the mandate of the Union and not duplicative of work for which other SDOs and institutions are responsible (instructs TSBDir 2) | Ongoing | √ |  |
|  | - TSB developed a knowledge transfer programme in 2022 under the ITU DFS Security Lab (set up during the Financial Inclusion Global Initiative) to enable regulators in emerging economies implement the security recommendations developed under the Financial Inclusion Global Initiative and conduct the tests for assessing the security of mobile payment applications used in their country. - TSBDir received requests from the telecom regulators in Uganda, Tanzania and Ghana and SBS Peru for setting up the DFS Security Lab to adopt the security recommendations for digital financial services developed under FIGI and to enable them to also conduct the security tests for mobile payments applications. In last quarter of 2023,requests for the knowledge transfer programme for adoption of the DFS Security Recommendations and setting up the Lab were received from RURA (Rwanda), PURA (The Gambia), Malawi (MACRA) and POTRAZ (Zimbabwe). ITU DFS Security Lab team is currently working with these telecom regulators to initiate the knowledge transfer programme with these countries. - The knowledge transfer process for TCRA, Uganda Communications Commission and SBS Peru were initiated in September 2022. - The Knowledge transfer for setting up the DFS Security Lab for Uganda was completed in December 2022 and for TCRA has been completed in April 2023.The period of inderpendent testing of mobile payment apps by the team in UCC and TCRA were completed in December 2023. - The Knowledge transfer process for SBS Peru has been completed for USSD and Android mobile payment app security testing. There was an interest from SBS Peru to also implement the testing for iOS mobile payment app and this expected to be completed in March 2024. - Security recommendations for digital financial services developed under FIGI has been adopted by CRASA in March 2023 and h East Africa Communication Organisation (EACO) in June 2023. West Africa Telecommunication Regulators Assembly (WATRA) has established a cybersecurity working group in December 2023 to consider adoption of the DFS Security Recommendations. - TSB is working on development of a cyber resilience toolkit for critical infrastructure for digital finance for DFS regulators in emerging economies. The cyberresilience toolkit for critical infrastructure for digital finance was completed in September 2023. This toolkit was developed by Deloitte following a tender exercise. The toolkit was presented during the CyberDrill organised in November 2023 as part of the activities of the Regional Group of ITU-T SG17 for Africa. ITU has received a request from TCRA to assist in implementing the Cyberresilience assessment toolkit . |  |  |  |
| 89-06 | TSBDir to establish a platform or, where possible, connect to those already existing, for peer learning, dialogue and experience-sharing in digital financial services among countries and regions, regulators from telecommunication and financial services sectors, industry experts and international and regional organizations (instructs TSBDir 3) | Ongoing |  |  |
|  | TSB has set up the DFS Security Lab (during the Financial Inclusion Global Initiative) in 2021, to provide guidance to regulators of telecommunications and financial services sectors of developing and low income countries on how to adopt the DFS Security recommendations and secure their infrastructure for digital finance. In November 2023, the DFS Security Lab has set up the knowledge sharing platform for regulators in emerging economies to share their experience on the adoption of the DFS Security recommendations, implementation of security measures to mitigate new threats in digital financial services and contribute to keeping up to date the security assurance framework developed under the Financial Inclusion Global Initiative. |  |  |  |
| 89-07 | TSBDir to organize workshops and seminars for the ITU membership in collaboration with other relevant SDOs, academia and institutions with primary responsibility for financial services standards development, implementation and capacity building, in order to raise awareness and identify regulators' particular needs and challenges in enhancing financial inclusion and in respect of applications of emerging technologies in digital finance, and to share lessons learned from different regions (instructs TSBDir 4) | Ongoing | √ |  |
|  | - SG12 workshop on QoS and QoE aspects of digital financial services (May 2022) - DFS Security Clinics TSB has organized some 27 DFS Security Clinics in countries in Africa, Latin America and Asia between February 2022 – December 2023. All the Security Clinics were conducted online. Over 1,300 participants from DFS regulators and DFS providers benefited from the DFS Security Clinics that were held in 2022 and 2023. The table below shows the DFS Security Clinics that were held in 2022 and 2023 by the ITU DFS Security Lab. Country /Region; Organized jointly with; Date. 1; Rwanda; RURA; 13-14 December 2023. 2; FIDO Workshop, Peru; Superintendencia de Banca, Seguros y AFP (SBS); 12-13 December 2023. 3; Zimbabwe; POTRAZ; 30-31 October 2023. 4; Democratic Republic of Congo; Autorité de Régulation de la Poste et des Télécommunication du Congo (ARPTC); 21-22 September 2023. 5; Asia Pacific Region; ITU Regional Development Forum; 13-15 September 2023. 6; Uganda; Uganda Communications Commission (for new staff of DFS Security Lab only); 11 September 2023. 7; Gambia; The Gambia Public Utilities Regulatory Authority (PURA); 10 - 11 July 2023. 8; Southern Africa; The Communications Regulators' Association of Southern Africa (CRASA); 15 - 16 June 2023. 9; Gambia; The Gambia Public Utilities Regulatory Authority (PURA); 5 – 6 June 2023. 10; East Africa; East African Communications Organization (EACO); 8 – 9 February 2023. 11; Eastern Caribbean; UNCDF-EU-OACP Partnership for Digital Financial Inclusion; 17 – 19 January 2023. 12; Peru; Superintendencia de Banca, Seguros y AFP (SBS); 1 – 2 December 2022. 13; West Africa region; West African Telecommunication Regulators Assembly (WATRA); 13-14 October 2022. 14; Sierra Leone; National Telecommunications Commission (NATCOM); 26 – 27 September 2022. 15; Peru; Superintendencia de Banca, Seguros y AFP (SBS); 8 – 9 September 2022. 16; Côte d’Ivoire; Autorité de Régulation des Télécommunications de Côte D'Ivoire (ARTCI); 6 – 7 September 2022. 17; Democratic Republic of Congo; Autorité de Régulation de la Poste et des Télécommunication du Congo (ARPTC); 26 – 27 July 2022. 18; Tanzania; Tanzania Communications Regulatory Authority (TCRA); 11 – 12 July 2022. 19; East Africa; East African Communications Organisation (EACO); 6 July 2022. 20; Gambia; The Gambia Public Utilities Regulatory Authority (PURA); 29 – 30 June 2022. 21; Pakistan; State Bank of Pakistan (SBP); 1 – 2 June 2022. 22; SADC Region; Communications Regulators' Association of Southern Africa (CRASA); 24 – 25 May 2022. 23; Rwanda; Rwanda Utilities Regulatory Authority (RURA); 12 – 13 April 2022. 24; Pakistan; State Bank of Pakistan (SBP); 12 – 13 April 2022. 25; East Africa Region; East African Communications Organisation (EACO); 30 – 31 March 2022. 26; Zimbabwe; Postal & Telecommunications Regulatory Authority (POTRAZ); 16 – 17 February 2022. 27; Zimbabwe; Postal & Telecommunications Regulatory Authority (POTRAZ); 9 – 10 February 2022. |
| 89-08 | ITU-T SGs to develop technical standards and guidelines that will help developing countries take advantage of emerging technologies related to digital financial services (instructs SGs 3) | Ongoing | √ |  |
|  | - SG12 in Question 20/12 is studying perceptual and field assessment principles for quality of service (QoS) and quality of experience (QoE) of digital financial services (DFS). - See 89-01 above. |  |  |  |
| 89-09 | ITU-T SGs to develop technical standards and guidance for developing countries to assess the security of their digital financial service infrastructure related to telecommunications (instructs SGs 4) | Ongoing |  |  |
|  | - Security recommendations for digital financial services developed under FIGI being implemented by telecom regulators in emerging economies (See 89/05) through the ITU DFS Security Lab - In 2022 and 2023, ITU DFS Security Lab received requests from the following countries to help them to test mobile payment applications: - Zimbabwe (USSD and Android mobile money applications) - The Gambia (USSD and Android mobile money applications) - DRC Telecom regulator (USSD, Android and iOS mobile money applications) - In addition, mobile payments applications were also tested during the knowledge transfer for the establishment of the DFS Security Lab for - TCRA (Tanzania), - Uganda Communications Commission - SBS Peru. - TSB is working on development of a cyber resilience toolkit for critical infrastructure for digital finance for DFS regulators in emerging economies. The cyber resilience toolkit for critical infrastructure for digital finance was completed in September 2023. This toolkit was developed by Deloitte under the guidance of the DFS Security Lab, following a tender exercise. The toolkit was presented during the CyberDrill organised in November 2023 as part of the activities of the Regional Group of ITU-T SG17 for Africa. ITU has received a request from TCRA to assist in implementation of the Cyber resilience toolkit - ITU entered in a MoU with FNSV Korea in June 2023, to provide guidance on adoption of passwordless authentication for digital financial services using blockchain. |  |  |  |

» Top

# Resolution 90 - Open source in the ITU Telecommunication Standardization Sector

resolves

that the Telecommunication Standardization Advisory Group (TSAG) continue to work on the benefits and disadvantages of the implementation of open-source projects in relation with the work of the ITU Telecommunication Standardization Sector (ITU-T), as appropriate,

instructs all applicable study groups of the ITU Telecommunication Standardization Sector, within available financial resources

1	to provide inputs to TSAG enquiries on open source as listed in TSAG Report 8, July 2016;

2	to consider output from TSAG on open source, in order to study the value of using open source to develop reference implementations of ITU-T Recommendations, as appropriate;

3	considering the output of the studies under instructs 2 above, to continue using open source as appropriate;

4	to support the use of open-source projects in their work, as appropriate, taking into account the outcome of the TSAG study;

5	to continue engaging with open-source projects,

instructs the Director of the Telecommunication Standardization Bureau

1	to provide open source related training (e.g. tutorials, seminars, workshops) to ITU-T participants, in collaboration with open-source communities and the Telecommunication Development Bureau, taking into account the ITU-T objective to bridge the standardization gap and digital gender gap and the budgetary constraints of the Union;

2	to submit a report to TSAG annually on progress achieved in implementing this resolution,

instructs the Telecommunication Standardization Advisory Group

to continue fulfilling of the outcomes of TSAG Report 8 concerning open source,

invites the ITU Council Working Group on financial and human resources

to evaluate any potential financial implications for the Union of implementing this resolution,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 90-03 | All ITU-T SGs to consider output from TSAG on open source, in order to study the value of using open source to develop reference implementations of ITU-T Recommendations, as appropriate; and considering the output of the studies under instructs 2 above, to continue using open source as appropriate (instructs SGs 2, 3) | Ongoing |  |  |
| 90-04 | All ITU-T SGs to support the use of open-source projects in their work, as appropriate, taking into account the outcome of the TSAG study; and to continue engaging with open-source projects (instructs SGs 4, 5) | Ongoing |  |  |
| 90-05 | TSBDir to provide open source related training (e.g. tutorials, seminars, workshops) to ITU-T participants, in collaboration with open-source communities and the Telecommunication Development Bureau, taking into account the ITU-T objective to bridge the standardization gap and digital gender gap and the budgetary constraints of the Union (instructs TSBDir 1) | Ongoing |  |  |
|  | Eight ITU-T Build-a-thon workshops have been hosted alongside FG-AN meetings since 2022 where participants/teams showcased demos of their open-source reference implementations. This activity is ongoing. |  |  |  |
| 90-06 | TSBDir to submit a report to TSAG annually on progress achieved in implementing this resolution (instructs TSBDir 2) | TSAG 2024 | √ |  |
| 90-07 | TSBDir to invite the ITU Council Working Group on financial and human resources, to evaluate any potential financial implications for the Union of implementing this resolution. | Council |  |  |
|  | Nothing can be reported so far. |  |  |  |

» Top

# Resolution 91 - Enhancing access to an electronic repository of information on numbering plans published by the ITU Telecommunication Standardization Sector

resolves to instruct Study Group 2 of the ITU Telecommunication Standardization Sector

to study this matter on the basis of contributions received and information from TSB and to organize the necessary work in order to determine the requirements for electronic access to a repository of numbering resources reserved, assigned or allocated to each operator/service provider (to the extent available) within every country, including presentation of E.164 national numbering plans on the basis of Recommendation ITU-T E.129, and international numbering resources assigned by the Director of TSB,

instructs the Director of the Telecommunication Standardization Bureau

1	to provide the necessary assistance for the ITU members by providing details of existing information resources relating to the presentation of national numbering plans and international numbering resources;

2	based on the results of the above-mentioned Study Group 2 studies, to organize and maintain such an electronic repository as described above, within the allocated budget,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 91-01 | ITU-T SG2 to study the matter of enhancing access to an electronic repository of information on numbering plans on the basis of contributions received and information from TSB and to organize the necessary work in order to determine the requirements for electronic access to a repository of numbering resources reserved, assigned or allocated to each operator/service provider (to the extent available) within every country, including presentation of E.164 national numbering plans on the basis of Recommendation ITU-T E.129, and international numbering resources assigned by the Director of TSB (resolves SG2) | Ongoing | √ |  |
|  | The ITU National Numbering Plan website is currently at the prototype stage. Further progress in SG2 depends on Contributions. |  |  |  |
| 91-02 | TSBDir to provide the necessary assistance for the ITU members by providing details of existing information resources relating to the presentation of national numbering plans and international numbering resources (instructs TSBDir 1) | Ongoing |  |  |
| 91-03 | TSBDir to organize and maintain such an electronic repository as described above, within the allocated budget (instructs TSBDir 2) | Ongoing | √ | √ |
|  | TSB has a repository for ITU national numbering plans (NNPs) based on methodology introduced in Recommendation ITU-T E.129. The new repository is now up to date allowing access to formal communications in MS Word format, and dynamic view with search criteria from one single website available at https://www.itu.int/itu-t/nnp. |  |  |  |

» Top

# Resolution 92 - Enhancing the standardization activities in the ITU Telecommunication Standardization Sector related to non-radio aspects of international mobile telecommunications

resolves to invite the Telecommunication Standardization Advisory Group

1	to facilitate coordination of the standardization activities related to the non-radio side of IMT systems (including IMT-2020 and beyond) among all relevant study groups, focus groups, joint coordination activities, etc.;

2	to strengthen and accelerate activities related to the development and deployment of IMT systems based on standards for open and interoperable network technologies and solutions, such as non-radio aspects of IMT systems for access networks, particularly recognizing challenges in developing countries;

3	to ensure collaboration among relevant ITU-T study groups and with relevant SDOs and forums and consortia for open and interoperable network technologies and solutions, including non-radio aspects of IMT systems for access networks;

4	to encourage, in cooperation with Study Group 13 and other relevant study groups, collaboration with other standards development organizations (SDOs) on a wide range of issues associated with the non-radio aspects of IMT systems,

instructs study groups of the ITU Telecommunication Standardization Sector

1	to strengthen the collaboration and coordination on IMT systems (including IMT-2020 and beyond) standardization activities with other relevant standards organizations, in order to ensure a productive and practical standard solution for the global ICT industry;

2	to promote efficient and effective standardization work on the non-radio aspects of IMT systems, including IMT-2020 and beyond, as well as applications of relevant network technologies;

3	to promote ITU-T standardization work on the requirements of developing countries related to IMT in general and IMT-2020 in particular;

4	to be responsible for the development and annual reporting of ITU-T's standards strategy on IMT,

instructs ITU-T Study Group 3

to consider the ITU-T studies related to, inter alia, regulatory and economic questions relevant to IMT systems including IMT-2020 and beyond within their mandate,

instructs Study Group 5

to pursue promoting the studies on standardization activities related to IMT environmental requirements, including energy efficiency,

instructs Study Group 11

to continue promoting the studies on standardization activities related to the non-radio aspects of IMT signalling, requirements, protocols and testing frameworks, specifications, methodologies, capabilities, and interoperability for IMT systems (including IMT-2020 and beyond),

instructs Study Group 12

to continue promoting the studies on standardization activities related of service, QoS and quality of experience (QoE) related to the non-radio aspects of IMT systems (including IMT-2020 and beyond),

instructs Study Group 13

1	to maintain the roadmap of, and continue promoting, IMT standardization activities in ITU-T, which should include work items to progress standardization work related to the non-radio aspects of IMT systems (including IMT-2020 and beyond), and share this with relevant groups of ITU-R and ITU-D and external organizations, such as through coordination work ensured by JCA-IMT-2020;

2	to maintain and update on an annual basis the supplement to the ITU-T Recommendation containing the current version of the IMT-2020 standardization roadmap;;

3	to continue promoting the studies on non-radio aspects of IMT system (including IMT-2020 and beyond) network requirements and architecture, including network softwarization, (e.g. non-radio aspects of Cloud RAN, multi-access edge computing, etc.), network slicing, network capability openness including open network interconnection and exposure, network management and orchestration, terrestrial (e.g. fixed-mobile) and non-terrestrial (e.g. satellite) convergence, emerging network technology, and the use of machine learning;

4	to promote JCA IMT-2020 and beyond and to continue coordinating the standardization activities of IMT systems (including IMT-2020 and beyond) among all relevant study groups, focus groups and other SDOs,

instructs Study Group 15

to continue promoting the studies on non-radio aspects of IMT's transport network (e.g. fronthaul and backhaul) standardization activities, including network requirements, architecture, function and performance, characteristics, enabling technologies, management and control, synchronization, etc., for IMT systems (including IMT-2020 and beyond),

instructs Study Group 17

1	to continue promoting the studies on standardization activities related to network and applications security for IMT-2020 and beyond;

2	to promote coordination and collaboration with ITU-R and other SDOs, such as 3GPP SA3, on security aspects of IMT-2020 and beyond in the course of development of the relevant specifications or ITU-T Recommendations,

instructs the Director of the Telecommunication Standardization Bureau

1	to bring this resolution to the attention of the Directors of the Radiocommunication Bureau and the Telecommunication Development Bureau;

2	to continue conducting seminars and workshops on non-radio aspects of IMT the standard strategic, technical solutions and network applications, taking into account specific national and regional requirements,

encourages the Directors of the three Bureaux

1	to investigate new ways to improve the efficiency of ITU work on IMT and to examine the possibility to establish an observatory for IMT-2020 and beyond, including appropriate guidelines if needed, taking into account budgetary considerations;

2	to promote the studies on standardization activities related to regulatory and economic questions relevant to accommodating non-radio aspects of IMT-2020 systems and beyond use cases, and to encouraging and supporting market growth, innovation, collaboration and ICT infrastructure investment;

3	to develop guidance on the economic drivers for IMT-2020 deployment,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 92-01 | TSAG to facilitate coordination of the standardization activities related to the non-radio side of IMT systems (including IMT-2020 and beyond) among all relevant study groups, focus groups, joint coordination activities, etc.; to strengthen and accelerate activities related to the development and deployment of IMT systems based on standards for open and interoperable network technologies and solutions, such as non-radio aspects of IMT systems for access networks, particularly recognizing challenges in developing countries; and to encourage, in cooperation with Study Group 13 and other relevant study groups, collaboration with other standards development organizations (SDOs) on a wide range of issues associated with the non-radio aspects of IMT; to ensure collaboration among relevant ITU-T study groups and with relevant SDOs and forums and consortia for open and interoperable network technologies and solutions, including non-radio aspects of IMT systems for access networks (resolves TSAG 1, 2, 3, 4) | Ongoing TSAG 2024 | √ |  |
|  | See items 92-02, 92-04 and 92-12 below for SG13 progress. |  |  |  |
| 92-02 | All ITU-T SGs to strengthen collaboration and coordination on IMT systems (IMT-2020 and beyond) standardization activities with other relevant standards organizations, in order to ensure a productive and practical standard solution for the global ICT industry; and to promote efficient and effective standardization work on the non-radio aspects of IMT systems, including IMT-2020 and beyond, as well as applications of relevant network technologies; to promote ITU-T standardization work on the requirements of developing countries related to IMT in general and IMT-2020 in particular; all ITU-T SGs to be responsible for the development and annual reporting to TSAG of ITU-T's standards strategy on IMT (instructs SGs 1, 2, 3, 4) | Ongoing | √ |  |
|  | - SG3 is continuing studies in work item STUDY_IMT2020MVNOs on 5G related policy considering MVNOs. SG3 also appointed a representative of ITU-T SG3 to the JCA-IMT2020 group. - JCA-IMT2020 and Beyond continues its operation in this study period with revised Terms of Reference. As part of its duties it maintains the IMT-2020 and Beyond standardization roadmap with collection to the standards in the area of IMT-2020 and Beyond published and under development in ITU and SDOs. Each JCA- IMT2020 meeting receives the presentation from one entity with its current and future work highlights. - SG13 regularly informs other SDOs (like 3GPP, ETSI, IEEE etc) on start of the new work in the area of IMT2020 and beyond. The first steps towards close collaboration with O-RAN Alliance were made at October – November SG13 meeting. SG13 regularly informs TSAG through its lead SG report about its progress, future plans and strategies in the area of mobile communications (network part). Q5/13 has one Recommendation under development to help developing countries to implement IMT-2020. SG15 collocates with a JCA-IMT2020 meeting and liaises with JCA-IMT2020 regularly. - SG15 develops Recommendation ITU-T G.8300 series on mobile network transport aspects. - SG17 sent a Liaison statement to ITU-R WP5D in which SG17 asked WP5D to consider the security and PII protection aspects in the vision documents for IMT 2030 and beyond. SG17 sent a Liaison Statement to JCA-IMT2020 in which SG17 asked them to consider the need for to security coordination in the ToR of this JCA at its September 2022 SG17 meeting. SG17 sent a Liaison Statement to JCA-IMT2020 in which SG17 provided the information in the IMT-2020 and beyond roadmap at its September 2022 SG17 meeting. SG17 approved - XSTP-5Gsec-RM, Technical Report: 5G Security Standardization Roadmap, - ITU-T X.1812 (5/2022), Security framework based on trust relationship for IMT-2020 ecosystem, - ITU-T X.1813 (9/2022), Security and monitoring requirements for the operation of vertical services supporting ultra-reliable and low latency communication (URLLC) in the IMT-2020 private networks, and - ITU-T X.1814 (9/2022), Security guidelines for the IMT-2020 communication system developed by Q2/17, - X.1815 (3/2023), Guidelines for classifying security capabilities in 5G network slice, and - X.1816 (3/2023), Security Framework for 5G Edge Computing Services. - X.1817 (9/2023): Security Requirements for IMT-2020 messaging service Q2/17 is working on draft new Recommendations - X.1818 (X.5Gsec-ctrl), Security controls for operation and maintenance of IMT-2020/5G network systems. - X.5Gsec-srocvs, Security Requirements for the Operation of IMT-2020 Core Network to Support Vertical Services, and - X.5Gsec-netec: Security capabilities of network layer for IMT-2020 edge computing - X.5Gsec-asra: Guidelines and Technical Requirements for 5G Network Asset Security Risk Analysis - TR.5Gsec-bsf: Technical Report - Guidelines of built-in security framework for telecommunications network Q2/17 maintains 5G security standardization roadmap and updates it in every SG17 meeting since March 2020 SG17 meeting. |  |  |  |
| 92-04 | SG13 to maintain the roadmap of, and continue promoting, IMT standardization activities in ITU-T, which should include work items to progress standardization work related to the non-radio aspects of IMT systems (including IMT-2020 and beyond), and share this with relevant groups of ITU-R and ITU-D and external organizations, such as through coordination work ensured by JCA-IMT-2020; to maintain and update on an annual basis the supplement to the ITU-T Recommendation containing the current version of the IMT-2020 standardization roadmap; to continue promoting the studies on non-radio aspects of IMT system (including IMT-2020 and beyond) network requirements and architecture, including network softwarization, (e.g. non-radio aspects of Cloud RAN, multi-access edge computing, etc.), network slicing, network capability openness including open network interconnection and exposure, network management and orchestration, terrestrial (e.g. fixed-mobile) and non-terrestrial (e.g. satellite) convergence, emerging network technology, and the use of machine learning; to promote JCA IMT-2020 and beyond and to continue coordinating the standardization activities of IMT systems (including IMT-2020 and beyond) among all relevant study groups, focus groups and other SDOs, (instructs SG13 1, 2, 3, 4) | Ongoing | √ |  |
|  | - SG13 promotes the studies and awareness of the work in the field of IMT-2020 and beyond via its JCA-IMT2020 activity. - SG13 approved 35 new Recommendations on IMT-2020 (March 2022 – January 2024). - JCA-IMT2020 regularly updates and maintains the IMT-2020 standardization roadmap, comprising a subset of ongoing and accomplished work in different ITU-T SGs, ITU-R WP5D and selected SDOs. A snapshot of this roadmap of late October 2023 was agreed at the October 2023 SG13 meeting as revised Supplement 59 to Y.3100-series of Recommendations. JCA-IMT2020 regularly assesses the potential new topics for collaboration as well as invites and receives the presentation from different bodies of their ongoing work in this subject area. SG13 workshop in July 2023 (Geneva) contributed to raising awareness of the ITU (ITU-R and ITU-T) work towards IMT-2030. So did the 9th SG13 Regional Workshop for Africa in Abidjan, Cote D'Ivoire, 19-20 September 2023. - The correspondence group on Artificial Intelligence in IMT-2030 (CG-AI6G), set up in November 2023 under SG13, is to elaborate the rationale and Terms of Reference for the new Focus Group on artificial intelligence in IMT-2030 (FG-AI6G). - An information session on the ITU-R work towards IMT-2030 was convened on 17 March 2013 alongside SG13 meeting for the benefit of SG13 delegates. |  |  |  |
| 92-07 | SG15 to continue promoting the studies on non-radio aspects of IMT's transport network (e.g. fronthaul and backhaul) standardization activities, including network requirements, architecture, function and performance, characteristics, enabling technologies, management and control, synchronization, etc., for IMT systems (including IMT-2020 and beyond) (instructs SG15) | Ongoing | √ |  |
|  | SG15 is working on the topics on transport technologies for the support of IMT systems (including IMT-2020 and beyond). SG15 collocates with a JCA-IMT2020 meeting and liaises with JCA-IMT2020 regularly. SG15 develops Recommendation ITU-T G.8300 series on mobile network transport aspects. |  |  |  |
| 92-08 | SG11 to continue promoting the studies on standardization activities related to the non-radio aspects of IMT signalling, requirements, protocols and testing frameworks, specifications, methodologies, capabilities, and interoperability for IMT systems (including IMT-2020 and beyond) (instructs SG11) | Ongoing | √ |  |
|  | SG11 continues promoting studies related to signalling aspects. SG11 organized two Webinars to provide overview of existing signalling protocols and their security, as follows: - Webinar on "Enhancing signalling security and privacy using globally interoperable digital signatures" (virtual, 16 June 2022) - ITU Webinar Series on Signalling Security - Episode 2: on "Securing legacy telecom network services" (virtual, 7 November 2022) TSB in close collaboration with SG11 management team developed a standalone webpage on signalling security which summarizes all SG11-related standards and events. See https://itu.int/go/SIG-SECURITY. |  |  |  |
| 92-09 | SG12 to continue promoting the studies on standardization activities related of service, QoS and quality of experience (QoE) related to the non-radio aspects of IMT systems (including IMT-2020 and beyond) (instructs SG12) | Ongoing | √ |  |
|  | SG12 is working on QoS and QoE matters for the support of IMT systems (including IMT-2020 and beyond). It regularly shares its progress with JCA-IMT2020. |  |  |  |
| 92-10 | SG17 to continue promoting the studies on standardization activities related to network and applications security for IMT-2020 and beyond; to promote coordination and collaboration with ITU-R and other SDOs, such as 3GPP SA3, on security aspects of IMT-2020 and beyond in the course of development of the relevant specifications or ITU-T Recommendations (instructs 1, 2 SG17) | Ongoing |  |  |
|  | See SG17 related activities reported under 92-01 above. |  |  |  |
| 92-11 | TSBDir to bring this resolution to the attention of the Directors of the Radiocommunication Bureau and the Telecommunication Development Bureau (instructs TSBDir 1) | 2022 |  | √ |
|  | BR and BDT were informed. |  |  |  |
| 92-12 | TSBDir to continue conducting seminars and workshops on non-radio aspects of IMT the standard strategic, technical solutions and network applications, taking into account specific national and regional requirements (instructs TSBDir 2) | Ongoing | √ |  |
|  | SG13 organized the workshop in July 2023, half day of it was devoted to IMT-2030 developments (network part). Part of the ITU SG13 9th Regional Workshop for Africa "Standardization of Future Networks and Emerging Network Technologies: African perspectives " focused on IMT-2020 & Beyond IMT-2020 Networks (non-radio part). |  |  |  |
| 92-13 | TSB+BDT+BR Directors to investigate new ways to improve the efficiency of ITU work on IMT and to examine the possibility to establish an observatory for IMT-2020 and beyond, including appropriate guidelines if needed, taking into account budgetary considerations; to promote the studies on standardization activities related to regulatory and economic questions relevant to accommodating non-radio aspects of IMT-2020 systems and beyond use cases, and to encouraging and supporting market growth, innovation, collaboration and ICT infrastructure investment. | Ongoing |  |  |
| 92-14 | SG3 to consider the ITU-T studies related to, inter alia, regulatory and economic questions relevant to IMT systems including IMT-2020 and beyond within their mandate (instructs SG3) | Ongoing | √ |  |
|  | SG3 is studying IMT-2020 policy issues in work item STUDY_IMT2020MVNOs “5G related policy considering MVNOs”. SG3 also appointed a representative of ITU-T SG3 to the JCA-IMT2020 group. |  |  |  |
| 92-15 | SG5 to pursue promoting the studies on standardization activities related to IMT environmental requirements, including energy efficiency (instructs SG5) | Ongoing |  |  |

» Top

# Resolution 93 - Interconnection of 4G, IMT-2020 networks and beyond

resolves

that ITU-T Recommendations to address network architectures, roaming principles, numbering issues, charging and security mechanisms as well as interoperability and conformance testing for interconnection of 4G, IMT-2020 networks and beyond shall be progressed as quickly as possible,

instructs the Director of the Telecommunication Standardization Bureau

1	to continue to conduct, as necessary, exploratory activities among telecommunication operators in order to identify and prioritize the problems related to achieving interconnection of IP-based networks such as 4G, IMT-2020 and beyond;

2	to submit the results of these activities to the ITU Council for its consideration and required actions,

instructs the study groups

1	to identify as soon as possible future ITU-T Recommendations that need to be developed associated with the interconnection of 4G, IMT-2020 networks and beyond;

2	to cooperate, as appropriate, with interested stakeholders and alliances in order to optimize studies on this particular subject,

further instructs Study Group 11

to develop ITU-T Recommendations which specify the framework and signalling architectures to be used for establishing interconnection of 4G, IMT-2020 networks and beyond to achieve interoperability worldwide,

further instructs Study Group 2

to develop ITU-T Recommendations which specify the ENUM architecture to be used for interconnection of 4G, IMT-2020 networks and beyond, including administrative control that could relate to the international telecommunication resources (including naming, numbering, addressing, and routing),

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 93-01 | SGs (SGs 2, 3, 11, 13, 17) to progress as quickly as possible ITU-T Recommendations to address network architectures, roaming principles, numbering issues, charging and security mechanisms as well as interoperability and conformance testing for interconnection of 4G, IMT-2020 networks and beyond; and to identify as soon as possible future ITU-T Recommendations that need to be developed associated with the interconnection of 4G, IMT-2020 networks and beyond; and to cooperate, as appropriate, with interested stakeholders and alliances in order to optimize studies on this particular subject (resolves, instructs SGs 1, 2) | Ongoing | √ |  |
|  | - SG3 is studying policy and regulatory aspects related to IMT-2020, such as IMT2020-related policy considering MVNOs. Several work items address roaming aspects at the international and regional level. - SG11 noted that Voice over LTE (VoLTE) and Voice over New Radio (VoNR) utilize the same IMS (IP Multimedia Subsystem) as defined in 3GPP. While the IP IMS framework remains the same, technological improvements in radio, core and devices are expected to provide superior user experience in VoNR compared to VoLTE. In this regard, SG11 started two new work items related to interconnection testing of Voice, Video over New Radio, as follows: - Q.FW-IVV5G: Framework for interconnection testing of Voice, Video over 5G; - Q.VoiNR-test: VoNR/ViNR interconnection testing for interworking and roaming scenarios. Also, SG11 approved ITU-T Q.3647 which defines signalling requirements for emergency service in IMS roaming environment. - SG17 designated its Q2/17 to lead on 5G security standardization. SG17 held an ITU workshop on security for 5G and beyond on 22 August 2022. See SG17 related activities reported under 92-01 above. |  |  |  |
| 93-02 | TSBDir to continue to conduct, as necessary, exploratory activities among telecommunication operators in order to identify and prioritize the problems related to achieving interconnection of IP-based networks such as 4G, IMT-2020 and beyond (instructs TSBDir 1) | Ongoing |  |  |
| 93-03 | TSBDir to submit the results of these activities to the ITU Council for its consideration and required actions (instructs TSBDir 2) | Council 2024 | √ |  |
|  | The TSB Director reports annually in the Council document on "ITU Internet activities: Resolutions 101, 102 and 133, 180, and 206", which includes updates regarding 4G and IMT-2020, if any; see S22-CL-C-0033. |  |  |  |
| 93-04 | SG11 to develop ITU-T Recommendations which specify the framework and signalling architectures to be used for establishing interconnection of 4G, IMT-2020 networks and beyond to achieve interoperability worldwide (instructs SG11) | Ongoing | √ |  |
|  | SG11 noted that Voice over LTE (VoLTE) and Voice over New Radio (VoNR) utilize the same IMS (IP Multimedia Subsystem) as defined in 3GPP. While the IP IMS framework remains the same, technological improvements in radio, core and devices are expected to provide superior user experience in VoNR compared to VoLTE. In this regard, in July 2022, SG11 started two new work items related to interconnection testing of Voice, Video over New Radio, as follows: - Q.FW-IVV5G: Framework for interconnection testing of Voice, Video over 5G; - Q.VoiNR-test: VoNR/ViNR interconnection testing for interworking and roaming scenarios. |  |  |  |
| 93-05 | SG2 to develop ITU-T Recommendations which specify the ENUM architecture to be used for interconnection of 4G, IMT-2020 networks and beyond, including administrative control that could relate to the international telecommunication resources (including naming, numbering, addressing, and routing) (instructs SG2) | Ongoing |  |  |

» Top

# Resolution 94 - Standardization work in the ITU Telecommunication Standardization Sector for cloud-based event data technology

resolves to instruct Study Groups 13, 16, 17 and 20 of the ITU Telecommunication Standardization Sector

1	to evaluate existing, evolving and new Recommendations with respect to cloud-based event data technology;

2	to make recommendations to the Telecommunication Standardization Advisory Group on how to address the topics that are outside the mandate of the study groups,

instructs the Telecommunication Standardization Advisory Group

to drive a concerted effort across relevant study groups to accelerate standardization work on cloud-based event data technology,

instructs the Director of the Telecommunication Standardization Bureau

1	to provide the necessary assistance to speed up standardization work on cloud-based event data technology and to encourage participation and contributions from Member States, particularly developing countries;

2	to organize (a) workshop(s) to collect requirements and inputs on this topic from a wide range of various stakeholders,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 94-01 | ITU-T SGs 13, 16, 17, 20 to evaluate existing, evolving and new Recommendations with respect to cloud-based event data technology (resolves 1) | Ongoing | √ |  |
|  | - SG13 confirmed commitment to encourage contributions to the technical topic of cloud-based event data technology. Call for contributions was dispatch at every SG13 meeting (Q17/13). - SG16 completed work on ITU-T F.747.13 (ex F.CEC) "Requirements and reference framework of cloud-edge collaboration in industrial machine vision systems". Additional 18 work items are listed in the SG16 work programme involving cloud and AI, video surveillance, machine vision and gaming. - Q8/17 is working on draft new Recommendation - X.gecds, Guideline on edge computing data security - X.sa-ec, Security architecture of edge cloud - X.sg-scmr, Security guidelines for selecting computing methods and resources from Cloud Service Providers. SG17 approved - X.1380 (3/2023), Security guidelines for cloud-based data recorders in automotive environment, developed by Q13/17. - SG20 is working on draft Recommendation ITU-T Y.AI-DECCS “Functional architecture of AI enabled device-edge-cloud collaborative services for IoT and smart city”, draft Recommendation ITU-T Y.IoT-CONV-fr “Convergence framework for enhancement of service intelligence based on Internet of Things”. SG20 approved Recommendation ITU-T Y.4486 “Framework of cross edge decentralized service by using DLT and edge computing technologies for IoT devices”. |  |  |  |
| 94-02 | ITU-T SGs 13, 16, 17, 20 to make recommendations to the Telecommunication Standardization Advisory Group on how to address the topics that are outside the mandate of the study groups (resolves 2) | TSAG 2024 |  |  |
|  | N/A |  |  |  |
| 94-03 | TSAG to drive a concerted effort across relevant study groups to accelerate standardization work on cloud-based event data technology (instructs TSAG) | TSAG 2024 |  |  |
| 94-04 | TSBDir to provide the necessary assistance to speed up standardization work on cloud-based event data technology and to encourage participation and contributions from Member States, particularly developing countries (instructs TSBDir 1) | Ongoing |  |  |
| 94-05 | TSBDir to organize (a) workshop(s) to collect requirements and inputs on this topic from a wide range of various stakeholders (instructs TSBDir 2) | Ongoing |  |  |

» Top

# Resolution 95 - ITU Telecommunication Standardization Sector initiatives to raise awareness on best practices and policies related to service quality

resolves that the ITU Telecommunication Standardization Sector

1	continue to develop the necessary Recommendations on performance, QoS and QoE, in particular for broadband networks and services;

2	in close collaboration with the ITU Telecommunication Development Sector (ITU-D), develop initiatives to raise awareness of the importance of keeping users informed about the quality of the services offered by operators;

3	in close collaboration with ITU-D and the ITU regional offices, provide references that assist developing and least developed countries in establishing a national quality measurement framework suitable to perform QoS and QoE measurement;

4	organize workshops, training programmes and further initiatives to promote wider participation of regulators, operators and suppliers in the international debate on service quality and raise awareness of the importance of QoS and QoE measurement,

instructs the Director of the Telecommunication Standardization Bureau

in order to implement resolves 2 and 4 above, to continue to support the activities of QSDG for open operational and regulatory discussions among regulators, operators and suppliers about new strategies to deliver better QoS and QoE to users,

instructs the Director of the Telecommunication Standardization Bureau, in close collaboration with the Director of the Telecommunication Development Bureau

1	to assist developing and least developed countries in identifying human and institutional capacity-building opportunities for establishing national quality measurement frameworks;

2	to conduct activities in each region in order to identify and prioritize the problems faced by developing and least developed countries related to the provision of acceptable service quality to users;

3	based on results of instructs 2 above, to assist developing and least developed countries in elaborating and implementing actions to improve service quality and keep users informed,

instructs study groups of the ITU Telecommunication Standardization Sector, according to their mandate

1	to elaborate Recommendations providing guidance to regulators in regard to defining strategies and testing methodologies to monitor and measure QoS and QoE, in particular for broadband networks and services;

2	to study QoS and QoE evaluation scenarios, measurement strategies, mapping, visualization and testing tools, and publication mechanisms, to be adopted by regulators and operators;

3	to study and provide guidance to regulators in regard to sampling methodologies for QoS measurements at a local, national and global level;

4	to provide references relating to minimal satisfactory key performance and key quality indicators for evaluating the quality of services;

5	to implement strategies to raise participation of developing and developed countries from all regions in all their activities,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 95-01 | ITU-T SG12 to continue to develop the necessary Recommendations on performance, QoS and QoE, in particular for broadband networks and services. (resolves 1) | Ongoing | √ |  |
|  | - SG12 has revised Recommendation ITU-T E.803 "Quality of service parameters for supporting service aspects". - SG12 has established new work item E.MVS (Mapping and visualization strategies for the assessment of connectivity and QoS) in response to WTSA call for work on mapping and visualization. |  |  |  |
| 95-02 | ITU-T SG12 and TSBDir in close collaboration with the ITU Telecommunication Development Sector (ITU-D), develop initiatives to raise awareness on of the importance of keeping users informed about the quality of the services offered by operators; and in close collaboration with ITU-D and the ITU regional offices, provide references that assist developing and least developed countries in establishing a national quality measurement framework suitable to perform QoS and QoE measurement (resolves 2, 3) | Ongoing | √ |  |
|  | - SG12 workshop on QoS and QoE aspects of digital financial services (May 2022). - Organized by QSDG, SG12 workshops held in Amman, Jordan, October 2022, Banjul, The Gambia, March 2023, Mexico City, Mexico, September 2023, hearing reports from stakeholders in the region. Regional Office involved in preparations. - Leveraging Recommendations developed by SG12, ITU Academy module “Introduction to Service Quality Regulation” equips participants with the tools to establish service quality regulatory frameworks to monitor and measure quality of service (QoS) and quality of experience (QoE). |  |  |  |
| 95-03 | ITU-T SG12 and TSBDir organize workshops, training programmes and further initiatives to promote wider participation of regulators, operators and suppliers in the international debate on service quality and raise the awareness of the importance of QoS and QoE measurement (resolves 4) | Ongoing | √ |  |
|  | - SG12 workshop on QoS and QoE aspects of digital financial services (May 2022) https://www.itu.int/en/ITU-T/Workshops-and-Seminars/2022/0512/Pages/default.aspx - Organized by QSDG, SG12 workshops held in Amman, Jordan, October 2022, Banjul, The Gambia, March 2023, Mexico City, Mexico, September 2023, hearing reports from stakeholders in the region. Regional Office involved in preparations. - Leveraging Recommendations developed by SG12, ITU Academy module “Introduction to Service Quality Regulation” equips participants with the tools to establish service quality regulatory frameworks to monitor and measure quality of service (QoS) and quality of experience (QoE). |  |  |  |
| 95-04 | TSBDir in order to implement resolves 2 and 4 above, to continue to support the activities of QSDG for open operational and regulatory discussions among regulators, operators and suppliers about new strategies to deliver better QoS and QoE to users (instructs TSBDir) | Ongoing | √ |  |
|  | - Organized by QSDG, SG12 workshops held in Amman, Jordan, October 2022, Banjul, The Gambia, March 2023, Mexico City, Mexico, September 2023, hearing reports from stakeholders in the region. Regional Office involved in preparations. |  |  |  |
| 95-05 | TSBDir to assist developing and least developed countries in identifying human and institutional capacity-building opportunities for establishing national quality measurement frameworks (instructs TSBDir 1) | Ongoing |  |  |
| 95-06 | TSBDir to conduct activities in each region in order to identify and prioritize the problems faced by developing and least developed countries related to the provision of acceptable service quality to users (instructs TSBDir 2) | Ongoing | √ |  |
|  | See 95-04 and 95-05. |  |  |  |
| 95-07 | TSBDir based on results of instructs 2 above, to assist developing and least developed countries in elaborating and implementing actions to improve service quality and keep users informed (instructs TSBDir 3) | Ongoing |  |  |
| 95-08 | Study groups to - elaborate Recommendations providing guidance to regulators in regard to defining strategies and testing methodologies to monitor and measure QoS and QoE, in particular for broadband networks and services. (instructs SGs 1) - to study QoS and QoE evaluation scenarios, measurement strategies, mapping, visualization and testing tools, and publication mechanisms, to be adopted by regulators and operators. (instructs SGs 2) - to study and provide guidance to regulators in regard to sampling methodologies for QoS measurements at a local, national and global level (instructs SGs 3) - to provide references relating to minimal satisfactory key performance and key quality indicators for evaluating the quality of services (instructs SGs 4) - to implement strategies to raise participation of developing and developed countries from all regions in all their activities (instructs SGs 5) | Ongoing | √ |  |
|  | - SG12 has established new work item E.MVS (Mapping and visualization strategies for the assessment of connectivity and QoS) in response to WTSA call for work on mapping and visualization. - SG12 has revised Recommendation ITU-T E.803 "Quality of service parameters for supporting service aspects". - SG13 has Question Q6/13 "Networks beyond IMT2020: Quality of service (QoS) mechanisms" looking after quality-of-service assurance in IMT-2020, machine learning and QKDN application areas - SG20 is working on draft Recommendation ITU-T Y.NCE.arch.EIoT “Functional architecture enhancement with network capability exposure to support flexible QoS/QoE requirements from enterprise IoT services and applications”, draft Recommendation ITU-T Y.IoT-SQMS “Requirements and functional architecture of IoT sensing quality management service” and draft Recommendation ITU-T Y.QE-DMI-SSC “Quality evaluation of digital models in industry for smart sustainable cities”. - SG20 approved Recommendation ITU-T Y.4603 “Requirements and functional model to support data quality management in IoT” and Recommendation ITU-T Y.4909 “Assessment framework of IoT sensing quality” Q3/20 addresses topics on IoT and SC&C architectures, protocols and QoS/QoE. |  |  |  |

» Top

# Resolution 96 - ITU Telecommunication Standardization Sector studies for combating counterfeit telecommunication/information and communication technology devices

resolves

1	to explore ways and means to combat and deter telecommunication/ICT device counterfeiting and tampering in order to protect industry, governments and consumers from counterfeit and tempered telecommunication/ICT devices;

2	that Study Group 11 should be the lead study group in the area of combating counterfeit and tampered telecommunication/ICT devices,

instructs the Director of the Telecommunication Standardization Bureau, in close collaboration with the Director of the Telecommunication Development Bureau

1	to organize workshops and events across the ITU regions to promote the work in this field, involving all stakeholders and raising awareness of the impact of counterfeit and tampered telecommunication/ICT devices;

2	to assist developing countries in preparing human resources to combat the spread of counterfeit and tampered telecommunication/ICT devices, by providing capacity-building and training opportunities;

3	to work in close collaboration with relevant stakeholders, such as WTO, WIPO, WHO and WCO, on activities relating to combating counterfeit and tampered telecommunication/ICT devices, including restricting the trading, export and circulation of these telecommunication/ICT devices internationally;

4	to coordinate activities relating to combating counterfeit and tampered telecommunication/ICT devices through study groups, focus groups and other related groups;

5	to assist Member States in taking the necessary actions to apply relevant ITU-T Recommendations for combating counterfeit and tampered telecommunication/ICT devices, including the use of conformity assessment systems,

instructs the Director of the Telecommunication Standardization Bureau

1	to collaborate with industry associations, consortia and forums to identify possible technological measures, both software and hardware, that may be developed to deter tampering and the use and spread of counterfeit and tampered telecommunication/ICT devices;

2	to submit the results of these activities to the ITU Council for its consideration and required action;

3	to involve experts and external entities as appropriate;

instructs the Director of the Telecommunication Standardization Bureau, in close collaboration with the Directors of the Radiocommunication and Telecommunication Development Bureaux

1	to assist Member States in addressing their concerns with respect to counterfeit and tampered telecommunication/ICT devices, through information sharing at regional or global level, including conformity assessment systems;

2	to assist all the membership, considering relevant ITU-T Recommendations, in taking the necessary actions to prevent or detect the tampering with and/or duplication of unique telecommunication/ICT device identifiers, interacting with other SDOs related to these matters,

instructs Study Group 11 of the ITU Telecommunication Standardization Sector, in collaboration with other study groups concerned

1	to continue developing Recommendations, technical reports and guidelines to address the problem of counterfeit and tampered ICT equipment and to support the Member States in anti-counterfeiting activities;

2	to collect, analyse and exchange information about counterfeiting and tampering practices in the ICT sector, and how ICTs could be used as a tool to combat them;

3	to study existing as well as new reliable, unique, persistent and secure identifiers, in collaboration with ITU-T Study Groups 2, 17 and 20, that have the potential to be used in combating counterfeit and tampered products and telecommunication/ICT devices, including their scope of application and level of security in the context of their possible duplication/cloning;

4	to develop methods of assessing and verifying identifiers used for purposes of combating counterfeit production;

5	with the involvement of relevant standardization organizations, to develop mechanisms as appropriate for identifying counterfeit production, by means of unique identifiers that are resistant to duplication and respond to confidentiality/security requirements;

6	to study possible solutions, including frameworks to discover identity management information, that could support combating of counterfeit and tampered telecommunication/ICT devices;

7	to identify a list of technologies/products, used for testing conformance with ITU-T Recommendations, in order to help in efforts to combat counterfeit ICT production,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 96-01 | All ITU-T study groups to explore ways and means to combat and deter telecommunication/ICT device counterfeiting and tampering in order to protect industry, governments and consumers from counterfeit and tempered telecommunication/ICT devices (resolves 1) | Ongoing | √ |  |
|  | - SG11 started consumer centric framework for combating counterfeit and stolen ICT mobile devices and SG11 continues its studies related to central equipment identity register (CEIR). All achievements and activities are available on dedicated webpage https://itu.int/go/CS-ICT. |  |  |  |
| 96-02 | SG11 is the lead study group in the area of combating counterfeit and tampered telecommunication/ICT devices (resolves 2) | Ongoing | √ |  |
|  | - See 96-01. |  |  |  |
| 96-03 | TSBDir to organize workshops and events across the ITU regions to promote the work in this field, involving all stakeholders and raising awareness of the impact of counterfeit and tampered telecommunication/ICT devices (instructs TSBDir 1) | Ongoing | √ |  |
|  | In February 2023, ITU started a series of Webinars and Workshops related to combating counterfeiting and stolen ICT devices. The first Episode “Existing challenges and solutions on combating counterfeiting of ICT devices” was held on 15 February 2023. All workshops and webinars as well as all outcomes and ongoing activities related to combating counterfeiting are listed on dedicated webpage https://itu.int/go/CS-ICT. |  |  |  |
| 96-04 | TSBDir to assist developing countries in preparing human resources to combat the spread of counterfeit and tampered telecommunication/ICT devices, by providing capacity-building and training opportunities (instructs TSBDir 2) | Ongoing | √ |  |
|  | All workshops and webinars as well as all outcomes and ongoing activities related to combating counterfeiting are listed on dedicated webpage https://itu.int/go/CS-ICT. |  |  |  |
| 96-05 | TSBDir to work in close collaboration with relevant stakeholders, such as WTO, WIPO, WHO and WCO, on activities relating to combating counterfeit and tampered telecommunication/ICT devices, including restricting the trading, export and circulation of these telecommunication/ICT devices internationally (instructs TSBDir 3) | Ongoing | √ |  |
|  | TSB participates in Coordination Meeting with IGOs Working in the Area of Building Respect for Intellectual Property (IP) and keeps them informed about ongoing activities on combating counterfeiting and mobile device theft. |  |  |  |
| 96-06 | TSBDir to coordinate activities relating to combating counterfeit and tampered telecommunication/ICT devices through study groups, focus groups and other related groups (instructs TSBDir 4) | Ongoing | √ |  |
|  | See 96-01. |  |  |  |
| 96-07 | TSBDir to assist Member States in taking the necessary actions to apply relevant ITU-T Recommendations for combating counterfeit and tampered telecommunication/ICT devices, including the use of conformity assessment systems (instructs TSBDir 5) | Ongoing |  |  |
| 96-08 | TSBDir to collaborate with industry associations, consortia and forums to identify possible technological measures, both software and hardware, that may be developed to deter tampering and the use and spread of counterfeit and tampered telecommunication/ICT devices (instructs TSBDir 1) | Ongoing | √ |  |
|  | New industry members become associates to SG11. Currently, they initiated SG11 studies related on equipment identity register (EIR and CEIR). SG11 started several work items on this subject matter. |  |  |  |
| 96-09 | TSBDir to submit the results of these activities to the ITU Council for its consideration and required action (instructs TSBDir 2) | Council 2024 | √ |  |
|  | The updates are highlighted in the TSB Director progress report. |  |  |  |
| 96-10 | TSBDir to involve experts and external entities as appropriate (instructs TSBDir 3) | Ongoing | √ |  |
|  | ITU works in collaboration with relevant stakeholders. |  |  |  |
| 96-11 | TSBDir to assist Member States in addressing their concerns with respect to counterfeit and tampered telecommunication/ICT devices, through information sharing at regional or global level, including conformity assessment systems (instructs TSBDir 1) | Ongoing | √ |  |
|  | All information about SG11 activities on combating counterfeiting and stolen mobile devices are highlighted on dedicated webpage https://itu.int/go/CS-ICT. |  |  |  |
| 96-12 | TSBDir to assist all the membership, considering relevant ITU-T Recommendations, in taking the necessary actions to prevent or detect the tampering with and/or duplication of unique telecommunication/ICT device identifiers, interacting with other SDOs related to these matters (instructs TSBDir 2) | Ongoing | √ |  |
|  | In February 2023, ITU started a series of Webinars and Workshops related to combating counterfeiting and stolen ICT devices. The first Episode “Existing challenges and solutions on combating counterfeiting of ICT devices” (15 February 2023) summarized the existing issues and challenges on circulation of counterfeit ICT devices that different stakeholders face for the time being and highlighted on how implementations of relevant ITU-T Recommendations which may help with combating such issues. |  |  |  |
| 96-13 | SG11 to continue developing Recommendations, technical reports and guidelines to address the problem of counterfeit and tampered ICT equipment and to support the Member States in anti-counterfeiting activities (instructs SG11 1) | Ongoing |  |  |
|  | SG11: see 96-01. |  |  |  |
| 96-14 | SG11 to collect, analyse and exchange information about counterfeiting and tampering practices in the ICT sector, and how ICTs could be used as a tool to combat them; (instructs SG11 2, 3) | Ongoing | √ |  |
|  | SG11 approved ITU-T Q.Suppl.75 "Use Cases on the Combat of Counterfeit ICT and Stolen Mobile Devices". Currently, SG11 continues collecting use cases from ITU Members that reflects challenges, opportunities and results on the combat of multimedia content misappropriation. |  |  |  |
| 96-15 | SG11 to study existing as well as new reliable, unique, persistent and secure identifiers, in collaboration with ITU-T Study Groups 2, 17 and 20, that have the potential to be used in combating counterfeit and tampered products and telecommunication/ICT devices, including their scope of application and level of security in the context of their possible duplication/cloning; and to develop methods of assessing and verifying identifiers used for purposes of combating counterfeit production (instructs SG11 3, 4) | Ongoing |  |  |
| 96-16 | SG11 with the involvement of relevant standardization organizations, to develop mechanisms as appropriate for identifying counterfeit production, by means of unique identifiers that are resistant to duplication and respond to confidentiality/security requirements (instructs SG11 5) | Ongoing |  |  |
| 96-17 | SG11 to study possible solutions, including frameworks to discover identity management information, that could support combating of counterfeit and tampered telecommunication/ICT devices (instructs SG11 6) | Ongoing | √ |  |
|  | SG11 continues its studies related to the equipment identity register (EIR). Among them is the draft supplement Q.Sup.CEIR-EIR-int “Common approaches and interfaces for data exchange between CEIR and EIR” which aims to identify current industry approach on the data exchange between central equipment identity register (CEIR) and EIR. In July 2022, SG11 started a new work item Q.CEIR “Technical requirement, interfaces and generic functions of CEIR”. |  |  |  |
| 96-18 | SG11 to identify a list of technologies/products, used for testing conformance with ITU-T Recommendations, in order to help in efforts to combat counterfeit ICT production (instructs SG11 7) | Ongoing |  |  |

» Top

# Resolution 97 - Combating mobile telecommunication device theft

resolves

1	that ITU-T should explore all applicable solutions and develop ITU-T Recommendations to combat and deter mobile device theft and its negative effects, offering all interested parties a forum for encouraging discussion, member cooperation, the exchange of best practices and guidelines and the dissemination of information on combating mobile device theft;

2	that ITU-T should, in collaboration with the relevant standards organizations, develop solutions to address the problem of replication of unique identifiers;

3	that ITU-Т Study Group 11 should be the lead study group at ITU-T on activities relating to combating mobile telecommunication device theft,

instructs the Director of the Telecommunication Standardization Bureau, in collaboration with the Directors of the Radiocommunication Bureau and Telecommunication Development Bureau

1	to compile and share information on best practices developed by industry or governments and promising trends in combating mobile device theft especially from regions where the rate of mobile phone theft has fallen, including statistics on their effectiveness;

2	to facilitate, in collaboration with industry organizations and standards development organizations (SDOs), the standardization and dissemination of Recommendations, technical reports and guidelines to combat mobile device theft and its negative effects, specifically regarding the exchange of identifiers of mobile devices reported stolen or lost, and to prevent lost or stolen mobile devices from accessing mobile networks;

3	to consult with the Sector's relevant study groups, manufacturers of mobile devices, manufacturers of telecommunication network components, operators, telecommunication SDOs as well as developers of promising technologies related to these matters, in order to identify existing and future technological measures, both software and hardware, to mitigate the consequences of the use of stolen mobile devices;

4	to provide assistance, within ITU-T's expertise and within available resources, as appropriate, in cooperation with relevant organizations, to Member States, if so requested, in order to reduce mobile device theft and the use of stolen mobile devices in their countries;

5	to share information and experiences on how to control tampering (unauthorized changing) of unique mobile telecommunication/ICT device identifiers and prevent tampered devices from accessing mobile networks,

instructs Study Groups 11 and 17 of the ITU Telecommunication Standardization Sector, within their mandates and in collaboration with other interested study groups,

1	to develop Recommendations, technical reports and guidelines to address the problem of mobile telecommunication device theft and its negative effects;

2	to study any possible solutions to combat the use of stolen mobile telecommunication devices with tampered (changed without authorization) identities and to prevent them from accessing the mobile network;

3	to study any technologies that can be used as a tool for combating mobile telecommunication device theft;

4	to draw up a list of identifiers used in mobile telecommunication/ICT devices,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 97-01 | ITU-T SGs should explore all applicable solutions and develop ITU-T Recommendations to combat and deter mobile device theft and its negative effects, offering all interested parties a forum for encouraging discussion, member cooperation, the exchange of best practices and guidelines and the dissemination of information on combating mobile device theft (resolves 1) | Ongoing | √ |  |
|  | All solutions regarding mobile device theft, which were developed by SG11, are listed in ITU-T Q.Suppl.74 “Roadmap for the Q.5050-series - Combat of Counterfeit ICT and Stolen Mobile Devices”. SG11 continues its studies related to the equipment identity register (EIR) which might be used as a tool to prevent spreading of stolen mobile devices. All information is available on dedicated webpage at: https://itu.int/go/CS-ICT. |  |  |  |
| 97-02 | ITU-T SGs should, in collaboration with the relevant standards organizations, develop solutions to address the problem of replication of unique identifiers (resolves 2) | Ongoing | √ |  |
|  | - SG11 developed ITU-T Q.5052 “Addressing mobile devices with duplicate unique identifier”. |  |  |  |
| 97-03 | SG11 should be the lead study group at ITU-T on activities relating to combating mobile telecommunication device theft (resolves 3) | Ongoing | √ |  |
|  | SG11 informs ITU SGs on the ongoing work related to mobile device theft and encourages their active participation on this matter. SG11 established an action plan for implementation of WTSA-20 Resolution 97. |  |  |  |
| 97-04 | TSBDir to compile and share information on best practices developed by industry or governments and promising trends in combating mobile device theft especially from regions where the rate of mobile phone theft has fallen, including statistics on their effectiveness (instructs TSBDir 1) | Ongoing | √ |  |
|  | SG11 will follow up the plan for implementation of Resolution 97 (WTSA-20). All information is available on dedicated webpage at: https://itu.int/go/CS-ICT. |  |  |  |
| 97-05 | TSBDir to facilitate, in collaboration with industry organizations and standards development organizations (SDOs), the standardization and dissemination of Recommendations, technical reports and guidelines to combat mobile device theft and its negative effects, specifically regarding the exchange of identifiers of mobile devices reported stolen or lost, and to prevent lost or stolen mobile devices from accessing mobile networks (instructs TSBDir 2) | Ongoing | √ |  |
|  | SG11 will follow up the plan for implementation of Resolution 97 (WTSA-20). |  |  |  |
| 97-06 | TSBDir to consult with the Sector's relevant study groups, manufacturers of mobile devices, manufacturers of telecommunication network components, operators, telecommunication SDOs as well as developers of promising technologies related to these matters, in order to identify existing and future technological measures, both software and hardware, to mitigate the consequences of the use of stolen mobile devices (instructs TSBDir 3) | Ongoing | √ |  |
|  | SG11 follows-up the plan for implementation of Resolution 97 (WTSA-20). New members were involved in SG11 related activities following consultations and ITU Workshops. |  |  |  |
| 97-07 | TSBDir to provide assistance, within ITU-T's expertise and within available resources, as appropriate, in cooperation with relevant organizations, to Member States, if so requested, in order to reduce mobile device theft and the use of stolen mobile devices in their countries (instructs TSBDir 4) | Ongoing | √ |  |
|  | All information is available on dedicated webpage at: https://itu.int/go/CS-ICT. |  |  |  |
| 97-08 | SGs 11 and 17 to develop Recommendations, technical reports and guidelines to address the problem of mobile telecommunication device theft and its negative effects (instructs SGs11+17 1) | Ongoing | √ |  |
|  | All information is available on dedicated webpage at: https://itu.int/go/CS-ICT. |  |  |  |
| 97-09 | SGs 11 and 17 to study any possible solutions to combat the use of stolen mobile telecommunication devices with tampered (changed without authorization) identities and to prevent them from accessing the mobile network (instructs SGs11+17 2) | Ongoing |  |  |
|  | SG11: see 97-08. |  |  |  |
| 97-10 | SGs 11 and 17 to study any technologies that can be used as a tool for combating mobile telecommunication device theft (instructs SGs11+17 3) | Ongoing |  |  |
|  | SG11, SG17: see 97-08. |  |  |  |
| 97-11 | SGs 11 and 17 to draw up a list of identifiers used in mobile telecommunication/ICT devices (instructs SGs11+17 4) | Ongoing |  |  |
| 97-12 | TSBDir to share information and experiences on how to control tampering (unauthorized changing) of unique mobile telecommunication/ICT device identifiers and prevent tampered devices from accessing mobile networks. (instructs TSBDir 5) | Ongoing | √ |  |
|  | ITU organized several Workshops and Webinars where best practices and use cases were provided. All information is available on dedicated webpage at: https://itu.int/go/CS-ICT. |  |  |  |

» Top

# Resolution 98 - Enhancing the standardization of Internet of things and smart cities and communities for global development

resolves to instruct Study Group 20 of the ITU Telecommunication Standardization Sector

1	to develop ITU-T Recommendations aimed at implementing IoT and SC&C, including, but not limited to, on issues related to emerging technologies and vertical industries;

2	to continue, within its mandate, to work with a special focus on the design of a roadmap and harmonized and coordinated international telecommunication standards for the development of IoT, taking into account the needs of each region and Member States, as well as the wide variety of use cases and applications, and the need for IoT to be open and adaptable, and fostering a competitive environment;

3	to collaborate with IoT-related standards organizations and other stakeholders such as industry forums and associations, consortia and SDOs, as well as other relevant ITU-T study groups, taking into account relevant work;

4	to collate, evaluate, assess and share IoT use cases from the interoperability and standardization standpoints for data and information exchange,

instructs the Director of the Telecommunication Standardization Bureau

1	to provide necessary assistance in order to take advantage of every opportunity, within the assigned budget, to promote quality standardization work in a timely manner, and to communicate with telecommunication and ICT industries in order to promote their participation in ITU-T's standardization activities on IoT and SC&C;

2	to carry out, in collaboration with Member States and cities, pilot projects in cities related to SC&C key performance indicator (KPI) assessment activities, aimed at facilitating the deployment and implementation of IoT and SC&C standards worldwide;

3	to continue to support U4SSC and share its deliverables with Study Group 20 and other study groups concerned;

4	to promote and encourage the implementation of U4SSC KPIs as a standard for smart sustainable cities' self-assessment in collaboration with Member States;

5	to continue encouraging cooperation with other international SDOs, industry forums, and other related organizations, and global projects and initiatives, in order to increase the development of international telecommunication standards and reports that facilitate the interoperability of IoT services,

instructs the Director of the Telecommunication Standardization Bureau, in collaboration with the Directors of the Telecommunication Development Bureau and the Radiocommunication Bureau

1	to prepare reports considering, in particular, the needs of developing countries in terms of the study of IoT and its applications, sensor networks, services and infrastructure, taking into account the results of work being done in ITU-R and ITU-D to ensure coordination of efforts;

2	to provide support to Member States to implement U4SSC KPIs for smart sustainable cities;

3	to foster joint work among ITU Sectors to discuss the various aspects related to the development of the IoT ecosystem and solutions for SC&C, in the context of the achievement of the SDGs and within the framework of the World Summit on the Information Society;

4	to continue disseminating ITU publications on IoT and SC&C, as well as organizing forums, seminars and workshops on the subject, taking into account the needs of developing countries, in particular;

5	to support Member States, especially developing countries, in the organization of forums, seminars and workshops on IoT and SC&C to promote innovation, development and growth in IoT technologies and solutions;

6	to report to the next world telecommunication standardization assembly on progress made in the organization of forums, seminars and workshops dedicated to developing the capacity of developing countries;

7	to assist developing countries in the implementation of recommendations, technical reports and guidelines related to IoT and SC&C,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 98-01 | SG20 to develop ITU-T Recommendations aimed at implementing IoT and SC&C, including, but not limited to, on issues related to emerging technologies and vertical industries (resolves SG20 1) | Ongoing | √ |  |
|  | SG20 continues to develop standards that leverage IoT and digital technologies to address urban and rural development challenges and to accelerate digital transformation. A key part of this study is the standardization of end-to-end architectures for IoT and mechanisms for the interoperability of IoT applications, digital services and datasets employed by various vertically oriented industry sectors. SG20 approved Recommendations on IoT and SC&C are available here.SG20 ongoing work items are available here. SG17 continued to work on IoT security in this study period and approved the following standard: - X.1352 (9/2022), Security requirements for IoT device and gateway. - XSTR.ba-iot (9/2023), Technical Report: Broadcast authentication scheme for IoT system. Q6/17 is working on - X.1353 (1/2024) Security methodology for zero-touch deployment in massive IoT based on blockchain - X.ra-iot, Security risk analysis framework for IoT devices, , and - X.sc-iot, Security controls for Internet of Things (IoT) systems, |  |  |  |
| 98-02 | SG20 to continue, within its mandate, to work with a special focus on the design of a roadmap and harmonized and coordinated international telecommunication standards for the development of IoT, taking into account the needs of each region and Member States, as well as the wide variety of use cases and applications, and the need for IoT to be open and adaptable, and fostering a competitive environment (resolves SG20 2) | Ongoing | √ |  |
|  | The IoT and Smart Cities and Communities Standards Roadmap documents complete as well as ongoing work on IoT and Smart Cities and Communities by ITU-T as well as a range of standards other standards bodies. This roadmap is maintained by the Joint Coordination Activity on Internet of Things and Smart Cities and Communities (JCA-IoT and SC&C) and is available online. The JCA IoT and SC&C Roadmap is also available as Supplement ITU-T Y.Suppl.58: Internet of Things and smart cities and communities standards roadmap. Joint Coordination Activity on Internet of Things and Smart Cities and Communities (JCA-IoT and SC&C) meetings took place as follows: - Geneva, 19 July 2022 - Geneva, 31 January 2023 - Arusha, 12 September 2023 |  |  |  |
| 98-03 | SG20 to collaborate with IoT-related standards organizations and other stakeholders such as industry forums and associations, consortia and SDOs, as well as other relevant ITU-T study groups, and taking into account relevant work (resolves SG20 3) | Ongoing | √ |  |
|  | - The Joint Coordination Activity on Internet of Things and Smart Cities and Communities (JCA-IoT and SC&C) is assisting in initiating active collaboration with relevant SDOs and Forums. The JCA is maintaining the IoT and Smart Cities and Communities Standards Roadmap which documents complete as well as ongoing work on IoT and Smart Cities and Communities carried out by ITU-T as well as by other SDOs and Forums. The IoT and SC&C standards roadmap is available online here. The JCA IoT and SC&C Roadmap is also available as Supplement ITU-T Y.Suppl.58: Internet of Things and smart cities and communities standards roadmap. - SG20 is closely collaborating with oneM2M, IEEE, IEC SyC Smart Cities and TMForum. - ITU-T SG20 is also closely collaborating with ISO and IEC. The Joint IEC-ISO-ITU Smart Cities Task Force (J-SCTF) has held the following meetings: - Virtual 10 and 12 May 2022 - Korea, 28-30 November 2022 - Geneva, 27-28 January 2023 - Geneva, 27-28 March 2023 - Virtual, 10-11 July 2023 - Virtual, 2-3 November 2023 |  |  |  |
| 98-04 | SG20 to collate, evaluate, assess and share IoT use cases from the interoperability and standardization standpoints for data and information exchange (resolves SG20 4) | Ongoing | √ |  |
|  | The Correspondence Group on Artificial intelligence of Things (CG-AIoT) carried out several activities to provide guidelines for future AIoT standardization in a timely and strategical way. CG-AIoT concluded its activities and the following Technical Paper on “Challenges of and Guidelines to Standardization on Artificial Intelligence of Things" was approved. The correspondence group has held the following meetings: - Geneva, 20 July 2022 - Virtual, 5 October 2022 - Virtual, 7 December 2023 - Geneva, 1 February 2023 - Virtual, 4 April 2023 - Virtual, 2 June 2023 - Paris, 11 July 2023 - Arusha, 13 September 2023 Several United for Smart Sustainable Cities (U4SSC) Key Performance Indicators’ city snapshots, city verification reports and city factsheets have been developed and are continuously being developed to highlight the SSC initiative and experience of other cities in implementing the KPIs for SSC. Find out more on ITU’s implementation of the U4SSC KPIs here. U4SSC KPIs reports are available here. See 98-03. |  |  |  |
| 98-05 | TSBDir to provide necessary assistance in order to take advantage of every opportunity, within the assigned budget, to promote quality standardization work in a timely manner, and to communicate with telecommunication and ICT industries in order to promote their participation in ITU-T's standardization activities on IoT and SC&C (instructs TSBDir 1) | Ongoing | √ |  |
|  | The newly created Digital Transformation Resource Hub provides a wide range of quality publications on digital transformation topics, including smart sustainable cities, cities' actions to tackle COVID-19, artificial intelligence, Internet of things, blockchain, digital twin, metaverse and digital transformation trends. All resources are freely available to all. It can be found at: https://www.itu.int/cities/dt-resource-hub/. The following events and activities have been organized: 2022: - Webinar series on Digital transformation for cities and communities (Virtual, 2022) - WSIS Forum 2022 workshop on "Towards People-Oriented Cities" (Virtual, 29 March 2022) - DT4CC Episode #14: Accelerating agricultural digital transformation through AI and IoT (Virtual, 29 March 2022) - DT4CC Episode #15: Smart city platforms for an integrated management in smart sustainable cities (Virtual, 28 April 2022) - STI Forum 2022 - Side Event on Building People-Oriented Cities Through Digital Transformation (Virtual, 6 May 2022) - WSIS 2022 - Beyond smart cities = “Smart for all” (Virtual, 10 May 2022) - Information Session on Toolkit on Digital Transformation for People-oriented Cities and Communities (Virtual, 21 June 2022) - Forum on Strengthening digital transformation in Latin America (Guatemala, 7-8 July 2022) - DT4CC Episode 16: Procurement for Smart and Sustainable Cities: Innovative mechanisms for Digital Transformation (Virtual, 9 September 2022) - Workshop on “Digital Agriculture at Scale: Sustainable Food Systems with IoT and AI” (Seongnam, Korea, 24 August 2022) - RECI Roundtable on “Sustainable and smart cities towards digital transformation” (Palma de Mallorca, 10 October 2022) - RECI Special Session on U4SSC (Palma de Mallorca, 11 October 2022) - ITU@COP27 Climate classroom - “Digital Transformation for People-oriented Cities and Communities” (Virtual, 10 November 2022) - DTC4CC Episode #17: Emergency responses in smart cities: Driving resilience in the post-pandemic era (Virtual, 22 November 2022) - DTC4CC Episode #18: Cities in the age of artificial intelligence: How to leverage technology for digital transformation (Virtual, 23 November 2022) - AI for Good webinar: Digital transformation for people-oriented cities and communities (Virtual, 29 November 2022) - DTC4CC Episode #19: Tourism in smart cities: Reimagining the road to digital tourism (Virtual, 7 December 2022) - DTC4CC Episode #20: A one-of-a-kind platform for digital transformation: the U4SSC Austrian Country Hub (Virtual, 7 December 2022) 2023: - DT4CC Episode #21: Digital Agriculture: Driving Digital Transformation for Food Security​​​​​ (Geneva, 17 February 2023) - DT Episode #22: Digital water in smart sustainable cities​ (Virtual, 14 March 2023​) - DT Episode #23: STI Forum Side event on Building the pathway to sustainable digital transformation (Virtual, 2 May 2023) - Episode #24: STI Forum Side event on Building back smarter and more sustainable cities through the United for Smart Sustainable Cities Initiative (Virtual, 3 May 2023) - Episode #25: STI Forum Side event on Leveraging the metaverse in cities to achieve the SDGs (Virtual, 4 May 2023) - Episode #26: Digital transformation of mobility: paving the way for road safety (Virtual, 14 June 2023) - Episode #27: Digital transformation of testing: federated testbeds as a service (Virtual, 21 June 2023) - Episode #28: Digital transformation and Ethical use of technology for animals (Virtual, 26 July 2023) - Episode #29: Decade of healthy aging: role of digital technologies (Virtual, 22 August 2023) - Episode #30: ChatGPT: risks and rewards of generative AI in cities (Virtual, 4 September 2023) - Episode #31: Digital tourism: bridging the gap between communities and destinations (Virtual, 27 September 2023) - Episode #32: “Fashioning” the metaverse to accelerate digital transformation: what has gone out of style (Virtual, 2 October 2023) - Episode #33: Disaster risk reduction in the digital transformation age: Leveraging emerging technologies (Virtual, 13 October 2023) - Episode #34: What is a citiverse? And how can it contribute to sustainable city development? (Virtual, 24 October 2023) - Episode #35: How to successfully develop People-Centred citiverse? (Virtual, 30 October 2023) - Episode #36: World cities day: digital transformation for a better urban life (Virtual, 31 October 2023) - Episode #37: Digital transformation in the pharma Industry (Virtual, 14 November 2023) - Episode #38: Localizing the Sustainable Development Goals: Invest NYC SDG Initiative (Virtual, 16 November 2023) - Episode #39: The Interplay Between Human Rights and Technology (Virtual, 8 December 2023) Other events can be found here. Upcoming events available at: https://www.itu.int/cities/meetings/ |  |  |  |
| 98-06 | TSBDir to carry out, in collaboration with Member States and cities, pilot projects in cities related to SC&C key performance indicator (KPI) assessment activities, aimed at facilitating the deployment and implementation of IoT and SC&C standards worldwide (instructs TSBDir 2) | Ongoing | √ |  |
|  | United for Smart Sustainable Cities Key Performance Indicators based on Recommendation ITU-T Y.4903 “Key performance indicators for smart sustainable cities to assess the achievement of sustainable development goals" are being implemented in over 200 cities worldwide. Please find ITU’s implementation of the U4SSC KPIs (city snapshots, verification reports, case studies and factsheets) available here. |  |  |  |
| 98-07 | TSBDir to continue to support U4SSC and share its deliverables with Study Group 20 and other study groups concerned; to promote and encourage the implementation of U4SSC KPIs as a standard for smart sustainable cities' self-assessment in collaboration with Member States. (instructs TSBDir 3, 4) | Ongoing | √ |  |
|  | The United for Smart Sustainable Cities (U4SSC) is a UN initiative coordinated by ITU, UNECE, UN-Habitat and UNEP, and supported by 19 other UN Agencies and Programmes namely: CBD, ECLAC, FAO, ITU, UNDESA, UNDP, UNECA, UNECE, UNESCO, UNEP, UNEP-FI, UNFCCC, UN-Habitat, UNIDO, UNOP, UNU-EGOV, UN-Women, UNWTO and WMO. The U4SSC advocates for public policies aimed at ensuring a catalytic role for information and communication technologies (ICTs) in enabling the transition to smart sustainable cities and also to achieve SDG11 “Make cities and human settlements inclusive, safe, resilient and sustainable”. - U4SSC is currently working on the following Thematic Groups: - Building Urban Economic Resilience at City Level During and After COVID-19 - Guiding principles for artificial intelligence in cities - Procurement Guidelines for Smart Sustainable Cities - City Platforms - Enabling People-Centred Cities through Digital Transformation - Digital Wellbeing - The U4SSC has developed the following deliverables: - Redefining smart city platforms: Setting the stage for Minimal Interoperability Mechanisms - Smart tourism: A path to more secure and resilient destinations - Compendium of practices on innovative financing for smart sustainable cities projects - Procurement guideline for smart sustainable cities - Reference framework for integrated management of a Smart Sustainable Cities Please find all U4SSC deliverables available here. The first United for Smart Sustainable Cities (U4SSC) Austrian U4SSC Country Hub will be hosted by the Austrian Economics Center in Vienna, Austria. The main objective of this country hub is to promote the work of U4SSC. The following events are co-organized with the Austrian U4SSC Country Hub: - DTC4CC Episode #18: Cities in the age of artificial intelligence: How to leverage technology for digital transformation - DTC4CC Episode #20: A one-of-a-kind platform for digital transformation: the U4SSC Austrian Country Hub. The city of Kyebi, Ghana, has also set up a U4SSC Country Hub in Ghana. A Digital Transformation Resource Hub has been created and provides references to external resources on these issues. See also 98-06. |  |  |  |
| 98-08 | TSBDir to continue encouraging cooperation with other international SDOs, industry forums, and other related organizations, and global projects and initiatives, in order to increase the development of international telecommunication standards and reports that facilitate the interoperability of IoT services (instructs TSBDir 4) | Ongoing | √ |  |
|  | Ongoing collaboration with ISO and IEC on the organization of World Smart City Forums and working team on Smart City Terminology and the recently created IEC-ISO-ITU Joint Smart City Task Force. Ongoing collaboration with TM Forum. Ongoing collaboration with oneM2M. Ongoing collaboration with IEEE. Ongoing collaboration with LoRa Alliance. See 98-03. |  |  |  |
| 98-09 | TSBDir to prepare reports considering, in particular, the needs of developing countries in terms of the study of IoT and its applications, sensor networks, services and infrastructure, taking into account the results of work being done in ITU-R and ITU-D to ensure coordination of efforts. (instructs TSBDir 1) | Ongoing | √ |  |
|  | - Other events can be found here. - All ITU-T publications on IoT and Smart Sustainable Cities are available here. - Latest publications: - Guide for smart and sustainable city leaders - Enabling digital transformation in smart sustainable cities – Master plan - Building a people-centred digital future for cities and communities |  |  |  |
| 98-10 | TSBDir to continue disseminating ITU publications on IoT and SC&C, as well as organizing forums, seminars and workshops on the subject, taking into account the needs of developing countries, in particular (instructs TSBDir 4) | Ongoing | √ |  |
|  | - Other events can be found here. - All ITU-T publications on IoT and Smart Sustainable Cities are available here. - Latest publications: - Guide for smart and sustainable city leaders - Enabling digital transformation in smart sustainable cities – Master plan\ - Building a people-centred digital future for cities and communities - See also 98-05. |  |  |  |
| 98-11 | TSBDir to provide support to Member States to implement U4SSC KPIs for smart sustainable cities (instructs TSBDir 2) | Ongoing | √ |  |
|  | - See 98-07. |  |  |  |
| 98-12 | TSBDir to foster joint work among ITU Sectors to discuss the various aspects related to the development of the IoT ecosystem and solutions for SC&C, in the context of the achievement of the SDGs and within the framework of the World Summit on the Information Society (instructs TSBDir 3) | Ongoing | √ |  |
|  | The following events and activities have been organized: 2022: - WSIS Forum 2022 workshop on "Towards People-Oriented Cities" (Virtual, 29 March 2022) - WSIS 2022 - Beyond smart cities = “Smart for all” (Virtual, 10 May 2022) - WSIS 2023 – Mayors High-Level Dialogue (Geneva, 13 March 2023) - See also 98-05. |  |  |  |
| 98-13 | TSBDir to support Member States, especially developing countries, in the organization of forums, seminars and workshops on IoT and SC&C to promote innovation, development and growth in IoT technologies and solutions (instructs TSBDir 5) | Ongoing | √ |  |
|  | - See also 98-05. |  |  |  |
| 98-14 | TSBDir to report to the next WTSA on progress made in the organization of forums, seminars and workshops dedicated to developing the capacity of developing countries (instructs TSBDir 6) | WTSA-24 |  |  |
| 98-15 | TSBDir to assist developing countries in the implementation of recommendations, technical reports and guidelines related to IoT and SC&C (instructs TSBDir 7) | Ongoing | √ |  |
|  | - See also 98-06. |  |  |  |

» Top

# Resolution 99 - Consideration of organizational reform of the ITU Telecommunication Standardization Sector study groups

resolves

1	to implement the action plan for the analysis of ITU-T study group restructuring that was produced by TSAG;

2	that TSAG has the responsibility to manage the analysis of ITU-T study group restructuring based upon contributions to TSAG from Member States and ITU-T Sector Members;

3	that the output of the possible reform and review is guidance for the next WTSA and its implementation is not mandatory,

instructs the Telecommunication Standardization Advisory Group

1	to undertake, monitor and guide the work through a rapporteur group or other appropriate group, and make a progress report on the analysis at each TSAG meeting;

2	to provide a progress report on the analysis to the study groups after each TSAG meeting;

3	to submit a report with recommendations for consideration by the next WTSA,

instructs study groups

1	to consider the progress reports from TSAG;

2	to review and share feedback, as appropriate, on the progress reports to TSAG,

instructs the Director of the Telecommunication Standardization Bureau

to provide the necessary assistance to TSAG in the implementation of this resolution,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 99-01 | TSAG to implement the action plan for the analysis of ITU-T study group restructuring, and to undertake, monitor and guide the work through a rapporteur group or other appropriate group, and make a progress report on the analysis at each TSAG meeting (instructs TSAG 1) | TSAG 2024 | √ |  |
|  | TSAG Rapporteur Group "Work Programme and Restructuring, SG work, SG Coordination (RG-WPR)" is progressing the discussion and reporting as appropriate. TSAG-RG-WPR developed in TSAG-TD152-R1 a project plan to implement the action plan for the analysis of ITU-T study group restructuring, which was liaised (in TSAG-LS05) with all ITU-T SGs. TSAG-RG-WPR developed TSAG-TD234R1 Report to TSAG on the implementation of the action plan for analysis of ITU-T structural alternatives and submitted it to the TSAG meeting in May/June 2023. TSAG-RG-WPR maintained the Baseline text for report of the analysis of ITU-T study group restructuring alternatives, TD214R1. |  |  |  |
| 99-02 | TSAG to provide a progress report on the analysis to the study groups after each TSAG meeting (instructs TSAG 2) | TSAG 2024 | √ |  |
|  | TSAG Rapporteur Group "Work Programme and Restructuring, SG work, SG Coordination (RG-WPR)" will follow-up. TSAG RG-WPR provides report from each interim meeting and from sessions during TSAG meetings. |  |  |  |
| 99-03 | TSAG to submit a report with recommendations for consideration by the next WTSA (instructs TSAG 3) | WTSA-24 |  |  |
| 99-04 | ITU-T SGs to consider the progress reports from TSAG, for SGs to review and share feedback, as appropriate, on the progress reports to TSAG (instructs SGs 1, 2) | Ongoing | √ |  |
|  | TSAG RG-WPR consults with SGs as appropriate for SGs to review outputs from RG-WPR and to reflect feedbacks from SGs. SG13 has a recurrent TD with TSAG highlights, including the restructuring, at its each SG meeting. SG15 reviews discussions within TSAG on SG restructuring at its each SG meeting. SG17 is reviewing its mandate and structure in preparation for WTSA-24, taking into consideration TSAG RG-WPR progress. |  |  |  |
| 99-05 | TSBDir to provide the necessary assistance to TSAG in the implementation of this resolution (instructs TSBDir 1) | Ongoing | √ |  |
|  | TSBDir will be providing the necessary assistance to TSAG in the implementation of this resolution. |  |  |  |

» Top

# Resolution 100 - A common emergency number for Africa

resolves to instruct the Director of Telecommunication Standardization Bureau in cooperation with the Director of the Telecommunications Development Bureau

1	to provide technical assistance to Member States in Africa in the implementation of a common emergency number in line with Recommendation ITU-T E.161.1;

2	to report to the World Telecommunication Standardization Assembly on the progress achieved in implementing this resolution, which is intended to improve access to emergency services,

| Action Item | Action | Milestone | Periodic goals met | Completed |
| --- | --- | --- | --- | --- |
| 100-01 | TSBDir, in cooperation with BDTDir, to provide technical assistance to Member States in Africa in the implementation of a common emergency number in line with Recommendation ITU-T E.161.1 (resolves 1) | Ongoing | √ |  |
|  | Initial study is in progress to investigate the technical, regulatory, policy and practical issues addressed in East African countries that have recently harmonized their emergency number(s), and to outline the steps/technical assistance that would be required for other Member States in Africa to implement WTSA Resolution 100. |  |  |  |
| 100-02 | TSBDir to report to WTSA on the progress achieved in implementing this resolution, which is intended to improve access to emergency services (resolves 2) | WTSA-24 |  |  |
|  | Implementation of this Resolution by African countries may be reviewed at SG13RG-AFR meeting on 25 April 2024 (virtual). |  |  |  |

» Top

# Opinion 1 - Practical application of network externality premium

Opinion 1

is of the opinion that

considering the progress achieved so far within Study Group 3 those Member States concerned may wish to review the respective positions at the WTSA 2008 and possibly withdraw the reservations about Recommendation ITU-T D.156,

invites Member States

to take all measures necessary for the effective implementation of Recommendation ITU-T D.156,

invites the Council

in its session of 2013, to report on this subject to the Plenipotentiary Conference 2014, in accordance with Plenipotentiary Resolution 22 (Rev. Antalya, 2006).

» Top

# Appendix I – Obsolete action items from WTSA-12 Action Plan

Note – Action items from the WTSA-12 Action Plan (WTSA-16 C35), which are obsolete or were considered completed at WTSA-16, are no longer listed in this Action Plan; but the provisions still exist in the in-force Resolutions:

- 07-02;

- 22-01, 22-02, 22-03 (action item numbers reused);

- 31-01;

- 33-02, 33-03, 33-04; (Resolution 33 suppressed)

- 35-01 (but provision still exists in Resolution);

- 43-01, 43-02, 43-03 (but provision still exists in Resolution);

- 44-04, 44-06, 44-08, 44-09, 44-10, 44-16, 44-17, 44-18, 44-22 (but provision still exists in Resolution);

- 54-02;

- 55-05 (new action item);

- 65-03 (but provision still exists in Resolution);

- 67-04;

- 69-02, 69-04 (but provision still exists in Resolution);

- 70-02 and 70-09 (but provision still exists in Resolution);

- 71-01;

- 74-01;

- 76-09, 76-10, 76-11, 76-17;

- 77-01, 77-02, 77-03 and 77-05 (but provision still exists in Resolution);

- 81-01, 81-02, 81-03 (Resolution 81 was suppressed);

- 82-01, 82-02, 82-03 (Resolution 82 was suppressed);

- OP-01-02.

___________

# Appendix II – Obsolete action items from WTSA-16 Action Plan

- Note – Action items from the WTSA-16 Action Plan (see WTSA-20 C34), which are obsolete or were considered completed at WTSA-20, or were consolidated are no longer listed in this Action Plan; but the provisions still exist in the in-force Resolutions:11-02;

- 22-10, 22-11, 22-12, 22-13;

- 40-02;

- 44-22, 44-25, 44-26;

- 48-01;

- 50-19;

- 52-04;

- 54-03, 54-08;

- 61-01;

- 64-01;

- 70-04, 70-05;

- 72-05;

- 76-09, 76-10, 76-17;

- 77-03, 77-10;

- 85-01;

- 90-01, 90-02;

- 92-03, 92-05, 92-06;

___________

1 	These include the least developed countries, small island developing states, landlocked developing countries and countries with economies in transition.

http://itu.int/ITU-T/inr/enum/.

2	Kyoto, Japan, 15-16 April 2008; London, United Kingdom, 17-18 June 2008; Quito, Ecuador, 8-10 July 2009; Seoul Virtual Symposium, 23 September 2009; Cairo, Egypt, 2-3 November 2010; Accra, Ghana, 7-8 July 2011; Seoul, Republic of Korea, 19 September 2011; and Montreal, Canada, on 29-31 May 2012, Turin, Italy, 6-7 May 2013; Kochi, India, 15 December 2014; Nassau, Bahamas, 14 December 2015; and Kuala Lumpur, Malaysia, 21 April 2016.

3	With respect to efficiency, promotion of efficient use of materials used in ICT devices and network elements should also be a consideration.

These include the least developed countries, small island developing states, landlocked developing countries and countries with economic in transition.

These include the least developed countries, small island developing states, landlocked developing countries and countries with economies in transition.