|  | INTERNATIONAL TELECOMMUNICATION UNION TELECOMMUNICATION STANDARDIZATION SECTOR STUDY PERIOD 2025-2028 |  |  | TSAG-TD10R1 |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | TSAG |  |
|  |  |  |  | Original: English |  |
|  |  |  |  | Geneva, 26-30 May 2025 |  |
| TD |  |  |  |  |  |
| Source: |  | TSB |  |  |  |
| Title: |  | WTSA-24 Action Plan Version 1.1 |  |  |  |
| Contact: |  |  | Xiaoya Yang SG17 Counsellor |  | E-mail xiaoya.yang@itu.int |

| Abstract: | WTSA-24 Action Plan is a monitoring and reporting tool to keep track of the implementation of WTSA-24 Resolutions, Opinion and Actions. This TD presents the initial draft framework of WTSA-24 Action Plan to be used for the 2025 – 2028 study period for review and endorsement by TSAG, including their mapping onto the various TSAG Rapporteur Groups (RGs). Revision 1 contains an updated Excel file (Att.2) with the final WTSA-24 Action numbers, a more granular of the reporting groups within TSAG, and a new column with the allocation of groups within TSAG (as per Table 2 in this TD) and WTSA (placeholder, to be updated). |
| --- | --- |

# Summary of WTSA-24 Action Plan

WTSA-24 (New Delhi, 14–24 October 2024) suppressed on Resolution and approved eight new and 45 revised Resolutions. Currently, there are 65 resolutions of WTSA, one Opinion and 15 WTSA-24 approved Actions in force.

In support of CV §197H, and of Rec. ITU-T A.1 clause 1.3.1, and in order to keep track of the implementation of so many Resolutions, TSB continued the established practice initiated after WTSA 2008 (ref. WTSA-12 DOC28, WTSA-16 DOC35, WTSA-20 DOC34, WTSA-24 DOC34) and developed a new WTSA-24 action plan as a monitoring and reporting tool to be used for the 2025-2028 Study Period.

The WTSA-24 Action Plan in this document reflects the initial framework for the new 2025-2028 study period. It is developed based on WTSA-24 DOC34, the final version of the WTSA-20 Action Plan. This new WTSA-24 Action Plan details 507 action items, their associated responsibilities, necessary collaborations, reports and current initial status (24% increase from 409 action items in the WTSA-20 Action Plan).

This document contains two attachments:

–	a WORD document which details the implementation progress report;

–	and an EXCEL sheet which illustrates the implementation status of each action item, and statistics.

In the WORD document, track-changes indicate the evolution of action items from the WTSA-20 Action Plan. Appendix I includes a table to demonstrate the (rough) evolution of all current action items since the beginning of this WTSA Action Plan practice (i.e., WTSA-08 Action Plan).

The EXCEL sheet serves as a reference tool to allow all action items to be displayed on a single sheet, or sorted by any of the key attributes identified in columns, such as all those for TSB action, or all those requested to report to Council, etc. It also uses colours to visualize the completion status of action items.

# Mapping of WTSA-24 Resolutions, Opinion and Actions to TSAG RGs in the 2025-2028 study period

| WP | RG | Resolutions |
| --- | --- | --- |
| WP1 | Rapporteur Group Working Methods (RG-WM) | - Res 1, 22, 31, 32, 40, 54, 67, 70, 75, 83, 87 - WTSA-24 Actions 1, 4, 11, 12, 15 - (ITU-T A-series of Recommendations and Supplements) |
|  | Rapporteur Group Industry Engagement and Strategic and Operational Planning (RG-IES) | - Res 7, 11, 18, 34, 43, 44, 55, 68, 74, 85, 90, 107, 108 - WTSA-24 Actions 3, 5, 6 |
| WP2 | Rapporteur Group Work Programme and Restructuring, SG Work, SG Coordination (RG-WPR) | - Res 2, 20, 29, 47, 48, 49, 50, 52, 60, 61, 62, 64, 65, 72, 73, 76, 77, 78, 79, 84, 88, 89, 91, 92, 93, 94, 95, 96, 97, 98, 99, 100, 101, 102, 103, 104, 105 - Opinion 1 - WTSA-24 Actions 2, 7, 8, 9, 10, 13, 14 |
|  | Rapporteur Group Sustainable Digital Transformation (RG-DT) | - Res 58, 69, 86, 106 |

It should be noted that the guiding principle in this mapping of the WTSA Resolutions, Opinion and Actions was to mirror their assignment in WTSA-24 COM3 and COM4 into TSAG WP1 & WP2, respectively, aiming to balance thematically the topics as well as the expected workload during the study period.

# Suggestion to TSAG

The WTSA-24 Action Plan will be used by TSB to track the implementation progress and updated and submitted to each TSAG meeting in this study period.

This TSAG is invited to review and endorse this document.

Attachments:

1.	WTSA-24 Action Plan, V1 (Word file)

2.	WTSA-28 Action Plan, Version 1.1, 23 May 2025 (Excel file)

_____________________