| Using ICT4DM Logical Framework |  |  |  |  |
| --- | --- | --- | --- | --- |
| Design Summary | Performance Target – Tangible Result | Monitoring and Oversight | Risks | Contingencies |
| Goal |  |  |  |  |
| Using ICT for Effective Disaster Management |  |  |  |  |
| Objectives |  |  |  |  |
| 1. Facilitate stakeholder dialogue | Trust protocol MOU, Cell broadcast enabled | Rapporter to inform stakeholders of progress | Lack of commitment to TCB process | Networks take their own initiatives |
| 2. Recommendations to our member organisations to upgrade ICT capabilities/compatibilities | Achieve convergences of resources through MOU with the major regional management agencies | Reports and follow-up from member organisations on progress | Apathy of the stakeholders. Absence of harmonisation of the regulations | Continue developing the existing resources to prepare for convergence |
| 3. Increase and have more effective dialogue (CIVIC) | Establish a Sub-group focused on developing ICT for Disaster Management (DM) | Develop and publish advocacy proposals within the 4 main phases of DM | Focus diverted due to current emphasis on defining the groups mandate | Obtain a commitment from the group at large to allow the sub-group members to talk on their behalf |
| Outputs |  |  |  |  |
| 1. Annual meeting stakeholders plus email discussion list | All stakeholders have at least one person on the discussion list | Chair of Trust Protocol Board moderates the list | Churn of people (constant changing of posts) | Moderator to make periodic personal contacts |
| 2. Implement strategies to have entities that are ready to get on board | Obtain MOU’s with the entities. Appoint person to drive convergence | Report and provide feedback by designated persons | Technical problems with compatibility and political will to implement | To ensure that you a technical team to work on problems of compatibility |
| 3. Advocacy proposals (for each disaster management areas) | Finalized and approved advocacy proposal by the group at large | Delivery of the approved reports to Disaster Management stakeholders | Lack of members time | Delegate to a sub-group of committed members |
| Inputs |  |  |  |  |
| 1. Meetings attended | People read the list | Trust Protocol Board looks for comment | Comments stop | Consensus |
| 2. Team leader and support staff | Establishment of clear guidelines and timeframe | Continue monitoring | Apathy and non performance |  |
| 3. Members time and efforts |  |  |  |  |

RECOMMENDATIONS

- Follow-up forum to include National Disaster/Emergency Agencies

- Listing of all entities that should participate in ICT (nationally and regionally). Contact lists to be created

- Standardizing of messaging format

- Identify the sources of information. Could be listed on a website.

- Clarify the ambiguity of the ICT term

- Inform and advise the political directorate on the importance of the development of ICT re Disaster Management

- Develop partnerships and linkages with the National and Regional ICT entities

- Establish MOU’s with National and Regional organisations re Disaster Management

- Encourage the ratification of the Tampere Convention by Governments

- Planning and conducting of local and regional exercises and simulations

- Inclusion of UWI Seismic as a critical player in the process

- Reestablishment of Caribbean wide communication links (National organisations and Amateur radio clubs)