## Slide 1: Regional Development Forum for Europe "Broadband for Sustainable Development”
20-22 April 2015 / Bucharest, Romania
EUROPE – Regional Initiative 3 Ensuring access to telecommunications/ICTs, in particular for persons with disabilities 2015-2017 IMPLEMENTATION PLAN

## Slide 2
EUROPE - RI-EUR3: Ensuring access to telecommunications/ICTs, in particular for persons with disabilities 2015-2017 IMPLEMENTATION PLAN

## Slide 3: RI-EUR3: Ensuring access to telecommunications/ICTs, in particular for persons with disabilities / 2015-2017 IMPLEMENTATION PLAN
2015
  April: Regional Workshop on Smart Accessibility on Connected TV (March, Barcelona) (AUB, EC, ITU)
June: Experts Group Meeting on Accessibility (June, Italy) back to back with International Symposium on Respeaking-live-subtitling-and-accessibility
July: Establishment of the list of European Member States with national ICT accessibility policies and analysis
August: Finalization of curriculums of two online trainings on accessibility
September: Setting up internet access points and provision of ICT equipment/software to be used by people with visual/hearing impairments (age related visual/hearing problems)
October: Regional Conference for Europe on Accessibility, Serbia
October: Online training for broadcasters on how to create audio description (AD) and closed caption (CC) files for television/video programming and how to transmit AD and CC.
  November: Online training for policy makers and regulators on Modules 1 and 4 of the ITU Model ICT Accessibility Policy report; ( Regulation, Policy, Strategies, Accessible TV)

## Slide 4: RI-EUR3: Ensuring access to telecommunications/ICTs, in particular for persons with disabilities / 2015-2017 IMPLEMENTATION PLAN
2016
February: Finalization of curriculum of an online course on Module 6: Accessible ICT public procurement policy framework based upon the Model ICT Accessibility Policy Report. (M. 6)
April: European benchmark with focus on non-EU countries based on the Model ICT Accessibility Policy Report
May: Online Training for procurers on Module 6: Accessible ICT public procurement policy framework
July: Finalization of curriculum of an online course on Modules 3: Mobile communications accessibility policy framework based upon the Model ICT Accessibility Policy Report. (M. 6)
April: Regional Conference for Europe on Accessibility
October: Online training for on Module 3 of the ITU Model ICT Accessibility Policy Report;
September: Setting up internet access points and provision of ICT equipment/software to be used by people with visual/hearing impairments (age related visual/hearing problems)
Dec: Reporting to Regional Preparatory Meeting for WTDC-14

## Slide 5: RI-EUR3: Ensuring access to telecommunications/ICTs, in particular for persons with disabilities / 2015-2017 IMPLEMENTATION PLAN
2017
April: Regional workshop for Europe and CIS on accessibility
May: Online training for on Module 5 (Module 5: Web accessibility policy framework) of the ITU Model ICT Accessibility Policy Report
September: Setting up internet access points and provision of ICT equipment/software to be used by people with visual/hearing impairments (age related visual/hearing problems)
October: Online training for on Module 2 (Module 2: ICT accessibility framework on public access) of the ITU Model ICT Accessibility Policy Report
Dec: Reporting to WTDC-14