## Slide 1: Regional Development Forum for Europe "Broadband for Sustainable Development”
20-22 April 2015
Bucharest, Romania
EUROPE - RI-EUR5: Entrepreneurship, innovation and youth 2015-2017 IMPLEMENTATION PLAN

## Slide 2
EUROPE - RI-EUR5: Entrepreneurship, innovation and youth 2015-2017 IMPLEMENTATION PLAN

## Slide 3: RI-EUR5: Entrepreneurship, innovation and youth 2015-2017 IMPLEMENTATION PLAN
2015
April: Stocktaking incubators
May: Innovation track at WSIS
June: Implementation Task Force on “ITU-ICT-Agora ” kickoff - Athens
August: End of consultation on the Implementation Plan open to all stakeholders looking for their engagement and financing of implementation plan
Sept: Benchmark of innovation capabilities in European ICT ecosystem
October: Launch of alpha version of “ITU-ICT-Agora ” platform – Budapest
Launch of regional competition of “Girls in new technologies”
Dec: Regional conference on ICT innovation ecosystem – Belgrade/Tirana

## Slide 4: RI-EUR5: Entrepreneurship, innovation and youth 2015-2017 IMPLEMENTATION PLAN
2016
March: Implementation Task Force on “ITU-ICT-Agora ” meeting - TBD
Guidelines on ICT innovation ecosystem / self assessment toolkit
April: Girls in ICT Day: national winners announced
launch of the regional network (incubation opportunities or exchange or internship)
May: Innovation track at WSIS: global approach with regional seeds
June: Fostering knowledge triangle for unlocking entrepreneurship and innovation/ (academia/community) - Prague
Sept: Development of curriculum for training based on guidelines under ITU academy
October: Launch of operational version of “ITU-ICT-Agora ” platform – TBD (Telecom)
Launch of regional competition of “Girls in new technologies”
Dec: Regional conference on financing mechanisms for ICT innovation ecosystem – Tirana/Belgrade
2016 Reporting to Regional Preparatory Meeting for WTDC-17 (date determined at the later stage)

## Slide 5: RI-EUR5: Entrepreneurship, innovation and youth 2015-2017 IMPLEMENTATION PLAN
2017
February: Training on ICT innovation ecosystem under ITU academy
March: Implementation Task Force on “ITU-ICT-Agora ” meeting - TBD
April: Girls in ICT Day: national winners announced
Upscaling of the regional network (incubation opportunities or exchange or internship)
May: Innovation track at WSIS: shared learning with all regions on ICT innovation ecosystem
June: Impact assessment of “ITU-ICT-Agora ” platform
Sept: Upscaling of curriculum for training on ICT Innovation ecosystem under ITU academy
October: Review of “ITU-ICT-Agora ” platform – TBD (Telecom)
Launch of regional competition of “Girls in new technologies”
Dec: Reporting to the WTDC-17
Side events on ICT innovation ecosystem at WTDC-17