RECOMMENDATIONS

INTRODUCTION

During the 3 months contract- February to April 2000- the consultant on gender issues has: a) carried out research and analysis on the programs and activities undertaken by ITU from a gender mainstreaming perspective and provide advice on gender issues b) produce a report on the ITU situation in terms of gender issues, including proposals for an action plan and establishing criteria for monitoring and evaluating the mainstreaming process; c) developing and implementing a program on capacity building. This last include 4 GGI tailored-modules, contains a strong gender and information/communication component as well as the required methodology for gender mainstreaming.

The capacity building program has involved the review of ITU's undertakings in terms of gender mainstreaming and the comparison of the process with other agencies, notably ILO and UNDP; the review of the terms of reference of ITU's Gender Focal Points: the design of the training modules and the selection and preparation of training material (overheads, models, case studies, discussion and brainstorming session, supporting material) the implementation program.

- Programmes and activities undertaken by ITU from the gender mainstreaming perspective

1.1 The implementation of Resolution 70 gave way to a number of initiatives oriented to

- integrate the gender perspective into the work of ITU, particularly in the field of

- accountability and institutional arrangements. Among them, the following can be

- mentioned:

- a) The creation of a Task Force on Gender Issues  (TFGI) established by the World

- Telecommunication Development Conference in 1998. The Task Force has held two

- annual meetings since its inception

- The nomination of an ITU Focal Point on Gender issues who chairs the Group on

- Gender Issues (GGI) in the ITU and the nomination of a BDT Focal Point who acts as a

- secretary of the Task Force and serves as Vice- Chair of the Group on Gender Issues.

1.2. The tasks proposed by the Group on Gender Issues are the following:

- Policy and Strategy Framework

- Awareness and Information

- Capacity building

- Networking

- Preparation of Meetings, Events and Conferences

- Work and Family Agenda

- Analysis and Research

- Monitoring and controlling Projects

1.3. Main progress and achievements in the implementation of the above mentioned

- tasks are regularly highlighted by the Operational Plan in relation to Res.70 (PP98).

- Progress relates to:

- Disaggregated statistics  of the internal job distribution  by sex and comparisons

- with other UN Agencies

- Preparation of meetings , events and conferences, notably the International Women’s Day 1999-2000;Council 99,Telecomm  Interactive 99  and the fifth inter-agency meeting

- Compilation of a good practices document

- Analysis and research of gender issues in the telecom community through the circulation of questionnaires and the analysis and report of the findings

- ITU’s situation in terms of gender issues

2.1. Following the commitments expressed in the Statement of the United Nations Advisory  Committee on Coordination (ACC), 2 March 1998, gender equality becomes a major strategic objective of the international community. Recommendations on gender mainstreaming were elaborated  in the 1998 Ecosoc Agreed Conclusions and efforts have been made to mainstream a gender perspective in all the institutions, policies and programs of the United Nations system.

Through the Resolution 70 (PP98), ITU endorsed WDTC-98 Resolution 7 and the incorporation of a gender perspective in the implementation of the ITU Strategic Plan, operational plan, financial plan and the approved recommendations of ITU-2000.

2.2. Like other institutions in the UN common system, ITU faces different problems in the institutionalization of a gender mainstreaming perspective. Some highlighted during a brainstorming session of the GGI focused on the following issues:

- Human resources devoted to gender mainstreaming are scarce, both in terms of number and time. GGI members have roles other than gender issue and their possibilities of dedication are limited.

- Financial resources are not enough to develop and implement policies and programs and to expand present undertakings.

- Discussion and awareness raising take place at the micro level, thus hampering the creation of an institutional enabling environment for gender equality

The group also identified UNDP institutional constraints for gender mainstreaming as relevant to the ITU case:

- Isolation of the  working level staff from the management concerns of the organization

- Lack of confidence among the staff about their skills in analysis, communication and strategic planning

- Compartmentalization of issues

- Hierarchical organizational culture

- Particular difficulties faced by women in achieving recognition as professional colleagues

- Limited opportunities for sharing experience and organizational learning

2.3. After two years efforts to incorporate the gender perspective into ITU’s work, areas that need continuos efforts or special development and support are:

- Policy formulation and strategic planning: As a first step for gender mainstreaming in the organization, policy formulation and elaboration of an action plan are basic to focus action and strengthen ITU's capacity to design ad deliver gender -sensitive programs and services. The following processus  should be considered;

- provide institutional basis for policy formulation and strategic planning activities

- provide methodological orientations for sectoral and institutional analysis of the Strategic Plan of Action 1999-2003 and the work programs of the different divisions ( indications about entry points for gender mainstreaming, accountability, team work, responsible units, implementation and assessment steps, measurements of progress and impacts in the short  and the long term, etc)

- adopt policy principles

- set global and sectoral measurable goals, outputs activities and specific time- frames for achieving gender equality

- assess relevance of proposed strategic objectives through consultation with staff members at all levels

- develop gender-sensitive indicators and regular monitoring process

- Internalization of the commitment for gender equality: Implementation of gender equality policies requires the participation and commitment of all staff members. This is a long process that requires to overcome negative attitudes or lack of interest and to enlist staff's commitment on the gender quest. The process requires for this part:

- promote gender awareness and  a system wide gender sensitiveness

- enhance gender expertise through training and information

- facilitate dissemination  of information on gender issues

- establish working teams with  specific assignments  in TU sectors

- support the establishment of a gender unit.

- create effective networks and mechanisms of coordination within the organization to accomplish the tasks entailed by gender mainstreaming

- consolidate outputs

- Enhanced commitment to gender issues at high political and administrative level: High level consensus and understanding of ITU's commitment to gender mainstreaming are critical to the implementation of the process:

- facilitating policy implementation and using decision making process effectively to support  implementation

- setting institutional mechanisms for the implementation, monitoring and evaluation of the mainstreaming process

- Strengthened capacity building for ITU staff at all levels and on regular basis

- Implementing gender awareness, gender analysis and gender mainstreaming training programs

- identifying training needs of the staff

- facilitating transmission of knowledge and skills to staff so enabling them to undertake mainstreaming strategies appropriate to their professional responsibilities

- disseminating training material and information

- Formulation of specific measures for gender balance within the institution

- preparing gender sensitive job descriptions and specifications

- broadening  the range of channels to prospect for female candidates

- identifying obstacles to women career development and make structural changes when necessary

- promoting career development opportunities  for General Services staff;

- promoting gender balance in senior posts  by reviewing recruitment policies to encourage women in professional and high decision making posts

- Promote an enabling working environment, for both, men and women by:

- developing habits of cooperation and teamwork

- promoting changes of attitudes to the gender issue

- promoting measures to break the cumulative effect of discriminatory attitudes towards women in the workplace ( glass ceiling)

- carrying out employee surveys to obtain regular feedbacks on the progress of mainstreaming policies

- Undertake research on Gender and Information and Communication Technology, This

- is a new subject included in the Inter- Agency Committee on Women and Gender

- Equalities work program, to which ITU can make substantial contributions.

- -

- carrying out surveys on ITU’s experiences and undertakings

- developing impact assessment tools

- determining, through relevant indicators, impacts of ICT on global process such as the feminization of poverty and marginalization of groups and strata of the population.

- developing proactive policies for adapting ICT to poor people needs and contents and to enhance women’s advancement in the education, health and trade fields.

- Proposals for an action plan

3.1.To make policies operational it is necessary to have an institutional-wide action plan.

Since gender mainstreaming is a crosscutting issue it requires organization-wide responsibility and the involvement of all the ITU sectors all along the mainstreaming process:

- preparation of the action plan

- implementation

- monitoring

- evaluation

- policy and strategic reorientation

3.2. Considering the necessity of accountability at every level of the institution, it would be advisable to design working teams and responsible persons who follow the process and report progress on a stable and regular basis. The nomination of stable working teams helps the institutionalization of the process as well as to the dissemination of results

- Specifications on main elements of the action plan. This plan indicates how proposed objectives will be implemented and which will be the major areas of concern.  One possible way of organizing them is::

- Strengthen  institutional mechanisms

- Introduce monitoring and accountability  mechanisms

- Allocate adequate resources

- Build up of staff competence

- Improve gender balance of staff

- The proposed  strategy, should include global and sectoral objectives for gender mainstreaming and the specification of related outputs, activities and responsible units for the implementation of each strategic goal;

- This process must be participative, involving management and staff of the

diverse ITU divisions, working at the institutional and service levels on a regular basis

- The composition of these working teams must be multi-disciplinary

3.5. A time frame should be established for the achievement of each proposed action and longer-term goals. Ideally a detailed timetable for the proposed first stages is required

3.6. It has to be born in mind that the former stages lead to a final, longer-term goal, which is gender equality.

- Criteria for monitoring, evaluating and reporting

- Measurement

The following methodologies are recommended:

- Measure and monitor progress along all the mainstreaming process, on a regular basis

- Develop a set of relevant  quantitative and qualitative indicators on a participatory basis

- Develop gender sensitive data and gender specific development tools and indicators

B) Benchmarks against which progress is measured

- Objectives stated in Res. 70 constitute first criteria against which monitoring and evaluation should be done. The main question to be answered is how far a gender perspective has been incorporated in the ITU strategic plans, operational plans, financial plans and recommendations of ITU 2000.

Assessment relates to:

- Identification of  the type and scope of policies and programs on gender issues on the diverse sectors and measurement of progress through indicators, guidelines and checklist

- Assessment of global and sectoral goals

- Assessment of  the incorporation of the gender perspective in sectoral  work programs, leadership and human resources development activities

- Assessment, on regular basis, of levels and occupations of men and women in the 3 ITU sectors and the Secretariat

- Assessment of  gender neutrality in  the language used in the basic instruments of the Union

4.2. Main elements of the Action Plan constitute a benchmark against which measure progress.

- Activities and indicators  for each one of these elements can be developed  and measured within a time-frame

4.3. Goals and achievements at different levels of analysis, including both, the headquarters and  the country level

4.4.Monitoring and evaluation of project cycle (during fieldwork at country level

4.5. ACC recommend the evaluation of managers' performance in reference to specific benchmarks and milestones on gender mainstreaming within their mandates (ACC, March 1999)

4.6. Impacts of Information and Communication Technologies on Gender

- Application of results

Results would be used for the following purposes:

- To develop sex disaggregated statistics, which permit monitoring and measure progress in the ITU sectors and the Secretariat. Changes in data collection  may entail special training  and establishment of guidelines

- To provide inputs to the planning process  and determine when strategic changes are required

- To compare achievements and obstacles with the rest of the UN system and share experiences and knowledge

- To advance on mainstreaming as a continuos process

- Programme on capacity building. Activities and recommendations

5.1.Tailored-modules for the GGI have been designed and delivered. They include conceptual and methodological elements related to the gender field of knowledge as well as specific elements related to ITU’s are of involvement (see attached

- material, which include the program, the modules, support material  and overheads)

5.2.These modules can serve as a basis for the development of an ITU Manual on Gender and Telecommunications. Research and work with the different ITU sectors as well as with organizations dealing with telecommunications (UNESCO, UNDP, OECD, etc may provide case studies and practical experiences to illustrate concepts and gender mainstreaming practical tools and methodologies

5.3. Other training packages can also developed. They can include ITU sectoral concerns as well as issues related to the different levels of involvement of the organization and of the staff, both at the institution and country levels. These training materials must be relevant to ITU's technical areas.

5.4.Contribute to the electronic database on gender training material, as recommended by the Inter-Agency Committee on Women and Gender Equality, Fifth Session, February 2000. "The main purpose of the electronic database is to organize training materials into a readily accessible resource that provides useful strategic links to institutions with expertise and experience in training" (See details in the report 'Data base on Gender training materials. Status report, IACWGE/V/8

5.5.Use telecommunication networks and infrastructure to make sure that electronic database on gender and telecommunications training material reach more marginal and poor regions. Make contents adapted to peoples needs and uses

5.6.Collect training material produced in ITU’s field/regional offices with emphasis on regional contents and training experiences so as to adapt training materials contents and tools and to cultural diversity.

5.7.Organize training sessions shared by two or more UN organizations, exchanging experiences, training material and producing joint views on specific situations and process (ex: gender and information society, gender and globalization; gender and liberalization of the economy, etc)

CONCLUSIONS

The process of incorporation of the gender mainstreaming perspective in the work of ITU should stress in particular:

- The strategic planning process  and the formulation of a plan of action

- Capacity building activities involving ITU's staff at all levels and on a regular basis

- Progressive elaboration of ITU's specific expertise on gender and telecommunication issues. This work requires research, group and sectoral discussions and elaboration of guidelines related to their field of involvement; compilation of institutional experiences at the headquarters and in the country level. The elaboration of training modules for the GGI constitutes a step towards this aim, which can be followed by a Manual on Gender and Telecommunications.

It seems extremely important that ITU becomes a leading agency on gender and telecommunication issues, making of this field its specific area of expertise.