|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Updated : 13 November 95 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Programme 1 | Policies, Strategies and Financing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Doreen Bogdan tel : 5643 |  |  |
| Activity |  |  |  | Ref. |  | Region |  | Place | Dates |  | Involved |  | Status |  |  | Comments |  |  |  |  |
| Document National Policies |  |  | 1.1 |  | GLO |  | GVA |  |  | Ongoing |  | HQ - Bogdan |  | In course |  |  | Create format for information collection; conduct survey; collect and analyze information |  |  |  |
| AFRICA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Restructuring the Telecommunication Sector Training Seminar for SADC countries |  |  | 1.3 |  | AFR |  | Maputo, Mozambique |  |  | 20-24 November |  | HQ- Bogdan, Herrera |  |  | Planned |  | This Workshop is a joint effort by Programmes 1 and 2. Fellowships for the training seminar will be funded by BAAP Programme 1. The consultant preparing the training materials is funded by Programme 2. |  |  |  |
| Consultative Meeting/Preparatory Meeting for the African Regional Telecommunication Development Conference |  |  | 1.3 |  | AFR |  | Tunis, Tunisia |  |  | 20-24 November |  | HQ - Bogdan, Kourouma, RO |  |  | Planned |  | This is a multipurpose meeting done together with programme 11. The Task Force for the next RDC will take place at this meeting. The meeting will review African Green Paper, discuss Trade in Services, etc. |  |  |  |
| Trade in Services Study |  |  | 1.5 |  | AFR |  | Ghana, Senegal, Guinea Uganda, Tanzania |  |  | February - September |  | HQ - Bogdan |  |  | Done |  | Two consultants have been contracted to carry out a case study in five African countries on Telecommunications Policy and GATS Negotiations and Concessions. The results of the study will be presented at the African Regional Policy Meeting. |  |  |  |
| National Regulatory/Policy Assistance |  |  | 1.5 |  | AFR |  | Swaziland Zambia Zimbabwe |  |  | October October August |  | HQ - Kourouma, AO Fergusson-Nicol |  |  | In course |  |  |  |  |  |
| AMERICAS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participate in the CITEL PCC-1 meeting to develop workplan to update the Blue Book |  |  | 1.1 |  | AM |  | Honduras |  |  | February |  | RO - Zavattiero |  |  | Done |  | Work Plan for the 1995 Blue Book presented to the Citel PCC-1 Meeting. |  |  |  |
| Blue Book Experts coordination meeting |  |  | 1.1 |  | AM |  | Brasilia |  |  | May |  | HQ - Stagliano; RO- Zavattiero |  |  | Done |  |  |  |  |  |
| Update of Blue Book (1995 Blue Book) |  |  | 1.1 |  | AM |  | GVA |  |  | May-October |  | HQ - Bogdan, RO - Zavattiero |  |  | In course |  | Consultant contracted to carry out the review. |  |  |  |
| Americas Policy Meeting/Indicators Seminar |  |  | 1.3 |  | AM |  | Uruguay |  |  | 5-8 December |  | HQ - Bogdan/Minges, RO - Zavattiero |  |  | Planned |  | To be done together with Programme 11. The results of the Blue Book will be presented and discussed. |  |  |  |
| Caribbean Policy Symposium |  |  | 1.3 |  | AM |  | St. Vincent |  |  | 25-28 July |  | AR - Cross RO - Zavattiero |  |  | Done |  | Done together with the CTU. |  |  |  |
| Study on Economic Impact of Cellular Telephony for Mercosur Countries |  |  | 1.5 |  | AM |  |  |  |  |  |  | RO - Zavattiero, HQ - Blanquart |  |  | Canc. |  | Activity was cancelled. Not in the priorities of the region. |  |  |  |

| Activity | Ref. | Region | Place | Dates | Involved | Status | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| AMERICAS (CONTINUED) |  |  |  |  |  |  |  |
| Study on strategic introduction of value added services (ASETA) | 1.5 | AM |  |  | RO - Zavattiero, HQ - Blanquart | Planned |  |
| Study of Regulatory matters & technical standards for earth stations (ASETA) | 1.5 | AM |  |  | RO - Zavattiero, HQ - Blanquart | Planned |  |
| Assistance to Haiti in financing | 1.5 | AM | Haiti | December | RO - Zavattiero, HQ - Blanquart | Planned |  |
| Assistance to Haiti in policies related to network development | 1.5 | AM | Haiti |  | RO - Zavattiero, HQ - Blanquart | Planned | Funded by Sectoral Support |
| Assistance to Haiti in policies and strategies related to informatics and training | 1.5 | AM | Haiti |  | RO - Zavattiero, HQ - Blanquart | Planned | Funded by Sectoral Support |
| ARAB STATES |  |  |  |  |  |  |  |
| Arab Book Mtg./AR-RDCC Mtg. | 1.3 | ARB | Damascus, Syria | March 1995 | HQ - Azodogbehou, RO - Bairi | Done | Implemented. |
| Arab Book Experts Meeting | 1.1 | ARB | Geneva | 17-21 July 1995 | HQ - Al Jeboori, Bogdan RO- Bairi | Done | New Activity emanating from Damascus meeting. |
| Revision of the Arab Book | 1.5 | ARB | Geneva | Nov - Dec | HQ -Bogdan, RO-Bairi | Planned |  |
| Tariff Study | 1.5 | ARB | Djibouti | Dec. | HQ- Papaioannou | Planned |  |
| Policy and Restructuring Study | 1.5 | ARB | Djibouti | to be determined | HQ- Papaioannou | Planned |  |
| ASIA PACIFIC |  |  |  |  |  |  |  |
| Studies and Analysis | 1.2 | ASP | Bangkok/HQ | March - September | HQ -Bogdan RO- Withers | In course | Done in conjunction with ongoing Project RAS/93/035 - Telecommunications Reform, Regulation, and Management |
| AS-RDC Coordination Mtg. | 1.3 | ASP | Bangkok | Postponed | HQ - Borkenhagen, RO- Davey | Postponed |  |
| Sub-regional Telecommunication Regulators Meeting | 1.3 | ASP | Cambodia | 1-3 November | HQ- Borkenhagen AR- Calvano | Done | Meeting for Cambodia, Lao PDR and Vietnam |
| Fellowships for Training in Regulatory matters | 1.4 | ASP | Bhutan Nepal | July | HQ- Borkenhagen AR-Hajela | Done | USTTI Courses on Sector Development, Restructuring, Privatization, etc. |
| Investment Analysis | 1.5 | ASP | Laos Vietnam Cambodia | September | AR - Calvano | Done |  |

| Activity | Ref. | Region | Place | Dates | Involved | Status | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ASP (continued) |  |  |  |  |  |  |  |
| Telecom Regulation Support | 1.5 | ASP | Lao PDR | Nov-Dec | HQ- Borkenhagen AR - Calvano | In course |  |
| Regulation and Tariffing for Value Added Services | 1.5 | ASP | Bangladesh | October - November | HQ- Borkenhagen AR - Hajela | In course |  |
| Regulatory and Financial Assistance | 1.5 | ASP | Nepal | November | HQ- Borkenhagen AR - Hajela | In course |  |
| Support for Telecom Standards | 1.5 | ASP | Indonesia | October - November | HQ-Borkenhagen AR - Calvano | In course |  |
| Tariff Restructuring | 1.5 | ASP | Indonesia | Cancelled | AR - Calvano | Cancelled |  |
| EUROPE |  |  |  |  |  |  |  |
| OECD/ITU Workshop on Monitoring and Enforcement of Licenses | 1.1 | EUR | Ukraine | 7-9 June 1995 | Keskivali, Minges | Done | This activity was successfully completed but was not initially planned for BAAP 1. |
| Production of Guidelines for Licensing | 1.2 | EUR | HQ | 1st Quarter | HQ - Keskivali | Done | Editing and printing in English and Russian. |
| Feasibility Study on creation of a standing body for telecom regulatory and policy advice | 1.5 | EUR | HQ | November-December | HQ - Bogdan, Keskivali | Planned | Study done to determine feasibility of establishing a Regional Regulatory Unit. |