|  |  | Updated : 30/07/2026 |
| --- | --- | --- |
| Programme 2 | Human Resources Management and Development Notice: Row with gray color = activity implemented Status column gray color = activity under organization | Jaime Herrera tel : 5421 |

| Activity |  | Ref. |  | Region |  | Place | Dates |  | Involved |  | Status |  | Comments |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-prog 2.1: MANDEVTEL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1-First field study F-Afr. |  |  | F-Afr. |  | Dakar |  |  | Implemented end 1994 |  | Suisse PTT donation; subcontract L&P/Soumah |  | Imple-mented |  | Under Suisse Gov. donnation, a subcontract with Loisir & Pedagogie was established and the activity was performed at the end of 1994 |
| 2.1.2-Second field st. F-Afr |  |  | F-Afr |  | Ouagadougou |  |  | Implemented at the end of January 95 |  | Subcontact with L&P and Soumah |  | Imple-mented |  | Second study under same contract as mentioned above; to collect the data requiered. |
| 2.1.3-Workshop mgte F-Afr |  |  | F-Afr |  | Libreville (no confirmation) |  |  | 4th quarter 95 |  | HQ to organize plus Sfr 20000--Fellows and Mr. Soumah |  | Planned |  | Validation of the material to be developed by L&P |
| 2.1.4-Workshop mgte F-Afr. |  |  | F-Afr |  | Dakar |  |  | 4th quarter 95 |  | HQ to organize plus Sfr 20.000--Fellows and Mr. Soumah |  | Planned |  | Validation of the material to be developed by L&P (Negotiations initiated with Burkina Faso to host |
| 2.1.5-Field study |  |  | Am |  | Brasilia |  |  | Chile 20-31 March |  | M.Maniewicz and Jaime Herrera, plus group 4 experts LA (20000 for missions and 12000 TCDC) |  | Imple-mented in Chile (Not in Brasilia) |  | Four experts are “in kind” donnation from Costa Rica, Colombia, Chile and Brasil. 16/2: Funds requested for missions of MM and JH (19200Sfr), as well as TCDC for the 4 experts LA (9000Sfr). Activity implemented. Next step is activity 2.1.6: management workshop (validation and implementation) |
| 2.1.6-Workshop mgte- Am |  |  | Am |  | San José, Costa Rica for Admins, and a second WS for operators in Buenos Aires, Argentina |  |  | 18-22 Sept 95 in Costa Rica and 30/10-3/11 in Argentina |  | M.Maniewicz, consultants (Sfr 34,000--) and TCDC (Sfr 6,000--) + JH |  | Under imple-mentation |  | Validation of the material to be developed by the 4 LA experts. 6/4/95: Fund requested to hire a consultant during one month to finish the material and validate it in a 3-day workshop in CTC-Chile in June (Sfr 15,000--) Regional workshop planed for October 13/6- Funds requested for the C.R. workshop produced (CR: Fellows Sfr 15000, missions Sfr 14000, TCDC Sfr 6000 and for Arg: missions Sfr 15000) 11/7-All funds requests approved. Brasilia Regional Office is sending the invitation letters. |
| 2.1.7-Workshop mgte-Arab |  |  | Arab |  | Cairo |  |  | February; delayed to 1-13/7/95 Implemented from 1 to 6 July |  | K. Aburizic, with consultant (Sfr 8500) and fellows (Sfr 10000--) |  | Imple-mented |  | 10/4- The activity is scheduled 1-13 July 95. Fund requests were sent, one for fellowships (Sfr 20000, 10000 originally budgeted plus budget for consultant that will not be recruited)-- and a second one using consultant budget for fellowships (8500--) 20/4 The second fund request was cancelled. According to BCS, it is not necessary 26/7 The workshop was implemented with the participation of 15 delegates from 11 countries |
| 2.1.8-Workshop mgte-Arab |  |  | Arab |  | Not defined yet |  |  | October |  | K. Aburizik with consultant (Sfr 8500) and fellows (10.000) |  | On-going |  | 20/4 Initial negotiations with Netherlands (Jan Joosten) to run this workshop on Policy and Regulations aspects (Aburizik started the conversations). |
| 2.1.9-Field Study-ASP |  |  | ASP |  | Not defined yet |  |  | 2nd quarter |  | HQs coordination and tcdc (Sfr 12000--) |  | On-going |  | 8/3--Funds requested for TCDC (Sfr 12000). Mr Calvano will try to identify the expert. Beginning of May a reminder was sent to Mr. Calvano, via E-Mail. Answer was that he is working on this matter and will advice soon. |
| 2.1.10-Workshop mgte- ASP |  |  | ASP |  | Malaysia |  |  | 11 - 13 December |  | Hqs coordination and TCDC (Sfr 6000--) and Fellows (Sfr 20000--) |  | Planned with the participa-tion of S. Iakovlev |  | 13/6- Funds requests produced. ( SI: Sfr 6000 and fellows Sfr 20000) 11/7- Mr. Calvano already started negotiations with Malaysia, to run (and validate) the new workshop on restructuring the telecom sector. 13/9 - negotiations finalized |
| 2.1.11-Field study -EUR |  |  | EUR |  | Slovak Rep |  |  | First mission: 31/7-4/8 to Zilina, formalize joint-venture. Possibility of a second mission during 4th quarter |  | S. Iakovlev (mission Sfr 9880.--) |  | Imple-mented |  | 26/7- Funds request produced and approved. First mission scheduled from 31/7 to 4/8: Zilina university to formalize joint-venture to develop 5 cases studies in management for telecom. Possible second mission at the end of the year 3/8 - agreement signed. |
| 2.1.12-Workshop mgte- EUR |  |  | EUR |  | Uzbekistan |  |  | scheduled for the 13 - 17 November |  | Hqs (SI) coordination Consultant (Sfr 17000--) and fellows (Sfr 12000--) |  | Under implen-tation |  | 13/6- Funds requests produced. (Exp+SI: 17000 and Fellowships Sfr 12000) |
| 2.1.13-Dev. case studies in mgte |  |  | GLO |  | Hqs coordination |  |  | by the end of the year |  | HQs coordination; (missions Sfr 16000 and TCDC Sfr 108000--)+ consutants (donnation in cash and in kind) |  | On-going |  | 1-Swiss donnation cash: Sfr 120,000-: Subcontract with Loisir & Pedagogie 6/6-Fax sent to L&P asking the presentation of first draft, according with contract needed to be ready at end of February. 2-Portugal AICEP; 3 experts in kind plus development work (US$ 150,000-- in kind) 3-Latin american countries, 4 experts (Sfr 100,000 in kind) assisted by TCDC 14/2-TCDC request for two persons to participate in the working meeting of Colombia in March. (Sfr 4800.--) |
| 2.1.14- Translation |  |  | GLO |  | Hqs coordination |  |  | by the end of the year |  | J.Herrera will coordinate the job, possible using facilities in the regions (Sfr 82000) |  | Under iimple-mentation |  | Fund request Sfr 10.000-- to translate 4 workshop to Arabic is approved. Agreement with the administration under preparation. Fund request of Sfr 15000 to translate into Russian. |
| 2.1.15-Production of TBT mat. |  |  | GLO |  | Hqs coordination; WS in Maputo |  |  | scheduled the 20 - 24 November |  | J. Herrera/ R. Cortinovis (Consultant Sfr 60000--and translation Sfr 44000-) |  | On-going |  | Negotiations started to develop a Policies workshop. (Later the TBT will be developed) 27/2: Funds requested to hire a consultant (Possible Svein Tenningas, from Brussels) Sfr 34000.--6/6-Recruitment requested to MFFosanelli, to produce the development of the workshop between 13 March and 20 July. 8/3-Funds request for Sfr 70.000- to contract specialized house in TBT production 21/8 - Invitation letter sent for WS in MOZ. |
| Sub-prog 2.2: TELEPROJECT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.0-Assistance at distance |  |  | GLO |  | Participant countries |  |  | During the year |  | R. Cortinovis |  | On-going activity |  | Using TIES and the virtual office concepts, a permanent “learning by doing” assistance is provided to the participants. |
| 2.2.1-Reg TBT workshop E-Afr |  |  | E-Afr |  | South Africa |  |  | 7-18 August |  | R. Cortinovis (Sfr 9000 for mission and Sfr 20000-- for fellows) |  | On-going |  | Negotiations started (Mr Tangen) with South Africa, in order to define the host country. 13/6-Funds request produced (Missions RC + KT: Sfr 15000 and Fellows Sfr 20000) 26/7- Invitation letters were sent, fellowships requests under process, all is ready. 22/8- Implemented, 10 foraneous participants from 9 different countries plus the local staff: |
| 2.2.2-Reg TBT workshop F-Afr |  |  | F-Afr |  | Dakar |  |  | 12-23 June (R. Cortinovis will be from 19 to 23, first week: Mr. Soumah) |  | R. Cortinovis (Sfr 9000 for mission and Sfr 20000-- for fellows) |  | On-going |  | 8/3 Funds request for RC mission (Sfr 9000) and fellowships (Sfr 20000) Implemented with a participation of 25 delegates from 18 countries. |
| 2.2.3-Reg TBT workshop AM |  |  | Am |  | Not defined yet, our preference is Brasilia. Already negotiated with Argentina |  |  | 17 - 21 Oct (including two days with top management on TBT applications, with J.H.) |  | R. Cortinovis (Sfr 10000-- for mission and Sfr 20.000-- for fellows) |  | On-going |  | Negotiations started with Brasilia, Telebras seems interested in hosting the meeting. 13/6- Confirmed Buenos Aires, Argentina 13/6 - Funds request produced (Mission RC: 10000 and fellows 20000) 26/7-Invitation letter prepared by HQ/HRD and sent out by Brasilia office. |
| 2.2.4-Distance trial -AM and some other places (Also sub-prog 2.4) |  |  | GLO |  | Not defined yet |  |  | 2nd or 3th quarter |  | R. Cortinovis |  | Planned |  | Financed with a donnation of US$ 20.000-- provide by the USA Government. Still awaiting funds. |
| 2.2.5-Reg TBT workshop Arab |  |  | Arab |  | Tunis |  |  | 15-19 May |  | R.Cortinovis (Sfr 8500 for mission and Sfr 20000-- for fellows) |  | Going on |  | 7/3- Funds request for fellowships (Sfr 20.000--) produced. Also funds request for Cortinovis mission (Sfr 8500) 13/6-Implemented with the participation of 18 participants from 11 administrations of the Arab States Region. |

| 2.2.6-Reg TBT workshop ASP |  | ASP | Fiji or Malaysia, not defined yet Last information: BANDUNG | 11-15 Sept for national workshop and 18-22 Sept for Regional workshop (to be confirmed) | R.Cortinovis (Sfr 11000--for mission and Sfr 10.000 for fellows) Carried out by McDermott of Ericsson | Under organiza-tion | 13/6- Funds request produced (Fellows 10000 and mission RC 11000) 26/7- Invitation letter under preparation. It is envisage to recruit one expert to run this workshop in order to give free time to R. Cortinovis to develop the Virtual Training Center maquete here at Hqs. 26/8- Invitation letters sent. One candidate from Ericsson Expertise is available to run the workshop. Negotiations completed. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2.2.7-Reg TBT workshop EUR |  | EUR | Not defined yet | Scheduled 20-24 Nov 1995 | R.Cortinovis/S.Iakovlev (Sfr10440-- for missions and Sfr 12000-- for fellows) | Under organiza-tion | 13/6-Funds request produced (Missions RC+SI: 11000 and fellows 12000) |
| 2.2.8- Donnation of PCs |  | GLO | Not defined yet | During second part of 1995 | Hqs coordination with Computer Department | Possible activity | If we get the PCs (second hand) from Computer Dpt and if we get the budget for transport from some external sources). |
| Sub-prog 2.3- Enhancing fellowships |  |  |  |  |  |  |  |
| 2.3.1-Needs identification system |  | GLO | Global application | Design of the system during first semester, test and use it during second semester | B. Wilson and HRD Regional Officers | Planned Going on with Study Group 2. | Under way with the Study Group 2, Question 5/2. HRD unit provided all inputs to the Study Group which will implement the survey. 22/8- Several E-Mail sent to the coordinator of Q5/2 to prepare the survey, to modify and improve the process of collecting information, and to provide LDCs list of countries and how to get the addresses from TIES. |
| 2.3.2-Negotiation of fellowships special agreements |  | GLO | Global application | Negotiation/ establishment of agreements during first quarter | B. Wilson. Once defined the agreement, it is administered by the Fellowships Unit | Imple-mented | Possible agreements: a) Swedtel (under Voluntary Programme funds) b) Temic, Cable and Wireles, Intelsat, AICEP and TRT, as well as Suisse-PTT special for F-Africa. Agreements authorized, budget assigned. From now Fellowships unit will implement the agreements. From HRD Coordinator the activity is finished succesfully. |
| 2.3.3-Providing information on trainig possibilities |  | GLO | Global | Information stored in the data bases of the ISS | ISS-sub-program 2.10 | On-going activity | a) Data bases available in TIES b) HRD quarterly publish the list of resources every six months. |
| Sub-prog 2.4- Distance learning |  |  |  |  |  |  |  |
| 2.4.1-Distance trial between 2 countries |  | Arab | Not defined yet | February or March | R.Cortinovis/ K. Aburizik (Consultant Sfr 5000 and TCDC Sfr 1500) | React-ivated | Delayed because the engineer in charge in Cairo passed away. Activity needs to be reorganized . Beginning Sept, circular letter sent out. |
| 2.4.2- Pilot trial in ASP |  | ASP | Not defined yet | 3rd quarter | R. Cortinovis (Consultant Sfr 25000--) | On-going | Organized with ABU and ICPT Trieste plus someone from Israel. |
| 2.4.3- Pilot trial in E-Eur |  | EUR | Zilina Univ., Slovakia | 4th quarter | R.Cortinovis/SI (Consultant Sfr 25000--) | Organiza-tion on-going | 26/7- Fund requests produced and approved. The subcontract with AT&T is under discussion. August: Circular letter drafted to set up a Virtual Task Force and to refine proposal. |
| 2.4.4-Feasibility study global system |  | GLO |  | Second semester and/or during 1996 | R.Cortinovis/JH (Consutants 150000--) | Under imple-mentation | First steps going on with the installation of the VTC (Virtual Training Center in Costa Rica, Colombia and possible Incatel to cover Central American countries). 16/2. Feasibility study started in association with the study for Global University. Fund request for Sfr 150000-- approved. 11/7- Job description for two experts produced and under coordination with Personnel Department. 22/8- we received 19 curriculums. The study of them is going on and before end of August two of the candidats will be recruited. 19/9 - Virtual Training Centre set up on the ITU server; and connections to be finalized. |
| Sub-prog 2.5- Stand/ guidelines |  |  |  |  |  |  |  |
| 2.5.1- Identification of needs |  | GLO | Different regions | first semester | Hqs coordination + HRD regional officers | Planned | Request/reminder sent the 7/9 to Regions for list of needs. |
| 2.5.2- Development of new stand/guide |  | GLO |  | During 1995 | HRD Hqs staff. | Imple-mented | Going on from last year with the up-date of the TDG, this year French and Spanish version. During 1995 a new stand/guide needs to be developed S. Iakovlev started with the guideline “management of modern training centers 22/8- Guideline produced in English by S. Iakovlev. Final name: “REFERENCE MANUAL, Guide for the production of a Diagnosis-Evaluation and Plan for Establishing or Improving a Telecommunication Training System”. Will be reproduced in English -50 copies to be tested. |
| Sub-prog 2.6- Global University |  |  |  |  |  |  |  |
| 2.6.1- Feasibility study |  | GLO | Different regions | First semester | R.Cortinovis/ JH (Consultants Sfr 135000--) | On-going | Invitation to interested parties was sent; electronic conference will be used to get inputs. Possible round table in May and a progress report needs to be submitted to the Council 1995. March: Round Table scheduled in Geneva 29, 30 and 31 May 1995 8/3- Funds request to recruit 2 consultants during 4 months was sent (Sfr 135000) 21/3 Funds request for a short mission in Switzerland (SI+RC) to discuss with the Zilina (Slovak) University authority, taking advantage that this person was in Switzerland. (Sfr 1000 approx) 11/7-Job description for the two consultants (experts) under coordination with Personnel Dpt. 22/8- Going on together with the feasibility study for distance education; sub-program 2.4 25/9 - both experts arriving in Geneva. |
| 2.6.1-Establishment of joint-ventures |  | GLO |  | Second semester | R.Corinovis/ J.H. | On-going | If project is approved, start negotiations to define possible joint-ventures with partners. Sept: many contacts and negotiations taking place |

| Sub-prog 2.7- Research & Dev Tr. |  | GLO | - | - | - | Nothing during 1995 | Activity with low priority. Nothing is planned during 1995. Needs will be defined during 1996. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-prog 2.8- Dir. Ass. BAAP |  |  |  |  |  |  |  |
| 2.8.0-Identification of needs for assistance in the area of HRM/D, OD, Management Dev. and Training |  | All Regions | - | During the year | HRD Regional Officers in their regions | Normal activity of the HRD reg officers | Normal HQs coordination for Global actions |
| 2.8.1-HRM/D regional meet E-Afr |  | E-Afr | After many negotiations, South Africa will host the 95 meeting. (Ghana wished to postpone to 1997) | Confirmed from 15 to 21 Nov . | B.Wilson / K. Tangen (Sfr 20000--for missions and Sfr 30000-- for fellows) | Under imple-mentation | The coordination with possible host country already started. 10/4: It seems Ghana is having difficulties to confirm their offer. Mr Tangen is now thinking to organize the meeting in Ethiopia 13/6- Confirmed in Accra. Funds request produced (Fellows Sfr 30000 and missions BW+KT Sfr 15000) 20/8 - Ghana unable to host; South Africa accepts. 18/9 - circular invitation letter mailed. |
| 2.8.2-HR reg workshop with Suisse-PTT contribution/participation |  | F-Afr | Yaounde | 13/11-30/11/95 ou 30/10-10/11 Now confirmed: 30/10-10/11 | Soumah (Mission Sfr 4400 and Fellows Sfr 30000) | Under imple-mentation | 2/5/95- funds request fellowships 30.000 Sfr. 13/6- Funds request mission Mr. Soumah produced |
| 2.8.3-HRM/D regional meet Am |  | Am | Santiago, Chile | 11-17 May 1995 | M. Maniewicz/ J. Herrera (Sfr 25000 for missions and Sfr 20.000 for fellows) | Imple-mented | Request to use fellows budget was sent 30/1/95. Invitation letter sent by R.O. 13/12/94 16/2: Process to select fellows is going on. Priority to the countries that finance partially the cost of the fellowship. 8/3 Funds request for ITU staff missions was sent (Sfr 20000) 13/6- Implemented with the participation of 75 persons comming from 11 Administration, 11 operator’s entities and 4 regional organizations |
| 2.8.4-HRM/D reg meet Arab countries |  | Arab | Cairo, Egypt | 14-18/1/95 | K. Aburizik | Imple-mented | Was implemented in combination with the HRM network group of Arab States under Aburizik coordination. |

| 2.8.5- Intelsat course Arab region |  | Arab | Damas | March Now scheduled 23-28 Sept. | K. Aburizik under agreement with Intelsat | Imple-mented | Agreement with Intelsat needs to be signed urgently (today 30/1/95 we are waiting a management decission in relation with fellowships agreements) 16/2- Agreement already signed. Aburizik is in charge of the organization |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2.8.6-HRM/D reg meet ASP |  | ASP | Vietnam (Hanoi) | Confirmed last week of November (30/11-6/12) | B.Wilson/M.Calvano ?? ( Missions Sfr 25000-- and Fellows Sfr 25000--) | Under imple-mentation | Informal agreement with Vietnam made by M. Calvano. We are waiting the official letter from the Vietnam Government. Confirmation received to host the meeting at the end of November. 20/4-Dates fixed from 30/11 to 6/12. 13/6- Funds request produced (Fellows Sfr 25000 and missions JH+MC+G staff: 25000) |
| 2.8.7-HRM/D reg meet EUR |  | EUR | Sofia, Bulgaria | 3-7/7/95 | S.Iakovlev, J.Herrera (Sfr 12000-for missions and Sfr 15700 for Fellows) Budget revision allow us to go until Sfr 22000 for fellowships EXTERNAL CONTRIBUTION from Japan (US$ 18000) | Organization going-on | Official contacts already done. Exploratory mission will be lunched in February. 16/2: Mission implemented. The results are that ITU needs to find another Host Country. It is not possible to organize the meeting in Moscow. 24/2-Meeting will be in Sofia, Bulgaria (3-7/7/95). Funds request to use fellowships budget was produced today.(Sfr 15700) 8/3: Fund requests for JH/SI missions was sent (Sfr 8000). Additional funds requested for support costs- 5000 Sfr to rent facilities. 11/7-Implemented with the participation of 44 delegates from 23 different telecom organizations. |
| 2.8.8-Assistance to support BAAP |  | GLO | Different countries | During 1995 | Several HQs HRD experts (Sfr 17000 for missions and Sfr 36000 for TCDC) | On-going | 1- Missions of Tangen/Brown requested 27/1 (Sfr 6000) 2- Missions of Soumah/Tangen/Director AFRALTI (Sfr 2600 each) |

| 2.8.9-Ad-hoc assistance outside of BAAP, in the area of HRM/HRD; OD and Training aspects. |  | GLO | Different Regions and countries | During 1995 | Sfr 350000-- for missions and Sfr 250000-- for fellowships agreements | On-going | 1) Sfr 350000--is for Ad-Hoc assistance, to be agreed with regional coordinators 2) Sfr 250000-- may cover the agreements with: a)TEMIC -- Sfr 75000-- b)Cable & Wireless-- Sfr 75000-- c)AICEP---Sfr 50000.-- d)INTELSAT---Sfr 20.000-- e) TRT- Sfr 30.000-- Agreements already formalized 7/3/95: under item 1: fund requests produced and sent for approval as follows: Sfr 20,000 for fellows, HRM-WS in Vietnam-April 24-28 (for Lao and Cambodia + 6 neighboring countries); second fund request of Sfr 10,000 for O.D.-WS in Vietnam-Jun 19-23 (Lao and Cambodia, 2 fellows each); and third fund request (Sfr 10,000 ) for Management of Training-WS same place and countries-August 14-18. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-prog 2.9- Integrated rural educ. |  | GLO | _ | _ | _ | Nothing planned for 1995 | Needs identification and feasibility studies will start in 1997 |
| Sub-prog 2.10- Information system in training and HRM/HRD |  |  |  |  |  |  |  |
| 2.10.1-Collection and process of information |  | GLO | All countries | During the year | HRD Regional Officers; HQs coordination | On-going activity |  |
| 2.10.2-Maintain the data bases up-dated and available through TIES |  | GLO | - | During the year | Actual G-staff | On-going activity | Data bases are available on TIES, Internet and WWW. |
| 2.10.3- Publication of the HRD quarterly |  | GLO | - | Sustainable activity to provide relevant articles produced by countries/organisations and/or ITU staff | HQs coordination + HRD Reg Officers | On-going activity | HRDQ to be published in January, April, July, and October of each year. HRDQ No 58 published in January 1995. HRDQ No 59 published in April 1995 HRDQ No 60 published in July 1995 These publications are also on TIES (the Virtual Library). |

Note: COST CENTER NUMBERs (PROGRAM No 2):

Mandevtel................... 450210

Teleproject.................. 450220

Enh.Fellowships.......... 450230

Dist. Learning............. 450240

Stand/guidelines.......... 450250

Global Univ................. 450260

Research & Dev. Tr.... 450270

Direct Assistance......... 450280

Integr. rural educat.... 450290

Inf. system (ISS).......... 450295

WORKING PLAN - 1 9 9 6

| Progr. No 2: | Human Resources Management and Development Notice: Row with gray color = activity implemented Status column gray color = activity under organization | Jaime Herrera tel : 5421 |
| --- | --- | --- |

| Activity |  | Ref. |  | Region |  | Place | Dates |  | Involved |  | Status |  | Comments |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-prog 2.1: MANDEVTEL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1-FIELD STUDIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1.1-Field Study to identify possible subjects to be developed as case studies |  |  | Arab |  | To be defined |  |  | First or second quarter |  | Aburizik + consultant |  |  |  | BDT mission of Aburizik= Sfr 3440.-- Consultant= Sfr 18000-- |
| 2.1.1.2-Field study to validate case studies developped. |  |  | ASP |  | To be defined |  |  | second or third quarter |  | TCDC or similar |  |  |  | TCDC= Sfr 12000.-- |
| 2.1.1.3-Field study to develop/ validate case studies. |  |  | E-Eur |  | To be defined |  |  | second quarter |  | S. Iakovlev + consultant |  |  |  | BDT mission SI= Sfr4940-- Consultant= Sfr 18000-- |
| 2.1.2-MANUALS AND CASE STUDIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2.1-Development of a new manual + case studies in one language plus production of2 tbt case studies developed in 95, in two other languages. |  |  | GLO |  |  |  |  | During the year |  | J. Herrera + consultants and TCDC. |  |  |  | BDT missions= Sfr 4970-- Consultant= Sfr45000-- TCDC= Sfr 33000-- |
| 2.1.3- TRANSLATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3.1-Translation of the manuals produced during 1995 in the other two languages and publication |  |  | GLO |  |  |  |  | During the year |  | J. Herrera + Documentation costs |  |  |  | Documentation costs= Sfr77970-- |
| 2.1.4- TBT & MULTIMEDIA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4.1- Production of multimedia material for Mandevtel (hypertext, case studies, simulations) |  |  | GLO |  |  |  |  | During the year |  | J. Herrera + contracts and consultants. |  |  |  | Consultant= Sfr30.000-- Doc-contracts= Sfr 43150-- |
| 2.1.5- COORDINATION MANDEVTEL WITH DONNORS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.5.1- Coordination/revision of the job produced together with the partners of Mandevtel |  |  | GLO |  |  |  |  | During the year |  | HRD Staff |  |  |  | Donnors for 1996: Suisse-PPT = Sfr 120000-- in cash AICEP= ??? in kind |
| 2.1.6- TRAINING OF MIDDLE AND TOP MANAGERS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.6.1-Management workshop for F-Africa (ws No 1-Afr) |  |  | F-Afr |  | to be defined |  |  | Second quarter |  | A. Soumah + consultant |  |  |  | Fellows= Sfr 20.000-- consultant= Sfr 6.000-- BDT mission A. Soumah=under normal budget of missions Africa Region. |
| 2.1.6.2- Management workshop for F-Africa (ws No 2-Afr) |  |  | F-Afr |  | to be defined |  |  | third quarter |  | A. Soumah + consultant |  |  |  | Fellows= Sfr 20.000-- consultant= Sfr 6.000-- BDT mission A.Soumah = Sfr 4.000-- |
| 2.1.6.3- Management workshop for Portugues speaking countries of Africa (ws No 3-Afr) |  |  | F-Afr Lusophone |  | to be defined |  |  | third quarter |  | B. Wilson + consultant |  |  |  | Fellows= Sfr 20.000-- consultant= Sfr10.000-- B. Wilson mission= Sfr 6.000 |
| 2.1.6.4- Management workshop for E-Africa (ws No 4-Afr) |  |  | E-Afr |  | To be defined |  |  | second quarter |  | R. Huang + consultant |  |  |  | Fellows= 20.000-- consultant= Sfr 6.000-- BDT mission R.Huang=under normal budget of missions Africa Region |
| 2.1.6.5- Management workshop for E-Africa (ws No 5-Afr) |  |  | E-Afr |  | To be defined |  |  | third or fourth quarter |  | R. Huang + consultant |  |  |  | Fellows= Sfr 25,300-- Consultant= Sfr 6.000-- BDT mission R.Huang=Sfr 3.940-- (Total Afr: fellows= 105.300+BDT travel= 13940+ Cosultant= 34.000; total of Sfr 153.240.--) |
| 2.1.6.6- Management workshop for AM Region (ws No 6-AM) |  |  | AM |  | To be defined |  |  | third or fourth quarter |  | M. Maniewicz + consultant+ J. Herrera-HQs |  |  |  | Fellows= Sfr 47700-- (fellows+instructors) BDT travel (M.M.+J.H.)= Sfr 10470-- Consultor for development/teaching= Sfr 30.000-- TCDC= for field study and training= Sfr 6000-- (Total AM= Sfr 94170--) |
| 2.1.6.7- Management workshop for Arab Countries (ws No 7-ARAB) |  |  | Arab |  | To be defined |  |  | third quarter |  | K. Aburizik + consultant |  |  |  | Fellows= Sfr 12000-- Consultant= Sfr 8.500-- BDT mission= under normal budget of mission Arab Region |
| 2.1.6.8- Management workshop for Arab Countries (ws No 8-ARAB) |  |  | Arab |  | To be defined |  |  | Fourth quarter |  | K. Aburizik + consultant |  |  |  | Fellows= Sfr 12000-- Consultant= Sfr 8500-- BDT mission KA= 4970.-- (Total ARAB= Fellows Sfr 24000-, consultant= 17000--, BDT travel 4970.-- total Sfr 45970--) |
| 2.1.6.9- Management workshop for ASP Region (ws No 9-ASP) |  |  | ASP |  | To be defined |  |  | third quarter |  | S. Iakovlev + Consultant |  |  |  | Fellows= Sfr 15000.-- Consultant= under TCDC=Sfr 6000-- BDT mission (SI) under normal budget of missions HRD Hqs division |
| 2.1.6.10- Management workshop for ASP Region (ws No 10-ASP) |  |  | ASP |  | To be defined |  |  | fourth quarter |  | J. Herrera |  |  |  | Fellows= Sfr 15000-- BDT mission (JH)= Sfr 7470.-- (Total ASP Region= Fellows Sfr 30000--+Consult TCDC Sfr 6000-- + BDT mission Sfr7470--; total Sfr 43470--`) |
| 2.1.6.11- Management workshop for E-EUR (ws No 11-E-EUR) |  |  | E-Eur |  | To be defined |  |  | Third or fourth quarter |  | S.Iakovlev + consultant |  |  |  | Fellows= Sfr 10000.-- BDT mission (SI)+ Sfr 3470-- Consultant= Sfr 17000-- (Total E-EUR Sfr 30470--) |
| sub-program 2.2 TELEPROJECT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1- DISTANCE ASSISTANCE. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1.1-assistance is provided using the virtual office, TIES and computer communication facilities |  |  | GLO |  | Participants countries |  |  | During the year |  | R. Cortinovis |  |  |  | Normal activity in Hqs. |
| 2.2.2-Regional TBT/Distance learning workshops. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2.1-Regional TBT ws E-Africa (TBT ws No 1-Afr) |  |  | E-Afr |  | To be defined |  |  | Third or fourth quarter |  | R. Cortinovis or recruited expert |  |  |  | BDT travel= normal budget of mission Hqs staff. Fellowships= 20000-- |
| 2.2.2.2- Regional TBT ws F-Afr (TBT ws No 2-Afr) |  |  | F-Afr |  | To be defined |  |  | Third or fourth quarter |  | R. Cortinovis or recruited expert |  |  |  | BDT travel (RC)+ Sfr 5970-- Fellows= Sfr 20000-- (Total TBT ws Africa= Fellows Sfr 40000--+BDT mission Sfr 5970--; total of Sfr 45970--) |
| 2.2.2.3- Regional TBT/dist learning ws AM (TBT ws No 3-AM) |  |  | AM |  | To be defined |  |  | Second half of the year |  | R. Cortinovis + TCDC consultant |  |  |  | Fellows= Sfr 20000-- TCDC = Sfr 12000-- BDT mission (RC)= Sfr8470-- (Total TBT ws AM= Sfr 40470--) |
| 2.2.2.4- Regional TBT ws ARAB States (TBT ws No 4-Arab) |  |  | Arab |  | To be defined |  |  | second or third quarter |  | R. Cortinovis or recruited expert |  |  |  | Fellows= Sfr 15000-- BDT mission (RC)+ Sfr 4970-- (Total TBT ws Arab= Sfr 19970--) |
| 2.2.2.5- Regional TBT/Distance learning ws ASP (TBT ws No 5-ASP) |  |  | ASP |  | To be defined |  |  | second or third quarter |  | R. Cortinovis |  |  |  | Fellows= Sfr20000-- BDT mission (RC)= Sfr 6480-- (Total TBT ws ASP= Sfr 26480--) |
| 2.2.2.6- Regional TBT ws E-EUR (TBT ws No 6) |  |  | E-Eur |  | To be defined |  |  | second quarter |  | R. Cortinovis |  |  |  | Fellows= Sfr 10000-- BDT mission (RC)= Sfr 3470-- (Total TBT ws E-Eur= Sfr 13470--) |
| 2.2.5-DISTANCE TRIALS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.5.1-distance trial AM |  |  | AM |  | Costa Rica and Colombia (to be confirmed) |  |  | second part of the year |  | Subcontract coordinated by R. Cortinovis |  |  |  | USA donnation of U S $ 20.000-- |
| 2.2.5.2-distance trial Arab |  |  | Arab |  | To be defined |  |  | second part of the year |  | Coordinated by R. Cortinovis |  |  |  | No cost in BAAP |
| 2.2.5.3-distance trial ASP |  |  | ASP |  | To be defined |  |  | second part of the year |  | subcontract with consultants. |  |  |  | Consultant: Sfr 25000-- |
| 2.2.5.4-distance trial E-Eur |  |  | E-Eur |  | To be defined |  |  | second part of the year |  | Subcontract with consultants. |  |  |  | Consultant: Sfr 25000-- |
| Sub-program 2.3: Enhancing FELLOWSHIPS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1-Needs identification system |  |  | GLO |  | all countries |  |  | first part of the year |  | HRD Regional Officers, using tool developed by the Study Group 2 |  |  |  | No cost for BAAP |
| 2.3.2-SPECIAL AGREEMENTS |  |  | GLO |  | all countries |  |  | during the year |  | Executed by FELLOWSHIPS UNIT. HRD Division only negotiate and stablish the agreement; supporting Fellowships Unit |  |  |  | 2.3.2.1-Cable & Wireless= Sfr 60.000-- 2.3.2.2-TEMIC= Sfr 60.000-- 2.3.2.3-AICEP= Sfr 50.000-- 2.3.2.4-INTELSAT= Sfr 20.000-- 2.3.2.5-Suisse PTT= Sfr 20.000-- (Total Special Agreements= Sfr 210.000--) |
| 2.3.3-Providing information on training possibilities |  |  | GLO |  | Global application |  |  | Information stored in the data bases of the ISS and in the VTC |  | ISS-sub-program 2.10 VTC-sub-program 2.4 and 2.6 |  |  |  | a)Data bases availables b)HRDQ publish the list of resources every six months No cost for BAAP |
| Sub-program 2.4: DISTANCE LEARNING SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.1.1-Continuing the stablishment of the distance training network of VTC nodes |  |  | GLO |  | Global application |  |  | During the year |  | R. Cortinovis |  |  |  | During 1995 was stablished the VTC-Virtual Training Center, principal node in TIES-Geneva, and a network with VTC-Nodes in Costa Rica and Colombia. During 1996 this network will be enhanced (Ex: VTC in Malta, VTC in Jakarta, etc) No cost for BAAP |
| 2.4.1.2-Distance Learning system (GTTI) |  |  | Afr |  | To joint the global system |  |  | second or thir quarter |  | R. Cortinovis + consultant |  |  |  | Consultant= Sfr 25000.-- |
| 2.4.1.3-Optional - Distance trial using VTC |  |  | E-Afr F-Afr |  | To be defined |  |  | during the year |  | R. Cortinovis |  |  |  | Without cost for BAAP |
| 2.4.1.4-Optional - Distance trial using VTC |  |  | Arab |  | To be defined |  |  | during the year |  | R. Cortinovis |  |  |  | Without cost for BAAP |
| Sub-program 2.5-STANDARDS AND GUIDELINES. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.1-Identification of needs/field studies if required |  |  | GLO |  | GLO |  |  | First semester |  | J. Herrera + consultant |  |  |  | Consultant= Sfr 67500-- |
| 2.5.2-Up-dating standards and guidelines |  |  | GLO |  | GLO |  |  | during the year |  | HRD Hqs experts |  |  |  | no cost for BAAP |
| 2.5.3- Developing new guidelines |  |  | GLO |  | GLO |  |  | during the year |  | HRD Hqs experts + consultants |  |  |  | Consultant= Sfr 22500-- |
| Sub-program 2.6- GLOBAL TELECOMUNICATIONS UNIVERSITY - GTU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.1-Finishing the feasibility study and getting acceptance to continue. |  |  | GLO |  | GLO |  |  | During first semester |  | R. Cortinovis J. Herrera and consultants. |  |  |  | Joint activity with the sub-program No 4- Distance Learning System. |
| 2.6.2- Looking for partners to start GTU/GTTI activities formally |  |  | GLO |  | GLO |  |  | During the year |  | R. Cortinovis J. Herrera and consultants. |  |  |  | Joint activity with the sub-program No 4- Distance Learning System |
| 2.6.3.1- Distance pilot trial |  |  | AM |  | To be defined |  |  | During the year |  | R. Cortinovis + consultant |  |  |  | Consultant= Sfr 25000-- |
| 2.6.3.2-Distance pilot trial |  |  | ASP |  | To be defined |  |  | During the year |  | R. Cortinovis + consultant |  |  |  | Consultant= Sfr 25000-- |
| Sub-program 2.7- TRAINING IN RESEARCH & DEVELOPMENT. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7.1-Training needs identification |  |  | GLO |  | GLO |  |  | At the end of 1996 |  | HRD Regional Officers |  |  |  | Joint action with program No 2.3. Implementation actions will be during 1997. |
| Sub-program 2.8-DIRECT ASSISTANCE BAAP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.8.1-Identification of needs for assistance in the area of HRM/D, OD, Management Development and Training |  |  | GLO |  | GLO |  |  | At end 1996 |  | HRD Regional Officers |  |  |  | Normal Hqs coordination. No cost for BAAP |
| 2.8.2.1-HRM/HRD Inter-regional meeting (world wide level meeting scheduled every 3 years- to support BAAP actions) |  |  | GLO |  | Kenya, Nairobi |  |  | Second part of 1996 |  | J.Herrera + HRD Hqs and regional officers |  |  |  | Fellowships= Sfr 45000-- |
| 2.8.2.2-HR sub-regional workshop with the cooperation of Suisse-PTT |  |  | F-Afr |  | To be defined |  |  | Second part of the year |  | A. Soumah |  |  |  | Fellows= special agreement with Suisse PTT (See sub-program No 3) BDT mission (AS)= Travel budget of the HRD Reg Office Africa. |
| 2.8.3-Direct assistance to support implementation of BAAP Program No 2-HRD |  |  | GLO |  | GLO |  |  | During the year |  | J. Herrera + consultants under TCDC |  |  |  | TCDC= Sfr 44000-- |
| Sub-program 2.9: INTEGRATED RURAL EDUCATION |  |  |  |  | No activity scheduled during 1996 |  |  |  |  |  |  |  |  |  |
| Sub-program 2.10-INFORMATION SYSTEM IN TRAINING AND HRD. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.10.1-Collection and process of information |  |  | GLO |  | GLO |  |  | During the year |  | HRD Regional Officers, Hqs coordination |  |  |  | no cost for BAAP |
| 2.10.2- Maintain the data bases updated and available through TIES in Gopher and in the VTC. |  |  | GLO |  | All countries |  |  | During the year |  | Actual G-Staff |  |  |  | no cost for BAAP |
| 2.10.3- Publication of the HRD quarterly |  |  | GLO |  | - |  |  | 4 issues during the year |  | Hqs coordination + HRD Reg Officers. |  |  |  | Documentation= Sfr 40880-- |