|  |  | Updated : 30-Jul-26 |
| --- | --- | --- |
| Programme 3 | Guidelines for Elaboration of Business-Oriented Development Plans | Thomas Fried tel : 5061 |

| Activity |  | Ref. |  | Region |  | Place | Dates |  | Involved |  | Status |  | Comments |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Finalising Draft Master Plan Guide | 3.1 |  | GLO |  | HQ |  |  | January 1995 |  | Fried |  | Done |  | ...printing 75 copies to send out for comments.. |
| Development of Training material | 3.2 |  | GLO |  | Stockholm |  |  | Dec 94 - Jun 95 |  | Leijon |  | Ongoing |  |  |
| Send Guide for comments to ROs, banks, UNDP,Administrations,"m"s | 3.1 |  | GLO |  | HQ |  |  | February 95 |  | Fried |  | Done |  |  |
| Get these comments ... | 3.1 |  | GLO |  | HQ |  |  | March 95 |  | Fried |  | Ongoing |  |  |
| Revision of Guidelines accordingly | 3.4 |  | GLO |  | HQ |  |  | Apr - Oct 95 |  | Ernberg,Fried, Young, Hajela, Seth |  | Ongoing |  |  |
| Printing of Guidelines (English) | 3.1 |  | GLO |  | HQ |  |  | October 95 |  | Fried |  | Planned |  |  |
| Translation to French | 3.5 |  | AFR |  |  |  |  |  |  |  |  | 1996 |  |  |
| Translation to Spanish | 3.5 |  | AM |  |  |  |  |  |  |  |  | 1996 |  |  |
| Test course | 3.3 |  | ASP |  | ALTTC, India |  |  | 30 Oct - 10 Nov '95 |  | Hajela,Leijon,Ernberg |  | Done |  | 2 Fellowships for LDCs, 1 for others |
| Course | 3.6 |  | AFR |  | E-speaking |  |  |  |  |  |  | Cancelled |  |  |
| Pilot study | 3.7 |  | ASP |  | Lao |  |  | October 95 |  | Roychoudhury |  | Done |  |  |
| Pre-investment study offer to WorldTel | 3.7 |  | AFR |  | HQ |  |  | September 95 |  | Sirha, Bogdan, Cherif, Ernberg, Fried |  | Done |  |  |
| Pilot study | 3.7 |  | AFR |  | E-speaking |  |  |  |  |  |  | Cancelled |  |  |

| Programme 3 | Guidelines for Elaboration of Business-Oriented Development Plans | Thomas Fried tel : 5061 |
| --- | --- | --- |