|  |  | Updated : 30/07/2026 |
| --- | --- | --- |
| Programme 9 | Integrated Rural Development (IRD) | Johan Ernberg tel : 5090 |

| Activity |  | Ref. |  | Region |  | Place | Dates |  | Involved |  | Status |  | Comments |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Drafting of proposals for policies | 9.1 |  | GLO |  |  |  |  |  |  | Members/Partners regional & HQ staff |  | Ongoing |  |  |
| Consideration of proposals in Study Group 1 (SG1). and in SG rapporteurs’’ meeting | 9.1 |  | GLO |  | SG1 Geneva |  |  | 6-16 March 95 27-30 Nov.95 4-7 Dec. 95 |  | HQ (D. Bogdan, J. Ernberg, L. Androuchko) |  | done planned |  | SG1 I depends on contributions from partners |
| Finalization, editing and translation of policies Guidelines | 9.1 |  | GLO |  | Geneva |  |  | Jan.-March 96 |  | J. Ernberg D. Bogdan |  | Planned |  |  |
| Initial discussions with potential partners (missions, participation meetings and seminars on rural telecoms, Assist in formulation of pilot projects, etc.) | 9.2 |  | GLO ASP ASP ASP AFR EU |  | Sem Djakarta Vietnam Bhutan Pretoria Hungary |  |  | 20-22 March Oct/Nov 95 Oct./Nov 95 5-9 June 95 first half 96 |  | HQ (BDT Mgmt, RMOB. Regional staff J. Ernberg, J. Ernberg L. Androuchko |  | Ongoing done Proposed Proposed done proposed |  | Conference on rural telecom organised by IBC Joint venture TRT Jointly with CTCC international with EU finance? |
| Inventory of planned and on-going IRD initiatives which require telecom support, selection and round-table discussions of pilots | 9.2 |  | GLO AM |  | Mexico |  |  | 15-19 May95 |  | HQ &Reg. staff J. Ernberg&consult. |  | done Planned done |  |  |
| Coordination meeting with partners -preliminary agreements | 9.2 |  | GLO AM |  | Geneva Barbados |  |  | 15 March95 25-27 Sept. 95 |  | HQ (J. Ernberg) J. Ernberg, Ph. Cross |  | done |  | In conjunction with SG1 meeting |
| Survey of existing rural telecom infrastructure and assistance in formulating pilot projects. | 9.3 |  | AM AM AFR AFR ASP EU |  | Chile Brasilia RCA, Uganda Laos,Vietnam,Cambodia Hungary, Kirgistan, Moldavia, Poland Russia, Ukraine Uzbekistan ? |  |  | May 95 Feb.-June Oct/Dec.95 Sept/Nov95 Oct./Nov.95 ? |  | Consultant Consultant, Consultant Consultant Consultant |  | Done Done planned ongoing planned planned |  | More assistance required |
| Activity |  | Ref. |  | Region |  | Place | Dates |  | Involved |  | Status |  | Comments |  |
| 9.3.2 Review of technology options SG 2 meeting | 9.3 |  | GLO |  | Geneva |  |  | all year 1-13 May |  | Consultants, partners HQ (J. Ernberg) |  | Ongoing Planned |  | Inputs also from RASCOM, SPACECOM & SG2 |
| Participation in planning of IRD in participating countries | 9.3 |  | GLO |  | participating countries |  |  | 1995 and onwards |  | Consultants, Regional; staff |  | Proposed |  |  |
| Planning of rural telecom network HREF="prog_05.doc | 9.3 |  | GLO |  | Participating countries |  |  | See BAAP HREF="prog_05.doc |  | HQ (T. Fried), Consultants, National staff |  | Planned |  | Network planning will be carried out by national planners trained through HREF="prog_05.docwith assistance from consultants when required |
| Detailed planning and specification of equipment in Telecentres) | 9.3 |  | GLO |  | Participating countries |  |  | 1996 onwards |  | Consultants, National staff |  | Planned |  | Subject to contributions from partners |
| Negotiations with partners (TELCOs, equipment and service providers) | 9.4 |  | GLO |  |  |  |  | Ongoing |  | HQ (J. Ernberg A. Enderlin) Regional staff |  |  |  |  |
| Establishment of joint ventures for development and delivery of (distance) training | 9.5 |  | GLO |  |  |  |  | See BAAP HREF="prog_02.doc |  | HQ (J.Herrera, J. Ernberg) |  | Planned |  | Subject to establishment of joint ventures with providers of distance learning courses and services. |
| Development of training material for Telecentre staff |  |  | GLO |  |  |  |  | starting toward mid 1996 |  | HQ (J. Ernberg) Consultant |  | Planned |  | Subject to contributions of partners |
| 9.6.1 Establishment of baseline situation in participating communities; Definition of goals and objectives and indicators to be monitored | 9.6 |  | GLO |  | participating countries |  |  | 96 and onwards |  | ROs/JE/Consultants/ Nationals |  | Planned |  | In conjunction with specification of pilots |