|  |  | Updated : 30/07/2026 |
| --- | --- | --- |
| Programme 10 | Broadcasting Infrastructure | Petko Kantchev tel : 5448 |

| Activity |  | Ref. |  | Region |  | Place | Dates |  | Involved |  | Status |  |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Elaboration of guides and development of master plans | 10.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Planning guides in acoustics and architectural design/air-conditioning | 10.1.1 |  | GLO |  | U.K . |  |  | Sept.-Dec1995 |  | Kantchev |  | in preparation | Experts |  |
| Planning guides for audio/video systems of programme acquisition /production | 10.1.2 |  | GLO |  | to be determined |  |  | Oct.1995- 1996 |  | Kantchev |  | in preparation | Experts |  |
| Planning guide in special lighting for TV broadcasting | 10.1.3 |  | GLO |  | Switzerland Germany |  |  | Sept-Dec.1995 |  | Kantchev |  | in preparation | Experts |  |
| Planning guide in contribution and distribution networks | 10.1.4 |  | GLO |  | Switzerland |  |  | Oct.1995-1996 |  | Kantchev |  | in preparation | Experts |  |
| Guide for FM/TV transmitter network and frequency planning | 10.1.5 |  | GLO |  | France U.K. |  |  | Oct.1995-1996 |  | Kantchev |  | in preparation | Experts |  |
| Guidelines for tendering and procurement of broadcasting systems equipment | 10.1.6 |  | GLO |  | Germany Turkey |  |  | Nov 1995-1996 |  | Kantchev |  | in preparation | Experts |  |
| Planning guide on broadcasting organizational structure and HRM/HRD | 10.1.7 |  | GLO |  | Belgium U.K. |  |  | 1996 |  | Kantchev |  |  | Experts |  |
| Planning guide on maintenance, costing and managerial economics of broadcasting technical services | 10.1.8 |  | GLO |  | to be determined |  |  | 1996 |  | Kantchev |  |  | Experts |  |
| TV Symposium and Exhibition/Two Ad-hoc Groups meetings | 10.1.9 |  | GLO |  | Switzerland |  |  | June 1995 |  | Kantchev |  | mission only | Ad-hoc Group meetings to be hold later with relation to the progress of 10.1.1. and 10.1.2 |  |
| IBC/TV Symposium and Exhibition/Ad-hoc Group meeting | 10.1.10 |  | GLO |  | Netherlands |  |  | Sept 1995 |  | Kantchev |  | mission only | Ad-hoc Group meetings to be organized latter when appropriate |  |
| Coordination of joint FES/BDT activities for 1996/1997 | 10.1.11 |  | GLO |  | Bonn, Germany |  |  | November 1995 |  | Kantchev |  | in preparation | Three days mission |  |
| Contingency(e.g. Interactive Television Applications ) | 10.1.12 |  | GLO |  | Paris, UNESCO |  |  | 13-20 March, 1995 |  | Stagliano, Herrera, Kantchev |  | in preparation | Expert's per diem |  |

| Planning manual for broadcasting technologies | 10.2 | GLO |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Manual scope and content | 10.2.1 | GLO | to be determined | Aug.-Oct.1995 | Kantchev | in preparation | Experts |
| Manual preparation | 10.2.2 | GLO | to be determined | Nov..1995-1996 | Kantchev | in preparation | Experts |
| Ad-hoc meeting during BR Radioassembly or Radioconference | 10.2.3 | GLO | Geneva | Oct.-Nov.1995 | Kantchev in cooperation with BR | in preparation | Fellowships/Expert perdiem |
| Final editing | 10.2.5 | GLO | to be determined | 1996 | Kantchev in cooperation with BR | in preparation | Experts |
| Supervisory tasks | 10.2.6 | GLO | to be determined | Aug.1995-1996 | Kantchev in cooperation with BR and Broadcasting Unions | in preparation | Two one-week missions |
| PC Software for FM/TV Frequency and Network Planning | 10.3 |  |  |  |  |  |  |
| Analysis of current software | 10.3.1 | GLO | Geneva | March-Sept.1995 | Kantchev&BR | in preparation | Headqtrs. activity |
| Definition of scope of work | 10.3.2 | GLO | Geneva | Nov.1995 | Kantchev&BR | in preparation | Do |
| Preparation of Report | 10.3.3 | GLO | Australia, Spain | 1996 | Kantchev&BR | in preparation | Experts |
| Submission via BR Study Groups | 10.3.4 | GLO | Geneva | 1996 | Kantchev&BR |  | Headqrs. activity |
| Creation of Special Task Group for preparation of software specifications | 10.3.5 | GLO | to be determined | 1996 | Kantchev&BR |  |  |
| Regional Seminars on New Technologies in Sound and Television Broadcasting | 10.4 |  |  |  |  |  |  |
| ABU/FES/ITU Regional Seminar on adoption of New Media Technologies | 10.4.1 | ASP | Kuala Lumpur, Malaysia | 20-21 Feb.1995 | Kantchev, John Budden FASP, Sadhu ABU, R.Welzel FES, G.Rossi BR | implemented | Lectureres provided in kind , Fellowships provided by BDT to 6 LDCs and by FES in kind, Logistics and support provided by FES and ABU in kind,Mission and Proceedings will be provided by BDT (FES has planned DM36000 for this Seminar) |
| ABU/FES/AMIC Seminar on Social and Development Aspects of Broadcasting | 10.4.1 | ASP | do | 22-24 Feb.1995 | O.Khushu ABU, G. Lehrke FES, Dr.Hering AMIC | implemented | Fellowships provided by BDT(LDCs) and FES, Lecturers provided in kind |

| VHF/VHU propagation measurement campaign for tropics | 10.5 | GLO |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pilot project on propagation and rain intensity | 10.5 | AFR | Tanzania | started | Yousif |  |  |
| Pilot project on propagation and rain intensity | 10.5 | AFR | Uganda | started | Yousif |  |  |
| Propagation measurements set up (Asia and Pacific) | 10.5 | GLO |  | to be determined | Yousif | in preparation | Expert |
| Setting up of propagation measuring equipment (Africa) | 10.5 | GLO |  | 1996 | Yousif | not foreseen in 1995 | Expert |
| Survey of propagation project ( Arab States) | 10.5 | GLO |  | 1996 | Yousif | in preparation | Expert |