|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Updated : 30/07/2026 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme 12 |  |  | Telematics and Computer Networks |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Johan Ernberg tel : 5090 |  |
|  | Activity |  |  | Ref. |  | Region |  | Place |  | Dates |  | Involved |  | Status |  | Comments |  |  |  |
|  |  | Drafting of proposals for policy guidelines with reference to Telematics Activities of ANI related to policy: - Survey of telematics infrastructure development plans for Africa; - Meeting of High level Advisory Group - Afristech meeting on Telematics in Africa - Regional African meeting on Information Policy to consider “White Paper” (inputs to ITU-D SG 1) |  |  | 12.1 |  | GLO AFR GLO/AFR AFR AFR AFR |  | Africa & donors Cairo Dakar Mozambique? |  | Febr.95-March 96 Oct./Nov. 95 12 October 1995 13 December 1995 January 1996? |  | Members, Partners D. Bogdan L. Androuchko African specialists, IDRC, ITU, UNECA, UNESCO |  | ongoing planned planned planned planned |  | A discussion paper prepared for the African Regional Symposium on Telematics for Development includes some recommendations. Following the symposium the sponsoring organisations in collaboration with African initiatives have launched the tentatively called “African Networking Initiative (ANI), which will establish a High level Advisory Group composed of prominent Africans active in this field in order to ensure active African involvement in the ANI One objective is to produce a Information Policy White Paper” which will provide inputs to ITU-D SG1 and SG 2 |  |  |
|  |  | Consideration of proposals in SG1 Consideration of proposals in SG1 & SG2 rapporteurs’ meeting. |  |  | 12.1 12.1 |  | GLO |  | Geneva Geneva |  | 6-16 March 95 27-30 Nov. 95 4-7 Dec. 95 |  | D. Bogdan L. Androuchko J. Ernberg |  | done planned |  | Insignificant inputs |  |  |
|  |  | Finalization, translation and printing of guidelines |  |  | 12.1 |  | GLO |  | Geneva |  | Jan-March 96 |  | D. Bogdan J. Ernberg |  | planned |  |  |  |  |
|  |  | Identification of partners and planning of activities in “Partners meeting” |  |  | 12.2 |  | GLO |  | Geneva |  | 15 March 95 |  | J. Ernberg A. Enderlin |  | done |  |  |  |  |
|  |  | Coordination with other development agencies during “Internet day” |  |  | 12.2 |  | GLO |  | Geneva |  | 28 March 95 |  | J. Ernberg |  | done |  | An Special Interest Group for Telematics for Development has been established as part of the Geneva ISOC Chapter created as one of the consequences of the Internet day. |  |  |
|  |  | Identification of participating countries. Coordination and project planning with partners in the ECA/ITU/UNESCO African Regional Symposium on Telematics for Development |  |  | 12.2 |  | AFR |  | Addis Ababa |  | 3-7 April 95 |  | Regional Office J. Ernberg |  | done |  | Sponsoring organisations (ITU, UNECA, UNESCO, IDRC) involved in follow-up of Recommendations including ANI (see above) |  |  |
|  |  | Identification of participating countries. Coordination and project planning with partners in Symposium on Information Highways in the Arab States (sponsored by UNDP SDN) |  |  | 12.2 |  | ARB |  | Tunis |  | April 95 |  | J. Ernberg |  | done |  | Follow-up in cooperation with UNESCO envisaged but not yet planned in detail |  |  |
|  |  | Identification of participating countries. Coordination and project planning with partners in APT meeting on Information Infrastructure |  |  | 12.2 |  | ASP |  | Tokyo |  | 18-20 Oct. 95. |  | Regional Office J. Ernberg |  | proposed |  | IDRC has through its Pan Asia Networking Programme made a survey of existing information infrastructure. IDRC may be a partner and should be invited to the Tokyo meeting (proposed t APT). |  |  |
|  |  | Identification of participating countries. Coordination and project planning with partners in Symposium with Telematics user groups and service providers |  |  | 12.2 |  | EU |  | Geneva |  | October 95? |  | A. Keskivali J. Ernberg |  | proposed |  | Perhaps during Telecom95? |  |  |
|  |  | Survey of existing Telematics infrastructure, initiatives and needs in participating countries |  |  | 12.3 |  | GLO |  | participating countries |  | Feb.-Dec. 95 |  | Regional Office J. Ernberg |  | proposed |  | The discussion paper for the African Symposium mentioned above includes a survey of existing infrastructure and initiatives in Africa |  |  |
|  |  | Pilot project on Access to telematics facilities |  |  | 12.3 |  | AM |  | Barbados, the Grenadines St. Lucia, St Vincent |  | Aug. 95 -first half 96 |  | ITU (J. Ernberg) PAHO/UNDP/ UNESCO |  | on-going |  | Mission to Barbados 25-27 Sept. by J. Ernberg |  |  |
|  |  | Planning and co-ordination with partners at InfoDev donors’ meeting |  |  | 21.2 |  | GLO |  | Washington |  | 28 Sept. 95 |  | A. Laouyane J. Ernberg |  | planned |  | InfoDev is a World Bank initiative. BDT (P12) participation to be defined. |  |  |
|  |  | Assistance in planning data networks |  |  | 12.3 |  | ASP |  | Bangladesh Nepal |  | Sept.-Oct. 95 |  | Regional Office Consultant |  | on-going |  |  |  |  |