|  | INTERNATIONAL TELECOMMUNICATION UNION | Document SATBAG-01/14-E 24 October 2001 Original: English |
| --- | --- | --- |
|  | SATELLITE BACKLOG ACTION GROUP MEETING GENEVA, 1-2 OCTOBER 2001 |  |

Chairman, SAT-BAG

SAT-BAG Action Plan

The Action Plan of the SAT-BAG agreed at its first meeting, 1–2 October 2001, is attached.

The role of the Contacts named in the Action Plan is to oversee the actions prescribed for the entities shown, with a view to assessing and reporting progress. The Contacts will provide an interim report to SATBAG members on each of their actions by 31 December 2001, and a final report to the next SATBAG meeting to be held 4-6 March 2002.

SAT-BAG Action Plan

| Factors | Interested Groups | Deadline for actions | Decision at | Contact | Action | Action Reference |
| --- | --- | --- | --- | --- | --- | --- |
| Regulatory |  |  |  |  |  |  |
| Non-planned services |  |  |  |  |  |  |
| Radio Regulations complexity | SC, appropriate Study Groups |  |  | Gary Brooks | To review the regulatory provisions of Articles S5, S9, S11, S21, S22 that are believed to have contributed to the backlog. | SBAG(01) 01 |
| Duplication of text/procedures/examination | SC |  |  | Gary Brooks | Remove duplication and combine examination at: - the coordination stage or - the notification stage. | SBAG(01) 02 |
| Simplify Appendix S4: Data structure, data elements | SC, and appropriate Study Groups |  |  | Dave Barrett | Remove duplication and rationalise structure. | SBAG(01) 03 |
| Resolution 49 | SC |  |  | Anders Frederich | Review its effectiveness and possible reinforcement and implementation | SBAG(01) 04 |
| Modifications: - How to treat modifications - How to process modifications relating to networks in operation - Number of modifications | - SC - SC - SATBAG |  |  | - TBD - TBD - Dave Barrett | - Either process modifications regardless of their initial date of receipt, or in conjunction with their initial date of receipt - Whether any priority should be given to such modifications - To understand the reasons behind the number of modifications | SBAG(01) 5/1 SBAG(01) 5/2 SBAG(01) 5/3 |
| Coordination arc or Delta T/T | SC, Study Groups 4, 6, 8 |  |  | Gary Brooks | Extension of the coordination arc concept to other frequency bands and other services. | SBAG(01) 6 |
| Multiple filings | SATBAG |  |  | Dave Barrett | To understand the reasons for the number of multiple filings | SBAG(01) 7 |
| Planned services |  |  |  |  |  |  |
| S30/S30A regulatory provisions | Study Group6 |  |  | Kavouss Arasteh | Review existing provisions for possible removal of deficiencies. | SBAG(01) 8 |
| S30B regulatory provisions | Study Group 4 |  |  | Kavouss Arasteh | Review existing provisions for possible removal of deficiencies. | SBAG(01) 9 |
| General |  |  |  |  |  |  |
| Development of Rules of Procedure | SC |  |  | Tom Walsh | Examine the way the Rules of Procedure are developed and processed. | SBAG(01) 10 |
| Role of the BR in the process | SATBAG |  |  | Ted. Antonacopoulos | Examine the extent to which the BR should be involved in the process | SBAG(01) 11 |
| WRC |  |  |  |  |  |  |
| Administrations proposals to change regulatory procedures | Administrations |  |  | Frank Williams | Encourage administrations, whilst observing time limits for submissions, to consider and review their proposals to conferences that may have an impact on the backlog. | SBAG(01) 12 |
| Roles of the RRB and BR | PP-02 |  |  | Frank Williams | Establish guidelines for the involvement of the RRB and BR at conferences and CPMs. | SBAG(01) 13 |
| Transformation of Rules of Procedure into regulatory text | SC, RRB |  |  | Anders Frederich | Examine the objectives of the Rules of Procedure | SBAG(01) 14 |
| RRB |  |  |  |  |  |  |
| RRB role in: - Conferences - Processing - Rules of Procedure | SC, RRB, PP-02 |  |  | Norbert Schroeder | What is the existing role? Should that role be changed? | SBAG(01) 15 |
| Software |  |  |  |  |  |  |
| Overall responsibility for software development. | BR, SATBAG |  |  | Gene Rappoport | To determine the most effective ways of developing software in the BR, taking into account the identification of requirements, specification, development, testing and implementation. | SBAG(01) 16 |
| Completeness of the database | BR, SATBAG |  |  | Dave Barrett | Identify missing data and complete its insertion in the database. | SBAG(01) 17 |
| Periodic updating of the database | BR, SATBAG |  |  | Dave Barrett | Updating the database appropriately. | SBAG(01) 18 |
| Validation software | BR, SATBAG |  |  | Dave Barrett | Improving the software. | SBAG(01) 19 |
| Automation | BR, SATBAG |  |  | Larry Reed Gene Rappoport Dave Barrett | Integrate the Bureau's software into a single package. Automate Article S5 examination. Develop electronic filing for graphics information. | SBAG(01) 20/1 SBAG(01) 20/2 SBAG(01) 20/3 |
| BR processing |  |  |  |  |  |  |
| Degree of precision in examination | BR, SATBAG, relevant ITU Study Groups |  |  | Olivier Nicol | Extent to which examination is to be performed | SBAG(01) 21 |
| Provision of information | BR, SATBAG |  |  | Dave Barrett | Continue to provide information to administrations, e.g. publish Space Network List and Preface to the IFL | SBAG(01) 22 |
| Completeness and correctness of submissions | BR, SATBAG |  |  | Dave Barrett | To identify the reasons why submissions are still incorrect or incomplete. | SBAG(01) 23 |
| Cost recovery and constraints | BR, Council, PP-02, General Secretariat |  |  | Bruce Gracie | Need for a thorough review of the whole process. (Note there are some regulatory aspects that need to be addressed) | SBAG(01) 24 |
| Budget inflexibility | Council |  |  | Bruce Gracie | Identify and review issues associated with this factor . | SBAG(01) 25 |

| Staffing |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Recruitment delays | Council, PP-02, General Secretariat |  |  | Malcolm Johnson | Identify and review issues associated with this factor. | SBAG(01) 26 |
| Contracts / staff tenure / staff mobility / staff motivation / staff careers | Council, PP-02, General Secretariat |  |  | Malcolm Johnson | Identify and review issues associated with these factors. | SBAG(01) 27 |

__________________________