|  |  |
| --- | --- |
| **Radiocommunication Study Groups** |  |
|  |  |
|  |  |
| Source: Document [5A/TEMP/31](http://www.itu.int/md/R12-WP5A-120522-TD-0031/en) | **Annex 9 toDocument 5A/79-E** |
| **1 June 2012** |
| **English only** |
| Annex 9 to Working Party 5A Chairman’s Report |
| Working Parties 5A and 5B |
| work plan for wrc-15 agenda item 1.18 |

| Working Party 5A/5B meetings | Work plan |
| --- | --- |
| 1st meetingMay 2012 | **Sub-Working Group meetings between WP 5A and WP 5B:**- develop and adopt a work plan, including.**Studies on technical and operational requirements (WP 5A / WP 5B according to the case) such as:**- spectrum requirements needed for automotive radars;- technical and operational requirements for automotive radars;- possible Recommendation on the technical and operational requirements for automotive radar applications within ITS;- review of other relevant existing ITS Recommendations and Reports;- developing new Recommendation and/or Report as appropriate;- liaise as needed with concerned Groups requesting further information.**Sharing studies and regulatory procedures (WP 5B lead) such as:**- the applicability of the existing Recommendations and other relevant studies to the required sharing studies under Agenda item 1.18;- possible new Recommendations or Reports needed to support Agenda item 1.18;- regulatory provisions needed for automotive radars;- sharing and compatibility studies between existing services and proposed radiolocation service including in-band and adjacent band compatibility;- liaise as needed with concerned Groups requesting further information. |

|  |  |
| --- | --- |
| Working Party 5A/5B meetings | Work plan |
| 2nd meetingNovember 2012 | - continue developing the PDN Recommendation on characteristics (WP 5A);- continue developing the PDN Report on sharing studies (WP 5B);- develop initial draft CPM text outline (WP 5B lead);- liaise as needed with concerned groups on progress of CPM text and sharing studies (WP 5B);- update work plan as needed (WP 5A/5B). |
| 3rd meetingMay 2013 | - continue developing the PDN Recommendation on characteristics (WP 5A);- continue developing the PDN Report on sharing studies (WP 5B);- start developing draft CPM text (WP 5B lead);- liaise as needed with concerned groups on progress of CPM text and sharing studies (WP 5B);- update work plan as needed (WP 5A/5B). |
| 4th meetingNovember 2013 | - continue working on CPM text (WP 5B lead);- continue working on Recommendation/Report (WP 5A/5B);- liaise as needed with concerned groups on progress of CPM text and sharing studies (WP 5B). |
| 5th meetingMay 2014  | - finalize CPM text and send to CPM management team (WP 5B);- complete draft Recommendation/Report to be finally considered at the 6th meeting in November 2014 (WP 5A/5B);- consider possible consequential changes to the existing ITU-R documentation as a result of adoption of proposed draft new Recommendation/Report (WP 5A/5B). |
| 6th meetingNovember 2014 | - finalize Recommendation/Report and submit to SG 5 meeting for approval (WP 5A/5B);- consider possible consequential changes to the existing ITU-R documentation as a result of adoption of proposed draft new Recommendation/Report (WP 5A/5B). |

|  |  |  |
| --- | --- | --- |
| **Contact:** | Satoshi (Sam) Oyama (WP 5A)Fatih Mehmet Yurdal (WP 5B) | **E-mail:** s-oyama@arib.or.jp**E-mail:** fatih-mehmet.yurdal@ties.itu.int |