|  |  |
| --- | --- |
| **Radiocommunication Study Groups** |  |
|  |  |
|  |  |
| Source: Document 5A/TEMP/83 | **Annex 7 to**  **Document 5A/198-E** |
| **20 November 2012** |
| **English only** |
| Annex 7 to Working Party 5A Chairman’s Report | |
| work plan for WRC-15 Agenda item 1.3 | |

| Working Party 5A Meetings | Work plan |
| --- | --- |
| 1st meeting (Meeting #9 of WP 5A), May 2012 | 1) Develop the work plan for the studies.  2) Determine the necessity of revision of other relevant PPDR ITU-R Recommendations and Reports (see Report ITU-R M.2033).  3) Develop outline of some of the proposed new/revised Recommendations and/or Reports.  4) Send an opening liaison statement to the concerned groups and external organisations advising them that Working Party 5A intends to coordinate with all relevant groups and seeking inputs for proposed development/revision of the Reports/Recommendations to reflect broadband PPDR applications.  5) Develop outline of the CPM text. |
| 2nd meeting (Meeting #10 of WP 5A), November 2012 | 1) Consider input contributions related to the scope of work.  2) Develop working documents towards new or revised Recommendations and/or Reports reflecting requirements for broadband PPDR; including a Report/Recommendation on technical requirements of broadband PPDR services and applications.  3) Further develop draft CPM text outline.  4) Liaise as required with other involved WPs and external organizations.  5) Revise work plan as appropriate. |

| Working Party 5A Meetings | Work plan |
| --- | --- |
| 3rd meeting (Meeting #11 of WP 5A), June 2013 | 1) Develop working documents towards new or revised Recommendations and/or Reports reflecting requirements for broadband PPDR; including a Report/Recommendation on technical requirements of broadband PPDR services and applications.  2) Continue drafting the CPM text taking into account the existing Reports and/or Recommendations, as well as those being developed.  3) Liaise as required with other involved WPs and external organizations.  4) Revise work plan as appropriate. |
| 4th meeting (Meeting #12 of WP 5A), November 2013 | 1) Consider input contributions related to the scope of work.  2) Continue further work on draft CPM text including the draft text of the revised Resolution 646 and an executive summary.  3) Progress the work on development of Recommendation(s) and/or Report(s) as appropriate.  4) Finalise Reports/Recommendations and submit to SG 5. |
| 5th meeting (Meeting #13 of WP 5A), May 2014 | 1) Consider input contributions related to the scope of work.  2) Finalize Report(s) and/or Recommendation(s) and submit to SG 5.  3) Complete the draft of the CPM text on review and revision of Resolution 646, including regulatory and procedural considerations, taking into account the above Reports and Recommendations. |