|  |  |
| --- | --- |
| **Radiocommunication Study Groups** |  |
|  |  |
|  |  |
| Source: [Annex 5](http://www.itu.int/md/dologin_md.asp?lang=en&id=R12-WP5A-C-0079!N05!MSW-E) to [Document 5A/79](http://www.itu.int/md/R12-WP5A-C-0079/en) | **Annex 5 to Document 5A/306-E** |
| **3 June 2013** |
| **English only** |
| Annex 5 to Working Party 5A Chairman’s Report | |
| work plan for WRC-15 Agenda item 1.4 | |
|  | |

| Working Party 5A meetings | Work plan |
| --- | --- |
| 1st meeting  22-31 May 2012 | – Begin work on identifying amateur service technical and operational characteristics for systems to be operated in the range 5 250-5 450 kHz.  – Develop a workplan for conducting studies and producing outputs relating to WRC-15 Agenda item 1.4.  – Transmit draft of characteristics and workplan to contributing groups.  – Request any needed technical and operational characteristics from contributing groups.  – Request CPM text input for sections 1, 2, and 3 from contributing groups. |
| 2nd meeting  November 2012 | – Complete review of amateur service technical and operational characteristics and develop preliminary draft new Report.  – Finalize workplan.  – Begin sharing studies between proposed amateur service stations and existing service stations.  – Provide any feedback on modelling and characteristics from other groups.  – Develop preliminary draft new Report(s) for sharing studies.  – Transmit preliminary draft new Report on amateur characteristics to contributing groups for final review.  – Transmit preliminary draft new Report(s) on sharing studies to contributing groups as appropriate for review.  – Develop draft CPM text for sections 1, 2, and 3, considering and incorporating from contributing groups.  – Transmit draft CPM text to contributing groups for review. |
| 3rd meeting  Second Quarter 2013 | – Complete amateur service technical and operational characteristics draft new report and send to Study Group 5.  – Continue sharing studies, taking into account feedback from contributing groups.  – Update preliminary draft new Report(s) for sharing studies as appropriate.  – Develop CPM text for section 4, considering and incorporating from contributing groups.  – Transmit updated preliminary draft new Report(s) on sharing studies to contributing groups as appropriate for review.  – Transmit draft CPM text to contributing groups for review. |
| 4th meeting  Fourth Quarter 2013 | – Complete sharing studies taking into account feedback from contributing groups.  – Prepare draft new Report(s) on sharing studies as appropriate.  – Develop CPM text for sections 5 and 6, considering and incorporating from contributing groups.  – Transmit draft new Report(s) on sharing studies to contributing groups as appropriate for final review.  – Transmit draft CPM text to contributing groups for review |
| 5th meeting  Second Quarter 2014 | – Complete draft new Report(s) on sharing studies and send to Study Group 5.  – Finalize CPM text, considering and incorporating from contributing groups.  – Transmit draft CPM text to chapter rapporteur. |

|  |  |  |
| --- | --- | --- |
| **Contact:** | Brennan PRICE | **E-mail:** [bprice@arrl.org](mailto:bprice@arrl.org) |