|  |  |
| --- | --- |
| **Radiocommunication Study Groups** |  |
|  |  |
|  |  |
| Source: [Annex 5](http://www.itu.int/md/dologin_md.asp?lang=en&id=R12-WP5A-C-0079!N05!MSW-E) to [Document 5A/79](http://www.itu.int/md/R12-WP5A-C-0079/en) | **Annex 5 toDocument 5A/306-E** |
| **3 June 2013** |
| **English only** |
| Annex 5 to Working Party 5A Chairman’s Report |
| work plan for WRC-15 Agenda item 1.4 |
|  |

| Working Party 5A meetings | Work plan |
| --- | --- |
| 1st meeting22-31 May 2012 | – Begin work on identifying amateur service technical and operational characteristics for systems to be operated in the range 5 250-5 450 kHz.– Develop a workplan for conducting studies and producing outputs relating to WRC-15 Agenda item 1.4.– Transmit draft of characteristics and workplan to contributing groups.– Request any needed technical and operational characteristics from contributing groups.– Request CPM text input for sections 1, 2, and 3 from contributing groups. |
| 2nd meetingNovember 2012 | – Complete review of amateur service technical and operational characteristics and develop preliminary draft new Report.– Finalize workplan.– Begin sharing studies between proposed amateur service stations and existing service stations.– Provide any feedback on modelling and characteristics from other groups.– Develop preliminary draft new Report(s) for sharing studies.– Transmit preliminary draft new Report on amateur characteristics to contributing groups for final review.– Transmit preliminary draft new Report(s) on sharing studies to contributing groups as appropriate for review.– Develop draft CPM text for sections 1, 2, and 3, considering and incorporating from contributing groups.– Transmit draft CPM text to contributing groups for review. |
| 3rd meetingSecond Quarter 2013 | – Complete amateur service technical and operational characteristics draft new report and send to Study Group 5.– Continue sharing studies, taking into account feedback from contributing groups.– Update preliminary draft new Report(s) for sharing studies as appropriate.– Develop CPM text for section 4, considering and incorporating from contributing groups.– Transmit updated preliminary draft new Report(s) on sharing studies to contributing groups as appropriate for review.– Transmit draft CPM text to contributing groups for review. |
| 4th meetingFourth Quarter 2013 | – Complete sharing studies taking into account feedback from contributing groups.– Prepare draft new Report(s) on sharing studies as appropriate.– Develop CPM text for sections 5 and 6, considering and incorporating from contributing groups.– Transmit draft new Report(s) on sharing studies to contributing groups as appropriate for final review.– Transmit draft CPM text to contributing groups for review |
| 5th meetingSecond Quarter 2014 | – Complete draft new Report(s) on sharing studies and send to Study Group 5.– Finalize CPM text, considering and incorporating from contributing groups.– Transmit draft CPM text to chapter rapporteur. |

|  |  |  |
| --- | --- | --- |
| **Contact:** | Brennan PRICE | **E-mail:** bprice@arrl.org  |