| INTERNATIONAL TELECOMMUNICATION UNION |  |  |  |
| --- | --- | --- | --- |
|  | COUNCIL |  | Document C2002/EP/3-E 5 February 2002 Original: English |
| GENEVA — SESSION 2002 — (22 APRIL - 3 MAY) |  |  |  |

Director, Telecommunication Development Bureau

ITU-D OPERATIONAL PLAN 
FOR 2002-2003

# TABLE OF CONTENTS

TABLE OF CONTENTS	2

PART 1 – INTRODUCTION	5

1.1	General	5

1.2	Structure and presentation of the Operational Plan 2002	5

1.3	Resources of the BDT for 2002	5

2.	The Strategic Plan of the ITU	6

PART 2 - THE VALLETTA ACTION PLAN	8

CHAPTER 1:  Programme of cooperation	8

1	World telecommunication development conferences	8

3	Telecommunication Development Advisory Group	8

4	Gender issues	9

5	Study groups	9

5.1	Study Group 1	9

5.2	Study Group 2	10

6	Information sharing	10

6.1	Information sharing - Publications	11

6.2	Information sharing - National databases	11

6.3	Information sharing - Workshops	11

6.4	Information sharing - Collaboration	12

7	Resource mobilization	12

8	Communication and promotion	12

CHAPTER 2:  Valletta Action Plan programmes	13

1	Reform, legislation and regulation of telecommunication	13

1.1	Studies and reports	13

1.2	Workshops/seminars	13

1.3	Regulatory library	14

1.5	Direct assistance	14

2	Technologies and global information infrastructure development and applications	15

2.1	Elaboration of guides, planning manuals and training material	15

2.2	Development of software tools/software support and provision of training courses	15

2.3	Regional seminars, symposia, workshops, etc. on new technologies	16

2.4	Pilot projects (methodological and expert assistance)	16

2.5	Technical assistance	17

2.6	Consultancy support (to United Nations and study groups)	17

3	Rural development and universal service/access	17

3.1	Multipurpose community telecentre pilot projects	17

3.2	Training	18

3.3	Website development	18

4	Finance and economics, including WTO issues, tariffs, accounting rates, etc.	19

4.1	Assistance in developing new configurations	19

4.2	Report on financial institutions	20

4.4	Assistance in setting up a mechanism for financing universal service	20

4.6	Workshops/subregional seminars/building national capabilities	20

4.8	Support to the work of ITU-T Study Group 3	21

4.9	Promotion of the application of tariffs for publicly funded services	21

5	Development partnership with the private sector	21

5.1	BDT cooperation	21

5.2	Private-sector collaboration	22

6	Capacity building through human resources development and management	22

6.1	Transfer of knowledge	22

6.2	Sharing of experience and know-how	23

6.3	Assistance	24

6.4	Dissemination of information	24

6.5	Training and human capacity building	24

6.6	The exchange of experiences and know-how	25

CHAPTER 3:  Special programme for least developed countries	25

1	Introduction of new technologies	25

2	Sector restructuring	26

3	Rural telecommunication development	26

4	Human resources development/management	26

5	Financing and tariffs	27

6	Other actions	27

CHAPTER 4:  Projects and other direct assistance	27

1	Africa	27

2	Americas	27

3	Arab States	28

4	Asia and the Pacific	28

5	Europe and CIS	28

CHAPTER 5:  TELECOM surplus programme	28

1	HRD Projects (9GLO/97/023)	28

Centre of Excellence for the Arab Region	28

Centre of Excellence for the English-speaking countries of Africa (9RAF/98/047)	29

Centre of Excellence for the French-speaking countries of Africa (9RAF/98/046)	29

Centre of Excellence for the Americas region	30

Centre of Excellence for the Asia & Pacific region (9RAS/98/014)	31

2	Infrastructure / Sector reform projects	31

INDAFTEL (9RAF/97/044)	31

Reform of telecom sector in Africa	31

7	Application of new technologies (E) – Other projects	32

Environment project for Mediterranean countries (9GLO/98/025)	32

8	Assistance to countries in special need	32

Sector reform assistance to countries in special needs	32

PART 3 - BDT OPERATION	32

1	BDT management and administration	32

2	Functioning of regional presence	33

3	Administrative services	33

4	Programming and ITU-D Members	34

5	Fellowship service	34

6	Contracts & procurement service	35

7	Field personnel service	35

8	Information systems support	36

Part 4 - Recapitulation of Resources	37

4.1	Budget resources	37

list of ABBREVIATIONS AND ACRONYMS	38

# PART 1 – INTRODUCTION

#### 1.1	General

The Operational Plan of the ITU Development Sector for 2002 is derived from the ITU strategic plan, as adopted by the 1998 Minneapolis Plenipotentiary Conference, from the Valletta Action Plan adopted by the 1998 World Telecommunication Development Conference, as well as from the 2002-2003 biennial budget approved by the 2001 session of the ITU Council.

The operational plan will be used as the basis for the effective management of the ITU-D’s activities. The operational planning process will include quarterly assessments of the progress being achieved in the various Valletta Action Plan activities. These assessments, which will be performed by using key performance indicators, will take into account both the workload placed on BDT as well as the resources available as decided by the Council.

#### 1.2	Structure and presentation of the Operational Plan 2002

The 2002 operational plan activities are grouped essentially into five chapters. Part 3 of the document provides Members States and ITU-D Sector Members with an overview of the internal management services of BDT.

The operational plan focuses on activities, products and services for which BDT has assigned the required human and financial resources to implement the Valletta Action Plan. In addition to being used as an internal management tool, the operational plan aims to clearly establish a link between the activities being carried out and the resources required for these activities, to increase the efficiency of our operations and to improve on the quality of service which our Member States and Sector Members require of us.

For each key activity, product or service, the operational plan shows the objective being pursued, the expected outcome of the activity, proposals of performance indicators and the planned resources allocated to each Programme and Subprogramme.

#### 1.3	Resources of the BDT for 2002

The 2002-2003 biennial budget of the ITU Development Sector has been approved by the 2001 session of the Council, in its Resolution 1174. The overall biennial budget of the Sector is CHF 65,882,636. The BDT budget for 2002 is CHF 33,891,139.

ITU is guided by its strategic plan (Resolution COM5/8, Minneapolis, 1998). BDT benefits in addition from the Valletta Action Plan, which is based on the goals and priorities of the strategic plan. Both plans are thus of relevance for the Operational Plan of the ITU Development Sector 2002.

#### 2.	The Strategic Plan of the ITU

The strategic plan of the ITU states the following five general goals, as well as the indicated priority areas for the Development Sector (Resolution COM5/8, Minneapolis, 1998). Under each goal the specific application to ITU-D is listed:

##### Goal 1 - Strengthen the multilateral foundations of international telecommunications

Developing new approaches to the provision of multilateral telecommunication assistance, inter alia by building partnerships for telecommunication development in priority areas, with special emphasis on telecommunication sector restructuring, regulatory reform, finance and resource mobilization, technology applications and human resources development.

Goal 2 - In addition to development of access to basic telecommunication and information services, promote global connectivity to the global information infrastructure (GII) and global participation in the global information society (GIS)

2.1	Promoting the development, expansion and operation of telecommunication networks and services, particularly in developing countries, taking into account the activities of other relevant bodies, with universal access as the objective.

2.2	Developing and/or sponsoring projects designed to connect developing countries to the GII.

2.3	Promoting the development of technology applications (e.g. tele-health, tele-education, electronic commerce, environmental protection, disaster relief) in cooperation with other international and regional organizations and NGOs.

##### Goal 3 - Coordinate international action to manage scarce telecommunication resources

3.1	Contributing to and coordinating actions between Member States and Sector Members aimed at developing human resources, especially in the associated regulatory and economic domains.

Goal 4 - Encourage and enable Member States, especially developing countries, to draw maximum benefit from technical, financial and regulatory changes in the telecommunication environment

4.1	Continuing to develop the telecommunication indicators and regulatory databases, and to add value to the information they contain through partnerships with other Sectors and organizations.

4.2	Assisting developing countries in addressing policy and regulatory issues arising from the liberalization, convergence and globalization of telecommunications, while taking account of the GATS principles inherent in the WTO basic telecommunication agreement and Reference Paper (e.g. through studies, workshops, missions and cooperative mechanisms).

4.3	Providing information about mechanisms for financing telecommunication development and assisting developing countries with the mobilization of resources for telecommunication investment.

4.4	Disseminating information about ITU-R and ITU-T activities that are of particular importance for developing countries.

Goal 5 - Improve the efficiency and effectiveness of Union structures, activities and processes

5.1	Strengthening BDT's advisory capabilities through redistribution of its resources, to respond to requests in priority areas such as international agreements and national regulation, tariffs and finance, new and convergent technologies and the feasibility stage of negotiations.

5.2	Developing its catalytic role in encouraging all actors, including global, regional and national organizations, to work together in assisting developing countries in their development and reform process as well as in their adaptation to the liberalized market.

5.3	Strengthening regional presence by increasing the decentralization of functions and authority to field offices and by strengthening the coordination functions of headquarters.

##### Priorities for the Development Sector

In addition to the above goals, the strategic plan states the following specific priorities for the Development Sector:

6.1	Respond effectively, rapidly and in a flexible way to requests for direct assistance from developing countries, including through the use of a significant part of TELECOM surplus funds, primarily for LDCs;

6.2	develop and mobilize resources for telecommunication development, including human and financial resources, technology, HRD/HRM tools and systems, information and expertise;

6.3	create partnership arrangements that benefit all parties, avoiding purely commercial approaches and concentrating on long-term benefits (as opposed to short-term gains);

6.4	promote partnership arrangements in and between the public and private sectors in both developed and developing countries;

6.5	strengthen the ITU regional presence and enhance collaboration with regional and subregional telecommunication organizations, including broadcasting organizations;

6.6	collaborate with the private sector in implementing the Valletta Action Plan, including partnerships with related entities in developing countries;

  - improve the working methods of the Sector, to strive for:

- greater use of user-friendly document exchange capabilities;

- greater participation by Sector Members and other organizations in ITU-D activities;

- the accelerated development of outputs and improvement of publication mechanisms, in particular through the wider use of information technology;

- a flexible organizational structure in the Bureau, with special attention to the training and development of BDT staff.

6.8	During the period 1999-2003, the strategic processes of the Telecommunication Development Sector should incorporate all resolutions and recommendations adopted by 
WTDC-98, as well as all other relevant resolutions and recommendations of ITU conferences.

# PART 2 - THE VALLETTA ACTION PLAN

#### CHAPTER 1:  Programme of cooperation

#### 1	World telecommunication development conferences

Purpose:

In conformity with Article 16 of the ITU Convention WTDCs shall establish work programmes and guidelines

for defining telecommunication development questions and priorities and shall provide direction and

guidance for the work programme of the Telecommunication Development Sector.

Annual objective:

- Plan, organize and conduct WTDC-02

Performance indicators:

- Meetings held as planned

- Registration form and relevant material prepared and dispatched sufficiently in advance of  meetings

- Satisfaction of participants with the organization and conduct of a meeting

- Level of satisfaction of participants expressed in conclusions and recommendations

- Expectations of participants met

- Increase of the total attendance of a meeting

- Quality and accessibility of final output

- All contributions posted electronically

Actions:

2128	World Telecommunication Development Conference  (WTDC-O2)

4829	Coordination meeting for the World Telecommunication Development Conference (WTDC-2002)

Budget in SFr:  1,443,000

#### 2	Telecommunication Development Advisory Group

Purpose:

In conformity with Nº 215 of the Convention:  to review priorities, programmes, operations, financial matters and strategies for activities in the Telecommunication Development Sector; to review progress in the implementation of the programme of work established under Nº 209 of the Convention; to provide guidelines for the work of study groups; and to recommend measures, inter alia, to foster cooperation and coordination with the Radiocommunication Sector, the Telecommunication Standardization Sector and the General Secretariat, as well as with other relevant development and financial institutions.

Annual objective:

- Plan, organize and conduct the seventh and eighth meetings of the TDAG

Performance indicators:

- Meetings held as planned

- Registration form and relevant material prepared and dispatched sufficiently in advance of meetings

- Satisfaction of participants with the organization and conduct of a meeting

- Level of satisfaction of participants expressed in conclusions and recommendations

- Expectations of participants met

- Increase of the total attendance of a meeting

- Quality and accessibility of final output

- All contributions posted electronically

Actions:

4011	Seventh meeting of the Telecommunication Development Advisory Group (TDAG)

4347	Eighth meeting of the Telecommunication Development Advisory Group (TDAG)

Budget in SFr:  170,000

#### 4	Gender issues

Purpose:

To facilitate, develop and take forward a range of activities aimed at ensuring that the benefits of telecommunications and the emerging information society are made available to all women and men on a fair and equitable basis.

Annual objectives:

- Promote gender-sensitive policy in Information and Communication Technologies (ICT) and provide capacity building that creates opportunities for women's empowerment in ICT sectors.

- Promote integration of gender perspective in telecommunications policy

- Advance initiatives for women's access to communication

Performance indicators:

  - On-going projects further developed and implemented

  - Gender issues integrated in the WTDC and Annual meeting of Task Force on Gender Issues held as

planned

- Capacity building to promote gender sensitive ICT policy carried out through BDT workshops and projects

- Gender-aware guidelines for policy-making and regulatory agencies finalized and disseminated.

Actions:

4210	Inter-Agency Meeting of Women and Gender Equality

4211	Fifth meeting of the Task Force on Gender Issues

4215	Regional workshop on ICTs for women from Central and West Africa

Budget in SFr:  100,000

#### 5	Study groups

Purpose:

In conformity with Article 17 of the ITU Convention telecommunication development study groups shall deal with specific telecommunication questions of general interest to developing countries.

##### 5.1	Study Group 1

Annual objectives:

- Study Questions and prepare Reports and Recommendations containing responses to issues raised by the

Questions.

- The  output of the studies is to be adopted in accordance with the procedures set out in the Convention

and in WTDC-02 Resolutions.

- All Reports and Recommendations should be ready and adopted preferably yearly and by September 2005

at the latest.

Performance indicators:

- Satisfaction of Study Group 1 participants as to: Publication of the output per Question in time according to the working procedures.

- Accessibility of final output by the participants.

- All contributions posted electronically.

- Good organization of meetings.

Actions:

4350	First meeting of ITU-D study group 1

4354	ITU-D Rapporteur group meeting on Question

4356	ITU-D Rapporteur group meeting on Question

4358	ITU-D Rapporteur group meeting on Question

4360	ITU-D Rapporteur group meeting on Question

4438	ITU-D Study groups regional meeting for

4440	Variable cost of documentation

4687	Consultant for final conclusions on Q9/1

4899	PTT expenses

Budget in SFr:  374,000

##### 5.2	Study Group 2

Annual objectives:

- Study Questions and prepare Reports and Recommendations containing responses to issues raised by the Questions.

- The output of the studies is to be adopted in accordance with the procedures set out in the Convention and in WTDC-02 Resolutions.

- All Reports and Recommendations should be ready and adopted preferably yearly and by September 2005 at the latest.

Performance indicators:

- Satisfaction of Study Group 2 participants as to:  Publication of the output per Question in time according to accessibility of final output by the participants.

- All contributions posted electronically.

- Good organization of meetings.

Actions:

4352	First Meeting of ITU-D study group 2

4362	ITU-D Rapporteur group meeting on Question

4364	ITU-D Rapporteur group meeting on Question

4366	ITU-D Rapporteur group meeting on Question

4368	ITU-D Rapporteur group meeting on Question

4443	ITU-D Rapporteur group meeting on

4445	PTT expenses

4447	Variable cost of documentation

4692	Consultant to finalize Fascicle 4 (Q16/2)

4933	SGs: Purchase of publications

Budget in SFr:  337,000

#### 6	Information sharing

Purpose:

To survey countries and produce world and regional reports which highlight country lessons and experience, in particular on trends in world telecommunication.

##### 6.1	Information sharing - Publications

Annual objectives:

- Produce telecommunication sector reports useful for policy makers and other key decision makers. Reports to include World Telecommunication Development Report, Yearbook of Statistics as well as regional publications. The data in the reports is the primary source of statistical information about development in the telecom industry worldwide.

Performance indicators:

- Number of copies sold/distributed.

- Number of favorable comments by industry.

- Number of citations / derivative works based on data.

Actions:

4464	Presentation of Asia-Pacific Telecom Indicators

4695	Internet presentation at Internet Society Conference

Budget in SFr:  20,000

##### 6.2	Information sharing - National databases

Annual objectives:

- Assist countries to better measure their Information and Communication Technology (ICT) sector.

- Third round of the Internet case studies, which will look at the best practice in ICT development.

Performance indicators:

- National Case Studies on Information and Communication Technology (ICT) diffusion.

Actions:

4328	 Internet case studies

Budget in SFr:  40,000

##### 6.3	Information sharing - Workshops

Annual objectives:

- Through workshops, to improve, refine and exchange experiences on the indicators used to track Information and Communication Technology around the world. Also to discuss policy and regulatory issues related to ICT development.

- Disseminate the findings of the third round of the Internet case studies.

Performance indicators:

- Create of relevant handbooks and toolkits.

- Successful workshop.

Actions:

4329	ICT case studies workshop

4465	Telecom Indicators Meeting

Budget in SFr:  80,000

##### 6.4	Information sharing - Collaboration

Annual objectives:

- Through cooperative ventures with partners (e.g., World Bank, UN, OECD, Eurostat, etc.) to enhance harmonization of ICT statistics and improve electronic dissemination (e.g., CD-ROM, Web). It also includes ventures with multilateral and bi-lateral assistance organizations and the private sector to jointly pursue national ICT assessments.

Performance indicators:

- Improved quality and availability of ICT statistics.

Actions:

4331	Collaboration with regional and international agencies on telecom statistics

Budget in SFr:  20,000

#### 7	Resource mobilization

Actions:

4372	ICT collaboration meeting with development agencies

4558	Comprehensive resource mobilization framework for 2003-2006

4563	TS - Resource mobilization for Internet Training Centers Initiative (ITCI)

4565	TS - Resource mobilization for Arab States Centre of Excellence

4567	Annual donor negotiations missions with foundations/banks/agencies - No. 1

4568	Annual donor negotiations missions with foundations/banks/agencies - No. 2

4772	Comprehensive annual report. Two parts: 1) ITU donor base, 2) TS & BDT projects and programmes

4773	Maintenance of prospect database and modern donor tracking system

4774	Publish research on new conditions of resource mobilization in BDT

4776	Annual collaboration roundtable of all sponsors and donors

4777	Annual student intern programme

4778	Annual loaned executive programme

4779	Enhancement of the resource mobilization website

4792	Gender issues in information and communications technologies

Budget in SFr:  75,500

#### 8	Communication and promotion

Annual objectives:

- Prominence and visibility for BDT's success stories

Performance indicators:

- Greater awareness of ITU-D programmes, successes and partnership opportunities

Actions:

4940	Interpretive website of digital divide initiatives and enhancement of BDT website

4941	Matchmakers' service on the website for buyer-seller meetings and trade missions

4942	Two-day press retreat tied to ITU Telecom Asia to conscientize them to development issues

4943	Regionalized press kits and promotion at World Summit on Sustainable Development

Budget in SFr:  130,000

#### CHAPTER 2:  Valletta Action Plan programmes

#### 1	Reform, legislation and regulation of telecommunication

Purpose:

- To assist governments in the preparation and implementation of reform and in developing the structure and financing of the regulatory bodies and to assist in training, licensing, staffing needs and overall management, taking into account the WTO reference paper.

##### 1.1	Studies and reports

Annual objectives:

- Develop best practices and models to inform the membership about matters of reform, legislation, and regulation of telecommunications.

- Publish world-class, in-depth analytical reports on the state of regulation of the information and communications technology (ICT) industry and case studies on how regulators are handling selected issues.

Performance indicators:

- Work completed as planned

- Number of copies sold/distributed (paper/Web)

- Number press citations

- Number of citations in other publications

- Number of repeat customers

- Reports and studies used as training material

Actions:

4238	Trends in Telecommunication Reform 2003

4239	Three (3) case studies in telecommunication regulation

4607	Regulatory environment study for Central America

4608	Case study for Central America with the Inter-American Development Bank (IADB)

4670	Visiting regulators programme

4848	Updating of the Arab Book

Budget in SFr:  298,000

##### 1.2	Workshops/seminars

Annual objectives:

- Provide venues in which national policy-makers; regulatory authorities and regional regulatory organizations can discuss key issues and, where relevant, obtain input from those to be regulated.

- Organize a series of symposia/seminars for regulators in order to provide a forum for the exchange of opinions, views and experiences among countries on specific areas/concerns in regulation.

- Continue to provide a global forum for regulators (Global Symposium for Regulators) to discuss key issues affecting regulators.

Performance indicators:

- Meetings held as planned

- Registration form and relevant material prepared and dispatched sufficiently in advance of meetings

- Satisfaction of participants with the organization and conduct of a meeting

- Level of satisfaction of participants expressed in conclusions and recommendations

- Expectations of participants met based on an evaluation form

- Increase/decrease of the total attendance of a meeting

- Timely delivery of final output

- All contributions posted electronically

Actions:

4279	Global Regulatory Symposium

4282	African Regulatory Forum

4284	Americas Regulatory Forum in partnership with CITEL/TIA

4503	Ninth Subregional Telecom Meeting for Cambodia, Lao PDR and Vietnam

4504	Seminar on competition and regulation of ICT for ASP

4613	ITU/Caribbean Regulatory Forum

4676	Universal Access and Services Seminar

4847	Support to regional regulatory association - WATRA

4860	Support to regional regulatory association - REGULATEL

Budget in SFr:  571,000

##### 1.3	Regulatory library

Annual objectives:

- Develop and maintain an up-to-date reference center for national, regional, and international ICT regulations and policies.

- Collect and collate national telecommunication policies and regulations through the dissemination of the ITU/BDT annual regulatory survey, tailored annually to pressing issues.

- Enhance the ITU/BDT World Regulatory Database; to maintain and expand the TREG Web site to include key regulatory information and other resources.

- Enhance the Global Regulators Exchange following the decisions of the 2001 Global Symposium for Regulators.

Performance indicators:

- Number of web site hits

- Feedback from customers

- Respond to requests for information in a timely manner

- Information kept up-to-date

- Relevant topics for regulators covered

- Information on SRU activities posted

Actions:

4288	Regulatory survey 2002

4289	Enhancement and maintenance of ITU World Telecommunication Regulatory Database and T-REG

website.

4290	Regulatory hotline / Global Regulators Exchange (G-REX)

Budget in SFr:  155,000

##### 1.5	Direct assistance

Annual objectives:

- Completion of assistance projects underway (West Africa, Oman, Mali, Lebanon).

- Initiate new projects depending on requests and availability of resources.

Performance indicators:

- Respond to requests in a timely manner.

- Number of requests met.

- Satisfaction of recipient countries/entities.

Actions:

4862	Study on economic regulation topics

4863	Study on revision of telecommunication law to take into account aspects of convergence

4904	Licensing and fee structure for Pakistan

4923	Assistance to Guinea-Bissau in definition of a numbering plan

Budget in SFr:  75,500

#### 2	Technologies and global information infrastructure development and applications

Purpose:

To assist developing countries to plan, build, operate, upgrade, manage and maintain technologies applicable in their networks and services. Particular attention should be given to resource mobilization.

##### 2.1	Elaboration of guides, planning manuals and training material

Annual objectives:

- Develop upgrade network planning tools and manuals for applications

Performance indicators:

- Regular update, completion and dissemination as planned

Actions:

4536	Development of PLANITU software for GSM and IP based applications

4585	Study on interactive TV broadcasting

4682	E-governance for Bulgaria

4766	Handbooks on IP telephony (follow-up to WTPF 2001 - Opinion D)

4910	Manual on telemedicine

Budget in SFr:  140,000

##### 2.2	Development of software tools/software support and provision of training courses

Annual objectives:

- Enhance local know-how of Internet Protocol, e-services and PLANITU.

- Enhance and update the Windows based Basic Automated Spectrum Management System (WinBASMS)

Performance indicators:

- Regular update of software tools

- Foster transfer of know-how at local level

Actions:

4152	WinBASMS enhancement and update

4485	Database and website maintenance

4544	Establishment of an administrative and accounting computer system for the CMTL SA activities

4625	Development of a database with CITEL

4767	IP and e-services workshop for all countries

4833	New PLANITU features and capabilities: training course for English and French speaking African

countries

4834	New PLANITU features and capabilities: training course for Asia Pacific Region

Budget in SFr:  412,000

##### 2.3	Regional seminars, symposia, workshops, etc. on new technologies

Annual objectives:

- Extend the geographical scope and scale of e-services and IP related activities

- Foster technology know-how transfer

Performance indicators:

- Meetings held as planned.

- Level of satisfaction of participants expressed in conclusions and recommendations.

- All contributions made available electronically.

Actions:

4228	WTPF2001: IP Telephony and Internet workshop for Arab States Region

4486	Regional seminar on e-business

4496	Improving efficiency of routing inter- & intra-regional Internet traffic (ASP)

4528	Frequency planning for digital terrestrial TV broadcasting (ITU/AIBD workshop)

4575	Technical training in IP, Internet and mobile networks

4576	Subregional workshop on ICT for African French and English speaking countries

4583	Symposium on transition to digital broadcasting

4683	E-Commerce, e-Commerce centres (regional)

4684	IP Telephony and Internet

4685	Third generation of mobile systems

4799	Next Generation Network (NGN)

4837	Central American telehealth project evaluation

4898	Workshop on maritime radiocommunications for the Gulf of Mexico, Caribbean and Central Americas

region

4909	Subregional seminar on digital TV broadcasting for Central America and Caribbean

Budget in SFr:  673,500

##### 2.4	Pilot projects (methodological and expert assistance)

Annual objectives:

- Enhance  deployment of new technologies, services and applications

Performance indicators:

- Projects progress in line with their objectives.

Actions:

4498	Setting up a pilot hybrid PSTN/IP network for Nepal

4642	Telemedicine project for Cameroon

4761	Interim management of the depository of the Worlde Trust MoU

4800	Expertise in the areas of IP and e-strategies

Budget in SFr:  376,000

##### 2.5	Technical assistance

Annual objectives:

- Assist, provide guidance and advice to developing countries in identified domaines

Performance indicators:

- Satisfaction of beneficiary countries.

Actions:

4502	Broadcasting frequency master plan for Indonesia

4546	Assistance for the purchase and the installation of equipment for the CMTL SA laboratories and

workshops

4617	Electronic commerce - Technical assistance for ASETA

4637	Assistance to Guinea on frequency management

4643	Feasibility study for the service of the rural areas in Equatorial Guinea

4644	Assistance in spectrum management in Burundi, Congo, Equatorial Guinea

4645	Evaluation of GAM/97/005 Project

4646	Assistance to Ghana reg. body in national MIS

4647	Assistance to Guinea Bissau for the opening of a new international link

4648	Assistance to Nitel for implementation of Maydugury-Koussery-Ndjamena link

4835	Technical assistance/seminar on new networks and services

4836	Strategies and guidelines for sustainable e-services using PKI

4901	Technical assistance - Universal Access Programme

4902	Technical assistance - environnment

4903	Technical assistance - maritime radiocommunications

Budget in SFr:  297,000

##### 2.6	Consultancy support (to United Nations and study groups)

Actions:

4569	Assistance to Africa region in ICT in partnership with other development partners

Budget in SFr:  60,000

#### 3	Rural development and universal service/access

Purpose:

To promote universal access, not only to basic telecommunications, but also to broadcasting and to value-added services and, in particular, the Internet, as tools for development. Priority will be given to continuing support to the ongoing programme of rural multi-purpose community telecentre (MCT) pilot projects, started by the BAAP Programme Nº 9 and the Spacecom project.

##### 3.1	Multipurpose community telecentre pilot projects

Annual objectives:

- Completion of pilot projects currently underway. Disseminate evaluation results. In keeping with the objectives laid down in the VAP Programme 3, initiate new projects following different organizational and implementation models. The projects will consist of a number of telecentres involving operation by franchises, community cooperatives, privately run small businesses, and government service centres (e.g. attached to a school, post office or library). The projects also involve a number of partners, both international and national and public and private.

Performance indicators:

- Mobilization of partners  with cash and in-kind contributions;

- Completion of the project document;

- Implementation of the project on the schedule;

- Recruitment of experts and purchase of equipment completed;

- Evaluation of the project.

Actions:

3868	Network of MCTs in Myanmar

3870	Network of MCTs in East Timor

4046	MCT for a refugee community

4376	Symposium and publication of evaluation of telecentre pilot projects

4538	Multipurpose Community Telecentre, Rajkot, India

4605	Technological developments on e-culture for rural areas

4614	IADB/CITEL/ITU initiative for rural access Puebla Panama - training

4615	Assistance in developing MCT's

4616	Training on telecentre operations/use for North Korea

4650	Policies for promoting universal access (ITU-CIDA MoU)

4652	Telecentres for peacekeeping and conflict resolution

4664	MCT and e-commerce project

4805	ITU-UPU collaboration on establishing telecentres in post offices in  Bhutan

4806	Network of telecentres at Ngara, K9 and Lukole Refugee Camps, Tanzania

4828	Establishment of a network of Multipurpose Community Telecentres in Madagascar

4840	Network of telecentres for women in Niger

Budget in SFr:  591,000

##### 3.2	Training

Annual objectives:

- Publication of case studies on universal access models and training on new technologies for rural applications.

Performance indicators:

- Publication of the case studies

- Identification and mobilization of training resources including experts (gratis)

- Implementation of the programme to the satisfaction of the participants.

Actions:

4374	Publication of case studies on universal access models

4679	New technologies for rural applications (Regional)

Budget in SFr:  70,500

##### 3.3	Website development

Annual objectives:

- Continued maintenance and development of the website as a major vehicle for dissemination of information on aspects related to universal access.

Performance indicators:

Actions:

4375	Maintenance of existing website and its further development.

Budget in SFr:  25,000

#### 4	Finance and economics, including WTO issues, tariffs, accounting rates, etc.

Purpose:

To help the developing countries, and in particular the LDCs, to adapt to the new telecommunication

environment by the putting into place of appropriate financial policies.

##### 4.1	Assistance in developing new configurations

Annual objectives:

- Assist developing countries in developing new configurations especially in financial aspects related to:

IP-based service provision; elasticity of supply and demand applied to developing countries; the utilization of cost & tariffs models in the framework of commercial and regulatory issues for the development of telecommunication business plans; WTO agreements related to the impact of the technological and commercial evolution of the telecom market.

Performance indicators:

- Results published as planned.

- Update and maintenance of FSU databases and website on a continuous basis.

Actions:

3787	Development of cost and tariff calculation tools on the basis of existing ITU regional models

4332	Usage of Cost Model (Cost of services, tariff regulation, competitivity and development of a

telecommunication company)

4333	Financial management and value of financial assets of telecom companies in a competitive

environment

4334	Elasticity of demand/price in a competitive environment

4335	IP based networks: pricing of  telecommunication services

4336	Evaluation of the GATS and of WTO reference paper related to the evolution of technology (IP

protocol, mobility, etc.)

4337	Survey on implementation of GATS issues

4338	Database on tariffs and traffic

4341	Regional expert group meeting on TAL cost model

4519	Costing and pricing of interconnection (Thailand)

4540	Follow up database on tariff policies

4541	Follow up of the initiative for financing telecommunication development

4628	Spectrum economic aspects (direct assistance)

4631	Direct assistance in tariffs

4632	Telecommunication annex revision  (direct assistance)

Budget in SFr:  377,000

##### 4.2	Report on financial institutions

Annual objectives:

- Provide countries with information on financial institutions and private sources for financing and investment in telecommunications development, information on pricing and telecommunications service market needs.

Performance indicators:

- Results published as planned and presented to the WTDC.

- Update and maintenance of the financial institutions and private fund sources information on a continuous basis.

Actions:

3918	Macroeconomic study on financing telecommunication development

##### 4.4	Assistance in setting up a mechanism for financing universal service

Annual objectives:

- Direct assistance and advice on financing strategies to the telecommunication administrations, Sector Members and the private sector, especially in pricing telecommunication services including interconnection and taking into account universal service obligations.  Implementation and follow up of the agreements of the World/Regional Telecommunications Conferences on trade of telecommunication services.

Performance indicators:

- Successful planning and execution of the assistance.

- Satisfaction of recipient countries.

Actions:

4630	Socio-economic indicators for universal access programmes  (direct assistance)

4634	Assistance issues in costing/financing (Caribbean countries)

Budget in SFr:  58,000

##### 4.6	Workshops/subregional seminars/building national capabilities

Annual objectives:

- Build national capabilities in cost calculation, tariff policies and frequency spectrum pricing throughout a series of workshops and seminars.

Performance indicators:

- Number of seminars and workshops held as planned.

- Number of participant countries.

- Satisfaction of participants expressed in conclusions and recommendations.

- Effective planning and organization of seminars and workshops.

- All contributions and results posted electronically.

Actions:

4342	Training workshop on the software of cost and tariffs calculations TAF model for French speaking

African countries

4343	Training workshop on the software of cost and tariffs calculations TAF model for English speaking

African countries

4633	Caribbean workshop on costing/interconnection

4677	Seminar on ITU Pricing Models

Budget in SFr:  138,000

##### 4.8	Support to the work of ITU-T Study Group 3

Annual objectives:

- Give the necessary support to Study Group 1 related to Questions 11/1 and 12/1, and co-organize regional seminars together with the regional meetings of tariff groups.

Performance indicators:

- Effective organization/participation of one seminar for each Tariff Groups (TAF, TAL, TAS).

- Regularity on the follow up of the work of the Study Groups, WTSA and WTDC.

Actions:

4344	Regional seminar on costs and tariffs for TAF Group

Budget in SFr:  86,000

##### 4.9	Promotion of the application of tariffs for publicly funded services

Performance indicators:

- Successful planning and execution of the assistance.

- Satisfaction of recipient country.

Actions:

4533	Technical assistance to Angola Telecom- restructure international services

Budget in SFr:  33,500

#### 5	Development partnership with the private sector

Purpose:

To promote various types of partnership arrangements with the private sector in activities related to

telecommunication development.

##### 5.1	BDT cooperation

Annual objectives:

- Encourage participation by new Sector Members in ITU-D

- Develop tools to promote partnerships and business opportunities with telecommunication entities in developing countries and in particular with LDCs

- Improve understanding between developing countries and the private sector

Performance indicators:

- Satisfaction of countries in region.

- "Market-quality" product useful to members."

- Quality of work-based documents, and number of copies sold.

- Description	- Result

- Quality of work-based documents, and number of copies sold.

Actions:

4241	Development and maintenance of specific databases  (operators, business associations)

4247	Participation in industry-led events

4249	Promotion of partnership opportunities and strategic alliances

4283	Development and implementation of a comprehensive strategy to attract new ITU-D Sector Members

4653	Private sector assessment study in Africa

Budget in SFr:  134,000

##### 5.2	Private-sector collaboration

Annual objectives:

- Give private sector a voice in ITU-D programs and projects

Performance indicators:

- Building new private sector partnership

- Satisfaction of participants in the TDAG Subgroup meetings

- Meeting with private sector held as planned in every region

Actions:

4254	Development of  business oriented partnership models and methods

4297	Seventh meeting of the TDAG Subgroup dealing with private sector issues, to prepare WTDC-02

4597	ICT Seminar for Telecom Industry Associations in ASP

4598	Private Sector Cooperation Meeting in the Arab Region

4602	Meeting with CITEL/TIA

4755	Eighth meeting of the TDAG subgroup dealing with private sector issues

Budget in SFr:  125,000

#### 6	Capacity building through human resources development and management

Purpose:

To assist developing countries in building institutional and organizational capacity through human resources

management and development and organizational development activities.

##### 6.1	Transfer of knowledge

Annual objectives:

- Provide high-level training in key areas for telecommunication management development with special emphasis on new managerial challenges such as: management skills in a competitive environment, managing the sector’s reform, introduction of new services, marketing and customer orientation, through face-to-face and distance-learning seminars/workshops, and development of new training material and case studies.

- Strengthen national and regional training centers to cope with new technologies, by using and demonstrating modern training techniques such as distance learning and web-assisted training, so as to increase effectiveness and reduce costs.

Performance indicators:

- 80% of the actions implemented on time

- at least 250 people trained

- at least 3 new courses produced

- at least 20 training sessions organized

- 80% of the participants satisfied with the organized activities

Actions:

4256	Regional workshop on "Reengineering Telecommunication Organizations" for English speaking

African countries

4259	Regional workshop on business planning for Latin America

4261	Regional workshop on "Reengineering of Telecommunication Organizations" for Latin America

4262	Distance seminar on e-learning for the Arab Region (on-line course + 1 week face-to-face)

4264	Regional workshop on "Reengineering Telecommunication Organizations" for the Asia-Pacific Region

4266	Distance seminar on e-learning for the Asia-Pacific Region (on-line course + 1 week face-to-face)

4270	Training agreement with Cable & Wireless Virtual Academy

4271	Training agreement with TEMIC (Telecommunication Executive Management Institute)

4272	Training agreement with United Kingdom Training Academy (UKTA)

4273	Training agreement with AICEP

4274	Training agreement with Malta College International

4275	Training agreement with Telia

4276	Training agreement with Thunderbird University

4278	Development and preparation of training material

4280	Re-packaging of materials to be used at distance

4281	Delivery of distance learning courses

4301	Update the Training Development Guidelines to reflect e-learning

4304	Distance seminar on telecommunications regulation for Latin America

4305	Distance seminar on telecommunication regulation for the Caribbean sub-region

4308	Distance seminar on IP Telephony for Latin America

4552	Regional workshop on marketing for Anglophone Africa

4669	Regional workshop on restructuring the telecommunication sector for CIS countries

4838	Training agreement with Korean Universities

4839	Training agreement with the Arab Academy for Science and Technology

4949	Training agreement with USTTI

Budget in SFr:  673,000

##### 6.2	Sharing of experience and know-how

Annual objectives:

- Facilitate the sharing of experience and know-how through regional and interregional HMR/D meetings, electronic discussions, the program of technical cooperation among developing countries (TCDC) and joint activities with regional organizations and other United Nations agencies.

Performance indicators:

- 80% of the actions implemented on time

- at least 3 regional and/or interregional meetings organized

- 80% of the participants satisfied with the organized activities

Actions:

4295	Regional HRM/D meeting for Anglophone Africa

4298	Regional HRM/D meeting for Francophone Africa

4302	Implementation of a web-based Human Resources benchmarking system for Francophone Africa

4303	HRM/D network annual meeting for the Arab Region

4681	Regional meeting on the use of Information and Communication Technologies in education for Latin

America

4714	Regional symposium on training and human resources for the Caribbean region

Budget in SFr:  148,500

##### 6.3	Assistance

Annual objectives:

- Provide direct assistance to countries in the fields of HRM and HRD, mainly through the implementation of short missions focused on specific subjects such as: training needs analysis, feasibility studies, drafting of project documents, as well as the use of models, guidelines and tools for practical applications. Also, to help in the identification of funding sources for the proposed projects and to provide professional support for their implementation.

Performance indicators:

- 85% of the approved direct assistance actions implemented

- 90% of the beneficiary countries satisfied with the assistance provided

Actions:

4322	Establishing an e-learning facility: direct assistance to selected countries in Anglophone Africa

4323	Establishing an e-learning facility: direct assistance to selected countries in francophone Africa

4324	Establishing an e-learning facility: direct assistance to selected countries in the Asia-Pacific Region

4553	Direct assistance to Zimbabwe in establishing an HRD plan for the Regulator

4554	Direct assistance to Angola in Human Resources Development

4555	Direct assistance to newly established regulators in developing an HR function

4657	Workshop on training management for SOCATEL (Central African Republic)

Budget in SFr:  73,000

##### 6.4	Dissemination of information

Annual objectives:

- Disseminate pertinent HRM/D information including: training opportunities, training materials and case studies, best practices and the directory of training centers, through the web and periodic publications such as the Human Resource Development Quarterly.

Performance indicators:

- Publication of 4 new issues of the HRD Quarterly

- All databases on training resources/opportunities up to date

- 90% of the requests for information answered in a timely manner

Actions:

4309	Publication of the HUMAN RESOURCES DEVELOPMENT QUARTERLY (HRDQ)

4310	Training resources data bases in the Virtual Training Center (on the web)

4311	Publication of guidelines, manuals and/or training material for workshops

##### 6.5	Training and human capacity building

Annual objectives:

- Strengthen the Centres of Excellence and GTU/GTTI mechanisms in order to help consolidate a network of institutions capable of providing senior government officials and executive level managers with high-quality training in areas such as:  telecommunication policies and regulation, restructuring of telecommunication organizations, spectrum management, network harmonization, business planning and corporate management.

Performance indicators:

- Work plan for each of the 5 Centers of Excellence and the GTU/GTTI established

- 80% of each project's work plan implemented on time

Actions:

4312	GTU/GTTI project for distance training and education

4313	Center of Excellence for the Arab Region

4314	Center of Excellence for the English-speaking countries of Africa

4315	Center of Excellence for the French-speaking countries of Africa

4316	Center of Excellence for the Americas Region

4317	Center of Excellence for the Asia-Pacific Region

4667	Regional workshop on interconnection of telecommunication networks for CEE

4668	Regional workshop on strategic management for CEE

Budget in SFr:  78,000

##### 6.6	The exchange of experiences and know-how

Annual objectives:

- Organize electronic forums on priority topics.

- Support the activities of the ITU-D Study Groups by developing case studies and training materials according to their needs.

- Upgrade the VTC through the addition of an e-learning platform and the development of a new Learning Management System.

Performance indicators:

- At least 2 electronic fora organized

- At least 2 case studies developed for the ITU-D Study Groups

- New e-learning platform operational

Actions:

4318	Electronic discussion fora or web-based round tables

4319	Development of case studies on human resources

4320	Development of an e-learning lab

4321	Publication of special reports to share experiences and know-how

Budget in SFr:  30,000

#### CHAPTER 3:  Special programme for least developed countries

#### 1	Introduction of new technologies

Annual objectives:

- Help countries to modernize their networks and introduce the most appropriate technologies in order to implement universal access and entry to Global Information Infrastructure

Performance indicators:

- Experts recruited in time as required by project objectives

- Experts responding to request in a timely manner

Actions:

4508	A strategy for migrating to new technologies, Bhutan

4517	Assistance to Mali for drafting interconnection guide in the framework of ICTs

4548	A proposal for the Malawi Communication Regulatory Authority's (MACRA's)  new numbering Plan for Malawi

4718	Direct Assistance to Haiti in the Introduction of new technologies

4842	Assistance to Djibouti in the introduction of new technologies

Budget in SFr:  212,500

#### 2	Sector restructuring

Annual objectives:

- Facilitate telecommunication sector reform in LDCs according to each country's special needs.

Performance indicators:

- Experts recruited in time and responding to requests in time

Actions:

4550	Assessment of the Communication Authority of Zambia (CAZ) needs both technical and human

resource

4639	Assistance to Central African Republic in implementing the sector reform

4719	Strengthening of regulatory body

4843	Assistance to Djibouti in sector restructuring

Budget in SFr:  275,000

#### 3	Rural telecommunication development

Annual objectives:

- Enhance universal access to telecommunication services in rural and remote areas under sustainable conditions including appropriate financing and tariff structures.

Performance indicators:

- 85% of actions implemented in time

Actions:

4721	Assistance in the establishment of MCTs

4844	Assistance to Djibouti in rural telecommunication development

Budget in SFr:  55,000

#### 4	Human resources development/management

Annual objectives:

- Expectations of participants met and responding to requests in a timely manner. All requirements for implementation of fellowships processed within deadlines

- Capacity building, particularly in the areas of network management, tariffs and billing.

Performance indicators:

- 90% of actions implemented on time and responding in time to requests

- Respond to requests in a timely manner and experts recruited in time

Actions:

4489	Assistance to Djibouti in HRD/M

4509	Technical support to Telecommunication Kiribati System

4547	Training of MACRA staff both on job and abroad

4551	On job training and fellowship for training abroad.

Budget in SFr:  225,000

#### 5	Financing and tariffs

Annual objectives:

- Create a self-sustaining economic basis for the telecommunication operator(s).

- "Market-quality" product useful to potential development partners and responding to requests in a timely manner.

Performance indicators:

- 85% of actions implemented on time and responding in to requests

Actions:

4518	Assistance to LDCs in fund raising

4846	Assistance to Djibouti in finance and tariffs

Budget in SFr:  135,000

#### 6	Other actions

Annual objectives:

- Enhance further capacity building through seminars/workshops and fellowships programmes and other activities.

Performance indicators:

- Respond to requests in a timely manner and experts recruited in time

- Respond to request in a timely manner and ensuring 90% of actions are implemented

Actions:

4510	Development of a Master Plan for Broadcasting, Bhutan

4542	Spectrum audit consultancy in Malawi

4543	FM Frequency Band Plan in Malawi

4845	Assistance to Djibouti in other actions (development of international telecommunications)

Budget in SFr:  137,000

#### CHAPTER 4:  Projects and other direct assistance

#### 1	Africa

Actions:

4595	Ad-hoc assistance

4935	Ad-hoc assistance in shipment of donated computers

Budget in SFr:  200,000

#### 2	Americas

Actions:

4476	Assistance to project 9-ARG/98-008, subcontract, analyze situation of 1400 CTC installed under

project 9-ARG/98/008.

4686	Ad-hoc assistance to countries and support for the implementation of projects

4897	Assistance to project 9-BRA/98/006-6 : Invitation to tender on "Brazilian Satellite

Telecommunications Market".

Budget in SFr:  291,000

#### 3	Arab States

Actions:

4896	Consultant in telecommunications training

4922	Expert in planning of rural telecom for the Yemeni Public Telecommunication Corporation, Sana'a

4929	Direct assistance to Arab States

Budget in SFr:  180,000

#### 4	Asia and the Pacific

Actions:

4073	Cooperation agreement with Information & Communication University (ICU), Republic of Korea

4599	ASP projects and other direct assistance

Budget in SFr:  180,000

#### 5	Europe and CIS

Actions:

4663	Direct assistance EUR and CIS

Budget in SFr:  180,000

#### CHAPTER 5:  TELECOM surplus programme

#### 1	HRD Projects (9GLO/97/023)

##### Centre of Excellence for the Arab Region

Actions:

4384	Regulatory issues workshop: fundamentals

4408	Centre of excellence programme coordinator recruitment

4780	Implementation of a CoE Web server + basic distance learning plateform

4781	Virtual forum on business drivers and data collection

4782	Workshop on international standards on ICT issues

4783	Workshop on benchmarking practices for market segmentation

4784	Workshop on telecom sector reform

4785	Extraordinary steering committee meeting

4786	Second workshop on regulatory issues

4787	Workshop on new technologies - last mile connection

4788	Workshop on rural connectivity

4789	Workshop on international standards in telecom policies

4790	3rd steering committee meeting

4857	Short-term contract for the centre of excellence programme coordinator

##### Centre of Excellence for the English-speaking countries of Africa (9RAF/98/047)

Actions:

4859	PLANITU workshop

4868	Business planning workshop

4869	Policy and regulatory issues workshop: competition policy

4870	Policy and regulatory issues workshop: Introduction

4871	Business management workshop:  corporate use of financial models

4872	Rural connectivity workshop: 1st workshop

4873	Universal access workshop: regulatory issues

4874	Technology awareness workshop: GSM mobile telephony

4875	Advanced spectrum management workshop(for operators)

4877	Business management workshop: interconnection scenario

4878	Policy and regulatory issues workshop: interconnection

4884	Spectrum management workshop: train-the-trainer

4885	Business management workshop: financial impact of liberalization

4887	Spectrum management workshop: regional mobile role-out

4888	Spectrum management workshop: regional mobile role-out

4889	Spectrum management workshop: regional mobile role-out

4891	Virtual forum on spectrum management issues

4962	Launch of AFRALTI as centre of excellence

4963	Finalize development of universal access and rural connectivity course modules

4964	Web-based spectrum management information exchange

4965	Spectrum management workshop: train-the-trainer follow-up programme

4966	Activity based costing (ABC) workshop

##### Centre of Excellence for the French-speaking countries of Africa (9RAF/98/046)

Actions:

4807	Support to research and development programme

4808	ENPT visit for the network implementation programme

4809	Support to the consultation programme

4810	Audit of the integration of the ESMT management tools

4811	Creation of Web pages for the centre of excellence

4812	ISO certification

4813	Training the trainer on distance learning issues

4814	Training for trainers to the spectrocan AFSM software for spectrum management

4815	Training to reinforce the marketing service

4816	Complementary educational and technical training

4817	Training to master Hélisa and other ESMT management tools

4818	Duplication of management certificate

4819	Design and implementation of a telecommunication business management certificate

4820	Regional workshop on e-commerce

4821	Forum on mobile and cellular radiocommunications

4822	Forum RURALCOM

4823	Workshop on spectrum management economical issues

4824	Workshop on spectrum management automation

4825	Mastering the advanced spectrum management tool (spectrocan)

4826	Business management workshop on economical aspects of interconnection

4827	Business management workshop on revenue and marketing forecasts

4831	Business management workshop on the implementation of activity based costing and assessment of

production process

4832	Technology awareness workshop (telecom overview)

4861	Regulatory issues programme: course development on regulation and sector evolution

4864	Regulatory issues programme: course development on tariff regulation and competition improvement

4865	Regulatory issues programme: course adaptation on licensing issues

4881	Technology awareness workshop (GSM presentation: piconode)

4882	Regional technology awareness seminar on IP V6

4883	UA/RC: workshop on universal access and rural connectivity (fundamentals)

4892	Workshop on spectrum management supervision

4893	Regulatory issues programme: course adaptation on interconnection

4894	UA/RC: workshop on universal access and rural connectivity development policies

4895	UA/RC: workshop on ICT impact on development

4930	20ème session du Conseil d'Administration de l'ESMT

4936	UA/RC: workshop on universal access and rural connectivity (fundamentals)

4937	Business management workshop on economical aspects of interconnection

4939	Workshop on spectrum management automation

##### Centre of Excellence for the Americas region

Actions:

4944	Pilot programme on telecommunications policies and regulatory issues

4945	On line course on optical telecommunication technology and normative aspects

4946	On-line course on corporate management  (first part)

4947	On line course on public network security (technical issues)

4948	On line course on business/strategic planning

4950	On line course on regulation and deregulation of new services

4951	On line course on optical networks engineering

4952	On line course on spectrum management

4953	On line course on designing  telecommunications corporate services

4954	On line course on intelligent network management

4955	On line course on ICT technical issues

4956	On line course on the regulation of the  telecommunications business

4957	CITEL annual meeting

4958	Workshop on corporate management  (second part)

4959	Human resources and training meeting for the Caribbean region

4968	Workshop on public network security (management and strategies issues)

4969	CoE sub-regional meeting

4970	CoE sub-regional meeting

##### Centre of Excellence for the Asia & Pacific region (9RAS/98/014)

Actions:

4791	Policy and regulation training programme - Philippines

4793	Policy and regulation training programme - Laos, Cambodia and Vietnam

4795	Policy and regulation training programme -  in a 5th country

4798	Waseda university workshop on new technology for regulators

4801	Edupac training on IT literacy for senior managers

4802	Re-engineering the Telco based on one country

4867	Development of training materials in broadcasting in association with ABU/AIBD

4911	Fifth centre of excellence steering committee meeting

4912	Sixth centre of excellence steering committee meeting

4913	Modules for training based on Thailand experience

4914	Materials for training based on telecom research project (TRP) Hong Kong SAR China experience

4915	Policy and regulation training - round table meeting for LDCs in ASP

4916	Modules for training based on Thailand policy and regulation training course

4917	Modules for training based on ACA experience

4921	Modules for training based on OFTA experience

#### 2	Infrastructure / Sector reform projects

##### INDAFTEL (9RAF/97/044)

Actions:

4925	Telecom industry study

4926	Mobilization of partners

4927	Project partnership meeting

##### Reform of telecom sector in Africa

Actions:

4708	Assessment of the telecommunication reforms in Africa Region

4854	Study of the structure and operations of a Committee of national regulators within UEMOA

#### 7	Application of new technologies (E) – Other projects

##### Environment project for Mediterranean countries (9GLO/98/025)

Actions:

4967	Establishment of satellite-based network for the remote monitoring of seawater quality

#### 8	Assistance to countries in special need

##### Sector reform assistance to countries in special needs

Actions:

4735	Workshop to launch the programme for all the countries in special need (total of 6 countries)

4736	Assistance towards the privatization of ONATEL, Burundi

4737	Strengthening the regulatory authority ARCT Burundi

4738	Assistance to the public operator

4741	Sector reform assistance to Liberia, legal framework

4742	Sector reform assistance, spectrum monitoring and universal access

4743	Assistance to Liberia in interconnection rules

4745	Drafting of a telecom development master plan towards a universal access in Rwanda

4747	Feasibility study and project document on the implementation of MCT's in Rwanda

4748	Assistance to Rwanda towards the establishment of a regulatory authority

4749	Preparation of terms of reference and project document related to the accounting processes for

Rwandatel

4750	Assistance to Rwanda on interconnection

4751	Feasibility study on the implementation of a telemedicine project in Rwanda

4754	Preparation of project document for technical assistance for Rwanda television

4757	Assistance in drafting the telecoms act and privatization of Sierratel

4758	Assistance in preparing interconnection rules  and spectrum management

4760	Assistance to Somalia in spectrum management training

# PART 3 - BDT OPERATION

#### 1	BDT management and administration

Annual objectives:

- Efficient planning and management of BDT resources

- Effective internal and external communications

- Support to ITU-D conferences and meetings

Performance indicators:

- All policies and regulations applied

- Good working climate

- All resources used efficiently

- High opinion of BDT among Member States and Sector Members

- Operational plan for 2003 (as a continuation of OP-2002) ready in time and approved

Actions:

2609	Presenting policy and strategy proposals to ITU conferences and meetings

2615	Implementation of policies decided by ITU conferences and Council

2616	Preparation, management and evaluation of the operational plan implementation

2617	Supervision, monitoring and support of field offices

2618	Representing the BDT in meetings

2619	Reporting to Council

#### 2	Functioning of regional presence

Annual objectives:

- Maximize the benefits of regional presence for the Union's membership

- Strengthen the visibility of the Field Offices

Performance indicators:

- Implementation of the regional operation plans and projects

- Proper and timely presentation of inputs for the OP-2003; prioritization of activities and direct assistance

- Percentage of countries visited; number of administrations, regulators etc. met; number of agreements signed

Actions:

3295	Close liaison with telecommunication administrations/regulators/operators/other enterprises and

regional organizations

3296	Analyzing the telecommunication development needs

3297	Broadening of the information dissemination functions of the regional presence

3298	Maintaining close liaison and cooperation with the other Sectors and the General Secretariat of the

ITU

3301	Participation of representatives of the Regional/Area Offices in important ITU/BDT events (PP, WTDC,

Council, TDAG and Study Group meetings etc.)

3302	Assistance to ISS Department to provision of modern logistic equipment and connectivity for the

Field Offices according to a separate plan

#### 3	Administrative services

Annual Objectives:

- Establishment of ITU-D budget and financial plan, budget control and cost analysis for products and services/activities with a view to optimizing resources and improving internal control.

- Establishment and control of budgets for projects (UNDP,  FIT, TELECOM Surplus, voluntary contributions).

- Provision of financial statements and analyses on various ITU-D activities to enable Director to take rapid decisions and establish appropriate priorities.

- Establishment and periodic review of ITU-D activities, evaluation of the relevance and efficiency of operational processes linked to budgets and proposition of appropriate modifications. Examination of the quality of operational methods and procedures and provision of proposals for optimization.

- Control and follow-up of the volumes of document production in order to optimise resource efficiency and improve methods and processes.

Performance Indicators:

- Approval by the Council and reliability of financial data (reactions from administrations, private sector, external auditors, General Secretariat).

- Speed and quality of service provided and accuracy of information supplied. Client satisfaction (UNDP, administrations and private sector).

- Fast and effective decision-making, top-level ITU-D management satisfaction.

- Pertinence of statistics provided and usage of financial data provided in the management of BDT/ITU.

Actions:

2610	Establishment of BDT biennial budget

2620	Financial management control

2621	Implementation of auditing and control systems and processes

2622	Financial control for projects entrusted to us by our partners

2623	Preparation of reports based on historical, real or projected data

#### 4	Programming and ITU-D Members

Annual objectives:

- Provide BDT staff with efficient administrative tools for cooperation with ITU-D Sector Members

- Increase the  number of ITU-D Sector Members

- Coordinate preparation of the ITU-D Operational Plan 2002 and prepare the final document

- Coordinate assessment of ITU-D activities and provide reports (posted on the Web) on progress in the implementation

- Weekly entering and updating of schedule of ITU-D meetings and corresponding links on the Web

Performance indicators:

- Timeliness and pertinence of replies to queries from ITU-D Sector Members and potential Sector Members

- Availability of updated data on ITU-D Sector Members

- Availability of the operational plan and other relevant reports on the Web

- Availability of the schedule of ITU-D meetings on the Web (updated weekly)

Actions:

2561	Serve as a BDT contact point for ITU-D membership

2624	Maintain updated the database on Sector Members

2625	Disseminate information on ITU-D Sector

Members on a regular basis

2626	Coordinate preparation of the operational plan

2627	Coordinate quarterly assessments of implementation of the current operational plan

2671	Disseminate information on operational plan and on its implementation

#### 5	Fellowship service

Annual objectives:

- Renewal of favorable training agreements with various telecommunication training institutions.

- Timely implementation of fellowships to the satisfaction of the fellows, their home administrations as well as the host training institutions.

Performance indicators:

- All training agreements renewed

- Percentage of fellowships implemented out of total requests received, for which all administrative prerequisites had been in place within deadlines

- Satisfaction within BDT with regard to the efficiency of the service

Actions:

2611	Prospecting and negotiation for training opportunities

2628	Travel/payment and reporting instructions to fellows

2629	Database update/statistics

2630	Cost estimates

2631	Transactions with host institutions, UNDP offices, government/private sector administrations

#### 6	Contracts & procurement service

Annual objectives:

- Correct formulation of the legal parts of project documents, administrative agreements and contracts as far as purchasing activities are concerned.

- No ITU-caused delays in the delivery of equipment and services as specified by project documents, administrative agreements and contracts.

- Inventory of non-expandable project equipment bought by the ITU is up-to-date.

Performance indicators:

- Percentage of delays caused by EQT

- Adherence to the rules and procedures in force

- Zero oversight of contractual and purchase order issues which are to the disadvantage of the ITU

- Satisfaction with the service by its BDT users

Actions:

2612	Maintenance of a roster of companies

2632	Review of administrative agreements

2633	All activities in connection with purchasing of equipment and services

2634	Keeping project inventories

#### 7	Field personnel service

Annual objectives:

- No ITU-caused delay in the recruitment of experts and consultants.

- Speedy settlement of travel claims. Administration of experts, outposted and locally-recruited ITU personnel according to the applicable rules.

- Satisfaction within BDT with regard to efficiency of the service.

Performance indicators:

- Maintenance of the expert roster up-to-date; contract offers timely and in conformity with rules, regulations and accepted practices

- Security procedures applied

- Prompt settlement of claims based on the verification that these are duly substantiated

- Satisfaction within BDT with regard to efficiency of the service

Actions:

2613	Recruitment of experts

2635	Maintenance of roster and updating of RCA database

2636	Administration of contracts, travel arrangements, verification of claims, entitlements and benefits

2637	Updating of RCA database and payroll database (SIGAGIP) and statistics required by UN system

2638	Coordination with UNDP offices, government or telecommunications entities

#### 8	Information systems support

Annual objectives:

- Adherence to deadlines when implementing and maintaining computerized support systems.

- A maximum of two ISS-caused problems with the consistency and transparency of BDT data.

- All BDT users trained in the BDT applications.

- 99% of the hardware and software required in the BDT ordered on time.

Performance indicators:

- Successful implementation of new systems and requests for maintenance

- Adherence to deadlines

- User satisfaction within BDT

Actions:

2614	Analyze current information flows and work procedures and design/implement new ones

2639	Prepare BDT administrative database systems for future requirements and exchange of information

outside BDT

2640	Upgrade hardware and software, conduct user support and train users in standard software and

BDT databases

# Part 4 - Recapitulation of Resources

#### 4.1	Budget resources

| Activities | Total Direct costs* |
| --- | --- |
| Valletta Action Plan (VAP) |  |
| Chapter 1: Programme of cooperation |  |
| WTDC-02 | 1'443'000 |
| Telecommunication Development Advisory Group | 170'000 |
| Gender Issues | 100'000 |
| Study Groups 1 & 2 | 711'000 |
| Information sharing | 160'000 |
| Resource mobilization | 75'500 |
| Communication and promotion | 130'000 |
| Chapter 2: Valletta Action Plan Programmes |  |
| Prog. 1 - Reform, legislation and regulation of telecommunications | 1'099'500 |
| Prog. 2 - Technologies and global information infrastructure development and applications | 1'958'500 |
| Prog. 3 - Rural development and universal service/access | 686'500 |
| Prog. 4 - Finance and economics, including WTO issues, tariffs, accounting rates, etc. | 692'500 |
| Prog. 5 - Development partnership with the private sector | 259'000 |
| Prog. 6 - Capacity building through human resources development and management | 1'002'500 |
| Chapter 3: Special Programme for LDCs | 1'039'500 |
| Chapter 4: Projects & Direct Assistance | 1'031'000 |
| BDT operation |  |
| TOTAL | 10'558'500 |

*   Direct costs

Direct costs are the costs, which can be directly attributed to a particular activity or product/service. They include:

- Primary costs – charged directly to the cost centre established for the activity of product/service, such as:

  - staff involved exclusively in the particular activity

  - travel expenditure

  - contractual services engaged exclusively for this activity

  - materials, premises, rental, public services and miscellaneous expenditure incurred exclusively for a particular activity:

- Invoiced costs – services regarding the documentation process: translation, typing and reprography.

(excerpt from Document C98/4)

# list of ABBREVIATIONS AND ACRONYMS

Liste d'abréviations et d'acronymes

Lista de Abreviaturas y acrónimos

| E F S | AFSM | Software commercialised by Spectrocan for the Automated Spectrum Management Logiciel commercialisé par Spectrocan pour la Gestion Automatisée du Spectre |
| --- | --- | --- |
| E F S | ABU | Asia and Pacific Broadcasting Union |
| E: F: S: | AIBD | Asia-Pacific Institute for Broadcasting Development Institut de Développement de la Radiodiffusion pour la région Asie-Pacifique Instituto Asia-Pacífico para el Desarrollo de la Radiodifusión |
|  | AICEP | Associaçao dos Operadores de Correios e Telecomunicaçoes dos Países e Territórios de Língua Oficial Portuguesa |
| E: F: S: | ASETA | Andean Telecommunications Enterprises Association Association des entreprises gouvernementales de télécommunications de l'Accord sous-régional Andin Asociación de Empresas de Telecomunicaciones del Acuerdo Subregional Andino |
| E: F: S: | ASMS | Advanced Spectrum Management System |
| E: F: S: | BAAP PABA PABA | Buenos Aires Action Plan (1994 – 1998) Plan d'action de Buenos Aires Plan de Acción de Buenos Aires |
| E: F: S: | BASMS | Basic Automated Spectrum Management System Système de base pour la gestion automatisée du spectre Sistema básico de Gestión Automatizada del Espectro |
| E: F: S: | CAZ | Communication Authority of Zambia |
| E: F: S: | CEE PECO CEE | Central and Eastern European countries Pays d'Europe centrale et orientale Países de Europe Central y Oriental |
| E: F: S: | CIDA ACDI CIDA | Canadian International Development Agency Agence canadienne de développement international Agencia Canadiense para el Desarrollo Internacional |
| E: F: S: | CIS CEI CEI | Commonwealth of Independent States Communauté des Etats indépendants Comunidad de Estados Independientes |

| E: F: S: | CITEL | Inter-American Telecommunications Commission Commission interaméricaine des télécommunications Comisión Interamericana de Telecomunicaciones |
| --- | --- | --- |
| E F S | CMTL | Centre régional de maintenance des télécommunications de Lomé (TOGO) |
| E F S | CTU | Caribbean Telecommunication Union |
| E F S | ESMT | Ecole Supérieure Multinationale des Télécommunications (basée à Dakar) |
| E: F: S: | ECOWAS CEDEAO | Economic Community of West African States Communauté Economique des Etats de l’Afrique de l’Ouest |
| E F S | ENPT | Ecole Nationale des Postes et Télécommunications (basée à Yaoundé) |
| E F S | GATS | General Agreement on Trade and Services |
| E F S | GIS | Global Information System |
| E: F: S: | GII | Global Information Infrastructure Infrastructure mondiale de l'information Infraestructura Mundal de la Información |
| E: F: S: | GSM | Global System for Mobile Communications Système mondial de communications mobiles Sistema Mundial de Comunicaciones Móviles |
| E: F: S: | GTTI | Global Telecommunications Training Institute Institut mondial de formation en télécommunications Instituto Mundial de Capacitación en Telecomunicaciones |
| E: F: S: | GTU | Global Telecommunication University Université mondiale des télécommunications Universidad Mundial de Telecomunicaciones |
| E: F: S: | HRD/HRM DRH/GRH DRH/GRH | Human Resource Development / Human Resource Management Développement des ressources humaines / Gestion des ressources humaines Desarrollo de los Recursos Humanos / Gestión de los Recursos Humanos |
| E F S | IADB | Inter-American Development Bank |

| E F S | ICU | Information, Communication University |
| --- | --- | --- |
| E: F: S: | ICT TIC TIC | Information and Communication Technology Technique de l'information et de la communication Tecnologías de la Información y las Telecomunicaciones |
| E: F: S: | IMT-2000 | International Mobile Telecommunications 2000 Télécommunications mobiles internationales 2000 Telecomunicaciones Móviles Internacionales 2000 |
| E: F: S: | IP | Internet Protocol Protocole Internet Protocolo Internet |
| E F S | INET2002 | Internet Society Conference |
| E: F: S: | IT | Information Technology Technologie de l'information Tecnologías de la Información |
| E: F: S: | ITCI | Internet Training Centres Initiative |
| E: F: S: | ITU-D UIT-D UIT-D | International Telecommunication Union – Development Sector Union internationale des télécommunications - Secteur du développement Unión Internacional de Telecomunicaciones - Sector de Desarollo |
| E: F: S: | ITU-R UIT-R UIT-R | International Telecommunication Union – Radiocommunication Sector Union internationale des télécommunications - Secteur des radiocommunications Unión Internacional de Telecomunicaciones - Sector de Radiocomunicaciones |
| E: F: S: | ITU-T UIT-T UIT-T | International Telecommunication Union – Standardization Sector Union internationale des télécommunications - Secteur de la normalisation Unión Internacional de Telecomunicaciones - Sector de Normalización |
| E: F: S: | LDCs PMA PMA | Least Developed Countries Pays les moins avancés Países Menos Adelantados |
| E F S | MACRA | Malawi Communication Regulatory Authorities |
| E: F: S: | MCM | Master in Communication Management Mastère en gestion des communications Maestría en Gestión de las Telecomunicaciones |
| E: F: S: | MCT | Multi-purpose Community Telecentre Télécentre communautaire polyvalent Telecentros Comunitarios Polivalentes |

| E F S | MIS | Management and Information System |
| --- | --- | --- |
| E F S | NGN | Next generation networks |
| E F S | OECD OCDE | Organisation for economic co-operation and development Organisation de coopération et développement économiques |
| E F S | ONATEL | Office national des télécommunications |
| EFS | PKI | Public Key Infrastructure |
| E: F: S: | PLANITU | Computer-aided network planning Planification des réseaux assistée par ordinateur Planificación de Redes Asistida por Ordenador |
| E: F: S: | PSTN/IP RTPC/IP RTPC/IP | Public switched telephone network / Internet Protocol Réseau téléphonique public commuté / Protocole Internet Red Telefónica Pública Conmutada / Protocolo Internet |
| E: F: S: | RCA database | Recruitment and Contract Administration system Système de gestion du recrutement et des contrats Sistema de Administración de Contratos y Contratación |
| E: F: S: | SISEI | Environmental information and monitoring system on the Internet Système d’information et de suivi de l’environnement sur Internet Sistema de Vigilancia e Información Ambiental por Internet |
| E: F: S: | SOCATEL | Société centrafricaine des télécommunications |
| E: F: S: | TAF, TAL, TAS | Tariff Groups for Africa (TAF), America (TAL) and Asia-Pacific (TAS) Groupes de tarification pour l'Afrique (TAF), l'Amérique (TAL) et l'Asie-Pacifique (TAS) Grupos de Tarificación para África (TAF), América (TAL) y Asia-Pacífico (TAS) |
| E: F: S: | TCDC | Technical Cooperation among Developing Countries Coopération technique entre pays en développement Cooperación Técnica entre Países en Desarrollo |
| E: F: S: | TDAG GCDT GADT | Telecommunication Development Advisory Group Groupe consultatif pour le développement des télécommunications Grupo Asesor de Desarrollo de las Telecomunicaciones |
| E: F: S: | TEMIC | Telecommunications Executive Management Institute of Canada Institut des cadres supérieurs en gestion des télécommunications du Canada Instituto de Gestión Ejecutiva de las Telecomunicaciones de Canadá |

| E F S | TIA | Telecommunication Industry Association |
| --- | --- | --- |
| E: F: S: | TRASA | Telecommunication Regulators Association for Southern African countries Association des responsables de la réglementation des télécommunications pour les pays d'Afrique australe Asociación de Organismos Reguladores de la Telecomunicaciones para los países del África Meridional |
| E F S | TREG | Telecom Regulation |
| E F S | TS | Telecom Surplus |
| EFS | UA/RC | Universal Access and Rural Connectivity |
| E: F: S: | UEMOA | West African Economic and Monetary Union Union économique et monétaire ouest-africaine Unión Económica y Monetaria del África Occidental |
| EFS | UKTA | United Kingdom Training Academy |
| E: F: S: | UNDP PNUD PNUD | United Nations Development Programme Programme des Nations Unies pour le développement Programa de las Naciones Unidas para el Desarrollo |
| EFS | UPU | Universal Postal Union Union postal universel Unión postal universal |

__________