| INTERNATIONAL TELECOMMUNICATION UNION |  |  |  |
| --- | --- | --- | --- |
|  | # COUNCIL |  | Document C2002/EP/4-E 5 February 2002 Original: English |
| GENEVA — SESSION 2002 — (22 APRIL - 3 MAY) |  |  |  |

Director, Telecommunication Standardization Bureau

ITU-T OPERATIONAL PLAN 
FOR 2002-2003

Introduction:

Pursuant to Resolution 72 (Minneapolis, 1998), the document presents the Operational Plan of the Telecommunication Standardization Sector for the year 2002 and the linkage between strategic, operational and financial planning.

For each ITU-T project or activity listed, the related allocation of financial and human resources is provided, as well as the relationship to the Strategic Plan adopted by the Plenipotentiary Conference (Minneapolis, 1998), the decisions adopted by the World Telecommunication Standardization Assembly (Montreal, 27 September - 6 October 2000) and the TSAG agreements reached at its March 2001 meeting.

The Operational plan for 2003 is also attached but for information purpose only, as the results of the Plenipotentiary Conference (Marrakech, 2002) may have an impact and modify our planning for 2003.

Summary:

A series of new activities will be launched in 2002 to respond to the concerns of ITU-T membership.

The newly created Study Group 17 “Data Networks and Telecommunication Software” will start its activities in 2002.  New Questions will steadily be put under study in other Study Groups according to technological evolution, while other items will complete.

Different technical workshops will be organized in order to disseminate expert knowledge on state-of-the-art technologies and increase awareness of ITU-T studies and projects.  Four workshops are already scheduled:

-  Tutorial Workshop on ENUM, on 8 February 2002, in Geneva, in collaboration with Study Group 2 and experts from the Internet Engineering Task Force (IETF)

-  Workshop on IP Cablecom/Mediacom 2004/Interactivity in Multimedia, from 25 to 28 March 2002, in Geneva, in collaboration with Study Group 9, 16, ITU-R Study Group 6, and the contribution of experts from several study groups and standards developing organizations.

-  Workshop on IP/Optical from 9 to 11 July 2002, in Chitose, Japan, in collaboration with Study Group 13, 15 and the experts from study groups and SDOs.

-  Workshop on the Role of Satellites in IP-based and Multimedia Networks and Services from 9 to 13 December in Geneva, organized in the framework of the activities conducted by the Intersector Coordination Group on Satellite Matters.

Regional presence will be strengthened according to Plenipotentiary Conference (Minneapolis, 1998) and Council 2001 decisions.  Some Study Group meetings and technical workshops will be convened in the regions; contributions from various regions reflecting regional concerns to the ITU-T activities will be encouraged.  A regional briefing session will be organized in each region focusing on priority questions and dissemination of ITU-T studies and Recommendations.

ITU will host the General Assembly of ICANN Protocol Supporting Organization in 2002 and assume the secretariat for one year.

In parallel, effort will be made to promote the ITU-T and its activities through active press release policy, presentation of the ITU-T products, activities and working methods at external fora or events.

In the technical field, strategic ITU-T priorities will remain in 2002:

- Interworking of IP-based and telecommunication networks

- The interoperability of IP-based services and telecommunication services means providing real time Internet or other IP based multimedia services with the speed, capacity, ease of use, reliability and integrity of the public telephone networks in use around the world. These are aspects of telecommunication network standardization in which the ITU-T has an excellent track record. These aspects of telecommunication network standardization are the main goals of IP Project.

- In particular, collaboration with IETF in the development of a Recommendation to enable the implementation of the ENUM protocol, which should facilitate the interconnection of circuit-switched (telephone) and packet-switched (IP) networks

- Another important step towards interoperability and interworking is the effort of GII Project . The ultimate goal of this project is to support communications anywhere at anytime in any medium and thus allow users to have access to a wide range of services. The GII also supports the goal of an international consensus on common principles governing the need of access to networks and applications and their operability based on a seamless federation of interconnected, interoperable communication networks, information processing equipment, databases and terminals

- Mobility, IMT-2000 and beyond

- The requirements for new or enhanced Mobility Management protocols are important to support Global Roaming in IMT-2000 and beyond.  The increasing desire for accessing services such as those available from Internet on the move has created new fields of services such as “mobile multimedia”.  Convergence of fixed and wireless networks and ultimately migration to interoperable and harmonised network architectures to provide services transparently to the users across different access arrangements is becoming an industry requirement. A major objective of the harmonization of IMT-2000 networks is the development of common network solutions that can facilitate cost-effective IMT-2000 network deployments based on the standardized open interfaces, stimulate the commercial uptake of IMT-2000 services, and foster global roaming across all evolving IMT-2000 systems

- Optical transport network

- An Optical Transport Network (OTN) is composed of a set of Optical Network Elements connected by optical fibre links, able to provide functionality of transport, multiplexing, routing, management, supervision and survivability of optical channels carrying client signals. Optical network functions include multiplexing function, cross connect function, including grooming and configuration, management functions and physical media functions.

- Optical networks will be able to create a network needed by the market requirements to deliver high speed service, that can be supported only partially by the existing copper network, to the customers.

- A distinguishing characteristic of the OTN is its provision of transport for any digital signal independent of client-specific aspects.

- Access networks

- Network access between Telecommunication Network Operators, Private Network Providers, Satellite and Cable TV Networks and Information Technologies is under study in the access network project.  Various Access Network Transport scenarios have been envisaged, such as:

- Voice/data/video services over existing infrastructures and Cable Networks

- Voice/data/video services over cable networks using B-ISDN

- ADSL or VDSL video BW over copper pairs

- Fiber accesses

- Use of radio in Local Loop

- Use of satellites

- Internet Access

- This project evaluates the different ANT scenarios with the corresponding standardization requirements. In the framework of this project have been developed all X-DSL standards and their interworking with the existing systems.

- Accounting rate reform

- A paradigm shift occurred in the international telecommunication sector. The emerging regime is based on cross-border interconnection and the trading of international traffic minutes. It is urgent to readapt traditional tariff/accounting principles to the new market situation and to provide also the transitional arrangements, in order to facilitate the transition to the new regime.

- Multimedia services and systems

- The standardization in this field, aimed at the creation of a global platform for the delivery of multimedia services and systems over all network types (including the internet), will also consider their access, the security and other related technical aspects going to the convergence.

- -		Signalling Requirements and Protocols

- for support of applications based on IP, intelligent and advanced networks

- Quality of Service and Performance

The works on end-to end Quality of service, for networks, equipments, protocols and interworking of them will progress on the definition of Classes of service for the different "layers" (user, applications, transport…) and for the different services (voice, multimedia, data…) to complete the global figure of the Quality of service and Performance. They should include principles and means for measurement, monitoring, signalling and guarantee of these QoS classes.

New initiatives and special ITU-T projects will be conducted in the field of IP, GII, Mediacom-2004, ASN.1, E-commerce, E-business and IP Cablecom.

ITU-T will continue its technical studies in cooperation with other standard developing organizations, regional entities and duly attention will also be paid on related IPR questions.

Use of TSB resources in 2002 - Overall recapitulation

| ITU-T activities | P staff-months | G staff-months | Direct costs CHF | Document costs CHF |
| --- | --- | --- | --- | --- |
| - TSAG (Telecommunication Standardization Advisory Group) | 9 | 8 | 127,000 | 120,000 |
| 1 planned meeting, 5 working days |  |  |  |  |
| - Chairmen’ meetings: | 1 | 1 | - | - |
| 1 planned meeting, 2 working days |  |  |  |  |
| - Study Group meetings: | 89 | 134 | 3,023,000 | 5,732,000 |
| 20 planned meetings, 151 working days |  |  |  |  |
| 12 Study Groups |  |  |  |  |
| 1 Special Study Group |  |  |  |  |
| 199 Questions under study |  |  |  |  |
| 315 new ITU-T Recommendations, |  |  |  |  |
| 12,500 pages of text |  |  |  |  |
| 16,880 pages of translation |  |  |  |  |
| 45,260 pages of typing pool |  |  |  |  |
| 37,620,000 pages of reprography |  |  |  |  |
| - Seminars and technical workshops: | 9 | 6 | 100,000 | - |
| 4 planned workshops, 13 working days |  |  |  |  |
| - Regional presence: | 9 | 9 | 225,000 |  |
| 4 regional briefing meetings |  |  |  |  |
| Study Group meetings in the regions |  |  |  |  |
| Workshops in the regions |  |  |  |  |
| Regional tariff group meetings |  |  |  |  |
| - Promoting ITU-T activities | 18 | 10 | 100,000 |  |
| - External cooperation | 9 | 12 |  |  |
| - ICANN-PSO General Assembly and Secretariat | 7 | 2 |  |  |
| - Study Group publications: | 22 | 178 | 264,500 | 232,000 |
| 12,000 pages of Recommendations to published |  |  |  |  |
| per language (x3) |  |  |  |  |
| - Operational Bulletin: | 15 | 16 | 14,500 | 20,000 |
| 24 issues a year |  |  |  |  |
| - Databases accessible to public | 5 | 3 | 5,000- | - |
| - UIFN registrar | 3 | 13 | 374,000 | - |
| (Universal International Freephone Numbers) |  |  |  |  |
| 3,750 UIFN |  |  |  |  |
| - UIPRN/UISCN registrar | 1 | 2 | 47,500 | - |
| (Universal International Premium Rate Numbers) |  |  |  |  |
| (Universal International Shared Cost Numbers) |  |  |  |  |
| 600 UIPRN/UISCN |  |  |  |  |
| - AESA registrar | 1 | 1 | - | - |
| (ATM End System Addresses) |  |  |  |  |
| 300 AESA |  |  |  |  |
| - Bureau support | 32 | 20 | 10,020,500 | 139,000 |
| - EDH (Electronic Document Handling) |  | 40 |  |  |
| Documents & information posted on ITU Website |  |  |  |  |
| Total of allocated resources | 230 | 455 | 14,301,000 | 6,243,000 |

Assumption: 10 staff-months per person per year

##### TSB - Linkage between Strategic, Financial and Operational Planning - 2002

| #### Operational Activities | #### Objectives | Allocated Resources | #### Relationship to Strategic |
| --- | --- | --- | --- |
|  | and Performance Indicators | from the 2002 budget | Policies and Plans / PP-98 |
|  |  |  | Article 14A of the Convention |
| Telecommunication Standardization Advisory Group |  |  |  |
|  |  |  | Res. 71 (Minneapolis, 1998): |
| Reviews priorities and strategies for ITU-T’s activities | Expected results: | 1 planned meeting | Strategic plan for the Union (1999-2003) |
| Reviews progress of work program & working methods |  | with its working parties | Res. 74 (Minneapolis. 1998): |
| Maintains the A Series (Organization of the work of | Advices to the TSB Director | 5 working days | Review and improvement of the management, |
| ITU-T) |  |  | functioning and structure of the ITU |
| Acts on behalf of the WTSA between WTSAs | A Series of Recommendations | 9 P staff-months | Res. 16 (Minneapolis, 1998): |
| Establishes / discontinues Study Groups | (Organization of ITU-T work) | 8 G staff-months | Refinement of the ITU-R and ITU-T Sectors |
| Advises on financial matters |  |  | Res. 82 (Minneapolis, 1998): |
| cooperation and coordination | Achievement indicators: | 127,000 F direct costs: | Approval of Questions and Recommendations |
|  |  | Interpretation, | Res. 72 (Minneapolis, 1998): Linking strategic, |
|  | Minimized duplication of work | Meeting staff | financial and operational planning in ITU |
| New activity: | Harmonized technical standards |  | Res. 66 (Minneapolis, 1998): |
|  | Enhanced operational efficiency | 120,000 F document costs : | Documents and publications of the Union |
| Preliminary draft Strategic Plan for 2003-2006 | of ITU-T | Translation, typing pool |  |
|  |  | Reprography | Res. 1141 Council 1999 |
|  |  |  | Reduction of the cost and volume of documentation |
|  |  |  | for Conferences and Assemblies and the Council |
|  |  |  | Res. 18 (WTSA-2000) |
|  |  |  | Principles and procedures for the allocation of work |
|  |  |  | to, and coordination between, the |
|  |  |  | Radiocommunication and Telecommunication |
|  |  |  | Standardization Sectors |
|  |  |  | Res. 22 (WTSA-2000) |
|  |  |  | Authorization for TSAG to act between WTSAs |
|  |  |  | Res. 32 (WTSA-2000) |
|  |  |  | Strengthening the use of electronic document |
|  |  |  | Handling for the work of ITU-T |
|  |  |  | Res. 33 (WTSA-2000) |
|  |  |  | Guidelines for ITU-T strategic activities |
| Chairmen's meeting |  |  |  |
| Definition and coordination of SG work plan |  | 1 planned meeting |  |
| Finalization of meeting schedule for following year |  | 2 working days |  |
| Discussion on budget allocation on the various SG |  |  |  |
| Improvement in communication amongst SG |  | 1 P staff-month |  |
| Priority in studies |  | 1 G staff-month |  |

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2002 budget | #### Relationship to Strategic Policies and Plans/ PP-98 |
| --- | --- | --- | --- |
| Study Group Meetings |  |  |  |
| Study Group responsibility and mandates: | Expected results: | Total for all the Study Groups: | Article 17 of the Constitution |
| See Res. 2 (WTSA-2000) |  |  |  |
|  | 315 new ITU-T Recommendations | 20 planned SG meetings | Article14 of the Convention |
| 12 Study Groups | totaling about 12,500 pages | with their working parties |  |
| 1 Special Study Group |  | 151 working days | Resolutions of Minneapolis, 1998 |
| 199 technical, operating and tariff Questions under study | Development of a programme of |  | See below |
|  | technical workshops | 89 P staff-months |  |
| Attention is paid to improvement of telecommunications |  | 134 G staff-months |  |
| in developing countries and cooperation with national, | Key performance indicators: |  |  |
| regional and international organizations |  | 3,023,000 F direct costs: |  |
|  | Worldwide utilization of ITU-T Recs. | Interpretation |  |
|  | Text quality & market response | Meeting staff |  |
|  | Reduction in time-to-market for | Mail expenses |  |
|  | Recs (AAP implementation) |  |  |
|  | Stability of texts and avoidance of | 5,732,000 F document costs : |  |
|  | document reprocessing | Total French +English +Spanish: |  |
|  | Membership satisfaction | 16,880 pages of translation |  |
|  |  | 45,260 pages of typing pool |  |
|  |  | 37,620,000 pages of reprography |  |
| Workshops |  |  |  |
| Dissemination of expert knowledge on state-of-the-art | Expected results: | 9 P staff-months |  |
| technologies, |  | 6 G staff-months |  |
| Promotion of awareness of ITU-T activities, | Participation of delegates from |  |  |
| working methods and priorities | developing countries in the | 100,000 F direct costs: |  |
|  | activities of the Sector | Fellowships for SG 3 |  |
| New initiatives |  |  |  |
| : - Tutorial workshop on ENUM, 8 February 2002, Geneva | Strengthening regional presence | 1 planned workshop, 1 day |  |
| - Workshop on IP Cablecom/Mediacom 2004 | Achievement indicators: | 1 planned workshop, 4 days |  |
| /Interactivity in Multimedia |  |  |  |
| 25-28 March 2002 in Geneva | Dissemination of expert technology |  |  |
| - Workshop on IP/Optical | Integration of developing countries | 1 planned workshop, 3 days |  |
| 9-11 July 2002 in Japan | concerns in ITU-T outputs |  |  |
| - Workshop on the role of Satellites in IP-based and | Coordination of activities within | 1 planned workshop, 5 days |  |
| Multimedia Networks and Services | Study Groups and with other SDOs |  |  |
| 9-13 December 2002 in Geneva |  |  |  |

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2002 budget | #### Relationship to Strategic Policies and Plans/ PP-98 |
| --- | --- | --- | --- |
| SG 2 – Operational aspects of service provision, |  |  | Res. 99 (Minneapolis, 1998): Status of Palestine in ITU |
| networks and performance |  |  | Res. 21 (Rev. Minneapolis, 1998): Alternative calling |
|  |  |  | procedures on international telecom. networks |
| Priorities: | Expected results: | 2 planned SG meetings |  |
| Service definition, Numbering, Routing and Global Mobility |  | and their WPs | Res. 79 (Minneapolis, 1998): |
| Numbering Coordination Team (NCT) | 25 Recommendations to be | 18 working days | International Telecommunication Regulations |
| Resolution 20 and coordination with TSB | approved in 2002 = 1,000 pages |  | Res. 101 (Minneapolis, 1998): |
|  |  | 7 P staff months | Internet Protocol (IP)-based networks |
| Lead Study group for service definition, numbering |  | 5 G staff months |  |
| and routing |  |  |  |
|  |  | 83,000 F direct costs | Res. 71 (Minneapolis, 1998) Goal 3: |
| New activities: |  | 205,000 F document costs | Developing and implementing administrative |
| ENUM |  |  | procedures for numbering plans for |
| Service level agreements (SLAs) |  | 2 Rapporteur Group meetings | international networks and services |
| Human factors |  |  | Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | facilitating the interworking of global personal |
|  |  |  | radiocommunication systems with public |
| 9 Questions |  |  | telecommunication networks |
|  |  |  | Res. 20 (WTSA-2000) |
|  |  |  | Procedures for allocation and management of |
|  |  |  | International numbering resources |
|  |  |  | Opinion D (WPTF-2001): |
|  |  |  | Essential studies by ITU to facilitate the introduction |
|  |  |  | Of “IP Telephony” |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2002 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SG 3 - Tariff and accounting principles, including |  |  |  |
| related telecommunications, economic and |  |  |  |
| policy issues |  |  |  |
|  | Expected results: | 2 planned SG meeting | Res. 71 (Minneapolis, 1998), F.4: |
| Priorities: |  | and its WPs | Develop Recommendations to achieve |
| Accounting rate reform and implementation of new | 5 Recommendations to be | 10 working days | accounting rate reform and to propose |
| remuneration systems | approved in 2002: 250 pages |  | means to encourage their implementation |
| Transitional arrangements |  | 5 P staff months | Res. 71 (Minneapolis, 1998), D.1, 28.2 |
| Development and implementation of cost methodologies |  | 6 G staff months | Achieving Accounting rate reform and proposing |
| Impact of new practices bypassing accounting rate system |  | 176,000 F direct costs | means to encourage their implementation |
| Tariff principles for services using new technologies |  | 153,000 F document costs |  |
|  |  |  | Res. 21 (Rev. Minneapolis, 1998): Alternative calling |
| New activities: |  |  | procedures on international telecom. networks |
| Impact of IP-Telephony |  | 2 Rapporteur meetings |  |
| Impact and tariff of Internet / IP-based Network |  | 5 working days | Res. 22 (Minneapolis, 1998): Apportionment of |
| Review of International Telecommunication Regulations |  |  | revenues in providing international telecom. services |
| 4 Questions |  |  | Res. 101 (Minneapolis, 1998): |
|  |  |  | Internet Protocol (IP)-based networks |
| Tariff Group for Africa (TAF) |  |  |  |
| Tariff Group for Latin America (TAL) |  |  | Res. 103 (Minneapolis, 1998): |
| Tariff Group for Asia and Oceania (TAS) |  |  | International Telecommunication Regulations |
| Priorities: | Expected results: | 3 planned meetings | Res. 26 (WTSA-2000) |
| TAF: Accounting rates system in connection |  | 10 working days | Assistance to the Regional Tariff Groups |
| with IP-Telephony, Tariff rebalancing, Cost model | Preparation of Recommendations |  |  |
| development and implementation | and regional cost model | 3 P staff months |  |
| TAL: Cost model development including interconnection |  | 3 G staff months |  |
| Determination of accounting rates for mobile services |  |  | Res. 29 (WTSA-2000) |
| TAS: New cost model development, |  |  | Alternative calling procedures on international |
| Regional case study on cost/price |  |  | telecommunication networks |
| Regional tariff model for Internet |  |  |  |
|  |  |  | Res. 41 (WTSA-2000) |
| New activities: |  |  | Accounting rate principles for international |
| TAF: Implication of new technologies for African |  |  | telephone services |
| incumbent operators |  |  |  |
| TAL: Impact of IP Telephony in the region |  |  |  |
| Tariff Group for Europe and the Mediterranean Basin |  |  |  |
| Activity in abeyance |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2002 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SG 4 – Telecommunication management, |  |  |  |
| including TMN |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting |  |
| Management of telecommunication services, networks, |  | and its WPs | Res. 71 (Minneapolis, 1998), F.4: |
| and equipment using the telecommunication management | 25 Recommendations to be | 10 working days | Further evolution of network infrastructures in the area |
| network (TMN) framework | approved in 2002: 1,250 pages |  | of control |
| Additionally responsible for other telecommunication |  | 8 P staff months |  |
| management studies relating to designations, |  | 8 G staff months |  |
| transport-related operations procedures, and test and |  |  |  |
| measurement techniques and instrumentation |  | 90,000 F direct costs |  |
|  |  | 517,000 F document costs |  |
| Cooperation with other standard developing organizations |  |  |  |
|  |  | 20 Rapporteur meetings |  |
| Lead Study Group on TMN |  | 100 working days |  |
| New activities: |  |  |  |
| CORBA based TMN and IP related TMN activities |  |  |  |
| Creation of IP-based SNMP infrastructure |  |  |  |
| Support of optical and IP-based networks |  |  |  |
| 17 Questions |  |  |  |
| SG 5 - Protection against electromagnetic |  |  |  |
| environment effects |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting | Res. 71 (Minneapolis, 1998), F.4: |
| Resistibility, EMC and safety aspects related to |  | and its WPs | Covering the further evolution of network infrastructures |
| telecommunications networks | 7 Recommendations to be | 5 working days |  |
| Cooperation with other international organizations | approved in 2002: 100 pages |  |  |
|  |  | 3 P staff months |  |
| New activity: |  | 3 G staff months |  |
| Protection against the effects of mobile equipment and |  | 46,000 F direct costs |  |
| radio systems |  | 107,000 F document costs |  |
| Workshop on SG 5 activities |  | 1 WP 1/5 & 2/5 meeting, 4 days |  |
| 14 Questions |  | 1 Rapporteurs’meeting, 5 days |  |
|  |  | (1 Panel session |  |
|  |  | at EMC Symposium, Wroclaw) |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2002 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SG 6 - Outside plant |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting | Res. 71 (Minneapolis, 1998), F.4: |
| Outside plant and access for telecommunication |  | and its WPs | Covering the further evolution of network infrastructures |
| networks | 5 Recommendations to be | 5 working days |  |
|  | approved in 2002 = 170 pages |  | Development of case studies, guidelines & handbooks |
| Cooperation with IEC |  | 2 P staff months |  |
|  |  | 2 G staff months |  |
| 10 Questions |  | 46,000 F direct costs |  |
|  |  | 115,000 F document costs |  |
| ###### SG 9 – Integrated broadband cable networks and |  |  |  |
| television and sound transmission |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting: | Res. 71 (Minneapolis, 1998), F.4: |
| IP and GII over cable distribution networks |  | and its WPs | Multimedia applications arising from the convergence |
| Television and sound over the core network | 20 Recommendations to be | 5 working days | of telecommunication, broadcasting, computer and |
| Coordination with ITU-R on broadcasting matters | approved in 2002: 1,500 pages |  | information technology |
|  |  | 6 P staff months |  |
| Lead Study Group on integrated broadband cable |  | 9 G staff months | Res. 101 (Minneapolis, 1998): |
| and television networks |  | 66,000 F direct costs | Internet Protocol (IP)-based networks |
|  |  | 596,000 F document costs |  |
| New activity |  |  |  |
| Webcasting |  | IPCablecom/Mediacom workshop |  |
| Packet cable, IP over cable |  | 4 working days |  |
| 21 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2002 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SG 11 - Signalling requirements and protocols |  |  |  |
| Priorities: | Expected results: | 2 planned SG meeting: | Res. 71 (Minneapolis, 1998), D.2, 29.2: |
|  |  | and its WPs | Developing Recommendations for new technologies |
| Signalling support for Internet (IP)-based applications | 47 Recommendations to be | 20 working days | and applications - global multimedia and mobility |
|  | approved in 2002: 2,350 pages |  |  |
| Intelligent Networks. |  | 8 P staff months | Res. 71 (Minneapolis, 1998), F.4: |
|  |  | 7 G staff months | Facilitating the integration of existing and new |
| Lead Study Group on intelligent networks |  | 162,000 F direct costs | transmission media in public networks, |
|  |  | 1,090,000 F document costs | in the area of signalling |
| Signalling for Access, N&B-ISDN, |  |  |  |
| and new generation networks |  |  | Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | Internet Protocol (IP) related aspects as well as the |
| Cooperation and development of ITU-T Recommendations |  |  | interoperability and convergence of IP-based networks, |
| with regional standards bodies/fora on IP |  |  | the Internet, with existing network infrastructures |
|  |  |  | Res. 71 (Minneapolis, 1998), F.4: |
| Cooperation and development of ITU-T Recommendations |  |  | Covering the future evolution of network infrastructures, |
| with regional standards bodies/for a on signalling-related |  |  | e.g. in the areas of network access, signalling and |
| activities for IP |  |  | control |
| Coordination with relevant ITU-T/ITU-R SGs/Wps for |  |  |  |
| signaling support of fixed-mobile aspects |  |  |  |
| 15 Questions |  |  |  |
| SG 12 - End-to-end transmission performance of |  |  |  |
| networks and terminals |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting |  |
| Performance assessment |  | and its WPs |  |
|  | 18 Recommendations to be | 5 working days | Res. 101 (Minneapolis, 1998): |
| Lead Study Group on Quality of services and performance | approved in 2002: 400 pages |  | Performance quality assessment of IP-based networks |
|  |  | 5 P staff months |  |
| New activities: |  | 6 G staff months | Res. 71 (Minneapolis, 1998), F.4: |
| Development of Recs. on Quality aspects of IP-based |  | 38,000 F direct costs | Multimedia applications |
| network |  | 276,000 F document costs |  |
| Workshop on ITU-T & SG 12 activities |  | 4 Rapporteurs meeting |  |
|  |  | 20 working days |  |
| 16 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2002 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SG 13 – Multi-protocol and IP-based networks |  |  |  |
| and their internetworking |  |  |  |
| Priorities: | Expected results: | 2 planned SG meeting: |  |
| General network aspects, Global Information |  | and its WPs | Res. 73 (Minneapolis, 1998): |
| Infrastructures (GII), B-ISDN and IP (Internet Protocol) | 31 Recommendations to be | 18 working days | World Summit on the information society |
| Fostering cooperation with IETF | approved in 2001: 1,550 pages |  |  |
|  |  | 3 P staff months | Res. 101 (Minneapolis, 1998): |
| Monitoring IP and GII projects |  | 3 G staff months | Internet Protocol (IP)-based networks |
|  |  | 130,000 F direct costs |  |
| Lead Study Group for IP related matters, B-ISDN, |  | 749,000 F document costs | Res. 71 (Minneapolis, 1998), D.2, 29.2: |
| Global Information Infrastructure and satellite matters |  |  | Developing Recommendations for new technologies |
|  |  | 10 Rapporteur meetings | and applications such as appropriate aspects of the GII |
|  |  | 50 working days | and global multimedia and mobility |
| New activities: |  |  | Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | Internet Protocol (IP) related aspects as well |
| NGW |  |  | as the interoperability and convergence of |
| VoIMPLS |  |  | IP-based networks, the Internet, with |
|  |  | 1 workshop | existing network infrastructures |
| Integrated communication architecture, including the |  | 1 day |  |
| impact of convergence |  |  | Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | Facilitating the integration of existing and |
| Workshop on ITU-T & SG 13 activities |  |  | new transmission media in public networks, |
|  |  |  | in cooperation with ITU-R for radio |
|  |  |  | transmission aspects |
| 16 Questions |  |  | Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | Further evolution of network infrastructures in |
|  |  |  | the areas of network access and interfaces |
|  |  |  | Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | Implementation of the GII |
|  |  |  | Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | Integration of existing and new |
|  |  |  | transmission media in public networks |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2002 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| ICG SAT |  |  |  |
| Intersector Coordination Group on Satellite Matters |  |  |  |
| Under the Lead of SG 13 for the ITU-T Sector |  |  |  |
| Priorities: | Expected results: | No planned meeting so far | Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | Facilitating the integration of existing and new |
| To take into account satellite specificity within | Performance |  | transmission media in public networks, in cooperation |
| telecommunication network including impact of | Achieved consistency of |  | with ITU-R for radio transmission aspects |
| IP-based network and multimedia network and system | Recommendations of various |  |  |
| Keeping up to date database | Study Groups for full integration |  |  |
|  | of the sat-transmission in |  |  |
| Coordination with ITU-R | public networks |  |  |
| New activity: |  |  |  |
| Organization of workshop |  |  |  |
| Strengthening relationship with ITU-D |  |  |  |
| SG 15 – Optical and other transport networks |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting | Res. 71 (Minneapolis, 1998), F.4: |
| Access Network |  | and its WPs | Further evolution of network infrastructures |
| - broadband optical access | 30 Recommendations to be | 10 working days | in the areas of network access, interfaces |
| - refinements & enhancements to SDL | approved in 2002: 1,000 pages |  | and optical networking |
| - phone line networking |  | 6 P staff months |  |
| - IP on Access Network |  | 7 G staff months | Res. 71 (Minneapolis, 1998), F.4: |
| Network signal processing |  | 90,000 F direct costs | Facilitating the integration of existing and |
| - interaction of signal processing (OTN) |  | 800,000 F document costs | new transmission media in public networks, |
| Optical transport network structure |  |  | in cooperation with ITU-R for radio |
| - automatic switched optical network (ASON) |  | 20 Rapporteur meetings | transmission aspects |
| - network management & control |  | 100 working days |  |
| OTN technology |  |  |  |
| -coarse & dense wavelength division multiplexing (WDM) |  | 1 IP/Optical workshop, 3 days |  |
| - fiber characteristics |  |  |  |
| - transmission technology |  |  |  |
| - IP on WDM |  |  |  |
| Cooperation with IEC and other SDOs |  |  |  |
| Lead Study Group on access network transport |  |  |  |
| Lead Study Group on optical technology |  |  |  |
| 19 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2002 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SG 16 - Multimedia services, systems and |  |  |  |
| terminals |  |  |  |
| Priorities: | Expected results: | 2 planned SG meetings |  |
| Modems and facsimile terminals |  | and its WPs |  |
| Multimedia platform and interworking | 50 Recommendations to be | 18 working days | Res. 71 (Minneapolis, 1998), F.4: |
| Media Coding | approved in 2002: 2,000 pages |  |  |
| Multimedia framework, MEDIACOM-2004 project |  | 10 P staff months |  |
| Cooperation with other Standard Development Org. |  | 8 G staff months | Multimedia applications arising from the convergence |
| Lead Study Group on multimedia services, |  | 142,000 F direct costs | of telecommunication, broadcasting, computer and |
| systems and terminals |  | 749,000 F document costs | information technology |
| Lead Study Group on e-business and e-commerce |  |  |  |
|  |  | 4 days workshop |  |
| New activities: |  |  | Res. 101 (Minneapolis, 1998): |
| Steering committee for MEDIACOM-2004 |  |  | Internet Protocol (IP)-based networks |
| Joint video team with ISO/IEC |  |  |  |
| Workshop on IP Cablecom/MEDIACOM-2004 |  |  |  |
| 23 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2002 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SG 17 - Data Networks and Telecommunication |  |  |  |
| Software |  |  |  |
| Priorities: | Expected results: | 2 planned SG meetings | Res. 71 (Minneapolis, 1998), F.4: |
| Additions to a set of Directory Recs. |  | and its WPs | Further evolution of networks infrastructures |
| Open Distributed Processing (ODP), Frame Relay | 50 Recommendations to be | 17 working days | in the area of security |
| Communication System Security and for interworking | approved in 2002: 2,000 pages |  | Interoperability of IP-based networks with |
| with IP-based networks |  | 6 P staff months | existing networks |
| Additions to/revision of the set of ASN.1 Recs |  | 6 G staff months |  |
| Cooperation with ISO/IEC |  |  |  |
| Contribution to the coordination effort with ISO, IEC and |  | 150,000 F direct costs | Res. 101 (Minneapolis, 1998) |
| UN/ECE for E-business standardization |  | 713,000 F document costs | Collaborative activities on IP-based network with |
|  |  |  | ISOC/IETF |
| Lead Study Group on Frame Relay |  |  |  |
| Lead Study Group on Communication System |  |  |  |
| Security |  |  | Network languages |
| Lead Study Group on Languages and Description |  |  |  |
| Techniques |  |  | TSAG (Geneva, 19-23 March 2001) |
|  |  |  | TSAG approved the merger of Study group 7 and 10 |
| New activities: |  |  | into a single Study Group 17 |
| Enhancement of communication system security for |  |  |  |
| E-commerce |  |  |  |
| Development of the ITU-T ASN.1 Project |  |  |  |
| Continuation of the provision of ASN.1 modules to the |  |  |  |
| ASN.1 database |  |  |  |
| Organization of a workshop on Security |  |  |  |
| 27 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2002 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SSG – Special Study Group IMT-2000 and beyond |  |  |  |
|  |  |  | Res. 38 (WTSA-2000) |
| Priorities: | Expected results: | 2 planned SSG meetings | Coordination among ITU-T, ITU-R and ITU-D for |
| Network aspects of IMT-2000 and beyond |  | and its WPs | IMT-2000 activities |
| (International Mobile Telecommunications-2000) | 10 Recommendations to be | 10 working days |  |
| Wireless access to IP-based networks | approved in 2002: 500 pages |  |  |
| Convergence of mobile and fixed networks |  | 8 P staff months |  |
| Mobility management, mobile multimedia functions | 2 Technical reports to be | 9 G staff months |  |
| Internetworking, interoperability | approved in 2002: 50 pages | 58,000 F direct costs |  |
|  |  | 147,000 F document costs |  |
| Enhancement of ITU-T Recommendations on IMT-2000 | 2 NTO (New Type of Output) to be |  |  |
|  | approved in 2002: 80 pages |  |  |
| Lead Study Group on IMT-2000 and beyond |  | 4 Rapporteur meetings |  |
| and for mobility | 1 handbook to be produced | 12 working days |  |
|  | together with ITU-R and ITU-D | 10 conference calls |  |
| New activities: | in 2002: 100 pages | 6 electronic meetings |  |
| Workshop on ITU-T & SSG activities |  | 1 workshop, 1 full day |  |
| Joint session with ITU-R WP 8F |  | 1 joint session with ITU-R WP 8F |  |
| Electronic meetings |  | 1 add. Editors’ meeting, 3 days |  |
| Development of New Types of Outputs |  | 1 add. WP meeting, ½ day |  |
| 8 Questions |  |  |  |
| Regional presence |  |  |  |
| Strengthening the regional presence | Expected results: | 4 regional briefing meetings | Res. 71 (Minneapolis, 1998), F.4: |
| Participation in external conferences |  | SG meetings in the regions | to work with BDT with special attention to |
| Assistance to ITU-D | Strengthened regional presence | Workshops in the regions | telecommunication development in developing |
|  | Awareness of ITU-T activities | Regional tariff group meetings | countries, and to cooperate with the other Sectors |
| New activities: |  |  | in the organization of information meetings, seminars |
|  | Achievement indicators: | 9 P staff-months | and workshops and in the development of |
| Organization of seminars in the field |  | 9 G staff-month | case studies, guidelines and handbooks. |
| Assistance to the Regions | Membership satisfaction |  |  |
| Regional briefing meetings | Dissemination of ITU-T studies | 225,000 F direct costs | Res. 25 (Rev. Minneapolis, 1998), |
|  | and Recommendations |  | Strengthening the Regional presence |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2002 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| Promoting the ITU-T |  |  |  |
| Press releases | Expected results: | 18 P staff-months |  |
| ITU-T presence in external events | Awareness of ITU-T activities | 10 G staff-month |  |
| Presentation of ITU-T activities during | Increased interest of Membership |  |  |
| external workshops |  | 100,000 F direct costs |  |
| Promotion events | Achievement indicators: |  |  |
|  | Higher number of Sector Members |  |  |
|  | Increased participation in the |  |  |
|  | Sector activities |  |  |
| External cooperation |  |  |  |
| Assistance to membership and Telecom community | Expected results: | 9 P staff-months |  |
| Assistance and cooperation with other Sectors | Worldwide coordination | 12 G staff-months |  |
| Liaison and coordination with international and regional | Promotion of ITU-T activities |  |  |
| organizations | Signature of MoUs |  |  |
| Cooperation with other standard organizations |  |  |  |
| Participation in external conferences | Achievement indicators: |  |  |
| IPR issues | Customer and membership |  |  |
|  | satisfaction |  |  |
|  | Dissemination of ITU-T studies |  |  |
|  | and Recommendations |  |  |
| ICANN-PSO General Assembly and Secretariat |  |  |  |
|  |  | 1 General Assembly meeting |  |
| Secretariat assumed for one year (rotation principle) |  |  |  |
| ITU will host the General Assembly |  | 7 P staff-months |  |
|  |  | 2 G staff-months |  |
| Conference calls with PSO-PC members, reports |  | Monthly conference calls |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2002 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| Study Group Publications |  |  |  |
| Editing and publication of approved texts in F, E, S | Expected results: | 22 P staff-months |  |
|  |  | 178 G staff-months | Res. 66 (Minneapolis, 1998): |
| Priorities: | Publication of 12,000 p. of Recs |  | Documents and publications of the Union |
| Availability of pre-published Recommendations within | and 1,000 p. of handbooks in | TSB Publication budget = |  |
| one month of approval. | three languages | 264,500 F direct costs |  |
|  |  | 232,000 F invoiced costs |  |
| Quickpub procedures | Key indicators: |  | Res. 71 (Minneapolis, 1998): |
|  |  | Covered by sales revenues | Production high-quality Recommendations |
| Quality control of texts | Decrease time to edit publications |  | quickly in response to market demands |
|  | Pre-published Recs within 1 month |  |  |
| Common text procedure with the ISO | Quality control of texts |  |  |
|  | Worldwide dissemination |  |  |
|  | Increased use of ITU-T Recs. |  |  |
| Operational Bulletin |  |  |  |
| Publication containing administrative and operational | Expected results: | 15 P staff-months | Res. 66 (Minneapolis, 1998): |
| information exchanged between administration, ROAs etc |  | 16 G staff-months | Documents and publications of the Union |
|  | 24 issues per year |  |  |
| Lists of country codes and dialing codes for all |  | 14,500 F direct costs |  |
| international services |  | 20,000 F invoiced costs |  |
| Priority: |  | Covered by sales revenues |  |
| Immediate posting of information to members |  |  |  |
| Increase the distribution of the Operational Bulletin |  |  |  |
| Relations with State Members and Sector Members |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2002 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| Database development available to public |  |  |  |
| List of ITU-T Sector Members | Expected results: |  |  |
| Work program database | Availability of the information | 5 P staff-months |  |
| Patent statement database | to public | 3 G staff-months |  |
| Software statement database |  |  |  |
| Terminology database | Achievement indicators: | 5,000 F direct costs |  |
| List of Recommendations in force |  |  |  |
| List of recognized SDOs | Rapid and up-to-date |  |  |
| General and Meeting schedule Information on the WEB | Consultation |  |  |
| International numbering resources |  |  |  |
|  | Dissemination of operational |  |  |
| Priority: | Information to public |  |  |
| Improve the user-friendliness of public databases |  |  |  |
| New activity: |  |  |  |
| ASN.1 Module database |  |  |  |
| AAP database |  |  |  |
| Development of new databases as per request of Study |  |  |  |
| Group |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2002 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| UIFN registration |  |  | Res. 91 (Minneapolis, 1998): |
|  |  |  | Cost recovery for some products and services |
| Universal International Free phone Numbers registrar | Expected results: | 3 P staff-months |  |
|  | 3,750 UIFN Reservations | 13 G staff-months | ITU-T Recommendation E.169 |
| Priority: |  |  |  |
| Immediate reservations of UIFN numbers | Achievement indicators: | 374,000 F direct costs |  |
|  | Immediate registration of UIFNs |  |  |
|  | Customer satisfaction |  |  |
|  |  | Full cost recovery |  |
| UIPRN & UISCN registration |  |  |  |
| Universal International Premium Rate Numbers registrar | Expected results: | 1 P staff-month | Res. 91 (Minneapolis, 1998): |
| Universal International Shared Cost Numbers registrar | 600 UIPRN/UISCN reservations | 2 G staff-months | Cost recovery for some products and services |
|  | Achievement indicators: | 47,500 F direct costs | ITU-T Recommendations E.169.2 and E.169.3 |
|  | Immediate registration |  |  |
|  | Customer satisfaction | Full cost recovery |  |
| AESAs registration |  |  |  |
|  |  |  | Res. 91 (Minneapolis, 1998): |
| New initiative: | Expected results: | 1 P staff-month | Cost recovery for some products and services |
| ATM End System Addresses registrar | 300 AESAs reservations | 1 G staff-month |  |
|  |  |  | ITU-T Recommendations E.191.1 |
|  | Achievement indicators: | Full cost recovery |  |
|  | Immediate registration |  |  |
|  | Customer satisfaction |  |  |
| Codes for Groups of countries Opening E.164 numbering resources UPT numbering administration |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2002 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| Bureau support |  |  |  |
| Membership |  | 32 P staff-months | Res. 72 (Minneapolis, 1998): Linking strategic, |
| Meeting organization and logistical support |  | 20 G staff-months | financial and operational planning in ITU |
| Document control |  |  | Res. 104 (Minneapolis, 1998): |
| Administrative support |  | 10,025,500 F direct costs | Reduction of the volume and cost of documentation |
| Finance and budget |  | 139,000 F document costs | for ITU conferences |
| Director Office |  |  | Res. 71 (Minneapolis, 1998), annex 2: |
| Internal management |  |  | Goals for improved management |
| Operational planning |  |  |  |
| Gender perspective issues |  |  | Res. 70 (Minneapolis, 1998): |
|  |  |  | Inclusion of gender perspective in the work of ITU |
| ###### Director’s Ad Hoc IPR Group |  |  | Res. 1187 Council 2001 |
|  |  | 2 P staff-months | Gender perspective in ITU Human Resource |
|  |  | 3 G staff-months | management policy and practice |
|  |  | 2 planned meetings 4 working days |  |
| EDH (Electronic Document Handling) |  |  | Res. 66 (Minneapolis, 1998): |
|  |  |  | Documents and publications of the Union |
| Posting of documents | Expected results: | 40 G staff-months | Res. 1141 Council 1999 |
| WEB development | Immediate posting of information |  | Reduction of the cost and volume of documentation for |
| Customer support (TSB helpdesk) |  |  | Conferences and Assemblies and the Council |
| Alternate Approval Process Implementation | Achievement indicators: |  |  |
|  | Increased number of visitors |  | Res. 32 (WTSA-2000) |
| Maintaining of the ITU-T Website and relevant information | Customer satisfaction |  | Strengthening the use of electronic document handling |
|  |  |  | for the work of ITU-T |

___________

Telecommunication Standardization Sector

Linkage between Strategic, Financial and Operational Planning for the year 2003

Resolution 72 (Minneapolis, 1998)

This document presents a general overview of the Operational Plan of the Telecommunication Standardization Sector for the year 2003.

Use of TSB resources in 2003 - Overall recapitulation

| ITU-T activities | P staff-months | G staff-months | Direct costs CHF | Document costs CHF |
| --- | --- | --- | --- | --- |
| - TSAG (Telecommunication Standardization Advisory Group) | 13 | 8 | 255,000 | 240,000 |
| 2 planned meetings, 10 working days |  |  |  |  |
| - Chairmen’ meetings: | 1 | 1 |  |  |
| 1 planned meeting, 2 working days |  |  |  |  |
| - Study Group meetings: | 89 | 134 | 3,45,000 | 5,850,000 |
| 22 planned meetings, 167 working days |  |  |  |  |
| 12 Study Groups |  |  |  |  |
| 1 Special Study Group |  |  |  |  |
| 199 Questions under study |  |  |  |  |
| 375 new ITU-T Recommendations, |  |  |  |  |
| 12,500 pages of text |  |  |  |  |
| 17,140 pages of translation |  |  |  |  |
| 46,030 pages of typing pool |  |  |  |  |
| 42,180,000 pages of reprography |  |  |  |  |
| - Seminars and technical workshops: | 9 | 6 | 100,00 |  |
| 3 planned workshops, 12 working days |  |  |  |  |
| - Regional presence: | 9 | 9 | 225,000 |  |
| 4 regional briefing meetings |  |  |  |  |
| Study Group meetings in the regions |  |  |  |  |
| Workshops in the regions |  |  |  |  |
| Regional tariff group meetings |  |  |  |  |
| - Promoting ITU-T activities | 18 | 10 | 100,000 |  |
| - External cooperation | 9 | 12 |  |  |
| - Study Group publications: | 22 | 178 | 264,500 | 232,000 |
| 12,000 pages of Recommendations to published |  |  |  |  |
| per language (x3) |  |  |  |  |
| - Operational Bulletin: | 15 | 16 | 14,500 | 20,000 |
| 24 issues a year |  |  |  |  |
| - Databases accessible to public | 5 | 3 | 5,000 |  |
| - UIFN registrar | 3 | 13 | 374,000 |  |
| (Universal International Freephone Numbers) |  |  |  |  |
| 3,750 UIFN |  |  |  |  |
| - UIPRN/UISCN registrar | 1 | 2 | 47,500 |  |
| (Universal International Premium Rate Numbers) |  |  |  |  |
| (Universal International Shared Cost Numbers) |  |  |  |  |
| 600 UIPRN/UISCN |  |  |  |  |
| - AESA registrar | 1 | 1 | - | - |
| (ATM End System Addresses) |  |  |  |  |
| 300 AESA |  |  |  |  |
| - Bureau support | 35 | 22 | 10,020,500 | 139,000 |
| - EDH (Electronic Document Handling) |  | 40 |  |  |
| Documents & information posted on ITU Website |  |  |  |  |
| Total of allocated resources | 230 | 455 | 14,451,000 | 6,481,000 |

Assumption: 10 staff-months per person per year

##### TSB - Linkage between Strategic, Financial and Operational Planning - 2003

| #### Operational Activities | #### Objectives | Allocated Resources | #### Relationship to Strategic |
| --- | --- | --- | --- |
|  | and Performance Indicators | from the 2003 budget | Policies and Plans / PP-98 |
| Telecommunication Standardization Advisory Group |  |  | Res. 71 (Minneapolis, 1998): |
|  |  |  | Strategic plan for the Union (1999-2003) |
| Reviews priorities and strategies for ITU-T’s activities | Expected results: |  | Res. 74 (Minneapolis. 1998): |
| Reviews progress of work program & working methods |  | 2 planned meeting | Review and improvement of the management, |
| Maintains the A Series (Organization of the work of | Advices to the TSB Director | with its working parties | functioning and structure of the ITU |
| ITU-T) |  | 10 working days | Res. 16 (Minneapolis, 1998): |
| Acts on behalf of the WTSA between WTSAs | A Series of Recommendations |  | Refinement of the ITU-R and ITU-T Sectors |
| Establishes / discontinues Study Groups | (Organization of ITU-T work) | 13 P staff-months | Res. 82 (Minneapolis, 1998): |
| Advises on financial matters |  | 8 G staff-months | Approval of Questions and Recommendations |
| cooperation and coordination | Achievement indicators: |  | Res. 72 (Minneapolis, 1998): Linking strategic, |
|  |  | 255,000 F direct costs: | financial and operational planning in ITU |
|  | Minimized duplication of work | Interpretation, | Res. 66 (Minneapolis, 1998): |
|  | Harmonized technical standards | Meeting staff | Documents and publications of the Union |
|  | Enhanced operational efficiency |  |  |
|  | of ITU-T | 240,000 F document costs : | Res. 1141 Council 1999 |
|  |  | Translation, typing pool | Reduction of the cost and volume of documentation |
|  |  | Reprography | for Conferences and Assemblies and the Council |
|  |  |  | Res. 18 (WTSA-2000) |
|  |  |  | Principles and procedures for the allocation of work |
|  |  |  | to, and coordination between, the |
|  |  |  | Radiocommunication and Telecommunication |
|  |  |  | Standardization Sectors |
|  |  |  | Res. 22 (WTSA-2000) |
|  |  |  | Authorization for TSAG to act between WTSAs |
|  |  |  | Res. 32 (WTSA-2000) |
|  |  |  | Strengthening the use of electronic document |
|  |  |  | Handling for the work of ITU-T |
|  |  |  | Res. 33 (WTSA-2000) |
|  |  |  | Guidelines for ITU-T strategic activities |
| Chairmen's meeting |  |  |  |
| Definition and coordination of SG work plan |  | 2planned meetings |  |
| Finalization of meeting schedule for following year |  | 4working days |  |
| Discussion on budget allocation on the various SG |  |  |  |
| Improvement in communication amongst SG |  | 1 P staff-month |  |
| Priority in studies |  | 1 G staff-month |  |

| #### Operational Activities | #### Objectives and Performance Indicators | Allocated Resources from the 2003 budget | #### Relationship to Strategic Policies and Plans/ PP-98 |
| --- | --- | --- | --- |
| Study Group Meetings | Expected results: | Total for all the Study Groups: |  |
| Study Group responsibility and mandates: | +/- 315 new ITU-T Rec. | 22 planned SG meetings | Article 17 of the Constitution |
| See Res. 2 (WTSA-2000) | totaling about 12,500 pages | with their working parties |  |
|  |  | 155 working days | Article14 of the Convention |
|  | Development of a programme of technical workshops | 2 planned workshops (see workshop activities) |  |
|  |  | 89 P staff-months | Resolutions of Minneapolis, 1998 |
|  |  | 134 G staff-months | See below |
| 12 Study Groups | Key performance indicators: | 3,04500 F direct costs: |  |
| 1 Special Study Group |  | Interpretation |  |
| 199 technical, operating and tariff Questions under study | Worldwide utilization of ITU-T Recs. | Meeting staff |  |
|  | Text quality & market response | Mail expenses |  |
| Attention is paid to improvement of telecommunications | Reduction in time-to-market for | 5,850,000 F document costs : |  |
| in developing countries and cooperation with national, | Recs (AAP implementation) | Total French +English +Spanish: |  |
| regional and international organizations | Stability of texts and avoidance of | 17,140 pages of translation |  |
|  | document reprocessing | 46,030 pages of typing pool |  |
|  | Membership satisfaction | 42,180,000 pages of reprography |  |
| SG 2 – Operational aspects of service provision, |  |  | Res. 99 (Minneapolis, 1998): Status of Palestine in ITU |
| networks and performance |  |  | Res. 21 (Rev. Minneapolis, 1998): Alternative calling |
|  |  |  | procedures on international telecom. networks |
| Priorities: | Expected results: | 1 planned SG meeting |  |
| Service definition, Numbering, Routing and Global Mobility |  | and their WPs | Res. 79 (Minneapolis, 1998): |
| Numbering Coordination Team (NCT) | 25 Recommendations to be | 9 working days | International Telecommunication Regulations |
| Resolution 20 and coordination with TSB | approved in 2003 = 1,000 pages |  | Res. 101 (Minneapolis, 1998): |
|  |  | 7 P staff months | Internet Protocol (IP)-based networks |
| Lead Study group for service definition, numbering |  | 5 G staff months | Res. 89 (Minneapolis, 1998): |
| and routing |  |  | Decreased use of international telex service |
|  |  | 43,000 F direct costs | Res. 71 (Minneapolis, 1998) Goal 3: |
| New activities: |  | 102,000 F document costs | Developing and implementing administrative |
| ENUM |  |  | procedures for numbering plans for |
| Service level agreements (SLAs) |  | 3 Working Party meetings | international networks and services |
| Human factors |  | 3 Rapporteur Group meetings | Res. 71 (Minneapolis, 1998), F.4: |
| Internet root system |  |  | facilitating the interworking of global personal |
|  |  |  | radiocommunication systems with public |
| 9 Questions |  |  | telecommunication networks |
|  |  |  | Res. 20 (WTSA-2000) |
|  |  |  | Procedures for allocation and management of |
|  |  |  | International numbering resources |
|  |  |  | Opinion D (WPTF-2001): |
|  |  |  | Essential studies by ITU to facilitate the introduction |
|  |  |  | Of “IP Telephony” |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2003 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SG 3 - Tariff and accounting principles, including |  |  |  |
| related telecommunications, economic and |  |  |  |
| policy issues |  |  |  |
|  |  |  | Res. 71 (Minneapolis, 1998), F.4: |
| Priorities: | Expected results: | 2 planned SG meeting | Develop Recommendations to achieve |
| Accounting rate reform and implementation of new |  | and its WPs | accounting rate reform and to propose |
| remuneration systems | 5 Recommendations to be | 10 working days | means to encourage their implementation |
| Implementation of Resolutions adopted by PP-02 | approved in 2003: 250 pages |  | Res. 71 (Minneapolis, 1998), D.1, 28.2 |
| Improvement and implementation of cost methodologies |  | 5 P staff months | Achieving Accounting rate reform and proposing |
| Impact of new practices bypassing accounting rate system |  | 6 G staff months | means to encourage their implementation |
| Tariff principles for services using new technologies |  | 176,000 F direct costs |  |
|  |  | 153,000 F document costs | Res. 21 (Rev. Minneapolis, 1998): Alternative calling |
| New activities: |  |  | procedures on international telecom. networks |
| Impact and tariff study on Internet / IP-based Networks |  |  |  |
| New Generation Network |  | 2 Rapporteur meetings | Res. 22 (Minneapolis, 1998): Apportionment of |
| Settlement of balance of account based on IP Detailed |  | 5 working days | revenues in providing international telecom. services |
| Records |  |  |  |
| Tariff principles for international mobile services |  |  | Res. 101 (Minneapolis, 1998): |
| 4 Questions |  |  |  |
|  |  |  | Internet Protocol (IP)-based networks |
| Tariff Group for Africa (TAF) |  |  |  |
| Tariff Group for Latin America (TAL) |  |  | Res. 103 (Minneapolis, 1998): |
| Tariff Group for Asia and Oceania (TAS) |  |  | International Telecommunication Regulations |
| Priorities: |  |  | Res. 26 (WTSA-2000) |
| TAF: Accounting rates, Call back, Cost model development | Expected results: | 3 planned meetings | Assistance to the Regional Tariff Groups |
| TAL: Cost model development |  | 10 working days |  |
| Determination of maximum accounting rates | Preparation of Recommendations |  | Res. 29 (WTSA-2000) |
| TAS: New cost model development, | and regional cost model | 3 P staff months | Alternative calling procedures on international |
| Regional case study on cost/price |  | 3 G staff months | telecommunication networks |
| Regional tariff model for Internet |  |  |  |
|  |  |  | Res. 41 (WTSA-2000) |
| New activities: |  |  | Accounting rate principles for international |
| TAF: Use of internet in Africa |  |  | telephone services |
| TAL: Impact of IP Telephony in the region |  |  |  |
| Tariff Group for Europe and the Mediterranean Basin |  |  |  |
| activity in abeyance |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2003 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SG 4 – Telecommunication management, |  |  |  |
| including TMN |  |  |  |
| Priorities: | Expected results : | 2 planned SG meetings |  |
| Management of telecommunication services, networks, | 35 Recommendations to be | and its WPs | Res. 71 (Minneapolis, 1998), F.4: |
| and equipment using the TMN framework | approved in 2003: 1,700 pages | 20 working days | Further evolution of network infrastructures |
| Other telecommunication management studies relating to |  |  | in the area of control |
| designations, transport-related operations procedures, |  | 8 P staff months |  |
| test and measurement techniques and instrumentation |  | 8 G staff months |  |
|  |  | 180,000 F direct costs |  |
| Cooperation with other standard developing organizations |  | 800,000 F document costs |  |
| Lead Study Group on TMN |  |  |  |
| New activities: |  | 30 Rapporteur meetings |  |
| ASON network Management activities |  | 170 working days |  |
| Management activities regarding optical networks and 3G wireless networks |  |  |  |
| XML-based activities including application of tML framework |  |  |  |
| 17 Questions |  |  |  |
| SG 5 - Protection against electromagnetic |  |  |  |
| environment effects |  |  |  |
| Priorities: | Expected results: | 2 planned SG meeting | Res. 71 (Minneapolis, 1998), F.4: |
| Resistibility, EMC and safety aspects related to |  | and its WPs | Covering the further evolution of network infrastructures |
| telecommunications networks | 7 Recommendations to be | 10 working days |  |
| Cooperation with other international organizations | approved in 2003: 100 pages |  |  |
|  |  | 3 P staff months |  |
| New activity: |  | 3 G staff months |  |
| Protection against the effects of mobile equipment and |  | 46,000 F direct costs |  |
| radio systems |  | 107,000 F document costs |  |
| Workshop on SG 5 activities |  |  |  |
| 14 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2003 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SG 6 - Outside plant |  |  |  |
| Priorities: | Expected results: | 2 planned SG meeting | Res. 71 (Minneapolis, 1998), F.4: |
| Outside plant and access for telecommunication |  | and its WPs | Covering the further evolution of network infrastructures |
| networks | 8 Recommendations to be | 10 working days |  |
|  | approved in 2003 = 300 pages |  | Development of case studies, guidelines & handbooks |
| Cooperation with IEC, especially TC 86 |  | 2 P staff months |  |
|  |  | 2 G staff months |  |
| 10 Questions |  | 46,000 F direct costs |  |
|  |  | 115,000 F document costs |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2003 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| ###### SG 9 – Integrated broadband cable networks and |  |  |  |
| television and sound transmission |  |  |  |
| Priorities: | Expected results: | 2 planned SG meeting: | Res. 71 (Minneapolis, 1998), F.4: |
| IP and GII over cable distribution networks |  | and its WPs | Multimedia applications arising from the convergence |
| Television and sound over the core network | 20 Recommendations to be | 10 working days | of telecommunication, broadcasting, computer and |
| Coordination with ITU-R on broadcasting matters | approved in 2003: 1,500 pages |  | information technology |
|  |  | 6 P staff months |  |
| Lead Study Group on integrated broadband cable |  | 9 G staff months | Res. 101 (Minneapolis, 1998): |
| and television networks |  | 66,000 F direct costs | Internet Protocol (IP)-based networks |
|  |  | 596,000 F document costs |  |
| Webcasting |  |  |  |
| Packet cable, IP over cable |  |  |  |
| 21 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2003 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SG 11 - Signalling requirements and protocols |  |  |  |
| Priorities: | Expected results: | 1 planned SG meeting: | Res. 71 (Minneapolis, 1998), D.2, 29.2: |
|  |  | and its WPs | Developing Recommendations for new technologies |
| Signalling support for Internet (IP)-based applications | 25 Recommendations to be | 10 working days | and applications - global multimedia and mobility |
|  | approved in 2003, 1200 pages |  |  |
| Intelligent Networks. |  | 8 P staff months | Res. 71 (Minneapolis, 1998), F.4: |
|  |  | 7 G staff months | Facilitating the integration of existing and new |
| Lead Study Group on intelligent networks |  | 80,000 F direct costs | transmission media in public networks, |
|  |  | 545,000 F document costs | in the area of signalling |
| Signalling for Access, N&B-ISDN, |  |  |  |
| and new generation networks |  |  | Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | Internet Protocol (IP) related aspects as well as the |
| Cooperation and development of ITU-T Recommendations |  |  | interoperability and convergence of IP-based networks, |
| with regional standards bodies/fora on signalling-related |  |  | the Internet, with existing network infrastructures |
| activities for IP |  |  | Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | Covering the future evolution of network infrastructures, |
| Coordination with relevant ITU-T/ITU-R SGs/Wps for |  |  | e.g. in the areas of network access, signalling and |
| signaling support of fixed-mobile aspects |  |  | control |
| 15 Questions |  |  |  |
| SG 12 - End-to-end transmission performance of |  |  |  |
| networks and terminals |  |  |  |
| Priorities: | Expected results: | 2 planned SG meeting |  |
| Performance assessment |  | and its WPs |  |
|  | 18 Recommendations to be | 10 working days | Res. 101 (Minneapolis, 1998): |
| Lead Study Group on Quality of services and performance | approved in 2003: 400 pages |  | Performance quality assessment of IP-based networks |
|  |  | 5 P staff months |  |
| New activities: |  | 6 G staff months | Res. 71 (Minneapolis, 1998), F.4: |
| Development of Recs. on Quality aspects of IP-based |  | 38,000 F direct costs | Multimedia applications |
| network |  | 276,000 F document costs |  |
| Workshop on ITU-T & SG 12 activities |  |  |  |
| 16 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2003 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SG 13 – Multi-protocol and IP-based networks |  |  |  |
| and their internetworking |  |  |  |
|  |  |  | Res. 73 (Minneapolis, 1998): World Summit on the information society |
| Priorities: | Expected results: | 1 planned SG meeting: |  |
| General network aspects, Global Information |  | and its WPs | Res. 101 (Minneapolis, 1998): Internet Protocol (IP)-based networks |
| Infrastructures (GII), B-ISDN and IP (Internet Protocol) | 31 Recommendations to be | 9 working days |  |
| Fostering cooperation with IETF | approved in 2003: 1,550 pages |  | Res. 71 (Minneapolis, 1998), D.2, 29.2: |
|  |  | 3 P staff months | Developing Recommendations for new technologies |
| Monitoring IP and GII projects |  | 3 G staff months | and applications such as appropriate aspects of the GII |
|  |  | 130,000 F direct costs | and global multimedia and mobility |
| Lead Study Group for IP related matters, B-ISDN, |  | 749,000 F document costs |  |
| Global Information Infrastructure and satellite matters |  |  | Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | Internet Protocol (IP) related aspects as well |
|  |  |  | as the interoperability and convergence of |
|  |  |  | IP-based networks, the Internet, with |
|  |  |  | existing network infrastructures |
| NGW |  |  | Res. 71 (Minneapolis, 1998), F.4: |
| VoIMPLS |  |  | Facilitating the integration of existing and |
|  |  |  | new transmission media in public networks, |
| Integrated communication architecture, including the |  |  | in cooperation with ITU-R for radio |
| impact of convergence |  |  | transmission aspects |
| Workshop on ITU-T & SG 13 activities |  |  | Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | Further evolution of network infrastructures in |
|  |  |  | the areas of network access and interfaces |
| 16 Questions |  |  | Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | Implementation of the GII |
|  |  |  | Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | Integration of existing and new |
|  |  |  | transmission media in public networks |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2003 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| ICG SAT |  |  |  |
| Intersector Coordination Group on Satellite Matters |  |  |  |
| Under the Lead of SG 13 |  |  | Res. 71 (Minneapolis, 1998), F.4: |
| Priorities: | Expected results: | No planned meeting so far | Facilitating the integration of existing and new |
|  |  |  | transmission media in public networks, in cooperation |
| To take into account satellite specificity within | Performance |  | with ITU-R for radio transmission aspects |
| telecommunication network including impact of | Achieved consistency of |  |  |
| IP-based network and multimedia network and system | Recommendations of various |  |  |
| Keeping up to date database | Study Groups for full integration |  |  |
|  | of the sat-transmission in |  |  |
| Coordination with ITU-R | public networks |  |  |
| Organization of workshop |  |  |  |
| Strengthening relationship with ITU-D |  |  |  |
| SG 15 – Optical and other transport networks |  |  |  |
| Priorities: | Expected results: | 2 planned SG meeting | Res. 71 (Minneapolis, 1998), F.4: |
| Access Network |  | and its WPs | Further evolution of network infrastructures |
| - broadband optical access | 28 Recommendations to be | 20 working days | in the areas of network access, interfaces |
| - refinements & enhancements to SDL | approved in 2003: 800 pages |  | and optical networking |
| - phone line networking |  | 6 P staff months |  |
| - IP on Access Network |  | 7 G staff months | Res. 71 (Minneapolis, 1998), F.4: |
| Network signal processing |  | 180,000 F direct costs | Facilitating the integration of existing and |
| - interaction of signal processing (OTN) |  | 1,600,000 F document costs | new transmission media in public networks, |
| Optical transport network structure |  |  | in cooperation with ITU-R for radio |
| - automatic switched optical network (ASON) |  |  | transmission aspects |
| - network management & control |  |  |  |
| OTN technology |  |  |  |
| -coarse & dense wavelength division multiplexing (WDM) |  |  |  |
| - fiber characteristics |  |  |  |
| - transmission technology |  |  |  |
| - IP on WDM |  |  |  |
| Cooperation with IEC and other SDOs |  |  |  |
| Lead Study Group on access network transport |  |  |  |
| Lead Study Group on optical technology |  |  |  |
| 19 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2003 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SG 16 - Multimedia services, systems and |  |  |  |
| terminals |  |  |  |
| Priorities: |  |  |  |
| IP mobility |  | 1 planned SG meetings |  |
| Multimedia platform and interworking |  | and its WPs | Res. 71 (Minneapolis, 1998), F.4: |
| Media Coding |  | 9 working days |  |
| Multimedia framework, MEDIACOM-2004 project |  |  |  |
| Cooperation with other Standard Development | Expected results: | 10 P staff months | Multimedia applications arising from the convergence |
| Organization |  | 8 G staff months | of telecommunication, broadcasting, computer and |
| Lead Study Group on multimedia services, | 40 Recommendations to be | 142,000 F direct costs | information technology |
| systems and terminals | approved in 2003: 1,500 pages | 749,000 F document costs |  |
| Lead Study Group on e-business and e-commerce |  |  |  |
|  |  |  | Res. 101 (Minneapolis, 1998): |
| New activities: |  |  | Internet Protocol (IP)-based networks |
| E-commerce, E-business |  |  |  |
| 23 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2003 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SG 17 - Data Networks and Telecommunication |  |  |  |
| Software |  |  |  |
| Priorities: | Expected results: | 1 planned SG meetings | Res. 71 (Minneapolis, 1998), F.4: |
| Additions to a set of Directory Recs. |  | and its WPs | Further evolution of networks infrastructures |
| Open Distributed Processing (ODP), Frame Relay | 50 Recommendations to be | 8 working days | in the area of security |
| Communication System Security and for interworking | approved in 2003: 2,000 pages |  | Interoperability of IP-based networks with |
| with IP-based networks |  | 6 P staff months | existing networks |
| Additions to/revision of the set of ASN.1 Recs |  | 6 G staff months |  |
| Cooperation with ISO/IEC |  |  |  |
| Contribution to the coordination effort with ISO, IEC and |  | 150,000 F direct costs | Res. 101 (Minneapolis, 1998) |
| UN/ECE for E-business standardization |  | 713,000 F document costs | Collaborative activities on IP-based network with |
|  |  |  | ISOC/IETF |
| Lead Study Group on Frame Relay |  |  |  |
| Lead Study Group on Communication System |  |  |  |
| Security |  |  | Network languages |
| Lead Study Group on Languages and Description |  |  |  |
| Techniques |  |  | TSAG (Geneva, 19-23 March 2001) |
|  |  |  | TSAG approved the merger of Study group 7 and 10 |
|  |  |  | into a single Study Group 17 |
| Enhancement of communication system security for |  |  |  |
| E-commerce |  |  |  |
| Development of the ITU-T ASN.1 Project |  |  |  |
| Continuation of the provision of ASN.1 modules to the |  |  |  |
| ASN.1 database |  |  |  |
| 27 Questions |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2003 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| SSG – Special Study Group IMT-2000 and beyond |  |  |  |
|  |  |  | Res. 38 (WTSA-2000) |
| Priorities: |  | 8 P staff months | Coordination among ITU-T, ITU-R and ITU-D for |
| Network aspects of IMT-2000 and beyond | Expected results: | 9 G staff months | IMT-2000 activities |
| (International Mobile Telecommunications-2000) |  | 75,000 F direct costs |  |
| Wireless access to IP-based networks |  | 210,000 F document costs |  |
| Convergence of mobile and fixed networks |  |  |  |
| Mobility management, mobile multimedia functions | 2 Recommendations to be | 3 planned SSG meeting |  |
| Internetworking, interoperability | approved in 2003: 100 pages | and its WPs |  |
|  |  | 15 working days |  |
| Lead Study Group on IMT-2000 and beyond | 2 NTO (New Type of Output) to be |  |  |
| and for mobility | approved in 2003: 50 pages | 4 Rapporteur meetings |  |
|  |  | 12 working days |  |
| New activities: |  |  |  |
| Workshop on ITU-T and SSG activities |  | 10 conference calls |  |
| Electronic meetings |  | 6 electronic meetings |  |
| 8 Questions |  | 1 workshop, 1 full day |  |
| Workshops |  | 2 planned workshops |  |
|  |  | 10 working days |  |
| Dissemination of expert knowledge on state-of-the-art | Expected results: | 9 P staff-months |  |
| technologies, |  | 6 G staff-months |  |
| Promotion of awareness of ITU-T activities, | Participation of delegates from |  |  |
| working methods and priorities | developing countries in the | 100,000 F direct costs: |  |
|  | activities of the Sector | Fellowships for SG 3 |  |
|  | Strengthening regional presence |  |  |
|  | Achievement indicators: |  |  |
|  | Dissemination of expert technology |  |  |
|  | Integration of developing countries |  |  |
|  | concerns in ITU-T outputs |  |  |
|  | Coordination of activities within |  |  |
|  | Study Groups and with other SDOs |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2003 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| Regional presence |  |  |  |
| Strengthening the regional presence | Expected results: | 4 regional briefing meetings | Res. 71 (Minneapolis, 1998), F.4: |
| Participation in external conferences |  | SG meetings in the regions | to work with BDT with special attention to |
| Assistance to ITU-D | Strengthened regional presence | Workshops in the regions | telecommunication development in developing |
|  | Awareness of ITU-T activities | Regional tariff group meetings | countries, and to cooperate with the other Sectors |
|  |  |  | in the organization of information meetings, seminars |
|  | Achievement indicators: | 9 P staff-months | and workshops and in the development of |
| Organization of seminars in the field |  | 9 G staff-month | case studies, guidelines and handbooks. |
| Assistance to the Regions | Membership satisfaction |  |  |
| Regional briefing meetings | Dissemination of ITU-T studies | 225,000 F direct costs | Res. 25 (Rev. Minneapolis, 1998), |
|  | and Recommendations |  | Strengthening the Regional presence |
| Promoting the ITU-T |  |  |  |
| Press releases | Expected results: | 18 P staff-months |  |
| ITU-T presence in external events | Awareness of ITU-T activities | 10 G staff-month |  |
| Presentation of ITU-T activities during | Increased interest of Membership |  |  |
| external workshops |  | 100,000 F direct costs |  |
| Promotion events | Achievement indicators: |  |  |
|  | Higher number of Sector Members |  |  |
|  | Increased participation in the |  |  |
|  | Sector activities |  |  |
| External cooperation |  |  |  |
| Assistance to membership and Telecom community | Expected results: | 9 P staff-months |  |
| Assistance and cooperation with other Sectors | Worldwide coordination | 12 G staff-months |  |
| Liaison and coordination with international and regional | Promotion of ITU-T activities |  |  |
| organizations | Signature of MoUs |  |  |
| Cooperation with other standard organizations |  |  |  |
| Participation in external conferences | Achievement indicators: |  |  |
| IPR issues | Customer and membership |  |  |
|  | satisfaction |  |  |
|  | Dissemination of ITU-T studies |  |  |
|  | and Recommendations |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2003 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| Study Group Publications |  |  |  |
| Editing and publication of approved texts in F, E, S | Expected results: | 22 P staff-months |  |
|  |  | 178 G staff-months | Res. 66 (Minneapolis, 1998): |
| Priorities: | Publication of 12,000 p. of Recs |  | Documents and publications of the Union |
| Availability of pre-published Recommendations within | and 1,000 p. of handbooks in | TSB Publication budget = |  |
| one month of approval. | three languages | 264,500 F direct costs |  |
|  |  | 232,000 F invoiced costs |  |
| Quickpub procedures | Key indicators: |  | Res. 71 (Minneapolis, 1998): |
|  |  | Covered by sales revenues | Production high-quality Recommendations |
| Quality control of texts | Decrease time to edit publications |  | quickly in response to market demands |
|  | Pre-published Recs within 1 month |  |  |
| Common text procedure with the ISO | Quality control of texts |  |  |
|  | Worldwide dissemination |  |  |
|  | Increased use of ITU-T Recs. |  |  |
| Operational Bulletin |  |  |  |
| Publication containing administrative and operational | Expected results: | 15 P staff-months | Res. 66 (Minneapolis, 1998): |
| information exchanged between administration, ROAs etc |  | 16 G staff-months | Documents and publications of the Union |
|  | 24 issues per year |  |  |
| Lists of country codes and dialing codes for all |  | 14,500 F direct costs |  |
| international services |  | 20,000 F invoiced costs |  |
| Priority: |  | Covered by sales revenues |  |
| Immediate posting of information to members |  |  |  |
| Increase the distribution of the Operational Bulletin |  |  |  |
| Relations with State Members and Sector Members |  |  |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2003 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| Database development available to public |  |  |  |
| List of ITU-T Sector Members | Expected results: |  |  |
| Work program database | Availability of the information | 5 P staff-months |  |
| Patent statement database | to public | 3 G staff-months |  |
| Software statement database |  |  |  |
| Terminology database | Achievement indicators: | 5,000 F direct costs |  |
| List of Recommendations in force |  |  |  |
| List of recognized SDOs | Rapid and up-to-date |  |  |
| General and Meeting schedule Information on the WEB | Consultation |  |  |
| International numbering resources |  |  |  |
|  | Dissemination of operational |  |  |
| Priority: | Information to public |  |  |
| Improve the user-friendliness of public databases |  |  |  |
| : |  |  |  |
| ASN.1 Module database |  |  |  |
| AAP database |  |  |  |
| Development of new databases as per request of Study |  |  |  |
| Group |  |  |  |
| UIFN registration |  |  | Res. 91 (Minneapolis, 1998): |
|  |  |  | Cost recovery for some products and services |
| Universal International Free phone Numbers registrar | Expected results: | 3 P staff-months |  |
|  | 3,750 UIFN Reservations | 13 G staff-months | ITU-T Recommendation E.169 |
| Priority: |  |  |  |
| Immediate reservations of UIFN numbers | Achievement indicators: | 374,000 F direct costs |  |
|  | Immediate registration of UIFNs |  |  |
|  | Customer satisfaction |  |  |
|  |  | Full cost recovery |  |
| UIPRN & UISCN registration |  |  |  |
| Universal International Premium Rate Numbers registrar | Expected results: | 1 P staff-months | Res. 91 (Minneapolis, 1998): |
| Universal International Shared Cost Numbers registrar | 600 UIPRN/UISCN reservations | 2 G staff-months | Cost recovery for some products and services |
|  | Achievement indicators: | 47,500 F direct costs | ITU-T Recommendations E.169.2 and E.169.3 |
|  | Immediate registration |  |  |
|  | Customer satisfaction | Full cost recovery |  |

| Operational Activities | Objectives and Performance Indicators | Allocated Resources from the 2003 budget | Relationship to Strategic Policies and Plans / PP-98 |
| --- | --- | --- | --- |
| AESAs registration |  |  |  |
|  |  |  | Res. 91 (Minneapolis, 1998): |
| New initiative: | Expected results: | 1 P staff-months | Cost recovery for some products and services |
| ATM End System Addresses registrar | 300 AESAs reservations | 1 G staff-months |  |
|  |  |  | ITU-T Recommendations E.191.1 |
|  | Achievement indicators: | Full cost recovery |  |
|  | Immediate registration |  |  |
|  | Customer satisfaction |  |  |
| Codes for Groups of countries Opening E.164 numbering resources UPT numbering administration |  |  |  |
| Bureau support |  |  |  |
| Membership |  | 35 P staff-months | Res. 72 (Minneapolis, 1998): Linking strategic, |
| Meeting organization and logistical support |  | 22 G staff-months | financial and operational planning in ITU |
| Document control |  |  | Res. 104 (Minneapolis, 1998): |
| Administrative support |  | 10,025,500 F direct costs | Reduction of the volume and cost of documentation |
| Finance and budget |  | 139,000 F document costs | for ITU conferences |
| Director Office |  |  | Res. 71 (Minneapolis, 1998), annex 2: |
| Internal management |  |  | Goals for improved management |
| Operational planning |  |  |  |
| Gender perspective issues |  |  | Res. 70 (Minneapolis, 1998): |
|  |  |  | Inclusion of gender perspective in the work of ITU |
| ###### Director’s Ad Hoc IPR Group |  |  | Res. 1187 Council 2001 |
|  |  |  | Gender perspective in ITU Human Resource |
|  |  |  | management policy and practice |
| EDH (Electronic Document Handling) |  |  | Res. 66 (Minneapolis, 1998): |
|  |  |  | Documents and publications of the Union |
| Posting of documents | Expected results: | 40 G staff-months | Res. 1141 Council 1999 |
| WEB development | Immediate posting of information |  | Reduction of the cost and volume of documentation for |
| Customer support (TSB helpdesk) |  |  | Conferences and Assemblies and the Council |
| Maintenance of electronic services in support of Alternate Approval Process | Achievement indicators: |  |  |
|  | Increased number of visitors |  | Res. 32 (WTSA-2000) |
| Maintenance of the ITU-T Website and relevant information | Customer satisfaction |  | Strengthening the use of electronic document handling |
|  |  |  | for the work of ITU-T |

___________