| INTERNATIONAL TELECOMMUNICATION UNION |  |  |
| --- | --- | --- |
|  | COUNCIL | Document C03/EP/4-E |
|  |  | 17 March 2003 |
|  |  | Original: English |
| GENEVA — 2003 SESSION — (5 - 16 MAY) |  |  |

ITU-T Operational Plan for 2003

Linkage between Strategic, Financial and Operational Planning for the year 2003 Resolution 72 (Minneapolis, 1998; revised Marrakesh, 2002) [Update 14 March 2003: updated workshops & editorial changes]

# Introduction:

The document presents an update of the Operational Plan of the Telecommunication Standardization Sector for the year 2003.  The first version had been submitted to Council at its 2002 session and was approved.

The total budget for 2003 remains unchanged, but the estimates for the number for the SG-meetings, workshops, the expected documentation and the associated costs have been updated.

The 2003 Operational Plan was reviewed and endorsed by the Telecommunication Standardization Advisory Group at its February 2003 session.

The 1-page table following the “Summary” below sums up the ITU-T activities and the associated financial and human resources. Details including the relationship with the strategic plan and policies are given on the remaining 18 pages.

The Operational Plan for 2004 can be found at http://www.itu.int/ITU-T/info/op-activities/index.html

# Summary:

- The TSB-budget for 2003 is 14,332,500 CHF. TSB-staff foreseen for 2003 is 23 P-staff and 44.5 G-staff (total 67.5).

- In 2003, the 12 Study Groups and the Special Study Group plan 24 meetings. Close to 200 questions are under study, expected to yield more than 300 texts (ITU-T Recommendations, amendments, corrigenda). ITU-T will continue its technical studies in cooperation with other standard developing organizations, regional entities.

- As in 2002, different technical workshops will be organized in order to disseminate expert knowledge on state-of-the-art technologies and increase awareness of ITU-T studies and projects.  The following workshops are already scheduled in 2003:

- “Telecommunications for Disaster Relief,” Geneva, 17-19 February 2003, in collaboration with Study Group 16 and experts from other Study Groups.

- “Member States’ Experiences with ccTLDs,” Geneva, 3-4 March 2003, in collaboration with Study Group 2 and the contribution of experts from several study groups.

- “Standardization in E-Health,” Geneva, 23-25 May 2003, in collaboration with SG 16, ITU-D, and experts from other Study Groups.

- “Challenges, Perspectives and Standardization Issues in E-Government”, Geneva, 5-6 June 2003.

- “Next Generation Networks: What, When and How? Encompassing Services, Transport Convergence, Mobility Issues and more ...”. Geneva, 9-10 July 2003; a joint workshop with SG 11, SG 13 and SSG.

- “Languages,” SG 17, Geneva, 13 September 2003.

- “QoS (Quality of Service),” SG 12, Geneva, 1-3 October 2003.

- “Telecommunications and the Automotive Industry”, tentative, 4th quarter.

- “Business and Economic Benefits of Standardization”, tentative, 4th quarter.

- A couple of topics are currently explored that may lead to additional workshops in 2003.

- Regional presence will continue according to Plenipotentiary Conferences (Minneapolis, 1998 & Marrakesh, 2002), WTSA resolution 17 (Montreal, 2000) and Council 2001 decisions.  Some Study Group meetings and technical workshops will be convened in the regions; contributions from various regions reflecting regional concerns to the ITU-T activities will be encouraged; a regional briefing session will be organized in each region focusing on priority questions and dissemination of ITU-T studies and Recommendations.

- Promotion of ITU-T will be increased, in accordance with Resolution 71 (Rev. Marrakesh, 2002) and Council Resolution 1181. Details are provided in a separate document.

- We expect a decrease in the number of UIFN (Universal International Freephone Numbers) registrations from the originally forecasted 3750 registrations to about 3000 registrations for 2003. There has been no take-off for UIPRN/UISCN (premium rate/shared cost numbers).

- Use of TSB resources in 2003 - Overall recapitulation

| - ITU-T activities | - P staff-months | - G staff-months | - Direct costs CHF (ITU-T Budget) | - Document costs CHF (Gen.Sec. Budget) |
| --- | --- | --- | --- | --- |
| - – TSAG (Telecomm. Standardization Advisory Group) - 2 planned meetings, 10 working days | - 13 | - 8 | - 253,000 | - 240,000 |
| - – Chairmen meetings: - 2 planned meetings, 4 working days | - 1 | - 1 |  |  |
| - – Study Group meetings: | - 74 | - 147 | - 3,045,000 | - 5,850,000 |
| - 24 planned meetings, 152 working days 12 Study Groups 1 Special Study Group 198 Questions under study 300 new ITU-T Recommendations, 12,770 pages of text 17,140 pages of translation in E, F, S 46,030 pages of typing pool 38,760,000 pages of reprography |  |  |  |  |
| - – Seminars and technical workshops: - 8 planned workshops, 19.5 working days | - 24 | - 7 | - 100,000 |  |
| - – Regional presence: - 4 regional briefing meetings Study Group meetings in the regions Workshops in the regions Regional tariff group meetings | - 10 | - 12 | - 225,000 |  |
| - – Promoting ITU-T activities | - 18 | - 9 | - 100,000 |  |
| - – External cooperation | - 9 | - 12 |  |  |
| - Study Group publications: - 12,000 pages of Recommendations to published per language (x3) | - 23 | - 157 | - 264,500 | - 232,000 |
| - – Operational Bulletin: 24 issues a year | - 17 | - 16 | - 14,500 | - 20,000 |
| - – Databases accessible to public | - 5 | - 8 |  |  |
| - – UIFN registrar - (Universal International Freephone Numbers) 3,000 UIFN | - 2 | - 13 | - 374,000 |  |
| - – UIPRN/UISCN registrar - (Universal International Premium Rate Numbers) (Universal International Shared Cost Numbers) 400 UIPRN/UISCN | - 1 | - 1 | - 47,500 |  |
| - – AESA registrar (ATM End System Addresses) 0 AESA | - – | - – | - – | - – |
| - – Bureau support | - 33 | - 20 |  | - 139,000 |
| - – EDH (Electronic Document Handling) - Documents & information posted on ITU Website |  | - 34 |  |  |
| - – TSB staff | -  = 230 | -  = 445 | - 9,909,000 |  |
| - Total of allocated resources |  |  | - 14,332,500 | - 6,481,000 |

- Assumption: 10 staff-months per person per year

##### TSB - Linkage between Strategic, Financial and Operational Planning - 2003

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - Telecommunication Standardization Advisory Group |  |  | - Res. 71 (Minneapolis, 1998): |
|  |  |  | - Strategic plan for the Union (1999-2003) |
| - Reviews priorities and strategies for ITU-T’s activities | - Expected results: |  | - Res. 74 (Minneapolis. 1998): |
| - Reviews progress of work program & working methods |  | - 2 planned meetings | - Review and improvement of the management, |
| - Maintains the A Series (Organization of the work of | - Advices to the TSB Director | - with its working parties | - functioning and structure of the ITU |
| - ITU-T) |  | - 10 working days | - Res. 16 (Minneapolis, 1998): |
| - Acts on behalf of the WTSA between WTSAs | - A Series of Recommendations |  | - Refinement of the ITU-R and ITU-T Sectors |
| - Establishes / discontinues Study Groups | - (Organization of ITU-T work) | - 13 P staff-months | - Res. 82 (Minneapolis, 1998): |
| - Advises on financial matters |  | - 8 G staff-months | - Approval of Questions and Recommendations |
| - cooperation and coordination | - Achievement indicators: |  | - Res. 72 (Minneapolis, 1998): Linking strategic, |
|  |  | - 253,000 F direct costs: | - financial and operational planning in ITU |
|  | - Minimized duplication of work | - Interpretation, | - Res. 66 (Minneapolis, 1998): |
|  | - Harmonized technical standards | - Meeting staff | - Documents and publications of the Union |
|  | - Enhanced operational efficiency |  |  |
|  | - of ITU-T | - 240,000 F document costs : | - Res. 1141 Council 1999 |
|  |  | - Translation, typing pool | - Reduction of the cost and volume of documentation |
|  |  | - Reprography | - for Conferences and Assemblies and the Council |
|  |  |  | - Res. 18 (WTSA-2000) |
|  |  |  | - Principles and procedures for the allocation of work |
|  |  |  | - to, and coordination between, the |
|  |  |  | - Radiocommunication and Telecommunication |
|  |  |  | - Standardization Sectors |
|  |  |  | - Res. 22 (WTSA-2000) |
|  |  |  | - Authorization for TSAG to act between WTSAs |
|  |  |  | - Res. 32 (WTSA-2000) |
|  |  |  | - Strengthening the use of electronic document |
|  |  |  | - Handling for the work of ITU-T |
|  |  |  | - Res. 33 (WTSA-2000) |
|  |  |  | - Guidelines for ITU-T strategic activities |
| - Chairmen's meeting |  |  |  |
| - Definition and coordination of SG work plan |  | - 2 planned meetings |  |
| - Finalization of meeting schedule for following year |  | - 4 working days |  |
| - Discussion on budget allocation on the various SG |  |  |  |
| - Improvement in communication amongst SG |  | - 1 P staff-month |  |
| - Priority in studies |  | - 1 G staff-month |  |

| #### Operational Activities | #### Objectives and Performance Indicators | - Allocated Resources - from the 2003 budget | #### Relationship to Strategic - Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - Study Group Meetings | - Expected results: | - Total for all the Study Groups: |  |
| - Study Group responsibility and mandates: | - +/- 300 new ITU-T Rec. | - 24 planned SG meetings | - Article 17 of the Constitution |
| - See Res. 2 (WTSA-2000) | - totaling about 12,770 pages | - with their working parties |  |
|  |  | - 152 working days | - Article14 of the Convention |
|  | - Development of a programme of |  |  |
|  | - technical workshops | - 74 P staff-months | - Resolutions of Minneapolis, 1998 |
|  |  | - 147 G staff-months | - See below |
| - 12 Study Groups | - Key performance indicators: | - 3,045,000 F direct costs: |  |
| - 1 Special Study Group |  | - Interpretation |  |
| - 198 technical, operating and tariff Questions under study | - Worldwide utilization of ITU-T Recs. | - Meeting staff |  |
|  | - Text quality & market response | - Mail expenses |  |
| - Attention is paid to improvement of telecommunications | - Reduction in time-to-market for | - 5,850,000 F document costs : |  |
| - in developing countries and cooperation with national, | - Recs (AAP implementation) | - Total French +English +Spanish: |  |
| - regional and international organizations | - Stability of texts and avoidance of | - 17,140 pages of translation |  |
|  | - document reprocessing | - 46,030 pages of typing pool |  |
|  | - Membership satisfaction | - 38,760,000 pages of reprography |  |

| #### Operational Activities | #### Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | #### Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - SG 2 – Operational aspects of service provision, |  |  | - Res. 99 (Minneapolis, 1998): Status of Palestine in ITU |
| - networks and performance |  |  | - Res. 21 (Rev. Marrakesh, 2002): Alternative calling |
|  |  |  | - procedures on international telecom. networks |
| - Priorities: | - Expected results: | - 2 planned SG meetings |  |
| - Service definition, Numbering, Routing and Global Mobility |  | - and their WPs | - Res. COM5/7 (Rev. Marrakesh, 2002): |
| - Numbering Coordination Team (NCT) | - 20 Recommendations to be | - 10 working days | - Review of the International Telecommunication |
| - Resolution 20 and coordination with TSB | - approved in 2003 = 400 pages |  | - Regulations |
|  |  | - 7 P staff months | - Res. 102 (Rev. Marrakesh, 2002): |
| - Lead Study group for service definition, numbering |  | - 5 G staff months | - Internet Protocol (IP)-based networks |
| - and routing |  |  | - Res. 89 (Minneapolis, 1998): |
|  |  | - 135,000 F direct costs | - Decreased use of international telex service |
|  |  | - 151,000 F document costs | - Res. 71 (Minneapolis, 1998) Goal 3: |
| - New activities: |  |  | - Developing and implementing administrative |
| - ENUM |  |  | - procedures for numbering plans for |
| - Service level agreements (SLAs) |  | - 3 Working Party meetings | - international networks and services |
| - Human factors |  | - 3 Rapporteur Group meetings | - Res. 71 (Minneapolis, 1998), F.4: |
| - Internet Domain Names and Addresses |  |  | - facilitating the interworking of global personal |
| - Disaster relief and Mitigation Operations (Formerly ETS) |  |  | - radiocommunication systems with public |
| - Security Aspects for Networks |  |  | - telecommunication networks |
| - Recommendation on future management of “.int” domain |  |  |  |
| - Community Connectivity Indicators |  |  | - Res. PLEN/1 (Marrakesh, 2002): |
|  |  |  | - Community Connectivity Indicators |
| - Workshop on Member States’ Experiences with ccTLDs |  | - 2 days |  |
|  |  |  | - Res. 20 (WTSA-2000) : |
|  |  |  | - Procedures for allocation and management of |
|  |  |  | - International numbering resources |
| - 9 Questions |  |  | - Opinion D (WPTF-2001): |
|  |  |  | - Essential studies by ITU to facilitate the introduction |
|  |  |  | - Of “IP Telephony” |
|  |  |  | - Res. PLEN/2 (Marrakesh, 2002): |
|  |  |  | - Strengthening the Role of ITU in Information and |
|  |  |  | - Communication Network Security |
|  |  |  | - Res. PLEN/5 (Marrakesh, 2002): |
|  |  |  | - Role of Administrations of Member States in the |
|  |  |  | - Management of Internationalized (multilingual) |
|  |  |  | - Domain Names |

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - SG 3 - Tariff and accounting principles, including |  |  |  |
| - related telecommunications, economic and |  |  |  |
| - policy issues |  |  |  |
|  |  |  | - Res. 71 (Minneapolis, 1998), F.4: |
| - Priorities: | - Expected results: | - 2 planned SG meetings | - Develop Recommendations to achieve |
| - Accounting rate reform and implementation of new |  | - and its WPs | - accounting rate reform and to propose |
| - remuneration systems | - 5 Recommendations to be | - 10 working days | - means to encourage their implementation |
| - Implementation of Resolutions adopted by PP-02 | - approved in 2003: 250 pages |  | - Res. 71 (Minneapolis, 1998), D.1, 28.2 |
| - Improvement and implementation of cost methodologies |  | - 5 P staff months | - Achieving Accounting rate reform and proposing |
| - Impact of new practices bypassing accounting rate system |  | - 5 G staff months | - means to encourage their implementation |
| - Tariff principles for services using new technologies |  | - 163,000 F direct costs |  |
|  |  | - 89,000 F document costs | - Res. 21 (Rev. Minneapolis, 1998): Alternative calling |
| - New activities: |  |  | - procedures on international telecom. networks |
| - Impact and tariff study on Internet / IP-based Networks |  |  |  |
| - New Generation Network |  | - 2 Rapporteur meetings | - Res. 22 (Minneapolis, 1998): Apportionment of |
| - Settlement of balance of account based on IP Detailed |  | - 5 working days | - revenues in providing international telecom. services |
| - Records |  |  |  |
| - Tariff principles for international mobile services |  |  | - Res. 101 (Minneapolis, 1998): |
| - 4 Questions |  |  |  |
|  |  |  | - Internet Protocol (IP)-based networks |
| - Tariff Group for Africa (TAF) |  |  |  |
| - Tariff Group for Latin America (TAL) |  |  | - Res. 103 (Minneapolis, 1998): |
| - Tariff Group for Asia and Oceania (TAS) |  |  | - International Telecommunication Regulations |
| - Priorities: |  |  | - Res. 26 (WTSA-2000) |
| - TAF: Accounting rates, Call back, Cost model development | - Expected results: | - 3 planned meetings | - Assistance to the Regional Tariff Groups |
| - TAL: Cost model development |  | - 10 working days |  |
| - Determination of maximum accounting rates | - Preparation of Recommendations |  | - Res. 29 (WTSA-2000) |
| - TAS: New cost model development, | - and regional cost model | - 3 P staff months | - Alternative calling procedures on international |
| - Regional case study on cost/price |  | - 3 G staff months | - telecommunication networks |
| - Regional tariff model for Internet |  |  |  |
| - 1 Workshop on tariff principles and methodologies in Mali |  | - 3 days |  |
| - 1 Workshop same topics in TAL region |  | - 3 days | - Res. 41 (WTSA-2000) |
|  |  |  | - Accounting rate principles for international |
| - New activities: |  |  | - telephone services |
| - TAF: Use of internet in Africa |  |  |  |
| - TAL: Impact of IP Telephony in the region |  |  |  |
| - TAS, TAF, TAL: Review of ITR |  |  | - Res. COM5/7 (Rev. Marrakesh, 2002): |
|  |  |  | - Review of the International Telecommunication |
| - Tariff Group for Europe and the Mediterranean Basin |  |  | - Regulations |
| - activity in abeyance |  |  |  |

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - SG 4 – Telecommunication management, |  |  |  |
| - including TMN |  |  |  |
| - Priorities: | - Expected results : | - 2 planned SG meetings |  |
| - TMN principles and architecture | - 30 Recommendations to be | - and its WPs | - Res. 71 (Minneapolis, 1998), F.4: |
| - - consolidation of functional requirements and | - approved in 2003: 1,200 pages | - 20 working days | - Further evolution of network infrastructures |
| - business approaches |  |  | - in the area of control |
|  |  | - 8 P staff months |  |
| - TMN infrastructure |  | - 8 G staff months |  |
| - - common working methods for specifying requirements |  |  |  |
| - and modelling |  | - 113,000 F direct costs |  |
| - - protocols |  | - 166,000 F document costs |  |
| - - open distributed management |  |  |  |
| - - IP-based TMN framework |  |  |  |
| - Support for inter-TMN (X) interfaces |  | - 25 Rapporteur meetings |  |
| - - application of telecommunication Markup Language |  | - 120 working days |  |
| - (tML) framework |  |  |  |
| - - management of emergency telecommunication service |  |  |  |
| - - QoS/SLA management |  |  |  |
| - Application of CORBA-based TMN framework |  |  |  |
| - Integrated management of hybrid circuit/packet/IP |  |  |  |
| - networks |  |  |  |
| - TMN information modelling |  |  |  |
| - - BPON management |  |  |  |
| - TMN support for 3G wireless |  |  |  |
| - Performance objectives and procedures, test equipment, |  |  |  |
| - and inter-operator designations |  |  |  |
| - - develop conversion guidelines for the current |  |  |  |
| - Recommendation M.1400 layer 1 extension |  |  |  |
| - Cooperation with outside SDOs, forums and consortia |  |  |  |
| - Lead Study Group on TMN |  |  |  |
| - 17 Questions |  |  |  |

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - SG 5 - Protection against electromagnetic |  |  |  |
| - environment effects |  |  |  |
| - Priorities: | - Expected results: | - 1 planned SG meeting | - Res. 71 (Minneapolis, 1998), F.4: |
| - Resistibility, EMC and safety aspects related to |  | - and its WPs | - Covering the further evolution of network infrastructures |
| - telecommunications networks | - 15 Recommendations to be | - 5 working days |  |
| - Cooperation with other international organizations | - approved in 2003: 170 pages |  |  |
|  |  | - 3 P staff months |  |
| - New activity: | - 1 handbook, 70 pages | - 3 G staff months |  |
| - Protection against the effects of mobile equipment and |  | - 34,000 F direct costs |  |
| - radio systems |  | - 47,000 F document costs |  |
| - 14 Questions |  |  |  |
| - SG 6 - Outside plant |  |  |  |
| - Priorities: | - Expected results: | - 2 planned SG meetings | - Res. 71 (Rev. Marrakesh, 2002), Goals 1,2,4,5: |
| - Outside plant and access for telecommunication |  | - and its WPs |  |
| - networks, bundling, access for multiservices/multioperators | - 14 Recommendations to be | - 10 working days |  |
|  | - approved in 2003 = 500 pages |  |  |
| - Cooperation with IEC, especially TC 86, TC 46 and SB4 |  | - 2 P staff months |  |
|  |  | - 2 G staff months |  |
| - 10 Questions |  | - 33,000 F direct costs |  |
|  |  | - 88,000 F document costs |  |

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| ###### SG 9 – Integrated broadband cable networks and |  |  |  |
| - television and sound transmission |  |  |  |
| - Priorities: | - Expected results: | - 2 planned SG meetings: | - Res. 71 (Minneapolis, 1998), F.4: |
| - IP and GII over cable distribution networks |  | - and its WPs | - Multimedia applications arising from the convergence |
| - Television and sound over the core network | - 15 Recommendations to be | - 10 working days | - of telecommunication, broadcasting, computer and |
| - Coordination with ITU-R on broadcasting matters | - approved in 2003: 1,000 pages |  | - information technology |
|  |  | - 6 P staff months |  |
| - Lead Study Group on integrated broadband cable |  | - 9 G staff months | - Res. 101 (Minneapolis, 1998): |
| - and television networks |  | - 304,000 F direct costs | - Internet Protocol (IP)-based networks |
|  |  | - 544,000 F document costs |  |
| - Webcasting |  |  |  |
| - Packet cable, IP over cable |  |  |  |
| - 19 Questions |  |  |  |
| - SG 11 - Signalling requirements and protocols |  |  |  |
| - Priorities: | - Expected results: | - 1 planned SG meeting: | - Res. 71 (Minneapolis, 1998), D.2, 29.2: |
|  |  | - and its WPs | - Developing Recommendations for new technologies |
| - Signalling support for Internet (IP)-based applications | - 25 Recommendations to be | - 10 working days | - and applications - global multimedia and mobility |
|  | - approved in 2003, 1200 pages |  |  |
| - Intelligent Networks. |  | - 7 P staff months | - Res. 71 (Minneapolis, 1998), F.4: |
|  |  | - 8 G staff months | - Facilitating the integration of existing and new |
| - Lead Study Group on intelligent networks |  | - 223,000 F direct costs | - transmission media in public networks, |
|  |  | - 536,000 F document costs | - in the area of signalling |
| - Signalling for Access, N&B-ISDN, |  |  |  |
| - and new generation networks |  |  | - Res. 71 (Minneapolis, 1998), F.4: |
|  |  | - 7 or 8 Rapporteur meetings | - Internet Protocol (IP) related aspects as well as the |
| - Cooperation and development of ITU-T Recommendations |  | - of 4 days each | - interoperability and convergence of IP-based networks, |
| - with regional standards bodies/fora on signalling-related |  |  | - the Internet, with existing network infrastructures |
| - activities for IP |  |  | - Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | - Covering the future evolution of network infrastructures, |
| - Coordination with relevant ITU-T/ITU-R SGs/Wps for |  |  | - e.g. in the areas of network access, signalling and |
| - signaling support of fixed-mobile aspects |  |  | - control |
| - New activities: |  |  |  |
| - - Signalling for New Generation Networks (NGN) |  |  |  |
| - - SIP – profiles |  |  |  |
| - - Signalling protocols for ATM over MPLS |  |  |  |
| - 1 workshop related to NGN (see SSG) |  | - 2 days |  |
| - 15 Questions |  |  |  |

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - SG 12 - End-to-end transmission performance of |  |  |  |
| - networks and terminals |  |  |  |
| - Priorities: | - Expected results: | - 2 planned SG meetings |  |
| - Performance assessment |  | - and its WPs |  |
|  | - 25 Recommendations to be | - 12 working days | - Res. 101 (Minneapolis, 1998): |
| - Lead Study Group on Quality of services and performance | - approved in 2003: 500 pages |  | - Performance quality assessment of IP-based networks |
|  |  | - 5 P staff months |  |
| - New activities: |  | - 6 G staff months | - Res. 71 (Minneapolis, 1998), F.4: |
| - Development of Recs. on Quality aspects of IP-based |  | - 60,000 F direct costs | - Multimedia applications |
| - network |  | - 97,000 F document costs |  |
| - 1 Workshop on QoS |  | - 3 days |  |
| - 16 Questions |  |  |  |

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - SG 13 – Multi-protocol and IP-based networks |  |  |  |
| - and their internetworking |  |  |  |
|  |  |  | - Res. 73 (Minneapolis, 1998): - World Summit on the information society |
| - Priorities: | - Expected results: | - 1 planned SG meeting: |  |
| - General network aspects, Global Information |  | - and its WPs | - Res. 101 (Minneapolis, 1998): - Internet Protocol (IP)-based networks |
| - Infrastructures (GII, NGN), B-ISDN and IP (Internet Protocol) | - 13 Recommendations to be | - 9 working days |  |
| - Fostering cooperation with IETF | - approved in 2003: 750 pages |  | - Res. 71 (Minneapolis, 1998), D.2, 29.2: |
|  |  | - 3 P staff months | - Developing Recommendations for new technologies |
| - Monitoring IP and NGN 2004 projects |  | - 3 G staff months | - and applications such as appropriate aspects of the GII |
|  |  | - 108,000 F direct costs | - and global multimedia and mobility |
| - Lead Study Group for IP related matters, B-ISDN, |  | - 179,000 F document costs |  |
| - Global Information Infrastructure and satellite matters |  |  | - Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | - Internet Protocol (IP) related aspects as well |
|  |  | - 5 Rapporteurs meetings | - as the interoperability and convergence of |
|  |  | - of 5 days each | - IP-based networks, the Internet, with |
|  |  |  | - existing network infrastructures |
| - NGN |  |  | - Res. 71 (Minneapolis, 1998), F.4: |
| - VoMPLS |  |  | - Facilitating the integration of existing and |
| - VPN (Virtual Private Network) |  |  | - new transmission media in public networks, |
| - Integrated communication architecture, including the |  |  | - in cooperation with ITU-R for radio |
| - impact of convergence |  |  | - transmission aspects |
| - Interworking |  |  |  |
| - Performance |  |  | - Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | - Further evolution of network infrastructures in |
|  |  |  | - the areas of network access and interfaces |
| - 16 Questions |  |  | - Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | - Implementation of the GII |
|  |  |  | - Res. 71 (Minneapolis, 1998), F.4: |
|  |  |  | - Integration of existing and new |
|  |  |  | - transmission media in public networks |
|  |  |  | - Res. PLEN/2 (Marrakesh, 2002) |
|  |  |  | - communication network security |

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - ICG SAT |  |  |  |
| - Intersector Coordination Group on Satellite Matters |  |  |  |
| - Under the Lead of SG 13 |  |  | - Res. 71 (Minneapolis, 1998), F.4: |
| - Priorities: | - Expected results: | - No planned meeting so far | - Facilitating the integration of existing and new |
|  |  |  | - transmission media in public networks, in cooperation |
| - To take into account satellite specificity within | - Performance |  | - with ITU-R for radio transmission aspects |
| - telecommunication network including impact of | - Achieved consistency of |  |  |
| - IP-based network and multimedia network and system | - Recommendations of various |  |  |
| - Keeping up to date database | - Study Groups for full integration |  |  |
|  | - of the sat-transmission in |  |  |
| - Coordination with ITU-R | - public networks |  |  |
| - Organization of 1 workshop will be considered |  |  |  |
| - Strengthening relationship with ITU-D |  |  |  |
| - SG 15 – Optical and other transport networks |  |  |  |
| - Priorities: | - Expected results: | - 2 planned SG meeting | - Res. 71 (Rev. Marrakesh, 2002): |
| - Access Network | - 60 Recommendations to be | - and its WPs | - Goals 1, 2, 4, 6 & Chapter 5 |
| - - broadband optical access, Multigigabit PONS | - approved in 2003: 3,600 pages | - 19 working days |  |
| - - refinement & enhancement to SDL |  |  |  |
| - - IP on Access Network |  | - 6 P staff months |  |
| - Network signal processing |  | - 7 G staff months |  |
| - - interaction of signal processing (OTN) |  | - 332,000 F direct costs |  |
| - Optical transport network structure |  | - 821,000 F document costs |  |
| - - automatic switched optical network (ASON) |  |  |  |
| - - network management & control |  |  |  |
| - OTN Technology |  |  |  |
| - - coarse & dense wavelength division multiplexing (WDM) |  |  |  |
| - - fiber characteristics |  |  |  |
| - - transmission technology |  |  |  |
| - - IP on WDM |  |  |  |
| - Cooperation with IEC and other SDOs |  |  |  |
| - Lead Study Group on access network transport |  |  |  |
| - Lead Study Group on optical technology |  |  |  |
|  |  |  | - transmission aspects |
| - 19 Questions |  |  |  |

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - SG 16 - Multimedia services, systems and |  |  |  |
| - terminals |  |  |  |
| - Priorities: | - Expected results: | - 1 planned SG meeting |  |
| - IP mobility |  | - and its WPs |  |
| - Multimedia platform and interworking | - 40 Recommendations to be | - 9 working days | - Res. 71 (Minneapolis, 1998), F.4: |
| - Media Coding | - approved in 2003: 1,500 pages |  |  |
| - Multimedia framework, MEDIACOM-2004 project |  |  |  |
| - Cooperation with other Standard Development |  | - 8 P staff months | - Multimedia applications arising from the convergence |
| - Organization |  | - 8 G staff months | - of telecommunication, broadcasting, computer and |
| - Lead Study Group on multimedia services, |  | - 151,000 F direct costs | - information technology |
| - systems and terminals |  | - 306,000 F document costs |  |
| - Lead Study Group on e-business and e-commerce |  |  |  |
|  |  | - 4 Rapporteur meetings | - Res. 101 (Minneapolis, 1998): |
| - New activities: |  | - 1 week each | - Internet Protocol (IP)-based networks |
| - E-commerce, E-business |  |  |  |
| - 1 workshop on Telecommunications for Disaster relief |  | - 3 days |  |
| - 1 workshop on Standardization in E-Health |  | - 3 days |  |
| - 1 workshop |  | - 3 days |  |
| - 23 Questions |  |  |  |

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - SG 17 - Data Networks and Telecommunication |  |  |  |
| - Software |  |  |  |
| - Priorities: | - Expected results: | - 1 planned SG meeting | - Res. 71 (Minneapolis, 1998), F.4: |
| - Communication System Security |  | - and its WPs | - Further evolution of networks infrastructures |
| - Revision of OID-related Recommendations | - 34 Recommendations to be | - 8 working days | - in the area of security |
| - Additions to a set of Directory Recommendations | - approved in 2003: 1,500 pages |  | - Interoperability of IP-based networks with |
| - Additions to/revision of the set of ASN.1 Recs |  | - 5 P staff months | - existing networks |
| - Language coordination and promotion |  | - 6 G staff months |  |
| - Cooperation with ISO/IEC |  |  |  |
| - Contribution to the coordination effort with ISO, IEC and |  | - 146,000 F direct costs | - Res. 101 (Minneapolis, 1998) |
| - UN/ECE for E-business standardization |  | - 306,000 F document costs | - Collaborative activities on IP-based network with |
| - Open Distributed Processing (ODP), Frame Relay |  |  | - ISOC/IETF |
|  |  |  | - Res. PLEN/2 (Marrakesh, 2002) |
| - Lead Study Group on Frame Relay |  |  | - Information and communication network security |
| - Lead Study Group on Communication System Security |  |  |  |
| - Lead Study Group on Languages and Description |  |  |  |
| - Techniques |  |  |  |
| - Enhancement of communication system security |  |  | - TSAG (Geneva, 19-23 March 2001) |
| - Development of the ITU-T ASN.1 Project |  |  | - TSAG approved the merger of Study group 7 and 10 |
| - Continuation of the provision of ASN.1 modules to the |  | - 15 Rapporteurs meetings | - into a single Study Group 17 |
| - ASN.1 database |  | - of 1 to 5 days each |  |
| - Development of the ITU-T language coordination project |  |  |  |
| - Development of the ITU-T Security project |  |  |  |
| - 1 workshop on “ Languages” |  | - 1 day |  |
| - 28 Questions |  |  |  |

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - SSG – Special Study Group IMT-2000 and beyond |  |  |  |
|  |  |  | - Res. 38 (WTSA-2000) |
| - Priorities: |  |  | - Coordination among ITU-T, ITU-R and ITU-D for |
| - Network aspects of IMT-2000 and beyond | - Expected results: | - 2 planned SSG meetings | - IMT-2000 activities |
| - (International Mobile Telecommunications-2000) |  | - and its WPs |  |
| - Wireless access to IP-based networks |  | - 10 working days |  |
| - Convergence of mobile and fixed networks |  |  |  |
| - Mobility management, mobile multimedia functions | - 4 Recommendations to be |  |  |
| - Internetworking, interoperability and harmonization | - approved in 2003: 200 pages | - 7 P staff months |  |
| - between IMT-2000 systems |  | - 8 G staff months |  |
| - Network vision of systems beyond IMT-2000 | - 5 Technical Report to be | - 37,000 F direct costs |  |
|  | - approved in 2003: 80 pages | - 73,000 F document costs |  |
| - Enhancement of ITU-T Recommendations on IMT-2000 |  |  |  |
|  | - 1 Handbook (2d Edition) to be | - 5 Rapporteur meetings |  |
| - Lead Study Group on IMT-2000 and beyond | - produced together with ITU-R | - 16 working days |  |
| - and for mobility | - and ITU-D in 2003: 20 pages |  |  |
|  |  | - 3 Editor’s meetings |  |
| - New activities: |  | - 10 working days |  |
| - Workshop on SSG activities related to NGN, |  | - 2.5 days |  |
| - organized jointly with ITU-T SG 11 and SG 13 |  |  |  |
| - Electronic meetings |  | - 6 electronic meetings |  |
| - 8 Questions |  |  |  |
| - Workshops |  |  |  |
| - Dissemination of expert knowledge on state-of-the-art | - Expected results: | - 24 P staff-months | - Resolution 71 (Rev. Marrakesh, 2002): |
| - technologies, |  | - 7 G staff-months | - Goal 3, 5, 6, Chapter 5 |
|  | - Participation of delegates from |  |  |
| - Promotion of awareness of ITU-T activities, | - developing countries in the | - 100,000 F direct costs: | - Resolution 25 (Rev. Marrakesh, 2002) |
| - working methods and priorities | - activities of the Sector | - Fellowships for SG 3 | - Strengthening the regional presence |
|  | - Strengthening regional presence |  | - WTSA Resolution 17 (Montreal, 2000) |
|  |  |  | - telecommunication standardization in relation |
|  | - Achievement indicators: |  | - to the interests of developing countries |
|  | - Dissemination of expert technology |  |  |
|  |  |  | - Council Resolution 1181 |
|  | - Integration of developing countries |  | - Recommendations on ITU Reform, WGR R7 |
|  | - concerns in ITU-T outputs |  |  |
|  | - Coordination of activities within |  | - Council Resolution 1183 |
|  | - Study Groups and with other SDOs |  | - ITU regional presence |

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - Regional presence |  |  | - Resolution 25 (Rev. Marrakesh, 2002) |
|  |  |  | - Strengthening the regional presence |
| - Strengthening the regional presence | - Expected results: | - 4 regional briefing meetings | - “regional meetings should be organized in the various |
| - Participation in external conferences |  | - SG meetings in the regions | - regions by the relevant Sectors, particularly ITU-D, in |
| - Assistance to ITU-D | - Strengthened regional presence | - Workshops in the regions | - order to improve the participation in and effectiveness |
|  | - Awareness of ITU-T activities | - Regional tariff group meetings | - of the corresponding global meetings” |
|  | - Achievement indicators: | - 10 P staff-months | - WTSA Resolution 17 (Montreal, 2000) |
| - Organization of seminars in the field |  | - 12 G staff-month | - telecommunication standardization in relation |
| - Assistance to the Regions | - Membership satisfaction |  | - to the interests of developing countries |
| - Regional briefing meetings | - Dissemination of ITU-T studies | - 225,000 F direct costs |  |
|  | - and Recommendations |  | - Council Resolution 1183 |
|  |  |  | - ITU regional presence |
|  |  |  | - Resolution 71 (Rev. Marrakesh, 2002): |
| - Promoting the ITU-T |  |  | - Goal 3, 5, 6, Chapter 5 |
|  | - Expected results: | - 18 P staff-months | - “to develop and execute a proactive plan, in |
| - Press releases | - Awareness of ITU-T activities | - 9 G staff-month | - collaboration with the secretariat, in order to promote |
| - ITU-T presence in external events | - Increased interest of Membership |  | - the value of ITU-T in the face of competition from |
| - Presentation of ITU-T activities during |  | - 100,000 F direct costs | - other standards bodies and to continue to enhance |
| - external workshops | - Achievement indicators: |  | - efforts in this regards” |
| - Promotion events | - Higher number of Sector Members |  |  |
|  | - Increased participation in the |  | - Council Resolution 1181 |
|  | - Sector activities |  | - Recommendations on ITU Reform, WGR R7 |
|  |  |  | - “Recognizing the need to improve awareness of |
|  |  |  | - ITU-T products and services, and the image of the |
|  |  |  | - Union in general, Council instructs the Secretary- |
|  |  |  | - General and the Director of the TSB to define and |
|  |  |  | - implement a corresponding promotion strategy |
|  |  |  | - and to allocate appropriate resources in the budget |
| - External cooperation |  |  |  |
|  | - Expected results: | - 9 P staff-months |  |
| - Assistance to membership and Telecom community | - Worldwide coordination | - 12 G staff-months |  |
| - Assistance and cooperation with other Sectors | - Promotion of ITU-T activities |  |  |
| - Liaison and coordination with international and regional | - Signature of MoUs |  |  |
| - organizations |  |  |  |
| - Cooperation with other standard organizations | - Achievement indicators: |  |  |
| - Participation in external conferences | - Customer and membership |  |  |
| - IPR issues | - satisfaction |  |  |
|  | - Dissemination of ITU-T studies |  |  |
|  | - and Recommendations |  |  |

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - Study Group Publications |  |  |  |
| - Editing and publication of approved texts in F, E, S | - Expected results: | - 23 P staff-months |  |
|  |  | - 157 G staff-months | - Res. 66 (Minneapolis, 1998): |
| - Priorities: | - Publication of 12,000 p. of Recs |  | - Documents and publications of the Union |
| - Availability of pre-published Recommendations within | - and 1,000 p. of handbooks in | - TSB Publication budget = |  |
| - one month of approval. | - three languages | - 264,500 F direct costs |  |
|  |  | - 232,000 F invoiced costs |  |
| - Quickpub procedures | - Key indicators: |  | - Res. 71 (Minneapolis, 1998): |
|  |  | - Covered by sales revenues | - Production high-quality Recommendations |
| - Quality control of texts | - Decrease time to edit publications |  | - quickly in response to market demands |
|  | - Pre-published Recs within 1 month |  |  |
| - Common text procedure with the ISO | - Quality control of texts |  |  |
|  | - Worldwide dissemination |  |  |
|  | - Increased use of ITU-T Recs. |  |  |
| - Operational Bulletin |  |  |  |
| - Publication containing administrative and operational | - Expected results: | - 17 P staff-months | - Res. 66 (Minneapolis, 1998): |
| - information exchanged between administration, ROAs etc |  | - 16 G staff-months | - Documents and publications of the Union |
|  | - 24 issues per year |  |  |
| - Lists of country codes and dialing codes for all |  | - 14,500 F direct costs |  |
| - international services |  | - 20,000 F invoiced costs |  |
| - Priority: |  | - Covered by sales revenues |  |
| - Immediate posting of information to members |  |  |  |
| - Increase the distribution of the Operational Bulletin |  |  |  |
| - Relations with State Members and Sector Members |  |  |  |

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - Database development available to public |  |  |  |
| - List of ITU-T Sector Members | - Expected results: |  |  |
| - Work program database | - Availability of the information | - 5 P staff-months |  |
| - Patent statement database | - to public | - 8 G staff-months |  |
| - Software statement database |  |  |  |
| - Terminology database | - Achievement indicators: |  |  |
| - List of Recommendations in force |  |  |  |
| - List of recognized SDOs | - Rapid and up-to-date |  |  |
| - General and Meeting schedule Information on the WEB | - Consultation |  |  |
| - International numbering resources |  |  |  |
|  | - Dissemination of operational |  |  |
| - Priority: | - Information to public |  |  |
| - Improve the user-friendliness of public databases |  |  |  |
| - ASN.1 Module database |  |  |  |
| - AAP database |  |  |  |
| - Development of new databases as per request of Study |  |  |  |
| - Group |  |  |  |
| - UIFN registration |  |  | - Res. 91 (Minneapolis, 1998): |
|  |  |  | - Cost recovery for some products and services |
| - Universal International Free phone Numbers registrar | - Expected results: | - 2 P staff-months |  |
|  | - 3,000 UIFN Reservations | - 13 G staff-months | - ITU-T Recommendation E.169 |
| - Priority: |  |  |  |
| - Immediate reservations of UIFN numbers | - Achievement indicators: | - 374,000 F direct costs |  |
|  | - Immediate registration of UIFNs |  |  |
|  | - Customer satisfaction |  |  |
|  |  | - Full cost recovery |  |
| - UIPRN & UISCN registration |  |  |  |
| - Universal International Premium Rate Numbers registrar | - Expected results: | - 1 P staff-months | - Res. 91 (Minneapolis, 1998): |
| - Universal International Shared Cost Numbers registrar | - 400 UIPRN/UISCN reservations | - 1 G staff-months | - Cost recovery for some products and services |
|  | - Achievement indicators: | - 47,500 F direct costs | - ITU-T Recommendations E.169.2 and E.169.3 |
|  | - Immediate registration |  |  |
|  | - Customer satisfaction | - Full cost recovery |  |

| - Operational Activities | - Objectives and Performance Indicators | - Allocated Resources from the 2003 budget | - Relationship to Strategic Policies and Plans / PP-98 / PP-02 |
| --- | --- | --- | --- |
| - AESAs registration |  |  |  |
|  |  |  | - Res. 91 (Minneapolis, 1998): |
|  | - Expected results: | - Full cost recovery | - Cost recovery for some products and services |
| - ATM End System Addresses registrar | - No longer AESAs reservations |  |  |
|  |  |  | - ITU-T Recommendations E.191.1 |
| - Codes for Groups of countries - Opening E.164 numbering resources - UPT numbering administration |  |  |  |
| - Bureau support |  |  |  |
| - Membership |  | - 33 P staff-months | - Res. 72 (Minneapolis, 1998): Linking strategic, |
| - Meeting organization and logistical support |  | - 20 G staff-months | - financial and operational planning in ITU |
| - Document control |  |  | - Res. 104 (Minneapolis, 1998): |
| - Administrative support |  | - 9,909,000 F direct costs | - Reduction of the volume and cost of documentation |
| - Finance and budget |  | - 139,000 F document costs | - for ITU conferences |
| - Director Office |  |  | - Res. 71 (Minneapolis, 1998), annex 2: |
| - Internal management |  |  | - Goals for improved management |
| - Operational planning |  |  |  |
| - Gender perspective issues |  |  | - Res. 70 (Minneapolis, 1998): |
|  |  |  | - Inclusion of gender perspective in the work of ITU |
| ###### Director’s Ad Hoc IPR Group |  |  | - Res. 1187 Council 2001 |
|  |  |  | - Gender perspective in ITU Human Resource |
|  |  |  | - management policy and practice |
| - EDH (Electronic Document Handling) |  |  | - Res. 66 (Minneapolis, 1998): |
|  |  |  | - Documents and publications of the Union |
| - Posting of documents | - Expected results: | - 34 G staff-months | - Res. 1141 Council 1999 |
| - WEB development | - Immediate posting of information |  | - Reduction of the cost and volume of documentation for |
| - Customer support (TSB helpdesk) |  |  | - Conferences and Assemblies and the Council |
| - Alternate Approval Process Implementation | - Achievement indicators: |  |  |
|  | - Increased number of visitors |  | - Res. 32 (WTSA-2000) |
| - Maintaining of the ITU-T Website and relevant information | - Customer satisfaction |  | - Strengthening the use of electronic document handling |
|  |  |  | - for the work of ITU-T |